## Sheet1
type | name | values
checklist-flat | Fire Damper
checkpoint | Is the location drawing approved for construction
checkpoint | Installation of duct completed as drawn
checkpoint | Is the Fire damper accessible
checkpoint | Testing of Fire dampers
checkpoint | Fire damper labeled
checkpoint | Photos taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Installation Fusiotherm Pipework
checkpoint | Is the drawing approved for construction
checkpoint | Is site safe for work start
checkpoint | Measure & mark off circuit dimensions on site
checkpoint | Carry out Fusiotherm checks to manufacturers recommendations
checkpoint | Has pipe been installed to the drawing
checkpoint | Check pipe is installed to correct levels and falls
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Photos taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Grilles & Diffusers QA Checklist
checkpoint | Is the drawing approved for construction
checkpoint | Is site safe for work start, report discrepancies
checkpoint | Grilles delivered are correct for the system/building
checkpoint | Check grilles & Diffusers for damage, report observations
checkpoint | Measure & mark off duct run dimensions on site
checkpoint | Install diffusers & grilles
checkpoint | Has diffuser been installed to level & plumb
checkpoint | Are fixings visible
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Photos taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Steel duct Install QA
checkpoint | Is the drawing approved for construction
checkpoint | Is site safe for work start
checkpoint | Duct delivered is correct for the system/building
checkpoint | Measure &amp; mark off duct run dimensions on site
checkpoint | Install duct
checkpoint | Has duct been installed to the drawing
checkpoint | Has duct been installed to correct levels &amp; falls
checkpoint | Is rigid duct supported at appropriate centres
checkpoint | Is flexible duct supported at appropriate centres
checkpoint | Verify &amp; record on drawing As-Built dimensions
holdpoint | Signoff by Main Contractor or Engineer, if required