## Sheet1
type | name | values
checklist-flat | Fire Damper
checkpoint | Is the location drawing approved for construction
checkpoint | Installation of duct completed as drawn
checkpoint | Is the Fire damper accessible
checkpoint | Testing of Fire dampers
checkpoint | Fire damper labeled
checkpoint | Photos taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Installation Fusiotherm Pipework
checkpoint | Is the drawing approved for construction
checkpoint | Is site safe for work start
checkpoint | Measure & mark off circuit dimensions on site
checkpoint | Carry out Fusiotherm checks to manufacturers recommendations
checkpoint | Has pipe been installed to the drawing
checkpoint | Check pipe is installed to correct levels and falls
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Photos taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Grilles & Diffusers QA Checklist
checkpoint | Is the drawing approved for construction
checkpoint | Is site safe for work start, report discrepancies
checkpoint | Grilles delivered are correct for the system/building
checkpoint | Check grilles & Diffusers for damage, report observations
checkpoint | Measure & mark off duct run dimensions on site
checkpoint | Install diffusers & grilles
checkpoint | Has diffuser been installed to level & plumb
checkpoint | Are fixings visible
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Photos taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Steel duct Install QA
checkpoint | Is the drawing approved for construction
checkpoint | Is site safe for work start
checkpoint | Duct delivered is correct for the system/building
checkpoint | Measure &amp; mark off duct run dimensions on site
checkpoint | Install duct
checkpoint | Has duct been installed to the drawing
checkpoint | Has duct been installed to correct levels &amp; falls
checkpoint | Is rigid duct supported at appropriate centres
checkpoint | Is flexible duct supported at appropriate centres
checkpoint | Verify &amp; record on drawing As-Built dimensions
checkpoint | Photos taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | AHU Install
checkpoint | Is the location drawing approved for construction
checkpoint | AHU is correct for the system/building and position shown on drawings
checkpoint | Check casing, fans, coils & duct for damage, report observations
checkpoint | AHU filters fitted and manometers connected
checkpoint | Is AHU installed level & plumb
checkpoint | Are seismic restraints installed
checkpoint | Are supports and fixings installed adequately
checkpoint | Have subcontractors completed all work.
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Photos taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Air Curtain Checklist
checkpoint | Is the location drawing approved for construction
checkpoint | Is site safe for work start, report discrepancies
checkpoint | Air Curtain is correct for the system and position shown on drawings
checkpoint | Check casing, fans, coils & duct for damage, report observations
checkpoint | Filters installed, size recorded
checkpoint | Is Air Curtain installed level & plumb
checkpoint | Are supports and fixings installed adequately
checkpoint | Electrically connected and fan going the correct way
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Photos taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Attenuator QA Checklist
checkpoint | Is the location drawings approved for construction
checkpoint | Attenuator is correct for the system/building
checkpoint | Check casing, report any damage
checkpoint | Orientation and connections correct, flow arrow correct
checkpoint | Attenuator is installed to manufacturers recommendations
checkpoint | Verify & record on drawings As-Built dimensions
checkpoint | Photos taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Chiller QA Checklist
checkpoint | Is the location drawing approved for construction
checkpoint | Chiller is correct for the system/building
checkpoint | Check for damage and report observations
checkpoint | Check antivibration mounts
checkpoint | Chiller installed to manufacturers recommendations, check all connections are correct
checkpoint | Is chiller installed level & plumb
checkpoint | Are seismic restraints installed
checkpoint | Sub-contractor work is complete
checkpoint | Check chemical dosing of system
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Photos taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Humidifier Install Template
checkpoint | Is the location drawings approved for construction
checkpoint | Humidifier is correct for the system/building
checkpoint | Check for damage and report defects
checkpoint | Is Humidifier installed level & plumb
checkpoint | Test drain tray and water trap works
checkpoint | Brackets are fitted and secure
checkpoint | Are seismic restraints installed
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Photos Taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Fan Install QA Checklist
checkpoint | Is the location drawing approved for construction
checkpoint | Fan is correct for the system/building
checkpoint | Check casing, fan blades, motor & cowl for damage, report observations
checkpoint | Anti vibration mounts are fitted
checkpoint | Fan is installed to manufacturers recommendations
checkpoint | Check brackets and seismic restraint if necessary
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Photos Taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | FCU Install QA Checklist
checkpoint | Is the location drawing approved for construction
checkpoint | Is site safe for work start, report discrepancies
checkpoint | FCU is correct for the system and position shown on drawings
checkpoint | Check casing, fans, coils & duct for damage, report observations
checkpoint | Filters installed, size recorded
checkpoint | Is FCU installed level & plumb
checkpoint | Are supports and fixings installed adequately
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Photos Taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Filters Template
checkpoint | Locate and verify the AHU
checkpoint | Identify correct filter is being installed
checkpoint | Has the Air Filter been installed in the correct position
checkpoint | Verify the last time Filter was changed and note current date on sign off sheet
checkpoint | Photos Taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Flexi duct QA checklist
checkpoint | Is the drawing approved for construction
checkpoint | Is site safe for work start, report discrepancies
checkpoint | Duct delivered is correct for the system/building
checkpoint | Measure & mark off duct run dimensions on site
checkpoint | Install duct
checkpoint | Has duct been installed to the drawing
checkpoint | Has duct been installed to correct levels & falls
checkpoint | Is flexible duct supported at appropriate centres
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Photos Taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Heat Exchanger QA Checklist
checkpoint | Is the drawing approved for construction
checkpoint | Is site safe for work start, report discrepancies
checkpoint | Heat exchanger is correct for the system/building
checkpoint | Check casing, plates for damage, report observations
checkpoint | Pipe work connection adequate
checkpoint | Heat exchanger is installed to manufacturers recommendations
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Photos Taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Heat Pump Install Template
checkpoint | Is the location drawing approved for construction
checkpoint | Is site safe for work start, report discrepancies
checkpoint | Heat Pumps is correct for the system/building
checkpoint | Check casing, fans, coils & duct for damage, report observations
checkpoint | Measure & mark location dimensions on site
checkpoint | Is Heat Pumps installed level & plumb
checkpoint | Are seismic restraints installed
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Photos Taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Heating Coils Template
checkpoint | Is the location drawing approved for construction
checkpoint | Heating Coil is correct for the system and position shown on drawings
checkpoint | Is Heating Coil installed level & plumb
checkpoint | Are supports and fixings installed adequately
checkpoint | Verify & record on drawing As-Built dimensions (if differ or required)
checkpoint | Photos Taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | MGPS installation
checkpoint | Is the drawing approved for construction
checkpoint | Is site safe for work start
checkpoint | Measure & mark off circuit dimensions on site
checkpoint | Has pipe been installed to the drawing
checkpoint | Has pipe been installed to manufacturers recommendations
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Has the system been kept free of any contaminants
checkpoint | Carry out pressure test & record results on all circuits to 10 BAR
checkpoint | Release test pressure
checkpoint | Photos Taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Humidifier Install Template
checkpoint | Is the location drawing approved for construction
checkpoint | Humidifier is correct for the system/building
checkpoint | Check casing, fans, coils & duct for damage, report observations
checkpoint | Measure & mark location dimensions on site
checkpoint | Is Humidifier installed level & plumb
checkpoint | Are seismic restraints installed
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Photos Taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Pipework Underground
checkpoint | Is the drawing approved for construction
checkpoint | Measure & mark off circuit dimensions on site
checkpoint | Has underground heating mains pipe work been joined in accordance with the specification
checkpoint | Has pipe work been installed to the drawing
checkpoint | Check pipe work is installed to correct levels and falls
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Photos Taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Pump Install QA
checkpoint | Is the location drawing approved for construction
checkpoint | Is site safe for work start, report discrepancies
checkpoint | Confirm the correct pump model is installed and labelled
checkpoint | Is the Pump installed the correct way around (arrow)
checkpoint | Has the Pump be mounted correct and fixed down
checkpoint | Is the pump accessible and have free area around it
checkpoint | Photos Taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | PVC Pipework Intall
checkpoint | Is the drawing approved for construction
checkpoint | Measure & mark off dimensions on site
checkpoint | Brackets installed and spaced correctly
checkpoint | Has pipe work been installed to the drawing
checkpoint | Check pipe work is installed to correct levels and falls
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Photos Taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | PVC Pipework Underground
checkpoint | Is the drawing approved for construction
checkpoint | Measure & mark off circuit dimensions on site
checkpoint | Has underground PVC mains pipe work been joined in accordance with the specification
checkpoint | Has pipe work been installed to the drawing
checkpoint | Check pipe work is installed to correct levels and falls
checkpoint | Pressure Test Pipe.
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Photos Taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Air conditioning unit
checkpoint | Is the location drawing approved for construction
checkpoint | Is site safe for work start, report discrepancies (floor, walls etc)
checkpoint | AC Unit is correct for the system and position shown on drawings
checkpoint | Check casing, fans, coils & duct for damage, report observations
checkpoint | All pipework (Pair coil & Condensate drain) is correct and ready for installation
checkpoint | Is AC Unit installed level & plumb
checkpoint | Fill drain tray to test condensate drain
checkpoint | Are supports and fixings installed adequately
checkpoint | Verify & record on drawing As-Built dimensions (if differ or required)
checkpoint | Check Electrical Supply to Indoor & Outdoor Units
checkpoint | Photos Taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Radiant heater template
checkpoint | Is the location drawing approved for construction
checkpoint | Radiant Heater is correct for the system and position shown on drawings
checkpoint | Is Radiant Heater installed level & plumb
checkpoint | Are supports and fixings installed adequately
checkpoint | Verify & record on drawing As-Built dimensions (if differ or required)
checkpoint | Photos Taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Seismic brackets
checkpoint | Is the drawing approved for construction
checkpoint | Is site safe for work start
checkpoint | Check spacing of brackets
checkpoint | Are brackets installed to drawings & specifications
checkpoint | Brackets are level and square
checkpoint | Check for 50mm separation to other services as required by the standard
checkpoint | Verify & record on drawing As-Built dimensions
checkpoint | Photos Taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Smoke Damper QA check list
checkpoint | Is the location drawing approved for construction
checkpoint | Installation of duct completed as drawn
checkpoint | Is the Smoke damper motor shaft accessible
checkpoint | Smoke dampers open & close manually (mark duct)
checkpoint | Smoke damper labelled
checkpoint | Photos Taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | Steel Pipe QA Checklist
checkpoint | Is the drawing approved for construction
checkpoint | Is site safe for work start
checkpoint | Measure & mark off circuit dimensions on site
checkpoint | Has steel pipe been tested as per Specification (photographs of test valves been recorded?)
checkpoint | Has pipe been installed to the drawing
checkpoint | Has the pipe been flushed and cleaned in accordance with specifications
checkpoint | Verify and record on drawing As-Built dimensions
checkpoint | Photos taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | VAV QA checklist
checkpoint | Is the VAV Box model correct and labelled (correct size?)
checkpoint | Is the VAV box installed the correct way around
checkpoint | Has it been mounted and seismically supported correct
checkpoint | Is the controller and Valves (water) accessible from below
checkpoint | Photos taken
holdpoint | Signoff by Main Contractor or Engineer, if required
checklist-flat | HTM02 -01 B1 carcus test
section | Carcus test
text | File number:
label | The following Pipeline Carcass Systems has been tested in accordance with Paragraph 15.47-15.51 and was found to comply with the following specifications:
label | During a test period of 2 hours, the maximum pressure loss should be ≤ 0.2 kPa for 400 kPa systems, ≤0.5kPa for 700 kPa systems, ≤ 0.2 kPa for vacuum & AGSS (plastic or copper).
label | Systems should be tested at a working pressure of;
label | For compressed medical gas systems - 10.0 bar (1,000 kPa);
label | For medical compressed air systems for surgical use - 18.0 bar (1,800 kPa);
label | For vacuum & AGSS systems constructed in copper 5.0 bar (500 kPa);
label | For vacuum & AGSS systems constructed in plastic 1 bar (100 kPa).
checkpoint | Gas Tested (Pass or Fail at end of test)
text | Test Pressure (kPa)
text | End Pressure (kPa)
text | Pressure Change (kPa)
text | Time started
text | Time ended
text | Final temp
checkpoint | Were any links made - make a note in the comments
checkpoint | Photos taken
holdpoint | Signoff by Main Contractor or Engineer, if required
section | Pipework 1st Fix QA Checks
checkpoint | Copper to AS/NZS 1571 Table B
checkpoint | Silfos 15%
checkpoint | Support Hanging, Spacing & Seismic Restraints
checkpoint | Inspection & Sectioning of Joints as Per HTM 13.36 – 13.38
checkpoint | Fire Rating / Penetration
checkpoint | Electrical Bonding & Earthing
checkpoint | Labelling & Direction Arrows
checkpoint | As-Builts Marked Up
checkpoint | Photos taken
holdpoint | Signoff by Main Contractor or Engineer, if required