## Table 1
[13 empty] | INSPECTION AND TEST PLAN | [16 empty] | Doc ID: FH-DP1-PM-ITP004B Rev: 01
Project: MAPMP 2.0 DP1
|  | Spray Seal | [10 empty] | Construction Process: Spray Sealing (Prime Coat, Primerseal and FibreDec) | [16 empty] | Prepared By: James Kremers
|  | Client: Melbourne Airport (APAM) | [10 empty] | Specification: 60692389-PS-01-AV-0001 - Revision 1 (27 Mar 2023) | [16 empty] | Approved By: Noriko Wood
[13 empty] | Structure/Component: Asphalt Pavement | [16 empty] | Date: 29/08/2023
Lot No. |  |  |  |  | Lot Details: | [5 empty] | Lot Size/Qty: | [14 empty] | Date:
|  |  | Item No. |  | Task/Activity Description |  |  | Inspection/Test | [13 empty] | Action Point |  | Responsibility |  | Comments |  | Checked by:
[8 empty] | Freq. |  |  | Acceptance Criteria |  |  |  |  | Reference Documents/ Clause |  | Inspection/ Test Method |  | Conformance Record | [7 empty] | AECOM |  | FH |  | Date
|  |  | 1 |  | Bitumen
|  |  | (a) |  | Bitumen |  |  | Delivery Docket upon request |  |  | Bitumen must be Class 170 complying with the requirements of AS 2008 |  |  |  |  | AECOM – MAPMP 2.0 DP1 Spec. Cl 11.4.2 |  | Verify |  | This ITP signed |  | IP |  | Lab Manager/SS Engineer
|  |  | (b) |  | Bitumen Emulsion |  |  | Delivery Docket upon request |  |  | Bitumen emulsion must comply with the requirements of AS 1160 Testing of the bitumen emulsion, as per ITP Bitumen Emulsions Manufacture Feb 2019 for Surfix 70 (for FibreDec), shall be done prior to releasing the product. Ensure minimal storage time (ideally use within 24 hours of production). |  |  |  |  | VicRoads Technical Spec 408.08 (b) ITP FH National – Bitumen Emulsions CAG 010812 Section 2 |  | Verify |  | This ITP signed |  | IP |  | Lab Manager/SS Engineer
|  |  | (c) |  | Cutback Bitumen |  |  | Delivery Docket upon request |  |  | Cutback bitumen must comply with the requirements of AS 2157 and must be Class AMC0 or AMC00 |  |  |  |  | AECOM – MAPMP 2.0 DP1 Spec. Cl 11.4.1 |  | Verify |  | This ITP signed |  | IP |  | Lab Manager/SS Engineer
|  |  | (d) |  | PMB and Proprietary Bitumen |  |  | Delivery Docket upon request |  |  | Viscosity-grade binders must comply with the requirements of AS/NZS 2008. The class of PMB shall comply with the requirements of Austroads Technical Specification ATS- 3110. |  |  |  |  | AECOM – MAPMP 2.0 DP1 Spec. Cl 11.4.3 |  | Verify |  | This ITP signed |  | IP |  | Lab Manager/SS Engineer
|  |  | 2 |  | Materials
|  |  | (a) |  | Cutter |  |  | Delivery Docket upon request |  |  | Any primer which is not prepared in a refinery must be prepared by mixing bitumen and cutter at the site |  |  |  |  | AECOM – MAPMP 2.0 DP1 Spec. Cl 11.4.4 |  | Verify |  | This ITP signed |  | IP |  | Lab Manager/SS Engineer
[12 empty] | INSPECTION AND TEST PLAN | [16 empty] | Doc ID: FH-DP1-PM-ITP004B Rev: 01
Project: MAPMP 2.0 DP1
Spray Seal | [11 empty] | Construction Process: Spray Sealing (Prime Coat, Primerseal and FibreDec) | [16 empty] | Prepared By: James Kremers
Client: Melbourne Airport (APAM) | [11 empty] | Specification: 60692389-PS-01-AV-0001 - Revision 1 (27 Mar 2023) | [16 empty] | Approved By: Noriko Wood
[12 empty] | Structure/Component: Asphalt Pavement | [16 empty] | Date: 29/08/2023
| Item No. |  |  | Task/Activity Description |  |  | Inspection/Test | [13 empty] | Action Point |  | Responsibility |  | Comments |  | Checked by:
[7 empty] | Freq. |  |  | Acceptance Criteria |  |  |  |  | Reference Documents/ Clause |  | Inspection/ Test Method |  | Conformance Record | [7 empty] | AECOM |  | FH |  | Date
of the Works. The cutter must be commercial quality power kerosene or aviation turbine fuel (Jet A-1). No other type of cutter oil must be used under any circumstances. The cutter must be a clean, clear liquid containing no dissolved solids, foreign material or matter in suspension and must be liquid at 4°C. The Contractor must declare the amount of cutter used in the primer or primerseal to the Contract Administrator.
| (b) |  |  | Fibreglass |  |  | Prior to commencing works |  |  | Ensure correct fibre is supplied. |  |  |  |  | CAG 010812 Section 2 |  | Verify |  | Fibreglass datasheet |  | IP |  | SS Engineer/ Supervisor
| 3 |  |  | Aggregate
| (a) |  |  | Aggregate Specification |  |  | Delivery Docket upon request Maximum lot size 350t of same class and size |  |  | VicRoads Standard Specification Sections:  801 - Source Rock;  831 – Aggregate; and  832 - Sands |  |  |  |  | VicRoads Technical Spec 408.11 (a) |  | Verify |  | This ITP signed |  | IP |  | Lab Manager/SS Engineer
| (b) |  |  | Aggregate Pre- coating Materials |  |  | Delivery Docket upon request |  |  | Distillate based product, cutback bitumen, emulsion based product or proprietary product. |  |  |  |  | VicRoads Technical Spec 408.09 (b) 408.11 (b) |  | Verify |  | This ITP signed |  | IP |  | Spray Seal Supervisor
| 4 |  |  | Operation
[12 empty] | INSPECTION AND TEST PLAN | [16 empty] | Doc ID: FH-DP1-PM-ITP004B Rev: 01
Project: MAPMP 2.0 DP1
Spray Seal | [11 empty] | Construction Process: Spray Sealing (Prime Coat, Primerseal and FibreDec) | [16 empty] | Prepared By: James Kremers
Client: Melbourne Airport (APAM) | [11 empty] | Specification: 60692389-PS-01-AV-0001 - Revision 1 (27 Mar 2023) | [16 empty] | Approved By: Noriko Wood
[12 empty] | Structure/Component: Asphalt Pavement | [16 empty] | Date: 29/08/2023
| Item No. |  |  | Task/Activity Description |  |  | Inspection/Test | [13 empty] | Action Point |  | Responsibility |  | Comments |  | Checked by:
[7 empty] | Freq. |  |  | Acceptance Criteria |  |  |  |  | Reference Documents/ Clause |  | Inspection/ Test Method |  | Conformance Record | [7 empty] | AECOM |  | FH |  | Date
| (a) |  |  | Material Test Reports |  |  | Prior to commencing works |  |  | Test reports for bitumen and proprietary emulsions must be submitted to the Contract Administrator. |  |  |  |  | AECOM – MAPMP 2.0 DP1 Spec. Cl 11.4.7 |  | Verify |  | This ITP signed |  | HP |  | Spray Seal Engineer / Contract Administrator / Principle’s Design Consultant
| (b) |  |  | Works Method Statement |  |  | Prior to commencing works |  |  | The Contractor must submit a Works Method Statement (WMS) to the Contract Administrator. |  |  |  |  | AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.1 |  | Verify |  | This ITP signed |  | HP |  | Spray Seal Engineer / Contract Administrator / Principle’s Design Consultant
| (c) |  |  | Calibration of Bitumen Sprayer |  |  | Prior to commencing works |  |  | Calibration Certificate to be provided. |  |  |  |  | VicRoads Technical Spec 408.07 AECOM – MAPMP 2.0 DP1 Spec. Cl 11.3.3 |  | Verify |  | This ITP signed & Compliance Certificate |  | HP* |  | Spray Seal Engineer/ Supervisor
| (d) |  |  | Commencement of works & Surface Preparation |  |  | Prior to commencing works |  |  | Works shall not commence until the Contractor & Superintendent of works agree that the prepared surface is ready & fit for sealing. Surface is free of loose material and the surface is dry. Priming shall not be carried out within 24 hours of forecast rain. |  |  |  |  | VicRoads Technical Spec 408.04 (b) 408.09 (d) AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.2, 11.5.3 |  | Verify |  | This ITP signed |  | HP |  | Spray Seal Engineer / Contract Administrator / Principle’s Design Consultant
[12 empty] | INSPECTION AND TEST PLAN | [16 empty] | Doc ID: FH-DP1-PM-ITP004B Rev: 01
Project: MAPMP 2.0 DP1
Spray Seal | [11 empty] | Construction Process: Spray Sealing (Prime Coat, Primerseal and FibreDec) | [16 empty] | Prepared By: James Kremers
Client: Melbourne Airport (APAM) | [11 empty] | Specification: 60692389-PS-01-AV-0001 - Revision 1 (27 Mar 2023) | [16 empty] | Approved By: Noriko Wood
[12 empty] | Structure/Component: Asphalt Pavement | [16 empty] | Date: 29/08/2023
| Item No. |  |  | Task/Activity Description |  |  | Inspection/Test | [13 empty] | Action Point |  | Responsibility |  | Comments |  | Checked by:
[7 empty] | Freq. |  |  | Acceptance Criteria |  |  |  |  | Reference Documents/ Clause |  | Inspection/ Test Method |  | Conformance Record | [7 empty] | AECOM |  | FH |  | Date
| (e) |  |  | Minimum Temperature |  |  | Prior to commencing works |  |  | The primer must be applied only when the surface temperature of the base course is at least 15°C and is expected to remain in excess of 15°C for the duration of the application of the primer. |  |  |  |  | AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.2 |  | Verify |  | This ITP signed |  | IP |  | Spray Seal Engineer/ Supervisor
| (f) |  |  | Primer Application Rate |  |  | All works carried out |  |  | The primer must be applied to the base course surface at an application rate of at least residual bitumen of 1.2 L/m2, measured at 15°C for priming crushed rock base. |  |  |  |  | AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.4.2 |  | Verify |  | This ITP signed |  | IP |  | Spray Seal Supervisor
| (g) |  |  | Application of Primerseal Aggregate |  |  | All works carried out |  |  | The primerseal must penetrate the prepared surface uniformly. The residual bitumen on the surface must be sufficient to retain the sealing aggregate firmly, with no loose aggregate left on primerseal after rolling and sweeping. After rolling, the sealing aggregate must be embedded into the film of residual bitumen and the surface for no more than 50% of its Average Least Dimension. |  |  |  |  | AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.6 |  | Visual Inspection |  | This ITP signed |  | IP |  | Spray Seal Supervisor
| (h) |  |  | Removal of loose aggregate |  |  | All works carried out |  |  | The primerseal must be swept and surface to be dry prior to the application of the next treatment. Sweeping must leave no loose aggregate on the surface. |  |  |  |  | AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.6 |  | Visual Inspection |  | This ITP signed off |  | IP |  | Spray Seal Supervisor
| 6 |  |  | FibreDec Specific Items
[12 empty] | INSPECTION AND TEST PLAN | [16 empty] | Doc ID: FH-DP1-PM-ITP004B Rev: 01
Project: MAPMP 2.0 DP1
Spray Seal | [11 empty] | Construction Process: Spray Sealing (Prime Coat, Primerseal and FibreDec) | [16 empty] | Prepared By: James Kremers
Client: Melbourne Airport (APAM) | [11 empty] | Specification: 60692389-PS-01-AV-0001 - Revision 1 (27 Mar 2023) | [16 empty] | Approved By: Noriko Wood
[12 empty] | Structure/Component: Asphalt Pavement | [16 empty] | Date: 29/08/2023
| Item No. |  |  | Task/Activity Description |  |  | Inspection/Test | [13 empty] | Action Point |  | Responsibility |  | Comments |  | Checked by:
[7 empty] | Freq. |  |  | Acceptance Criteria |  |  |  |  | Reference Documents/ Clause |  | Inspection/ Test Method |  | Conformance Record | [7 empty] | AECOM |  | FH |  | Date
| (a) |  |  | FibreDec Box Check |  |  | Each Lot |  |  | Applicator box is clean and rubber skirts are free from binder/glass build up |  |  |  |  | CAG 010812 Section 2 |  | Visual Inspection |  | This ITP signed |  | IP |  | Spray Seal Engineer/ Supervisor
| (b) |  |  | Aggregate spreading |  |  | Each Lot |  |  | The correct aggregate spread rate shall be measured and assessed. |  |  |  |  | AGTP Part 4K 6.7 408.1 408.13.e |  | Verify |  | This ITP signed |  | IP |  | Spray Seal Engineer/ Supervisor
| (c) |  |  | Removal of loose aggregate |  |  | Each Lot |  |  | All areas – within 8 hours of sealing unless otherwise agreed with the Superintendent. NB: For seal of nominal size ≥ 10mm, < 40 loose stones/m2 to remain after removal of loose aggregate. For seal of nominal size ≤ 7mm, < 60 loose stones/m2 to remain afterwards. |  |  |  |  | VicRoads Technical Spec 408.14 |  | Visual Inspection |  | This ITP signed |  | IP |  | Spray seal Supervisor
| 7 |  |  | Post-Operation
| (a) |  |  | Records |  |  | Each Lot |  |  | Job completion report (Spray Sheets) to be submitted within seven days of completion of sealing works. |  |  |  |  | VicRoads Technical Spec 408.17 |  | Verify |  | Spray Sheet Record |  | IP |  | Spray Seal Engineer
| (b) |  |  | Primer Curing |  |  | Each Lot |  |  | Following the application of the primer, the surface must be allowed to cure without being disturbed for a period of not less than 48 hours or longer as may be necessary to attain penetration into the surface and evaporation of the volatiles from the primer. |  |  |  |  | AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.4.4 |  | Verify |  | This ITP signed |  | IP |  | Spray Seal Engineer
[12 empty] | INSPECTION AND TEST PLAN | [16 empty] | Doc ID: FH-DP1-PM-ITP004B Rev: 01
Project: MAPMP 2.0 DP1
Spray Seal | [11 empty] | Construction Process: Spray Sealing (Prime Coat, Primerseal and FibreDec) | [16 empty] | Prepared By: James Kremers
Client: Melbourne Airport (APAM) | [11 empty] | Specification: 60692389-PS-01-AV-0001 - Revision 1 (27 Mar 2023) | [16 empty] | Approved By: Noriko Wood
[12 empty] | Structure/Component: Asphalt Pavement | [16 empty] | Date: 29/08/2023
| Item No. |  |  | Task/Activity Description |  |  | Inspection/Test | [13 empty] | Action Point |  | Responsibility |  | Comments |  | Checked by:
[7 empty] | Freq. |  |  | Acceptance Criteria |  |  |  |  | Reference Documents/ Clause |  | Inspection/ Test Method |  | Conformance Record | [7 empty] | AECOM |  | FH |  | Date
Comments
| ACTION POINT LEGEND: |  |  |  |  | HP/S HP/C WP AP IP TP SCP |  |  | HOLD POINT - SUPERINTENDENT HOLD POINT – CONTRACTOR (Internal FH)) WITNESS POINT APPROVAL POINT INSPECTION POINT TEST POINT SURVEY CONFORMANCE POINT |  |  |  |  | Work shall not proceed past the HP until released by the Superintendent Work shall not proceed past the HP* until released by FH An inspection point that may be witnessed by the Superintendent Written or verbal approval given by the Superintendent Formal Inspection activity to be undertaken and recorded Product compliance test to be undertaken and recorded/reported A qualified surveyor to check product/section/structure and report
| FINAL INSPECTION: (LOT CONFORMANCE SIGN OFF) | [7 empty] | This is to verify that the final inspection has been carried out in accordance with the FH’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications: Print Name: Position/Company: Signature: Date: