## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP004B – Spray Sealing | itp |  |  |  | Yes | ITP004B – Spray Sealing
section | 1. Bitumen
checkpoint | (a) Bitumen
label | Freq. - Delivery Docket upon request
label | Acceptance Criteria - Bitumen must be Class 170 complying with the requirements of AS 2008
label | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.4.2
label | Inspection/ Test Method - Verify
label | Conformance Record - This ITP signed
label | IP
label | Responsibility - Lab Manager/SS Engineer
checkpoint | (b) Bitumen Emulsion
label | Freq. - Delivery Docket upon request
label | Acceptance Criteria - Bitumen emulsion must comply with the requirements of AS 1160
label | ○ Testing of the bitumen emulsion, as per ITP Bitumen Emulsions Manufacture Feb 2019 for Surfix 70 (for FibreDec), shall be done prior to releasing the product.
label | ○ Ensure minimal storage time (ideally use within 24 hours of production).
label | Reference Documents/Clause - VicRoads Technical Spec 408.08 (b) ITP FH National – Bitumen Emulsions CAG 010812 Section 2
label | Inspection/ Test Method - Verify
label | Conformance Record - This ITP signed
label | IP
label | Responsibility - Lab Manager/SS Engineer
checkpoint | (c) Cutback Bitumen
label | Freq. - Delivery Docket upon request
label | Acceptance Criteria - Cutback bitumen must comply with the requirements of AS 2157 and must be Class AMC0 or AMC00
label | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.4.1
label | Inspection/ Test Method - Verify
label | Conformance Record - This ITP signed
label | IP
label | Responsibility - Lab Manager/SS Engineer
checkpoint | (d) PMB and Proprietary Bitumen
label | Freq. - Delivery Docket upon request
label | Acceptance Criteria - Viscosity-grade binders must comply with the requirements of AS/NZS 2008. The class of PMB shall comply with the requirements of Austroads Technical Specification ATS- 3110.
label | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.4.3
label | Inspection/ Test Method - Verify
label | Conformance Record - This ITP signed
label | IP
label | Responsibility - Lab Manager/SS Engineer
section | 2. Materials
checkpoint | (a) Cutter
label | Freq. - Delivery Docket upon request
label | Acceptance Criteria - Any primer which is not prepared in a refinery must be prepared by mixing bitumen and cutter at the site of the Works. The cutter must be commercial quality power kerosene or aviation turbine fuel (Jet A-1).
label | ○ No other type of cutter oil must be used under any circumstances. The cutter must be a clean, clear liquid containing no dissolved solids, foreign material or matter in suspension and must be liquid at 4°C.
label | ○ The Contractor must declare the amount of cutter used in the primer or primerseal to the Contract Administrator.
label | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.4.4
label | Inspection/ Test Method - Verify
label | Conformance Record - This ITP signed
label | IP
label | Responsibility - Lab Manager/SS Engineer
checkpoint | (b) Fibreglass
label | Freq. - Prior to commencing works
label | Acceptance Criteria - Ensure correct fibre is supplied.
label | Reference Documents/Clause - CAG 010812 Section 2
label | Inspection/ Test Method - Verify
label | Conformance Record - Fibreglass datasheet
label | IP
label | Responsibility - SS Engineer/ Supervisor
section | 3. Aggregate
checkpoint | (a) Aggregate Specification
label | Freq. - Delivery Docket upon request Maximum lot size 350t of same class and size
label | Acceptance Criteria - VicRoads Standard Specification Sections:
label | ○ 801 - Source Rock;
label | ○ 831 – Aggregate; and
label | ○ 832 - Sands
label | Reference Documents/Clause - VicRoads Technical Spec 408.11 (a)
label | Inspection/ Test Method - Verify
label | Conformance Record - This ITP signed
label | IP
label | Responsibility - Lab Manager/SS Engineer
checkpoint | (b) Aggregate Pre- coating Materials
label | Freq. - Delivery Docket upon request
label | Acceptance Criteria - Distillate based product, cutback bitumen, emulsion based product or proprietary product.
label | Reference Documents/Clause - VicRoads Technical Spec 408.09 (b) 408.11 (b)
label | Inspection/ Test Method - Verify
label | Conformance Record - This ITP signed
label | IP
label | Responsibility - Spray Seal Supervisor
section | 4. Operation
checkpoint | (a) Material Test Reports
label | Freq. - Prior to commencing works
label | Acceptance Criteria - Test reports for bitumen and proprietary emulsions must be submitted to the Contract Administrator.
label | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.4.7
label | Inspection/ Test Method - Verify
label | Conformance Record - This ITP signed
label | HP
label | Responsibility - Spray Seal Engineer / Contract Administrator / Principle’s Design Consultant
holdpoint | AUTHORITY HOLDPOINT
checkpoint | (b) Works Method Statement
label | Freq. - Prior to commencing works
label | Acceptance Criteria - The Contractor must submit a Works Method Statement (WMS) to the Contract Administrator.
label | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.1
label | Inspection/ Test Method - Verify
label | Conformance Record - This ITP signed
label | HP
label | Responsibility - Spray Seal Engineer / Contract Administrator / Principle’s Design Consultant
holdpoint | AUTHORITY HOLDPOINT
checkpoint | (c) Calibration of Bitumen Sprayer
label | Freq. - Prior to commencing works
label | Acceptance Criteria - Calibration Certificate to be provided.
label | Reference Documents/Clause - VicRoads Technical Spec 408.07 AECOM – MAPMP 2.0 DP1 Spec. Cl 11.3.3
label | Inspection/ Test Method - Verify
label | Conformance Record - This ITP signed & Compliance Certificate
label | HP*
label | Responsibility - Spray Seal Engineer/ Supervisor
checkpoint | (d) Commencement of works & Surface Preparation
label | Freq. - Prior to commencing works
label | Acceptance Criteria - Works shall not commence until the Contractor & Superintendent of works agree that the prepared surface is ready & fit for sealing.
label | ○ Surface is free of loose material and the surface is dry.
label | ○ Priming shall not be carried out within 24 hours of forecast rain.
label | Reference Documents/Clause - VicRoads Technical Spec 408.04 (b) 408.09 (d) AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.2, 11.5.3
label | Inspection/ Test Method - Verify
label | Conformance Record - This ITP signed
label | HP
label | Responsibility - Spray Seal Engineer / Contract Administrator / Principle’s Design Consultant
holdpoint | AUTHORITY HOLDPOINT
checkpoint | (e) Minimum Temperature
label | Freq. - Prior to commencing works
label | Acceptance Criteria - The primer must be applied only when the surface temperature of the base course is at least 15°C and is expected to remain in excess of 15°C for the duration of the application of the primer.
label | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.2
label | Inspection/ Test Method - Verify
label | Conformance Record - This ITP signed
label | IP
label | Responsibility - Spray Seal Engineer/ Supervisor
checkpoint | (f) Primer Application Rate
label | Freq. - All works carried out
label | Acceptance Criteria - The primer must be applied to the base course surface at an application rate of at least residual bitumen of 1.2 L/m2, measured at 15°C for priming crushed rock base.
label | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.4.2
label | Inspection/ Test Method - Verify
label | Conformance Record - This ITP signed
label | IP
label | Responsibility - Spray Seal Supervisor
checkpoint | (g) Application of Primerseal Aggregate
label | Freq. - All works carried out
label | Acceptance Criteria - The primerseal must penetrate the prepared surface uniformly. The residual bitumen on the surface must be sufficient to retain the sealing aggregate firmly, with no loose aggregate left on primerseal after rolling and sweeping.
label | ○ After rolling, the sealing aggregate must be embedded into the film of residual bitumen and the surface for no more than 50% of its Average Least Dimension.
label | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.6
label | Inspection/ Test Method - Visual Inspection
label | Conformance Record - This ITP signed
label | IP
label | Responsibility - Spray Seal Supervisor
checkpoint | (h) Removal of loose aggregate
label | Freq. - All works carried out
label | Acceptance Criteria - The primerseal must be swept and surface to be dry prior to the application of the next treatment. Sweeping must leave no loose aggregate on the surface.
label | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.6
label | Inspection/ Test Method - Visual Inspection
label | Conformance Record - This ITP signed off
label | IP
label | Responsibility - Spray Seal Supervisor
section | 6. FibreDec Specific Items
checkpoint | (a) FibreDec Box Check
label | Freq. - Each Lot
label | Acceptance Criteria - Applicator box is clean and rubber skirts are free from binder/glass build up
label | Reference Documents/Clause - CAG 010812 Section 2
label | Inspection/ Test Method - Visual Inspection
label | Conformance Record - This ITP signed
label | IP
label | Responsibility - Spray Seal Engineer/ Supervisor
checkpoint | (b) Aggregate spreading
label | Freq. - Each Lot
label | Acceptance Criteria - The correct aggregate spread rate shall be measured and assessed.
label | Reference Documents/Clause - AGTP Part 4K 6.7 408.1 408.13.e
label | Inspection/ Test Method - Verify
label | Conformance Record - This ITP signed
label | IP
label | Responsibility - Spray Seal Engineer/ Supervisor
checkpoint | (c) Removal of loose aggregate
label | Freq. - Each Lot
label | Acceptance Criteria - All areas – within 8 hours of sealing unless otherwise agreed with the Superintendent.
label | NB:
label | ○ For seal of nominal size ≥ 10mm, < 40 loose stones/m2 to remain after removal of loose aggregate.
label | ○ For seal of nominal size ≤ 7mm, < 60 loose stones/m2 to remain afterwards.
label | Reference Documents/Clause - VicRoads Technical Spec 408.14
label | Inspection/ Test Method - Visual Inspection
label | Conformance Record - This ITP signed
label | IP
label | Responsibility - Spray seal Supervisor
section | 7. Post-Operation
checkpoint | (a) Records
label | Freq. - Each Lot
label | Acceptance Criteria - Job completion report (Spray Sheets) to be submitted within seven days of completion of sealing works.
label | Reference Documents/Clause - VicRoads Technical Spec 408.17
label | Inspection/ Test Method - Verify
label | Conformance Record - Spray Sheet Record
label | IP
label | Responsibility - Spray Seal Engineer
checkpoint | (b) Primer Curing
label | Freq. - Each Lot
label | Acceptance Criteria - Following the application of the primer, the surface must be allowed to cure without being disturbed for a period of not less than 48 hours or longer as may be necessary to attain penetration into the surface and evaporation of the volatiles from the primer.
label | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.4.4
label | Inspection/ Test Method - Verify
label | Conformance Record - This ITP signed
label | IP
label | Responsibility - Spray Seal Engineer
checkpoint | Final Inspection
note | This is to verify that the final inspection has been carried out in accordance with the FH’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP