## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP004C – Asphalt Production (SP1 Patching Mix) | itp |  |  |  | Yes | ITP004C – Asphalt Production (SP1 Patching Mix)
section | 1. Preliminary Activities
checkpoint | 1.1 - Submission of Production Plan
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The production plan must demonstrate that the production capacity and the hot storage capacity of the mixing plant is sufficient to supply asphalt to complete the work undertaken within any work period on time.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.13.15.1
label | Inspection / Test Method - Verify
label | Record of conformity - Aconex Correspondence
label | HP
label | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Checking of Weighting Devices and Certificates
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The Contractor must supply details of current certification of weighing equipment including belt weighers and weighbridges to the Contract Administrator.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.13.15.6
label | Inspection / Test Method - Verify
label | Record of conformity - Aconex Correspondence
label | WP
label | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
label | Checked by: WP released as per DCWC Mgt- GCOR-001444
checkpoint | 1.3 - Calibration of the mixing plant
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Calibrating all necessary devices and parameters at the mixing plant to achieve the “Job Mix”. Established plants must provide historical records of the asphalt production over the previous one (1) month to verify consistency.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.13.15.11
label | Inspection / Test Method - Verify
label | Record of conformity - Historical records of asphalt production, This ITP signed
label | WP
label | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
label | Checked by: WP released as per DCWC Mgt- GCOR-001444
checkpoint | 1.4 - Aggregate Reference Samples
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The Reference Samples must be divided into two representative portions, with one being held by the Contractor and the second portion by the Principal’s Design Consultant until completion of the Works.
label | Minimum quantities for each aggregate fraction:
label | ○ 14mm: 50kg 10mm: 40kg 7mm: 30kg Dust: 20kg
label | ○ Sand: 20kg
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.16.2, Table 14-17
label | Inspection / Test Method - Verify
label | Record of conformity - Aconex Correspondence
label | HP
label | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Submission and review of mix design
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Submission and review of a mix design report detailing the mix which meets the requirements of the specification.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.11.4
label | Inspection / Test Method - Verify
label | Record of conformity - Aconex Correspondence
label | HP
label | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
label | Checked by: HP released as per DCWC Mgt- GCOR-001429
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Production Trial
label | Frequency - Prior to commencing construction trial
label | Acceptance Criteria - Successful trial of asphalt production with the mixing plant where the asphalt produced shows that the mix complies to the specification requirements.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.12.1
label | Inspection / Test Method - Verify
label | Record of conformity - Aconex Correspondence
label | HP
label | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
label | HP released as per DCWC Mgt- GCOR-001429
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Construction Trial
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The Contractor must subject all the placing, compaction and finishing equipment and operating and supervisory personnel proposed for use on the Works to a trial using the construction procedures proposed for the Work.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.12.3
label | Inspection / Test Method - Verify
label | Record of conformity - Aconex Correspondence
label | HP
label | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
label | Checked by: HP released as per DCWC Mgt- GCOR-001429
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Production and Construction Trial Report
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The Contractor must provide the Contract Administrator with a Production and Construction Trial Report detailing the results of both production and construction trials as well as all compliance testing.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.12.5
label | Inspection / Test Method - Verify
label | Record of conformity - Aconex Correspondence
label | HP
label | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
label | Checked by: HP released as per DCWC Mgt- GCOR-001429
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.9 - Nomination of Job Mix
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The Contractor must issue an updated asphalt mix design report with the details of the Job Mixture within 3 working days after completion of the construction trial.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.11.6
label | Inspection / Test Method - Verify
label | Record of conformity - Aconex Correspondence
label | HP
label | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
label | Checked by: HP released as per DCWC Mgt- GCOR-001429
holdpoint | AUTHORITY HOLDPOINT
section | 2. Coarse Aggregates Material Properties – Initial Testing
checkpoint | 2.1 - Particle Density
label | Frequency - Initial
label | Acceptance Criteria - Not less than 2300 kg/m3
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | Inspection / Test Method - AS 1141.6.1
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 2.2 - Water Absorption
label | Frequency - Initial
label | Acceptance Criteria - Not more than 2.0%
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | Inspection / Test Method - AS 1141.6.1
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 2.3 - Material Finer than 0.075mm in Aggregates (by washing)
label | Frequency - Initial
label | Acceptance Criteria - Not more than 2.0%
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | Inspection / Test Method - AS1141.11.1
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 2.4 - Particle Shape by Proportional Calliper (using a 3:1 ratio)
label | Frequency - Initial
label | Acceptance Criteria - Not more than 5.0% of misshapen particles
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | Inspection / Test Method - AS1141.14
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 2.5 - Flakiness Index (nominal 10 mm and larger aggregate)
label | Frequency - Initial
label | Acceptance Criteria - Maximum 25%
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | Inspection / Test Method - AS 1141.15
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 2.6 - Los Angeles Abrasion
label | Frequency - Initial
label | Acceptance Criteria - Not more than 25% loss (B or K Test Grading)
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | Inspection / Test Method - AS 1141.23
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 2.7 - Soundness (using Sodium Sulphate)
label | Frequency - Initial
label | Acceptance Criteria - Not more than 3% weighted loss
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | Inspection / Test Method - AS 1141.24
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 2.8 - Wet Strength
label | Frequency - Initial
label | Acceptance Criteria - Not less than 180kN
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | Inspection / Test Method - AS 1141.22
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 2.9 - Wet / Dry Strength Variation
label | Frequency - Initial
label | Acceptance Criteria - Not more than 25%
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | Inspection / Test Method - AS 1141.22
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 2.10 - Secondary Mineral Content
label | Frequency - Initial
label | Acceptance Criteria - Not more than 20% (Basic rock types only)
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | Inspection / Test Method - AS 1141.26
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 2.11 - Friable particles
label | Frequency - Initial
label | Acceptance Criteria - Not more than 0.2%
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | Inspection / Test Method - AS 1141.32
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 2.12 - Polished Aggregate Friction Value
label | Frequency - Initial
label | Acceptance Criteria - Not less than 48
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | Inspection / Test Method - AS 1141.41
label | Record of conformity - VicRoads Assigned Value
label | TP
label | Responsibility - Laboratory Technician
section | 3. Coarse Aggregates Material Properties – Ongoing Production Testing
checkpoint | 3.1 - Particle Size Distribution
label | Frequency - 1 per 500 tonnes aggregate
label | Acceptance Criteria - To be reported
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.1 Table 14-18
label | Inspection / Test Method - AS1141.11.1
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 3.2 - Apparent Particle Density
label | Frequency - 1 per 2000 tonnes aggregate
label | Acceptance Criteria - Not less than 2300 kg/m3
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.1 Table 14-18
label | Inspection / Test Method - AS 1141.6.1
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 3.3 - Flakiness Index (nominal 10 mm and larger aggregate)
label | Frequency - 1 per 1000 tonnes aggregate
label | Acceptance Criteria - Maximum 25%
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.1 Table 14-18
label | Inspection / Test Method - AS 1141.15
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 3.4 - Wet Strength
label | Frequency - 1 per 2500 tonnes aggregate
label | Acceptance Criteria - Not less than 180kN
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.1 Table 14-18
label | Inspection / Test Method - AS 1141.22
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 3.5 - Weak/Friable particles
label | Frequency - 1 per 1000 tonnes aggregate
label | Acceptance Criteria - Not more than 0.2%
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.1 Table 14-18
label | Inspection / Test Method - AS 1141.32
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 3.6 - Unsound Stone Content by Visual Assessment
label | Frequency - 1 per 5000 tonnes aggregate
label | Acceptance Criteria - To be reported
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.1 Table 14-18
label | Inspection / Test Method - RC 372.01
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
section | 4. Fine Aggregates Material Properties – Initial Testing
checkpoint | 4.1 - Particle Density
label | Frequency - Initial
label | Acceptance Criteria - Not less than 2300kg/m3
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-2
label | Inspection / Test Method - AS 1141.5
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 4.2 - Water Absorption
label | Frequency - Initial
label | Acceptance Criteria - Not more than 2.5% (crushed aggregate), Not more than 2.0% (uncrushed aggregate)
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-2
label | Inspection / Test Method - AS 1141.5
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 4.3 - Soundness (using Sodium Sulphate)
label | Frequency - Initial
label | Acceptance Criteria - Not more than 3% for any fraction
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-2
label | Inspection / Test Method - AS 1141.24
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 4.4 - Degradation Factor (Note: only applicable to dust)
label | Frequency - Initial
label | Acceptance Criteria - Not less than 60
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-2
label | Inspection / Test Method - AS 1141.25.3
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 4.5 - Plasticity Index
label | Frequency - Initial
label | Acceptance Criteria - Non-Plastic
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-2
label | Inspection / Test Method - AS 1289.3.3.1 (wet preparation)
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 4.6 - Linear Shrinkage
label | Frequency - Initial
label | Acceptance Criteria - Not more than 1%
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-2
label | Inspection / Test Method - AS 1289.3.4.1 (wet preparation)
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 4.7 - Methylene Blue Value (Crushed aggregate only)
label | Frequency - Initial
label | Acceptance Criteria - Not more than 5mg/gram
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-2
label | Inspection / Test Method - AS 1141.66
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 4.8 - Sand Equivalent (natural sands)
label | Frequency - Initial
label | Acceptance Criteria - Not less than 45
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-2
label | Inspection / Test Method - AS 1289.3.7.1
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 4.9 - Material Finer than 0.075mm in Aggregates
label | Frequency - Initial
label | Acceptance Criteria - Not more than 20%
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-2
label | Inspection / Test Method - AS 1141.11.1
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
section | 5. Fine Aggregates Material Properties – Ongoing Production Testing
checkpoint | 5.1 - Particle Size Distribution
label | Frequency - 1 per 500 tonnes aggregate
label | Acceptance Criteria - To be reported
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-19
label | Inspection / Test Method - AS1141.11.1
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 5.2 - Plasticity Index
label | Frequency - 1 per 1000 tonnes aggregate
label | Acceptance Criteria - Non-Plastic
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-19
label | Inspection / Test Method - AS 1289.3.3.1 (wet preparation)
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 5.3 - Linear Shrinkage
label | Frequency - 1 per 1000 tonnes aggregate
label | Acceptance Criteria - Not more than 1%
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-19
label | Inspection / Test Method - AS 1289.3.4.1 (wet preparation)
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 5.4 - Methylene Blue Value (Crushed aggregate only)
label | Frequency - 1 per 2000 tonnes aggregate
label | Acceptance Criteria - Not more than 5mg/gram
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-19
label | Inspection / Test Method - AS 1141.66
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
section | 6. Binder Testing – Jetbind E (PMB)
checkpoint | 6.1 - Bituminous Binder Sampling and Submission
label | Frequency - Every delivery of bitumen to the mixing plant
label | Acceptance Criteria - All samples of bitumen must be obtained in accordance with Appendix B of AS 2008.
label | ○ The samples shall consist of two (2) 0.5 litre (minimum) sealed containers labelled appropriately identifying the relevant lot and traceability to the source.
label | ○ These samples to be submitted to the Contract Administrator / Principal’s Design Consultant.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.5
label | Inspection / Test Method - AS 2008 Appendix B Verify
label | Record of conformity - This ITP signed / Aconex Correspondence
label | HP
label | Responsibility - Laboratory Technician / FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 - Viscosity at 165ºC
label | Frequency - 1 test per manufactured batch of binder (minimum 1 test per 250T of bitumen used)
label | Acceptance Criteria - To be reported
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.7
label | Inspection / Test Method - AG:PT/T111
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 6.3 - Torsional recovery at 25ºC, 30 s
label | Frequency - 1 test per manufactured batch of binder (minimum 1 test per 250T of bitumen used)
label | Acceptance Criteria - To be reported
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.7
label | Inspection / Test Method - AG:PT/T122
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 6.4 - Softening point
label | Frequency - 1 test per manufactured batch of binder
label | Acceptance Criteria - To be reported
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.7
label | Inspection / Test Method - AG:PT/T131
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 6.5 - Submission of binder test results
label | Frequency - 1 test per manufactured batch of binder
label | Acceptance Criteria - Completion of the specified set of tests on the binder and submission of the test results to the Contract Administrator / Principal’s Design Consultant.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.7
label | Inspection / Test Method - Verify
label | Record of conformity - NATA - accredited test certificate
label | HP
label | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint | AUTHORITY HOLDPOINT
section | 7. Asphalt Production Testing
checkpoint | 7.1 - Sampling
label | Frequency - Up to 100T: 1 test per work period / shift; 100T to 200T:
label | ○ 2 tests per work period / shift;
label | ○ Above 200T: 3 tests per work period / shift.
label | ○ Note: AECOM can request additional testing if any concerns are raised with the asphalt material during the works.
label | Acceptance Criteria - Mix to be sampled from asphalt delivery trucks.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.11, Table 14-21 Frequency amended as per DCWC Mgt-RTRFI- 000069
label | Inspection / Test Method - AS 2891.1.1
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 7.2 - Asphalt mix temperature
label | Frequency - Once per sample obtained as per Item 7.1 of this document
label | Acceptance Criteria - The temperature of the mix immediately following discharge from the mixer shall be within 10ºC of that nominated by the Contractor but shall not be greater than 175ºC (for polymer modified bitumen).
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.14.1
label | Inspection / Test Method - Verify
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 7.3 - Moisture content
label | Frequency - Once per sample obtained as per Item 7.1 of this document
label | Acceptance Criteria - To be reported
label | Reference Documents - FH Internal
label | Inspection / Test Method - RC 211.01
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 7.4 - Combined aggregate grading
label | Frequency - Once per sample obtained as per Item 7.1 of this document
label | Acceptance Criteria - Grading to be within the “job mix” envelope grading:
label | – – – – – – – – – – – – – –
label | Sieve Size (mm) ¦¦ Job Mix ¦¦ Job Mix Envelope
label | – – – – – – – – – – – – – –
label | 13.2 ¦¦ 100 ¦¦ 94 - 100
label | 9.5 ¦¦ 85 ¦¦ 79 - 91
label | 6.7 ¦¦ 72 ¦¦ 66 - 78
label | 4.75 ¦¦ 59 ¦¦ 54 - 64
label | 2.36 ¦¦ 45 ¦¦ 40 - 50
label | 1.18 ¦¦ 35 ¦¦ 31 - 39
label | 0.600 ¦¦ 26 ¦¦ 23 - 29
label | 0.300 ¦¦ 17 ¦¦ 15 - 19
label | 0.150 ¦¦ 10.3 ¦¦ 8.3 - 12.3
label | 0.075 ¦¦ 5.5 ¦¦ 4.0 - 7.0
label | – – – – – – – – – – – – – –
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.14.8, Table 14-14 Job Mix Formula as submitted in FHPL- GCOR- 000464
label | Inspection / Test Method - AS 2891.3.3
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 7.5 - Average Added Filler Content
label | Frequency - At the end of each production shift
label | Acceptance Criteria - Average added filler content to be within ± 0.2% of the “job mix” target.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.14.8, Table 14-14
label | Inspection / Test Method - Verify
label | Record of conformity - Batch Records
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 7.6 - Bitumen content
label | Frequency - Once per sample obtained as per Item 7.1 of this document
label | Acceptance Criteria - Within ± 0.3% of the “job mix” bitumen content by mass. From JMF: Within 5.2% - 5.8%
label | Reference Documents - DP1 Spec. Cl 14.14.8, Table 14-14 Job Mix Formula as submitted in FHPL-GCOR-464
label | Inspection / Test Method - AS 2891.3.3
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 7.7 - Average bitumen content
label | Frequency - At the end of each production shift
label | Acceptance Criteria - The Contractor shall determine the average bitumen content of each size of asphalt produced during each continuous mixing period or shift based on the total quantity of bitumen used and total asphalt produced.
label | ○ Average bitumen content must be not less than the bitumen content of the “job mix” (Job Mix Bitumen Content is 5.5%).
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.13.15.7, 14.14.8, Table 14-14 Job Mix Formula as submitted in FHPL- GCOR- 000464
label | Inspection / Test Method - Verify
label | Record of conformity - Batch Records
label | TP
label | Responsibility - Laboratory Technician / FH Project Engineer
checkpoint | 7.8 - Maximum density
label | Frequency - Once per sample obtained as per Item 7.1 of this document
label | Acceptance Criteria - To be reported
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.11
label | Inspection / Test Method - AS 2891.7.1
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 7.9 - Bulk density
label | Frequency - Once per sample obtained as per Item 7.1 of this document
label | Acceptance Criteria - To be reported
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.11
label | Inspection / Test Method - AS 2891.7.1
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 7.10 - Voids in mineral aggregate (VMA)
label | Frequency - Once per sample obtained as per Item 6.1 of this document
label | Acceptance Criteria - 15% minimum
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.14.8, Table 14-13
label | Inspection / Test Method - AS 2891.8
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 7.11 - Voids filled with bitumen (VFB)
label | Frequency - Once per sample obtained as per Item 6.1 of this document
label | Acceptance Criteria - 70% minimum to 80% maximum
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.14.8, Table 14-13
label | Inspection / Test Method - AS 2891.8
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 7.12 - Marshall Air Voids
label | Frequency - Once per sample obtained as per Item 6.1 of this document
label | Acceptance Criteria - 2.5% minimum to 4.5% maximum
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.14.8, Table 14-13 Job Mix Formula as submitted in FHPL- GCOR- 000464
label | Inspection / Test Method - AS 2891.8
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 7.13 - Marshall stability
label | Frequency - Once per sample obtained as per Item 6.1 of this document
label | Acceptance Criteria - 10kN minimum
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.14.8, Table 14-13
label | Inspection / Test Method - AS 2891.8
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 7.14 - Marshall flow
label | Frequency - Once per sample obtained as per Item 6.1 of this document
label | Acceptance Criteria - Report only
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.14.8, Table 14-13
label | Inspection / Test Method - AS 2891.8
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP