## Table 1
[9 empty] | Inspection and Test Plan – Control and Supervision of the Works | [13 empty] | Doc ID: FH-DP1-PM-ITP004D Rev: 00
Principal’s: Melbourne Airport (APAM) | [13 empty] | Contract No: CP1002 | [6 empty] | Prepared By: Michael Natalizio
Project: MAPMP 2.0: DP1 – Minor Asphalt Works | [17 empty] | Reviewed By: Noriko Wood |  |  |  |  | Date: 19/05/2022
Construction Process: Hot Mix Asphalt Production – Type H Shoulder Mix | [17 empty] | Approved By: Joseph Stella |  |  |  |  | Date: 19/05/2022
Specifications: 60692389-PS-01-AV-0001 - Revision 1 (27 Mar 2023)
Structure / Component: Asphalt Pavement
Lot No: |  | Lot Details: |  |  |  |  | Lot size/Quantity: | [12 empty] | Date:
Item No. |  | Task/Activity Description |  | Inspection/Test | [14 empty] | HP/ WP/ AP/IP/ TP/ SCP | Responsibility Project Engineer Superintendent Surveyor Foreman |  | Checked by:
|  |  |  | Frequency |  |  | Acceptance Criteria | [5 empty] | Reference Documents |  | Inspection / Test Method |  | Record of conformity |  |  |  |  | AECOM |  | FH | Date
1 |  | Preliminary Activities
1.1 |  | Submission of Production Plan |  | Prior to commencing works |  |  | The production plan must demonstrate that the production capacity and the hot storage capacity of the mixing plant is sufficient to supply asphalt to complete the work undertaken within any work period on time. | [5 empty] | AECOM – MAPMP 2.0 DP1 Spec. Cl 14.13.15.1 |  | Verify |  | Aconex Corresponde nce |  | HP | FH Project Engineer / Contract Administrator / Principal’s Design Consultant
1.2 |  | Checking of Weighting Devices and Certificates |  | Prior to commencing works |  |  | The Contractor must supply details of current certification of weighing equipment including belt weighers and weighbridges to the Contract Administrator. | [5 empty] | AECOM – MAPMP 2.0 DP1 Spec. Cl 14.13.15.6 |  | Verify |  | Aconex Corresponde nce |  | WP | FH Project Engineer / Contract Administrator / Principal’s Design Consultant
1.3 |  | Calibration of the mixing plant |  | Prior to commencing works |  |  | Calibrating all necessary devices and parameters at the mixing plant to achieve the “Job Mix”. Established plants must provide historical records of the asphalt production over the previous one (1) month to verify consistency. | [5 empty] | AECOM – MAPMP 2.0 DP1 Spec. Cl 14.13.15.11 |  | Verify |  | Historical records of asphalt production This ITP signed |  | WP | FH Project Engineer / Contract Administrator / Principal’s Design Consultant
1.4 |  | Submission and review of mix design |  | Prior to commencing works |  |  | Submission and review of a mix design report detailing the mix which meets the requirements of the specification. | [5 empty] | AECOM – MAPMP 2.0 DP1 Spec. Cl 14.11.4 |  | Verify |  | Aconex Corresponde nce |  | HP | FH Project Engineer / Contract Administrator / Principal’s Design Consultant
[9 empty] | Inspection and Test Plan – Control and Supervision of the Works | [13 empty] | Doc ID: FH-DP1-PM-ITP004D Rev: 00
Principal’s: Melbourne Airport (APAM) | [13 empty] | Contract No: CP1002 | [6 empty] | Prepared By: Michael Natalizio
Project: MAPMP 2.0: DP1 – Minor Asphalt Works | [17 empty] | Reviewed By: Noriko Wood |  |  |  |  | Date: 19/05/2022
Construction Process: Hot Mix Asphalt Production – Type H Shoulder Mix | [17 empty] | Approved By: Joseph Stella |  |  |  |  | Date: 19/05/2022
Specifications: 60692389-PS-01-AV-0001 - Revision 1 (27 Mar 2023)
Structure / Component: Asphalt Pavement
Item No. |  | Task/Activity Description |  | Inspection/Test | [14 empty] | HP/ WP/ AP/IP/ TP/ SCP | Responsibility Project Engineer Superintendent Surveyor Foreman |  | Checked by:
|  |  |  | Frequency |  |  | Acceptance Criteria | [5 empty] | Reference Documents |  | Inspection / Test Method |  | Record of conformity |  |  |  |  | AECOM |  | FH | Date
2 |  | Asphalt Production – Type H Shoulder Mix
2.1 |  | Temperature |  | Every loaded truck or at intervals of 15 minutes if more than one truck is dispatched in 15 minutes. |  |  | ≤175oC | [5 empty] | Section 407.11(a), 407.15 |  | Thermometer |  | Load inspection sheet / docket |  | TP | Plant Operator / Laboratory Technician
2.2 |  | Temperature |  | One test per 250 tonnes (or part thereof) if lot is >40 tonnes |  |  | ≤175oC | [5 empty] | Internal |  | Thermometer |  | Load inspection sheet / test report |  | TP | Laboratory Technician
2.3 |  | Visual inspection for segregation, uncoated particles, separated binder, excess binder or overheating |  | Every loaded truck |  |  | >95% coarse aggregate coated with binder, no obvious separated binder or uncoated particles | [5 empty] | Section 407.11 (b) |  | Visual Check |  | Load inspection sheet |  | TP | Plant Operator
[9 empty] | Inspection and Test Plan – Control and Supervision of the Works | [13 empty] | Doc ID: FH-DP1-PM-ITP004D Rev: 00
Principal’s: Melbourne Airport (APAM) | [13 empty] | Contract No: CP1002 | [6 empty] | Prepared By: Michael Natalizio
Project: MAPMP 2.0: DP1 – Minor Asphalt Works | [17 empty] | Reviewed By: Noriko Wood |  |  |  |  | Date: 19/05/2022
Construction Process: Hot Mix Asphalt Production – Type H Shoulder Mix | [17 empty] | Approved By: Joseph Stella |  |  |  |  | Date: 19/05/2022
Specifications: 60692389-PS-01-AV-0001 - Revision 1 (27 Mar 2023)
Structure / Component: Asphalt Pavement
Item No. |  | Task/Activity Description |  | Inspection/Test | [14 empty] | HP/ WP/ AP/IP/ TP/ SCP | Responsibility Project Engineer Superintendent Surveyor Foreman |  | Checked by:
|  |  |  | Frequency |  |  | Acceptance Criteria | [5 empty] | Reference Documents |  | Inspection / Test Method |  | Record of conformity |  |  |  |  | AECOM |  | FH | Date
2.4 |  | Visual inspection for segregation, uncoated particles, separated binder, excess binder or overheating |  | One test per 250 tonnes (or part thereof) if lot is >40 tonnes |  |  | >95% coarse aggregate coated with binder, no obvious separated binder or uncoated particles | [5 empty] | Internal |  | Visual Check |  | Load inspection sheet |  | TP | Laboratory Technician
2.5 |  | Maximum density |  | On every production day |  |  | ± 35 kg/m3 of its 6-point rolling average | [5 empty] | Section 407.11(e), 407.15 |  | AS2891.7.1 |  | NATA- accredited test certificate |  | TP | Laboratory Technician
2.6 |  | Binder content |  | One test per 250 tonnes (or part thereof) if lot is >40 tonnes |  |  | ±0.3% of mix design specification | [5 empty] | Section 407.10, 407.15 |  | AS2891.3.3 or AGPT/T234 |  | NATA- accredited test certificate |  | TP | Laboratory Technician
2.7 |  | Full sieve analysis |  | One test per 250 tonnes (or part thereof) if lot is >40 tonnes |  |  | See Table 1Table 1 of this document. | [5 empty] | Section 407.10, 407.15 |  | AS2891.3.3 or AGPT/T234 |  | NATA- accredited test certificate |  | TP | Laboratory Technician
2.8 |  | Moisture content |  | One test per 250 tonnes (or part thereof) if lot is >40 tonnes |  |  | ≤0.5% moisture | [5 empty] | Section 407.11 (b) |  | RC 211.01 |  | NATA- accredited test certificate |  | TP | Laboratory Technician
3 |  | RAP Testing (1) - RAP Level 1 and 2 (as per Table 407.121 Section 407)
[9 empty] | Inspection and Test Plan – Control and Supervision of the Works | [13 empty] | Doc ID: FH-DP1-PM-ITP004D Rev: 00
Principal’s: Melbourne Airport (APAM) | [13 empty] | Contract No: CP1002 | [6 empty] | Prepared By: Michael Natalizio
Project: MAPMP 2.0: DP1 – Minor Asphalt Works | [17 empty] | Reviewed By: Noriko Wood |  |  |  |  | Date: 19/05/2022
Construction Process: Hot Mix Asphalt Production – Type H Shoulder Mix | [17 empty] | Approved By: Joseph Stella |  |  |  |  | Date: 19/05/2022
Specifications: 60692389-PS-01-AV-0001 - Revision 1 (27 Mar 2023)
Structure / Component: Asphalt Pavement
Item No. |  | Task/Activity Description |  | Inspection/Test | [14 empty] | HP/ WP/ AP/IP/ TP/ SCP | Responsibility Project Engineer Superintendent Surveyor Foreman |  | Checked by:
|  |  |  | Frequency |  |  | Acceptance Criteria | [5 empty] | Reference Documents |  | Inspection / Test Method |  | Record of conformity |  |  |  |  | AECOM |  | FH | Date
3.1 |  | Moisture content of RAP |  | One test per 500 tonnes of RAP |  |  | Not exceeding the maximum moisture content acceptable for the asphalt plant nominated in the RAP Management Plan – Fulton Hogan Infrastructure Services. Any materials with moisture content greater than the nominated moisture content should be allowed to drain before being utilised. | [5 empty] | Section 407.13(c) FH RAP Managemen t Plan Section 3.2 |  | AS2891.10 |  | NATA- accredited test certificate |  | TP | Laboratory Technician / RAP Yard Supervisor
3.2 |  | Binder content of RAP |  | One test per 500 tonnes of RAP |  |  | ± 0.5 of target binder content 1 out of 10 consecutive results is allowed outside tolerance | [5 empty] | Section 407.13(c), 407.11 |  | AS2891.3.3 |  | NATA- accredited test certificate |  | TP | Laboratory Technician / RAP Yard Supervisor
3.3 |  | Sieve analysis of RAP |  | One test per 500 tonnes of RAP |  |  | See Table 2 Table 2 of this document. | [5 empty] | Section 407.13(c) |  | AS2891.3.3 |  | NATA- accredited test certificate |  | TP | Laboratory Technician / RAP Yard Supervisor
4 |  | RAP Testing (1) - RAP Level 2 (as per Table 407.121 Section 407)
[9 empty] | Inspection and Test Plan – Control and Supervision of the Works | [13 empty] | Doc ID: FH-DP1-PM-ITP004D Rev: 00
Principal’s: Melbourne Airport (APAM) | [13 empty] | Contract No: CP1002 | [6 empty] | Prepared By: Michael Natalizio
Project: MAPMP 2.0: DP1 – Minor Asphalt Works | [17 empty] | Reviewed By: Noriko Wood |  |  |  |  | Date: 19/05/2022
Construction Process: Hot Mix Asphalt Production – Type H Shoulder Mix | [17 empty] | Approved By: Joseph Stella |  |  |  |  | Date: 19/05/2022
Specifications: 60692389-PS-01-AV-0001 - Revision 1 (27 Mar 2023)
Structure / Component: Asphalt Pavement
Item No. |  | Task/Activity Description |  | Inspection/Test | [14 empty] | HP/ WP/ AP/IP/ TP/ SCP | Responsibility Project Engineer Superintendent Surveyor Foreman |  | Checked by:
|  |  |  | Frequency |  |  | Acceptance Criteria | [5 empty] | Reference Documents |  | Inspection / Test Method |  | Record of conformity |  |  |  |  | AECOM |  | FH | Date
[7 empty] | Viscosity of the blend of virgin and | [7 empty] | AGPT/T192 or AS 2341.2, AGPT/T193 |  | NATA- accredited test certificate
RAP binder shall fall within the
|  |  |  | One test per |  |  | range in the table below:
1000 tonnes
4.1 |  | Binder viscosity | [8 empty] | Binder Blend Viscosity Range (Pa.s @ 60°C) |  | Section 407.13(e) | [5 empty] | TP | Laboratory Technician
|  |  |  | lot of RAP used for Level 2 mixes as per Table 407.121 |  |  |  | Specified Binder Class
[8 empty] | C170 |  |  | 170 – 240
[8 empty] | C320 |  |  | 320 – 500
[8 empty] | C600 |  |  | 600 – 880
Final Inspection The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: Date: / /
Legend:
| HP | Hold Point |  |  | Work shall not proceed past the HP until released by the Superintendent | [10 empty] | IP | Inspection point |  |  | Formal Inspection to be done and recorded
| HP* | Fulton Hogan Hold Point |  |  | Work shall not proceed past the HP* until released by Fulton Hogan | [10 empty] | TP | Test Point |  |  | Product compliance test to be undertaken and recorded/reported
| WP | Witness Point |  |  | An inspection which must be witnessed by the Superintendent | [10 empty] | SCP | Survey conformance point |  |  | A qualified surveyor to check product/section/structure and report
| AP | Approval Point |  |  | Written or verbal approval given by the Superintendent
[9 empty] | Inspection and Test Plan – Control and Supervision of the Works | [13 empty] | Doc ID: FH-DP1-PM-ITP004D Rev: 00
Principal’s: Melbourne Airport (APAM) | [13 empty] | Contract No: CP1002 | [6 empty] | Prepared By: Michael Natalizio
Project: MAPMP 2.0: DP1 – Minor Asphalt Works | [17 empty] | Reviewed By: Noriko Wood |  |  |  |  | Date: 19/05/2022
Construction Process: Hot Mix Asphalt Production – Type H Shoulder Mix | [17 empty] | Approved By: Joseph Stella |  |  |  |  | Date: 19/05/2022
Specifications: 60692389-PS-01-AV-0001 - Revision 1 (27 Mar 2023)
Structure / Component: Asphalt Pavement
Notes (1): An approved RAP management plan addressing RAP stockpile management, RAP sampling and testing, RAP process control, RAP traceability, RAP binder blend viscosity (RAP Level 2) and asphalt plant capability shall be submitted to DoT at least 14 days prior to the asphalt works. No asphalt containing RAP shall be supplied until DoT approves the management plant. Table 1: Production tolerances for mix grading (Table 407.101 in DoT Section 407) 1. If post compaction grading is checked by binder extraction and sieve analysis after placement, the positive tolerances shall be increased by one percentage point. Table 2: RAP grading tolerances (Table 407.131 in DoT Section 407)
Sieve size AS (mm) |  |  | Tolerance on percentage passing (by mass)
|  |  | Size 7 |  | Size 10 |  | Size 14 |  |  | Size 20
37.5 |  |  | Nil |  | Nil |  | Nil |  |  | Nil
26.5 |  |  | Nil |  | Nil |  | Nil |  |  | Nil
19 |  |  | Nil |  | Nil |  | Nil |  |  | ± 6
13.2 |  |  | Nil |  | Nil |  | ± 6 |  |  | ± 6
9.5 |  |  | Nil |  | ± 6 |  | ± 6 |  |  | ± 6
6.70 - 4.75 |  |  | ± 6 |  | ± 6 |  | ± 6 |  |  | ± 6
2.36 – 0.600 |  |  | ± 5 |  | ± 5 |  | ± 5 |  |  | ± 5
0.300 – 0.150 |  |  | ± 3 |  | ± 3 |  | ± 3 |  |  | ± 3
0.075 |  |  | ± 1.0 |  | ± 1.0 |  | ± 1.0 |  |  | ± 1.0
Description | [5 empty] | Tolerance (from target grading) | [5 empty] | Allowable number of results outside of tolerance
Passing 26.5 mm sieve and larger | [5 empty] | ± 10 | [5 empty] | 1 out of 5 consecutive results
Passing 4.75 mm to 19.0 mm sieve | [5 empty] | ± 8 | [5 empty] | 1 out of 5 consecutive results
Passing 1.18 mm and 2.36 mm | [5 empty] | ± 6 | [5 empty] | 1 out of 5 consecutive results
Passing 0.300 mm and 0.600 mm | [5 empty] | ± 5 | [5 empty] | 1 out of 5 consecutive results
Passing 0.150 mm | [5 empty] | ± 3 | [5 empty] | 1 out of 5 consecutive results
Passing 0.075 mm | [5 empty] | ± 2 | [5 empty] | 1 out of 10 consecutive results