## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP004D – Asphalt Production (Type H Shoulder Mix) | itp |  |  |  | Yes | ITP004D – Asphalt Production (Type H Shoulder Mix)
section | 1. Preliminary Activities
checkpoint | 1.1 - Submission of Production Plan
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The production plan must demonstrate that the production capacity and the hot storage capacity of the mixing plant is sufficient to supply asphalt to complete the work undertaken within any work period on time.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.13.15.1
label | Inspection / Test Method - Verify
label | Record of conformity - Aconex Corresponde nce
label | HP
label | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Checking of Weighting Devices and Certificates
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The Contractor must supply details of current certification of weighing equipment including belt weighers and weighbridges to the Contract Administrator.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.13.15.6
label | Inspection / Test Method - Verify
label | Record of conformity - Aconex Corresponde nce
label | WP
label | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
checkpoint | 1.3 - Calibration of the mixing plant
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Calibrating all necessary devices and parameters at the mixing plant to achieve the “Job Mix”. Established plants must provide historical records of the asphalt production over the previous one (1) month to verify consistency.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.13.15.11
label | Inspection / Test Method - Verify
label | Record of conformity - Historical records of asphalt production, This ITP signed
label | WP
label | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
checkpoint | 1.4 - Submission and review of mix design
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Submission and review of a mix design report detailing the mix which meets the requirements of the specification.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.11.4
label | Inspection / Test Method - Verify
label | Record of conformity - Aconex Corresponde nce
label | HP
label | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint | AUTHORITY HOLDPOINT
section | 2. Asphalt Production – Type H Shoulder Mix
checkpoint | 2.1 - Temperature
label | Frequency - Every loaded truck or at intervals of 15 minutes if more than one truck is dispatched in 15 minutes.
label | Acceptance Criteria - ≤175oC
label | Reference Documents - Section 407.11(a), 407.15
label | Inspection / Test Method - Thermometer
label | Record of conformity - Load inspection sheet / docket
label | TP
label | Responsibility - Plant Operator / Laboratory Technician
checkpoint | 2.2 - Temperature
label | Frequency - One test per 250 tonnes (or part thereof) if lot is >40 tonnes
label | Acceptance Criteria - ≤175oC
label | Reference Documents - Internal
label | Inspection / Test Method - Thermometer
label | Record of conformity - Load inspection sheet / test report
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 2.3 - Visual inspection for segregation, uncoated particles, separated binder, excess binder or overheating
label | Frequency - Every loaded truck
label | Acceptance Criteria - >95% coarse aggregate coated with binder, no obvious separated binder or uncoated particles
label | Reference Documents - Section 407.11 (b)
label | Inspection / Test Method - Visual Check
label | Record of conformity - Load inspection sheet
label | TP
label | Responsibility - Plant Operator
checkpoint | 2.4 - Visual inspection for segregation, uncoated particles, separated binder, excess binder or overheating
label | Frequency - One test per 250 tonnes (or part thereof) if lot is >40 tonnes
label | Acceptance Criteria - >95% coarse aggregate coated with binder, no obvious separated binder or uncoated particles
label | Reference Documents - Internal
label | Inspection / Test Method - Visual Check
label | Record of conformity - Load inspection sheet
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 2.5 - Maximum density
label | Frequency - On every production day
label | Acceptance Criteria - ± 35 kg/m3 of its 6-point rolling average
label | Reference Documents - Section 407.11(e), 407.15
label | Inspection / Test Method - AS2891.7.1
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 2.6 - Binder content
label | Frequency - One test per 250 tonnes (or part thereof) if lot is >40 tonnes
label | Acceptance Criteria - ±0.3% of mix design specification
label | Reference Documents - Section 407.10, 407.15
label | Inspection / Test Method - AS2891.3.3 or AGPT/T234
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 2.7 - Full sieve analysis
label | Frequency - One test per 250 tonnes (or part thereof) if lot is >40 tonnes
label | Acceptance Criteria - See Table 1 Table 1 of this document.
label | – – – – – – – – – – – –
label | Table 1: Production tolerances for mix grading (Table 407.101 in DoT Section 407)
label | 1. If post compaction grading is checked by binder extraction and sieve analysis after placement, the positive tolerances shall be increased by one percentage point.
label | – – – – – – – – – – – –
label | Sieve size AS (mm) ¦¦ Tolerance on percentage passing (by mass)
label | Sieve size AS (mm) ¦¦ Size 7 ¦¦ Size 10 ¦¦ Size 14 ¦¦ Size 20
label | – – – – – – – – – – – –
label | 37.5 ¦¦ Nil ¦¦ Nil ¦¦ Nil ¦¦ Nil
label | 26.5 ¦¦ Nil ¦¦ Nil ¦¦ Nil ¦¦ Nil
label | 19.0 ¦¦ Nil ¦¦ Nil ¦¦ Nil ¦¦ ± 6
label | 13.2 ¦¦ Nil ¦¦ Nil ¦¦ ± 6 ¦¦ ± 6
label | 9.5 ¦¦ Nil ¦¦ ± 6 ¦¦ ± 6 ¦¦ ± 6
label | 6.70 - 4.75 ¦¦ ± 6 ¦¦ ± 6 ¦¦ ± 6 ¦¦ ± 6
label | 2.36 – 0.600 ¦¦ ± 5 ¦¦ ± 5 ¦¦ ± 5 ¦¦ ± 5
label | 0.300 – 0.150 ¦¦ ± 3 ¦¦ ± 3 ¦¦ ± 3 ¦¦ ± 3
label | 0.075 ¦¦ ± 1.0 ¦¦ ± 1.0 ¦¦ ± 1.0 ¦¦ ± 1.0
label | – – – – – – – – – – – –
label | Reference Documents - Section 407.10, 407.15
label | Inspection / Test Method - AS2891.3.3 or AGPT/T234
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | 2.8 - Moisture content
label | Frequency - One test per 250 tonnes (or part thereof) if lot is >40 tonnes
label | Acceptance Criteria - ≤0.5% moisture
label | Reference Documents - Section 407.11 (b)
label | Inspection / Test Method - RC 211.01
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
section | 3. RAP Testing - RAP Level 1 and 2 (as per Table 407.121 Section 407)
checkpoint-no-status | Notes
label | (1) An approved RAP management plan addressing RAP stockpile management, RAP sampling and testing, RAP process control, RAP traceability, RAP binder blend viscosity (RAP Level 2) and asphalt plant capability shall be submitted to DoT at least 14 days prior to the asphalt works. No asphalt containing RAP shall be supplied until DoT approves the management plant.
checkpoint | 3.1 - Moisture content of RAP
label | Frequency - One test per 500 tonnes of RAP
label | Acceptance Criteria - Not exceeding the maximum moisture content acceptable for the asphalt plant nominated in the RAP Management Plan – Fulton Hogan Infrastructure Services. Any materials with moisture content greater than the nominated moisture content should be allowed to drain before being utilised.
label | Reference Documents - Section 407.13(c) FH RAP Managemen t Plan Section 3.2
label | Inspection / Test Method - AS2891.10
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician / RAP Yard Supervisor
checkpoint | 3.2 - Binder content of RAP
label | Frequency - One test per 500 tonnes of RAP
label | Acceptance Criteria - ± 0.5 of target binder content, 1 out of 10 consecutive results is allowed outside tolerance
label | Reference Documents - Section 407.13(c), 407.11
label | Inspection / Test Method - AS2891.3.3
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician / RAP Yard Supervisor
checkpoint | 3.3 - Sieve analysis of RAP
label | Frequency - One test per 500 tonnes of RAP
label | Acceptance Criteria - See Table 2 Table 2 of this document.
label | – – – – – – – – – – – –
label | Table 2: RAP grading tolerances (Table 407.131 in DoT Section 407)
label | – – – – – – – – – – – –
label | Description ¦¦ Tolerance (from target grading) ¦¦ Allowable number of results outside of tolerance
label | – – – – – – – – – – – –
label | Passing 26.5 mm sieve and larger ¦¦ ± 10 ¦¦ 1 out of 5 consecutive results
label | Passing 4.75 mm to 19.0 mm sieve ¦¦ ± 8 ¦¦ 1 out of 5 consecutive results
label | Passing 1.18 mm and 2.36 mm ¦¦ ± 6 ¦¦ 1 out of 5 consecutive results
label | Passing 0.300 mm and 0.600 mm ¦¦ ± 5 ¦¦ 1 out of 5 consecutive results
label | Passing 0.150 mm ¦¦ ± 3 ¦¦ 1 out of 5 consecutive results
label | Passing 0.075 mm ¦¦ ± 2 ¦¦ 1 out of 10 consecutive results
label | – – – – – – – – – – – –
label | Reference Documents - Section 407.13(c)
label | Inspection / Test Method - AS2891.3.3
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician / RAP Yard Supervisor
section | 4. RAP Testing - RAP Level 2 (as per Table 407.121 Section 407)
checkpoint-no-status | Notes
label | (1) An approved RAP management plan addressing RAP stockpile management, RAP sampling and testing, RAP process control, RAP traceability, RAP binder blend viscosity (RAP Level 2) and asphalt plant capability shall be submitted to DoT at least 14 days prior to the asphalt works. No asphalt containing RAP shall be supplied until DoT approves the management plant.
checkpoint | 4.1 - Binder viscosity
label | Frequency - One test per 1000 tonnes lot of RAP used for Level 2 mixes as per Table 407.121
label | Acceptance Criteria - Viscosity of the blend of virgin and RAP binder shall fall within the range in the table below:
label | – – – – – – – – – – – –
label | Specified Binder Class ¦¦ Binder Blend Viscosity Range (Pa.s @ 60°C)
label | – – – – – – – – – – – –
label | C170 ¦¦ 170 – 240
label | C320 ¦¦ 320 – 500
label | C600 ¦¦ 600 – 880
label | – – – – – – – – – – – –
label | Reference Documents - Section 407.13(e)
label | Inspection / Test Method - AGPT/T192 or AS 2341.2, AGPT/T193
label | Record of conformity - NATA - accredited test certificate
label | TP
label | Responsibility - Laboratory Technician
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP