## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP - Pavement Rehabilitation - Gretna Corner |  |  |  |  | Yes | ITP - Pavement Rehabilitation - Gretna Corner | 1d111e5b-9dbc-428f-bcf2-e3d2c7a2e5f6
checkpoint-status |  |  | checkpoint | 2 - CONSTRUCTION – CERTIFICATE/TESTING/INSPECTION (HWIP)
checkpoint-status |  |  | checkpoint | 2.1 - Production Testing
checkpoint-status |  |  | checkpoint | 2.1.1 - Grading Binder Content Maximum Theoretical SG
label | 1f2e5e03-63c4-52f9-b795-70ef8b4129a5 |  | note | Frequency - 1 test sample per 200 tonnes
label | ef1d71aa-4925-5a1b-9620-2e41e8404cdf |  | note | Ref Docs -
label | ad25f63a-d7ef-555f-94c2-fd4fb292cb9c |  | note | Verification Method Requirement - Test Report
label | d636c948-2e74-5cb7-83a1-b09b38bff557 |  | note | Acceptance Criteria - As per Mix Design/JMF
label | c98880ff-f19f-524a-a34c-2cc867262821 |  | note | Action Point - IP
label | 2409b1b2-b601-5cc7-ac86-7e2afd2abb16 |  | note | Responsibility - Manufacturing Manager/Operator
checkpoint-status |  |  | checkpoint | 2.1.2 - Volumetric ( Air Voids, Bulk Density etc)
label | 4cbba3e6-294d-5149-9386-b26619cfdd09 |  | note | Frequency - 1 test sample per 600 tonnes
label | 7a4a99c1-d3ea-5430-9611-813c0b4c2b50 |  | note | Verification Method Requirement - Test Report
label | ea354dc2-ebdc-5ed6-b078-4b18799a871c |  | note | Acceptance Criteria - As per Mix Design/JMF
label | 8a525e9e-355b-51fe-9c61-269e8a93341f |  | note | Action Point - IP
label | 7fd95ce3-24b6-5d29-9088-9faa4d44b8d0 |  | note | Responsibility - Manufacturing Manager/Operator
checkpoint-status |  |  | checkpoint | 3 - On-site Testing
checkpoint-status |  |  | checkpoint | 3.1 - Digout
checkpoint-status |  |  | checkpoint | 3.1.2 - Visual Inspection of Digout Surface
label | 71a26dae-9fed-51c5-ab75-68f5bbea85e8 |  | note | Frequency - Site walk-over.
label | 38da4f56-3a73-512c-9017-09252d5874d4 |  | note | Verification Method Requirement - Visual & Photos
label | e80fc124-a68e-526a-b60b-b7bf5de0a09b |  | note | Acceptance Criteria - Area needs to be swept and free from debris and checked for any obvious cracks and there is no sign of any surface ponding
label | 3500d1cf-0057-5a9a-b3a6-af76616c00c2 |  | note | Action Point - IP
label | 72022a02-12ac-5c7f-92ae-99ead080c84c |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3.2 - Asphalt
checkpoint-status |  |  | checkpoint | 3.2.1 - Shape & Level
label | 3ec14ec2-fd24-517c-87a1-648edcfd1596 |  | note | Frequency - Each Truck
label | 236aba09-3914-567f-8b41-445a9bfd7acf |  | note | Verification Method Requirement - Daily QA spread rate Sheets
label | 0ef19130-b270-5fd1-abf4-f204750c70a3 |  | note | Acceptance Criteria - Individual asphalt layer shall comply with the following thickness tolerances: -0mm & +5mm
label | 276083c8-c1bf-500f-8d49-68979a45e593 |  | note | Action Point - HP
label | 96268838-8637-5787-92bd-163c3a37961e |  | note | Responsibility - Site/QA Engineer
checkpoint-status |  |  | checkpoint | 3.2.2 - Visual Inspection of AC20 Surfacing
label | 8b07d69d-462f-551f-b81b-06b02053657d |  | note | Frequency - Site walk-over.
label | d53b3e85-5f40-540b-8dd6-30c1b9f6f130 |  | note | Verification Method Requirement - Visual & Photos
label | f72dffec-0216-5acb-a0ef-0c2043ad7b3d |  | note | Acceptance Criteria - There are no obvious defects related to poorly constructed longitudinal or transverse joints. No areas of the completed surface have any depression that will allow water to pond where the specified levels are such that the slope is greater than 1 in 50. No visible cracking.
label | 2d570531-123b-5604-b2a2-c41f230ac130 |  | note | Action Point - IP
label | cf5ea67d-1198-5b83-8754-0d434a9b6e92 |  | note | Responsibility - Site/QA Engineer
checkpoint-status |  |  | checkpoint | 3.2.3 - Temperature - Asphalt for Paving
label | 27806308-a288-51bc-ade6-60be96777c9b |  | note | Frequency - 1 x Temp record per truck Load for every days paving
label | 849f507c-4337-5b84-b199-01dc22834893 |  | note | Ref Docs - In House
label | 14e70adb-da8a-5826-968d-3e130aeea4bd |  | note | Verification Method Requirement - Higgins Report
label | ff3348bb-aca9-5f0d-87e9-81d03490d1b6 |  | note | Acceptance Criteria - If trucks have been sitting for 3 hours or longer then they will be checked before going into the paver with asphalt probe Below 140 degree – call Manager Below 120 degree – Goes to waste.
label | a100f2cf-e193-54ee-917d-2108077890ce |  | note | Action Point - Hold Point
label | 1f4122fa-5928-51ca-acd2-3a798872b59f |  | note | Responsibility - Paving Supervisor & Site/QA Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2.4 - Tack Coat / Membrane Seal
label | 21e37f6d-e869-5dc4-8657-7aff60902560 |  | note | Frequency - A Spray sheet for every day
label | 698f1d72-bedc-52b1-9c20-4fc5f08894bd |  | note | Ref Docs - In House
label | 44079155-efb6-55ac-bc00-74786908fc71 |  | note | Verification Method Requirement - Spray Sheet
label | c076350f-a879-54b8-9a9f-03a3848e3625 |  | note | Acceptance Criteria - It must show as a minimum: area sprayed, litres sprayed, tank dip, Req. spray rate, Actual Spray rate, Chip Type, Material Sprayed, Date & Location, any cutters &/or Additives
label | d4e3574d-15c0-5eaa-ae5c-e67cd8ece587 |  | note | Action Point - IP
label | 2f5ef4d6-5385-5c6b-b9fb-86671d53b6ab |  | note | Responsibility - Site/QA Engineer
checkpoint-status |  |  | checkpoint | 3.2.5 - Nuclear Density Testing (NDM)
label | 8fbb83e3-0808-5f69-aea7-ed9b61a6bcb7 |  | note | Frequency - Random
label | fb442b6e-4a54-5436-8e0b-326e11afda89 |  | note | Ref Docs - In House
label | 1b21de8b-993c-517f-8a64-bb62465f6e15 |  | note | Verification Method Requirement - NDM Log Sheet
label | c62df534-9b5e-5e9d-b737-6586d2bda05b |  | note | Acceptance Criteria - This is for Internal QA checks to make sure adequate rolling is being achieved and rolling patterns are correct and being adhered to. We will be applying +3, -2 to the designed air voids for our checks.
label | 98be3174-d0b5-592c-ac9d-0ea0820b6006 |  | note | Action Point - IP
label | 0b2c259b-cb83-5367-b6b7-c25d48fe479d |  | note | Responsibility - Site/QA Engineer
checklist-flat |  |  | checklist | ITP - Basecourse Overlay & Stabilise | itp |  |  |  | Yes | ITP - Basecourse Overlay & Stabilise | 2270d4ae-d822-4922-ac45-52820692836c
checkpoint-status |  |  | checkpoint | Material - Approval of M4 AP40 Material for basecourse
label | cb37071a-98da-5a8f-8708-1edab397f0cb |  | note | Reference - TNZ M/4: 2006
label | e29a97e8-0c79-5e2e-a59a-27a43daccbe1 |  | note | Requirement - Quarry Material Test Results to meet standards and specification
label | 56a2f0d8-a403-5f7c-94e0-400d467a20ec |  | note | Frequency - 1 Test Every 10,000m3
label | 9fa391ea-cfb5-50b0-a920-2ef74080bd12 |  | note | Verify
label | 7f714402-942b-5fb2-9307-79185808c2dd |  | note | Responsibility - Project Manager/Project Engineer
text | 3d1a1574-4346-5bad-866a-6470de442921 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Material - UCS testing to confirm cement %
label | b18c0f80-63e0-5a37-a249-07f43be38c79 |  | note | Reference - Chapter 7 of AustStab (AustStab 2015).
label | 7aa86092-316d-5172-b73a-51f091220eb0 |  | note | Requirement - Test representative aggregate samples at 1%, 2% and 3% to determine optimum cement content
label | 5686c1c9-ee29-5651-a942-05ef7042bd3a |  | note | Frequency - Per Lot
label | 52ca9230-cd0a-5fa3-a6e6-7890d5795122 |  | note | Hold Point
label | 49ae7f29-acb3-5ede-9f8b-038a4bc4ff47 |  | note | Responsibility - NOC Renewals Manager
text | 13bae706-2e16-5b47-be4d-9da146acb56e |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Drainage - Driveway culverts, manholes etc
label | 94f83890-310c-596d-9258-c88ac801da00 |  | note | Requirement - As directed by NOC Renewal Manager
label | aa2ffe18-7741-5e39-9aad-f67581c8e5e0 |  | note | Frequency - On-Site confirmation
label | e8cf08b2-72b7-5d68-a008-78e2f00ee309 |  | note | Hold Point
label | 1d866012-ed3d-5e00-8679-3bb707bdcc79 |  | note | Responsibility - Site Supervisor/ NOC Renewals Manager
text | 7d9e7101-df7d-5069-9131-81870881e997 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Existing Seal Surface Removal - Saw cut existing road surface ends and rip with grader
label | 96c6aa60-068f-5da3-ad56-c7a80591ac9d |  | note | Requirement - Rip existing road surface layer
label | 4940a784-0675-5898-bca5-09d8a5cec8b9 |  | note | Frequency - As required. To be agree with NOC Renewals Manager
label | 3afa1011-f68d-5bb5-af78-b477f027a01c |  | note | Hold Point
label | 5577a82b-ad4a-5c91-9cab-8cb1e6f68d62 |  | note | Responsibility - Site Supervisor/ NOC Renewals Manager
text | 220cacd0-222f-567f-b0df-36612df24ff0 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Tie-In - Excavate & backfill
label | b230333d-3f58-5633-83c3-708a7068b67c |  | note | Requirement - Mark-out, excavate & backfill as directed by NOC
label | 47425b8e-3369-5467-b4a7-c5737ccbddfa |  | note | Frequency - As required. To be agree with NOC Renewals Manager
label | d5162f6b-a32c-56d0-90f6-8d0dc22d51e2 |  | note | Verify
label | e32715f2-7375-5904-a468-36920b74e88b |  | note | Responsibility - Site Supervisor/ NOC Renewals Manager
text | 5b1feb3c-fb2d-5d1e-b6a7-ad9525b0c94d |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Basecourse layer - Place Basecourse layer to design level
label | 625cda79-2371-5570-a18f-5386ca0e5881 |  | note | Reference - TNZ B/5:2008 - 7.3, 7.7 , 7.8
label | 07c1e25e-752b-5103-b991-dfd60c54d040 |  | note | Requirement - 150mm thick M4 AP40
label | 3ece2131-d4dc-5364-ae21-68cba63e267d |  | note | Frequency - Each Lot of Basecourse. Confirm with Survey Manager
label | b0e60caa-5cfe-59df-b35d-a0d99921ef95 |  | note | Verify
label | ca09440d-8036-520f-8bc3-756f56f98afe |  | note | Responsibility - Site Supervisor / Project Manager / Project Engineer/Survey Manager
text | 839f6992-da99-5877-80d6-cde1e1850562 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Approval to stabilise basecourse - Acceptance of basecourse layer
label | 4bfbf0da-5e02-55cd-9fd5-d5bdaf6ae85c |  | note | Reference - TNZ B/5:2008 - 7.2.1
label | 3ca75383-c896-5e0c-ae57-61a9cedbb4c3 |  | note | Requirement - NOC Renewals Manager to authorise stabilising to proceed
label | 59a62cac-0f27-56d5-b33a-291f16d12c89 |  | note | Frequency - Each section of stabilising
label | c0b3e913-0a51-5209-a272-0c5785a37d1e |  | note | Hold Point
label | edc575ac-5ce0-564e-bc3e-5b7ae85c8794 |  | note | Responsibility - NOC Renewals Manager
text | fcd578a2-3d99-549c-b88a-ee7492316744 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Cement Content Testing - Spreading of lime and/or cement
label | b5ba8a25-376f-59ed-af15-d9c34c95bcd3 |  | note | Reference - TNZ B/5:2008 - 7.3
label | 64d783e1-5d7e-51f8-a64e-fe7d0ce70c5d |  | note | Requirement - Mat test: (1 m2 canvas)
label | 58219216-327b-5b75-8fcf-0a93b6e6f5e3 |  | note | Within ±0.5 kg/m2 of the specified rate
label | 6d69f820-4059-5d06-a556-106b5bc3fd44 |  | note | Frequency - Every 500 m2
label | 7733bd1d-a5e8-513b-add2-ef536e8162d9 |  | note | Verify
label | 3b8627cb-5f11-5ed5-8726-4123cf36b2b0 |  | note | Responsibility - Site Supervisor / Foreman
label | bd757791-8473-5027-8e94-3d8e4144a6e3 |  | note | Check the weight of cement & take photos
text | fe4eb3c6-a0a1-5c3f-9924-88a8d7904c3c |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Stabilised Basecourse - Stabilised Basecourse
label | 0f0ffc62-35af-57fe-a005-033e1231b201 |  | note | Reference - TNZ B/5:2008 - 7.6
label | df2a279f-4281-5c99-8fa2-4d24c75426dd |  | note | Requirement - Stabilised Basecourse 250mm thick with 1.5% cement
label | 4f3ac6d8-6605-5091-9c14-e1cc8a773ba3 |  | note | Frequency - Cut depth shall be physically measured at both ends of the stabilising drum at least once every 200m along the cut length of miller run.
label | 401be580-aca4-59cb-8c77-518298d14f8a |  | note | Maximum variation from the specified depth of cut is –5 mm and +15 mm.
label | 8f38a4dd-34fb-566c-a28d-0bb43392b02a |  | note | Verify
label | 296ffc27-0879-5aec-b14f-812fc96c2300 |  | note | Responsibility - Site Supervisor / Foreman
label | 40f42f4c-e331-585a-bf4c-9ff64174dc02 |  | note | Check the depth of mill & take photos
text | 8cb511cb-725b-5a4d-967b-c48cf6f97ffe |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Plateau Density Tests - Acceptance criteria for stabilised layer compaction
label | bb270d43-966f-5aaa-ac9d-b3c97f316bba |  | note | Reference - TNZ B/5:2008 - 7.7.1
label | fc8bd37b-c60f-5e36-af99-d722da106bab |  | note | Requirement - The Contractor shall undertake plateau density tests for the purpose of determining the target density
label | ec96fcab-68ed-53d0-aadd-fdc9a57bcd26 |  | note | Frequency - One OWC/MDD test per 5000 m2.
label | 0b993a7d-2b0c-592f-bea7-2474d82c3079 |  | note | Hold Point
label | 310f0e9d-79a5-5372-8f0e-bdc2904f87b7 |  | note | Responsibility - Site Supervisor/ Project Engineer/ NOC Renewals Manager
label | c0abd7c4-962a-5b96-bf98-2102465917b3 |  | note | During construction, the agreed maximum dry density (MDD) for the stabilised material shall be determined by the Contractor and the Engineer using the test data obtained from the laboratory testing before construction, and the in-situ plateau density during construction.
text | ed4a4a12-7738-56c3-8594-dc6dd601e918 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Compaction Testing - Nuclear Density Test
label | 1480a6da-dca4-5255-820c-6507e46eebab |  | note | Reference - TNZ B/5:2008 - 7.7.1
label | 937ba7df-6176-5b54-9211-1542639b81a7 |  | note | Requirement - Base MDD - Average ≥ 98% - Minimum ≥ 95%
label | 58b6ef40-ac82-5851-b8bb-a0cf612aed02 |  | note | Frequency - 1 test every 20 lineal metres
label | 90b18ba8-1b14-53dd-b689-128e3f86b6a9 |  | note | Hold Point
label | 2a0bec36-9699-5c19-9571-99a49b912c2e |  | note | Responsibility - Project Engineer / NOC Renewals Manager
label | 7a12ec74-8c4f-51e1-bfb4-2cd4f7ae0390 |  | note | Engineer has to sent the results to NOC Renewal Manager for approval
text | 98cc1278-1c15-5273-b5c6-6b02802090f8 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Acceptance - Acceptance of Basecourse - visual inspection of surface
label | 7933f68b-d0ab-5f06-8370-7105a0a4d878 |  | note | Reference - TNZ B/5:2008-7.8
label | 3cdb43e6-c81a-561e-b7ca-b65ea7e02fb6 |  | note | Requirement - No Chipseal to be placed until acceptance of Basecourse layer by Engineer
label | a7345e5e-9ecd-5475-9e64-7a85bb567cb1 |  | note | Frequency - Per Lot
label | 151811fb-3323-5ca1-a0cf-86e97d7c81f8 |  | note | Hold Point
label | e444dc4d-adcf-597b-833f-5a64fe73f44a |  | note | Responsibility - Site Supervisor / NOC Renewals Manager
label | 26ca45e1-3115-5d1d-8950-972ecaf405b8 |  | note | Supervisor has to contact NOC Renewal Manager to approve the final basecourse.
text | 593e56d4-c941-5141-b5c2-681445dab375 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Basecourse Acceptance - Degree of saturation (DOS)
label | 63717315-bd8d-5161-8c32-a51f7de97c53 |  | note | Reference - TNZ B/5:2008
label | d9912a7d-66c3-5795-b2b6-5f49f48772b2 |  | note | Requirement - < 60% (or 80% on consultation with the pavement designer)
label | 9eace9b0-187e-5450-bc31-a5fbe4a166cf |  | note | Frequency - 5 (five) randomly selected areas
label | 978cb6ad-1251-5ef8-9249-f2408cbf13d6 |  | note | Hold Point
label | 48776ef8-279d-542a-8e17-d94d3d6b8a6a |  | note | Responsibility - Project Engineer / NOC Renewals Manager
label | a808bbfb-509e-521a-914d-664116cac0cd |  | note | Pavement layer compaction test results may be used for this purpose where the Engineer is satisfied that the water content has not had a chance to rise between testing and sealing. (i.e. it has not rained or additional watering has not been applied to the pavement).
text | 17faf2cc-5ae5-552f-b800-efeca5df0142 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Chip - Check chip in stockpile
label | 9dc8dcd0-9c06-500c-9ce2-24f7a5da66d0 |  | note | Requirement - confirm size, quantity, cleanliness
label | 81dfb7f0-0710-5bfc-a03f-8d6f52aba5d2 |  | note | Frequency - Per Lot
label | 4df03f59-e936-5309-a24c-396436165253 |  | note | Hold Point
label | 0b2a4e33-53bc-5d46-b8a4-e382bdca2b3a |  | note | Responsibility - Project Engineer / NOC Renewals Manager
text | 50fbf9cd-0502-5f0c-b4e1-3b2685f45a9b |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Sealing - Pre-surveyed seal area
label | 004a423b-a595-5988-b424-57ca2b347886 |  | note | Requirement - Prior to first coat, confirm seal extent and get confirmation from Renewals Manager
label | 8dca7044-6849-50b5-9b15-a7e405b9591e |  | note | Frequency - Per Lot
label | df7b10fd-fc01-595f-8888-7ee5024a6864 |  | note | Hold Point
label | cc6e5ea7-d9c5-5100-b0e4-159b91e8e7c2 |  | note | Responsibility - Project Engineer / NOC Renewals Manager
text | 17ce7fc9-b02b-5bbb-8ddd-caec4687fbe9 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checklist-flat |  |  | checklist | ITP - Construction |  |  |  |  | Yes | ITP - Construction - Gretna Corner | 301d22e8-84ae-40f3-83a8-ec18200ddc33
checkpoint-status |  |  | checkpoint | Material - Approval of M4 AP40 Material for basecourse
label | 1616dcd1-0497-53a3-8a41-a21f48aca17f |  | note | Reference - TNZ M/4: 2006
label | bc2f32d5-90c2-5629-8c33-1b4289203a38 |  | note | Requirement - Quarry Material Test Results to meet standards and specification
label | 768e61bb-0357-5e9e-b144-87534db3a370 |  | note | Frequency - 1 Test Every 10,000m3
label | 6becff9f-4aee-5c96-bd83-6a50c4280d5a |  | note | Hold Points - Verify
label | 9f447976-5b17-5220-964d-e6d897631f01 |  | note | Responsibility - Project Manager/Project Engineer
text | 794e4213-7b0f-508f-a0bd-f2f3a8b6becb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Drainage - Driveway culverts, manholes etc
label | b2cfbdda-c9ca-552c-a873-894fd97f48a4 |  | note | Requirement - As directed by NOC Renewal Manager
label | aaa28b28-fd11-521f-b8c7-7921d0665fa7 |  | note | Frequency - On-Site confirmation
label | 125c7909-ed07-518f-a863-7d546f94585a |  | note | Hold Points - Hold Point
label | 2eb4b481-c7bd-52d7-be56-37eac1af4f96 |  | note | Responsibility - Site Supervisor/ NOC Renewals Manager
label | e603f9d4-e670-5989-805c-8bb1603710d0 |  | note | Comments - 1 manhole cover is replaced
text | 8d59b42b-84e7-5867-a00b-acbef56a6ce5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Pavement Dig-outs to 180 mm - Excavate only to approved level
label | c8d786d8-61be-5ccb-81db-97585eb09975 |  | note | Requirement - Mark-out & excavate as directed by NOC
label | 393961f4-fe94-508a-bf06-83551791b0c9 |  | note | Frequency - On-Site confirmation
label | c0a09959-0feb-5d04-8ef4-84e41c6acabd |  | note | Hold Points - Hold Point
label | 03b8666f-97dc-5fe5-bf69-029c16d6cc35 |  | note | Responsibility - Site Supervisor/ NOC Renewals Manager
text | 8d401155-becf-5988-8f60-e8206ef249e1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Tie-In - Excavate & backfill
label | df9c0a77-934a-502d-9d2b-a7316bd6a076 |  | note | Requirement - Mark-out, excavate & backfill as directed by NOC
label | 5270433e-7088-551a-aa66-04429598ce0a |  | note | Frequency - As required. To be agree with NOC Renewals Manager
label | ff650c15-bb40-58f8-80ff-27afe65bc27f |  | note | Hold Points - Verify
label | 17526d57-16d1-560a-87ed-52550b5fc68d |  | note | Responsibility - Site Supervisor/ NOC Renewals Manager
text | ea78df5c-2c68-53f4-a0c3-5afc9236b5e3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Approval to stabilise subbase - Acceptance of subbase layer
label | 4f6bcf97-9829-5eca-bf28-5cc6a913de6c |  | note | Reference - TNZ B/5:2008 - 7.2.1
label | 4faf5422-5844-5291-9702-fc1d7ecdf887 |  | note | Requirement - NOC Renewals Manager to authorise stabilising to proceed
label | 534f7867-8541-5752-a4c5-8b2fe2e487bd |  | note | Frequency - Each section of stabilising
label | c09574a3-083e-5fde-b4d1-049ad42d1001 |  | note | Hold Points - Hold Point
label | c01b3dbd-a0c0-5735-990d-ec56e328aa32 |  | note | Responsibility - NOC Renewals Manager
text | a8b5d19f-55ca-50fb-9fda-341d4ffebb7c |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Cement Content Testing sub-base - Spreading of lime and/or cement
label | 58644803-f659-5f91-be74-84a88cf50d08 |  | note | Reference - TNZ B/5:2008 - 7.3
label | 80891110-cae4-5c19-bf99-346d802892c1 |  | note | Requirement - Mat test: (1 m2 canvas) Within ±0.5 kg/m2 of the specified rate
label | ffe28441-1399-520a-a85d-399adf4c6a26 |  | note | Frequency - Every 500 m2
label | 150e5917-a6d0-5de7-98bf-880c12b50aac |  | note | Hold Points - Verify
label | c9a4130a-d1de-5766-8540-2c7c59048bc5 |  | note | Responsibility - Site Supervisor / Foreman
label | a8136d1c-89f3-58f9-880f-1bbbbbd88877 |  | note | Comments - Check the weight of cement & take photos
text | b9998b6d-97c3-589e-b7a0-9a87a913a650 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Stabilised Subbase - Stabilised Subbase
label | 2de4d62b-0eb1-5e50-91f9-c7896296e119 |  | note | Reference - TNZ B/5:2008 - 7.6
label | ae70daeb-799c-5eb6-97a8-51d06cf24db7 |  | note | Requirement - Stabilised subbase 250mm thick 5% cement
label | 3c5724c8-2f25-50c6-88ce-b80ac48ba610 |  | note | Frequency - Cut depth shall be physically measured at both ends of the stabilising drum at least once every 200m along the cut length of miller run. Maximum variation from the specified depth of cut is –5 mm and +15 mm.
label | 758db18c-1a97-53dd-ab98-af80ccc56d81 |  | note | Hold Points - Verify
label | 008ef6b7-2eee-5bfe-9402-3759a47ce325 |  | note | Responsibility - Site Supervisor / Foreman
label | 3d18930a-e3cc-5644-8bc0-fb481c7c0164 |  | note | Comments - Check the depth of mill & take photos
text | 3d3d60fc-ff67-52c9-a246-9492ac6a6899 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Plateau Density Tests sub-base - Acceptance criteria for stabilised layer compaction
label | e44abcd1-936e-5fb2-b8e6-48a97fdaf2eb |  | note | Reference - TNZ B/5:2008 - 7.7.1
label | 55ee34f6-2a1e-533b-94de-794d2163a88a |  | note | Requirement - The Contractor shall undertake plateau density tests for the purpose of determining the target density
label | e210250c-2b81-5b15-8d8d-91a40668f2f7 |  | note | Frequency - One OWC/MDD test per 5000 m2.
label | de1b4ea2-20a6-534a-93fe-23be853824f6 |  | note | Hold Points - Hold Point
label | 3d242d19-d7f8-517c-a436-6eb88813eb72 |  | note | Responsibility - Site Supervisor/ Project Engineer/ NOC Renewals Manager
label | d73a461c-8316-5e91-8fe0-87914c3686b4 |  | note | Comments - During construction, the agreed maximum dry density (MDD) for the stabilised material shall be determined by the Contractor and the Engineer using the test data obtained from the laboratory testing before construction, and the in-situ plateau density during construction.
text | a3e814b2-fbcf-5b76-ac58-3ae32545097c |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Compaction Testing sub-base - Nuclear Density Test
label | 880a4736-4d3a-5686-8371-8b5cae368b31 |  | note | Reference - TNZ B/5:2008 - 7.7.1
label | a1d17a16-86c4-57b8-ac7e-fb8f1db841a3 |  | note | Requirement - Base MDD - Average ≥ 98% - Minimum ≥ 95%
label | 95253a86-c4b6-58bc-a30e-fb624ef94cda |  | note | Frequency - 1 test every 20 lineal metres
label | e2a8d00d-a82e-5184-ac8e-ad2ab2593553 |  | note | Hold Points - Hold Point
label | 2cf30297-360b-5ab7-9450-fcf2afb218e6 |  | note | Responsibility - Project Engineer / NOC Renewals Manager
label | 8447111a-7ae8-57e2-a4bf-4d64f44b359b |  | note | Comments - Engineer has to sent the results to NOC Renewal Manager for approval
text | 4f549d34-81a2-5c4e-be85-23d2e1803a85 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Subbase Acceptance - Acceptance of subbase - visual inspection of surface
label | dd496f40-20f6-5ddc-8dda-c5abd5ef5143 |  | note | Reference - TNZ B/5:2008-7.8
label | 54730ebf-0ea6-5561-af8b-bdccaa0f6ec5 |  | note | Requirement - No Basecourse layer to be place until approval of subbase by Engineer
label | ed5a4faf-8fb6-5366-831d-104e309f14a1 |  | note | Frequency - Per Lot
label | 37e411ff-aac4-5c8d-b21f-51a02d113332 |  | note | Hold Points - Hold Point
label | b4000e7d-72e5-5227-8338-2b2168ccfb9c |  | note | Responsibility - Site Supervisor / NOC Renewals Manager
label | 3457b939-c30e-5e9d-a556-b7a80bc092f8 |  | note | Comments - Supervisor has to contact NOC Renewal Manager to approve the final basecourse.
text | 30373540-fd66-5717-b5d0-883445c1138a |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Subbase Acceptance - Degree of saturation (DOS)
label | dcd147ef-b18a-5d31-9482-9439f4b27f08 |  | note | Reference - TNZ B/5:2008
label | ef822a33-dbad-5bf9-94d1-066a334b87e7 |  | note | Requirement - < 60% (or 80% on consultation with the pavement designer)
label | 3f256d98-2a13-5679-a04e-536df82f287f |  | note | Frequency - 5 (five) randomly selected areas
label | 27aa73cf-408a-5383-8c52-afdebdadacef |  | note | Hold Points - Hold Point
label | 1cee1e71-e081-5e8c-a4ee-5d49069dccc4 |  | note | Responsibility - Project Engineer / NOC Renewals Manager
label | 804f0b83-a979-5df8-9b5c-2ba3f7f18228 |  | note | Comments - Pavement layer compaction test results may be used for this purpose where the Engineer is satisfied that the water content has not had a chance to rise between testing and sealing. (i.e. it has not rained or additional watering has not been applied to the pavement).
text | db6030f5-6dfb-5c28-9683-f78054b51cd5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Basecourse layer - Place Basecourse layer to design level
label | df07a914-00f4-523a-8905-5e83edf38c24 |  | note | Reference - TNZ B/5:2008 - 7.3, 7.7 , 7.8
label | 8c5caa83-4bd4-51f2-af68-a25e92ca7e16 |  | note | Requirement - 180mm thick AP40 (average depth)
label | 5edcaa37-bc3d-5fc8-b8c7-7299f6d55a79 |  | note | Frequency - Each Lot of Basecourse. Confirm with Survey Manager
label | 5bc319cb-5241-5647-87ac-e8d6ff6e4a7a |  | note | Hold Points - Verify
label | bca9553c-e05d-5bfa-a6b1-31e22263535d |  | note | Responsibility - Site Supervisor / Project Manager / Project Engineer/Survey Manager
text | 07145c70-30fc-5a42-ac21-1e823c3015f1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Approval to stabilise basecourse - Acceptance of basecourse layer
label | b3729b43-0fef-5aa9-9442-e0967289bd32 |  | note | Reference - TNZ B/5:2008 - 7.2.1
label | 4b19b833-b141-55cb-addc-baaf473947b8 |  | note | Requirement - NOC Renewals Manager to authorise stabilising to proceed
label | 93b16217-4993-510b-abf5-8328144b7343 |  | note | Frequency - Each section of stabilising
label | 921fdfdc-8582-5cd6-ba21-492282704104 |  | note | Hold Points - Hold Point
label | 9315ebea-dbdc-53f6-8524-48af9b88db3b |  | note | Responsibility - NOC Renewals Manager
text | f0b643cd-22c6-55a0-8082-4c8a4eb81311 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Cement Content Testing - Spreading of lime and/or cement
label | e80dab1f-d98d-5e08-9362-837784e78255 |  | note | Reference - TNZ B/5:2008 - 7.3
label | c72e54c7-5959-51ee-853a-1d1d6e505ed9 |  | note | Requirement - Mat test: (1 m2 canvas) Within ±0.5 kg/m2 of the specified rate
label | 9fb6f442-058b-5a7c-a4de-5b49af162a25 |  | note | Frequency - Every 500 m2
label | df1ac2c5-bfa9-59a5-80e7-2acfeff1a610 |  | note | Hold Points - Verify
label | 27a4a9e3-0824-5cc6-9b88-7c436694b2b7 |  | note | Responsibility - Site Supervisor / Foreman
label | 1e48633b-ab39-5ed5-97e8-36e18679733a |  | note | Comments - Check the weight of cement & take photos
text | 0908c289-fce6-5a6f-ba64-e8bf47b1270b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Stabilised Basecourse - Stabilised Basecourse
label | fddb1503-6f36-53ea-aeda-4bbbc7b40c31 |  | note | Reference - TNZ B/5:2008 - 7.6
label | 401d7047-0b98-5b46-849d-9961489d4044 |  | note | Requirement - Stabilised Basecourse 180mm thick with 1.5% cement
label | 23eef145-5611-56aa-9768-533ceade807b |  | note | Frequency - Cut depth shall be physically measured at both ends of the stabilising drum at least once every 200m along the cut length of miller run. Maximum variation from the specified depth of cut is –5 mm and +15 mm.
label | 1c1a5e0b-16c4-511b-a7d3-6bf13dc325df |  | note | Hold Points - Verify
label | 7c01d6d9-7cd2-5bbd-8e9d-6e06e03bc14f |  | note | Responsibility - Site Supervisor / Foreman
label | 0d45378b-1814-5941-86d9-c64cbe936db6 |  | note | Comments - Check the depth of mill & take photos
text | e021132a-eba7-565f-9d51-b07007e6cb4b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Plateau Density Tests - Acceptance criteria for stabilised layer compaction
label | 952f02f0-b14a-57be-b61c-9e864c02f093 |  | note | Reference - TNZ B/5:2008 - 7.7.1
label | 6452cc95-5473-52f4-910e-156e8018277f |  | note | Requirement - The Contractor shall undertake plateau density tests for the purpose of determining the target density
label | cea1b406-4531-5a66-adec-69f69376cdb3 |  | note | Frequency - One OWC/MDD test per 5000 m2.
label | 5c61d3b5-9fe9-571d-853f-375a247bdfb8 |  | note | Hold Points - Hold Point
label | 6caeed38-abdb-5a88-a9b5-4c1e0873c5d4 |  | note | Responsibility - Site Supervisor/ Project Engineer/ NOC Renewals Manager
label | 9a919a80-fd23-50d1-85a2-40e59cf3e742 |  | note | Comments - During construction, the agreed maximum dry density (MDD) for the stabilised material shall be determined by the Contractor and the Engineer using the test data obtained from the laboratory testing before construction, and the in-situ plateau density during construction.
text | 60d45b23-3e9d-5ec7-95b9-686d09c98e2f |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Compaction Testing - Nuclear Density Test
label | 29c75ee5-d591-561d-81e5-0ea521be723a |  | note | Reference - TNZ B/5:2008 - 7.7.1
label | feaef24b-6bcd-5bcb-a8ff-e0c556b2f92c |  | note | Requirement - Base MDD - Average ≥ 98% - Minimum ≥ 95%
label | 580d6610-7015-5691-b719-8c6cd99007c1 |  | note | Frequency - 1 test every 20 lineal metres
label | 6b4af1d1-2087-5267-b2bd-38dd1458660e |  | note | Hold Points - Hold Point
label | 5e5202d7-f24a-58c5-8fe0-02fe603204ef |  | note | Responsibility - Project Engineer / NOC Renewals Manager
label | eb7b0b95-29a4-5392-bf20-c9e735b71cd8 |  | note | Comments - Engineer has to sent the results to NOC Renewal Manager for approval
text | c02b58ae-6eaa-5065-b466-3926e224f770 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Acceptance - Acceptance of Basecourse - visual inspection of surface
label | 8542ab8d-e7c7-5ba1-b1c8-f1aca4ce02ed |  | note | Reference - TNZ B/5:2008-7.8
label | 71f5fbfa-25b2-55e9-878d-a91ccfefbbad |  | note | Requirement - No Chipseal to be placed until acceptance of Basecourse layer by Engineer
label | 9e7ac7a8-b841-51fa-85d3-4d3aa4d74bea |  | note | Frequency - Per Lot
label | 30e07476-0076-58c0-8c94-50acd2a778e1 |  | note | Hold Points - Hold Point
label | dc94d721-fb96-5314-bc89-5c00a639e160 |  | note | Responsibility - Site Supervisor / NOC Renewals Manager
label | 09519431-6680-5365-8873-91345bbe5725 |  | note | Comments - Supervisor has to contact NOC Renewal Manager to approve the final basecourse.
text | 4771c004-f30a-550d-9b6b-f9ee97261991 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Basecourse Acceptance - Degree of saturation (DOS)
label | 0b53fa74-e0e4-5d9d-ab29-ebf3c1841b67 |  | note | Reference - TNZ B/5:2008
label | 1c0b4f47-a004-51eb-a8b1-77dc1382332d |  | note | Requirement - < 60% (or 80% on consultation with the pavement designer)
label | 9a7db47b-59e9-574c-890d-1f87dbcf8eab |  | note | Frequency - 5 (five) randomly selected areas
label | 7efe0e11-131e-50f3-a53f-052e21462006 |  | note | Hold Points - Hold Point
label | ae61525c-714e-537d-8550-4735c7780ccf |  | note | Responsibility - Project Engineer / NOC Renewals Manager
label | dd8dd756-439a-505f-9016-e897cf54e142 |  | note | Comments - Pavement layer compaction test results may be used for this purpose where the Engineer is satisfied that the water content has not had a chance to rise between testing and sealing. (i.e. it has not rained or additional watering has not been applied to the pavement).
text | 69f3ca95-88e6-5c72-9e8a-45b903788a3c |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Works Completed and conforming
text | fa1f2dc3-69fa-5671-b1fc-9ad43c539c5a |  | textbox | Authorised By:
text | 76ecc787-bbfe-5a95-b1b0-420196004877 |  | textbox | Date:
label | 4355a497-cc07-5e4b-bed3-96ef23470fea |  | note | Ensure All relevant documents attached to Inspection Test Plan for Area of Works completed.
checklist-flat |  |  | checklist | ITP 2 - Sealing |  |  |  |  | Yes | ITP 2 - Sealing | 35444f26-50f5-4dcc-903d-2aede2c59f54
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | 2afd5524-4b03-5834-8fbe-61ea24a81427 |  | note | Reference - NZTA M/6 3.2
label | a12c2995-0497-54f2-b105-1a1b12ba2622 |  | note | Requirement - Crushing Resistance Test
label | 27519c60-04d9-59c4-975e-0103c94c2a73 |  | note | Frequency - 1 Test
label | b05f9273-9c60-5fca-bff8-06db4b3aea5a |  | note | Hold Points - T
label | f71151da-c376-55ad-b046-860699aa4ab2 |  | note | Responsibility - IANZ accredited laboratory
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | 78dfed5b-391c-5184-8ef3-fe7f82339d04 |  | note | Reference - NZTA M/6 3.3
label | 358cbe2d-0e72-5716-8356-67384db0b0c2 |  | note | Requirement - Weathering Quality Index Test
label | 95947bf3-82c1-5417-b65e-15e3d52baa4d |  | note | Frequency - 1 Test
label | 576652af-0e06-50e5-a540-f1805b166354 |  | note | Hold Points - T
label | 22db1e0a-6fa9-5506-ace0-776dd06c8dda |  | note | Responsibility - IANZ accredited laboratory
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | 4fd1a44e-593c-5955-ad21-4e8599953b83 |  | note | Reference - NZTA M/6 3.5
label | 6e6941bc-6545-5e61-87d6-1cea5ad27860 |  | note | Requirement - Polished Stone Value Test
label | 1aa4272e-265c-574c-bf65-cc0099017846 |  | note | Frequency - 1 Test
label | a66d799c-1a99-5b53-8a3f-b25b3121ce06 |  | note | Hold Points - T
label | 07278078-1595-53d3-8870-a92586e0c48d |  | note | Responsibility - Accredit PSV testing laboratory
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | 67e99f28-66d5-5ee4-9b9a-70a0c623e543 |  | note | Reference - NZTA M/6 4.1.1
label | 8782d4bb-a875-5668-8403-5d66be662ba7 |  | note | Requirement - Cleanliness Test
label | 9a5ed7cd-034e-58b5-ac0c-95852a8191c9 |  | note | Frequency - 1 Test
label | 74336ac9-0bfd-50bf-82ac-753708cbd4d8 |  | note | Hold Points - T
label | 4077b8f1-b952-54c8-a189-41b101c014b6 |  | note | Responsibility - IANZ accredited laboratory
checkpoint-status |  |  | checkpoint | Material - Bitumen
label | 823c92ef-ae1c-5659-8082-9f1e2a10b2b2 |  | note | Reference - NZTA M/1 Table 1
label | 1a870911-519d-59d5-8cd1-23be32d97b56 |  | note | Requirement - Confirm viscosity of bitumen
label | 2b3c3c5b-4840-5af9-8bda-5e975e3de4d1 |  | note | Frequency - 1 Test
label | 775acc36-67bd-567f-ab5d-b5b5fab5cb36 |  | note | Hold Points - T
label | 42d89d66-bba5-5cd4-9802-e25e80aee74a |  | note | Responsibility - IANZ accredited laboratory
checkpoint-status |  |  | checkpoint | Material - Bitumen
label | 66b34931-38f3-5816-8eb7-cc315dec68df |  | note | Reference - NZTA M/1 Table 1
label | cfb2a473-0c8f-518b-9f19-33b5a96c2da9 |  | note | Requirement - Confirm penetration grade of bitumen
label | 14b30761-22d0-5b3c-a295-291ae832b0fd |  | note | Frequency - 1 Test
label | d5568fc4-0668-5ed1-92df-0b7a62c1d166 |  | note | Hold Points - T
label | e5ca37d4-9c21-546b-9b48-e75b713f9569 |  | note | Responsibility - IANZ accredited laboratory
checkpoint-status |  |  | checkpoint | Material - Bitumen
label | 79c16126-ad62-5c10-b414-9c88ab6d6be6 |  | note | Reference - TNZ P/3 : 1996
label | 599c6106-a58a-5f5a-92c4-51483c794d10 |  | note | Requirement - Spray bitumen, then place chip and roll – refer design for chipseal grade
label | 77c8ef01-21ff-5f9d-83b8-945e7f311a84 |  | note | Frequency - 1 Test
label | e47688c8-7d09-5945-84aa-db06cf061eb8 |  | note | Hold Points - H
label | d21f8f99-8b89-5aa0-8227-6a2653073216 |  | note | Responsibility - Sealing Supervisor
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | 273b5b09-7d56-5972-96d7-d033fb650531 |  | note | Reference - TNZ P/3 : 1996
label | f35db1b6-80d8-5b7d-b6f8-b82cc9f34d50 |  | note | Requirement - Removal of loose chip
label | 5b31743a-b359-534e-aef9-c4e7afcf8de2 |  | note | Frequency - As per document
label | 3570e54d-2f03-5573-8619-d6145e1c592b |  | note | Hold Points - I
label | 91675f85-f667-5d00-840e-929e91fa590a |  | note | Responsibility - Sealing Supervisor
checkpoint-status |  |  | checkpoint | Line Marking
label | 8f17aba2-e12b-535c-86e5-52892e720e65 |  | note | Reference - TNZ P/12
label | e1eaeb2c-7a68-5868-bf7b-78babe4a13f0 |  | note | Requirement - Pavement markers/line marking
label | 1f2e0922-d034-536f-bd89-53b8a8546b6f |  | note | Frequency - As per document
label | bd31e639-3c7d-56ce-a1ba-d0ac22874774 |  | note | Hold Points - I
label | 4c765cb8-f6e4-53e4-b92a-f1c12f48df5d |  | note | Responsibility - Supervisor
checkpoint-status |  |  | checkpoint | Data
label | 5ba0730a-0bdb-53b3-b4a0-5338f7dbc585 |  | note | Reference - CMP Document
label | cabcf696-94a8-5189-bd36-730071c620ac |  | note | Requirement - Collection of RAMM data
label | 487562eb-ae18-5255-a73a-1aa731cbfe6f |  | note | Frequency - As per CMP Document
label | 45be038d-17a6-5451-80fc-a2dfafbd4bdd |  | note | Hold Points - H
label | 2f3d5303-7310-5939-bb19-97db58e3cfc6 |  | note | Responsibility - Supervisor
checkpoint-status |  |  | checkpoint | Works Completed and conforming
text | ac7306f5-eb16-5352-bcae-18a3971f57d9 |  | textbox | Authorised By:
text | c67fba33-5df8-5a1c-88eb-9bc7058b1205 |  | textbox | Date:
label | 0567ce9b-91b5-5431-a9dd-8bfe7909ea3e |  | note | Ensure All relevant documents attached to Inspection Test Plan for Area of Works completed.
checklist-flat |  |  | checklist | ITP - Basecourse Overlay & Stabilise | itp |  |  |  | Yes | ITP - Basecourse Overlay & Stabilise - Cambridge - AWPT | 3623b8d0-a3b3-4b44-86f8-2b0b97966b4f
checkpoint-status |  |  | checkpoint | Material - Approval of M4 AP40 Material for basecourse
label | f8b28cf9-cdab-59b5-b4c8-044a573bf68c |  | note | Reference - TNZ M/4: 2006
label | cf22f766-c030-55d1-b5e0-2a67d9bcace3 |  | note | Requirement - Quarry Material Test Results to meet standards and specification
label | 31106b7f-b710-5e8d-9234-158a684bdcc8 |  | note | Frequency - 1 Test Every 10,000m3
label | 5f131270-26f5-53ea-a205-b944a00b8d25 |  | note | Verify
label | 043273bb-9822-52f3-80e5-6cc8e9444f98 |  | note | Responsibility - Project Manager/Project Engineer
label | 56abde7c-58f4-51ca-99c4-9c00085e60cb |  | note | Check the depth of mill & take photos
text | b7471f3b-0ddb-5f76-97d4-c167e37d9299 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Material - UCS testing to confirm cement %
label | d448ef8b-60c3-5dd1-902e-6d1c3b0fbe8a |  | note | Reference - Chapter 7 of AustStab (AustStab 2015).
label | 5e1f1b59-c714-5180-860f-4c27fa6522fc |  | note | Requirement - Test representative aggregate samples at 1%, 2% and 3% to determine optimum cement content
label | 0ebf783c-25e6-5704-b56b-1fab22bf4144 |  | note | Frequency - Per Lot
label | a282253c-a34f-5ebb-9971-518842f6a2ab |  | note | Hold Point
label | 841a04f9-f6da-5547-aea8-03ab3c12d2cb |  | note | Responsibility - NOC Renewals Manager
label | 6f20aeaa-40f5-5133-93a6-d3ff6a14562c |  | note | Check the depth of mill & take photos
text | 36235a72-8452-54fd-b3f4-978bf04354b5 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Drainage - Driveway culverts, manholes etc
label | cc160397-5d8b-58b3-a782-d60b2441459e |  | note | Requirement - As directed by NOC Renewal Manager
label | 3679771a-5ef7-5e60-9d5a-a6e387231692 |  | note | Frequency - On-Site confirmation
label | bff7733a-e5d0-50d9-946c-cc29b21ea4a2 |  | note | Hold Point
label | 195b1833-3516-515a-a1a9-d1a034c7a88d |  | note | Responsibility - Site Supervisor/ NOC Renewals Manager
label | 894a9555-69cb-5a43-9cb0-ba78cbcd631c |  | note | Check the depth of mill & take photos
text | 87d25bc7-894b-5af2-a692-1b8e002e15ed |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Existing Seal Surface Removal - Saw cut existing road surface ends and rip with grader
label | cfbc455e-8105-58d0-8cd2-b7b1d25ea42e |  | note | Requirement - Rip existing road surface layer
label | aba77c0e-04c9-5ae2-8041-5bb2e89a5843 |  | note | Frequency - As required. To be agree with NOC Renewals Manager
label | 25035b86-9956-5254-9d01-ce41f141f8fa |  | note | Hold Point
label | 904c83d6-346b-5210-8748-a7a5da7e211d |  | note | Responsibility - Site Supervisor/ NOC Renewals Manager
label | c9050869-b4a0-500a-a154-6069cad2ee08 |  | note | Check the depth of mill & take photos
text | 8bd0e6fa-bc12-58b4-b325-0f3e142a1f8d |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Tie-In - Excavate & backfill
label | 6dc0a3f4-669a-5e8d-bfdb-394a3a54aee6 |  | note | Requirement - Mark-out, excavate & backfill as directed by NOC
label | 979b5bcd-d343-5e51-ab40-e0af909fa88e |  | note | Frequency - As required. To be agree with NOC Renewals Manager
label | eaf99478-e58d-5d67-a09b-3acd726af402 |  | note | Verify
label | 6ef62326-1483-52f8-8b2e-9bdfb478099f |  | note | Responsibility - Site Supervisor/ NOC Renewals Manager
label | f5517659-a8b7-59c7-a145-2b0aba1f040c |  | note | Check the depth of mill & take photos
text | e90472a6-0535-5766-9abb-e4babef40c75 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Basecourse layer - Place Basecourse layer to design level
label | 4c7370bf-fba0-5e55-8021-f1173db14f0c |  | note | Reference - TNZ B/5:2008 - 7.3, 7.7 , 7.8
label | 521c5323-e9f2-5943-b0ca-aac1c28e7c33 |  | note | Requirement - 150mm thick M4 AP40
label | 3ed02614-24b7-5e80-9af8-e0e7997cdb01 |  | note | Frequency - Each Lot of Basecourse. Confirm with Survey Manager
label | ca921fb9-9fac-5ffa-a597-de1f475df5a6 |  | note | Verify
label | 7ea46b4a-efb8-5b88-8d06-6310246a287c |  | note | Responsibility - Site Supervisor / Project Manager / Project Engineer/Survey Manager
label | 7c43c532-f119-53f3-8ba3-f12cd5b3d209 |  | note | Check the depth of mill & take photos
text | 62e5a55a-ce1f-5238-bcd5-9ac1f789edd6 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Approval to stabilise basecourse - Acceptance of basecourse layer
label | 9a45522e-1035-577b-8c55-ce6019029f19 |  | note | Reference - TNZ B/5:2008 - 7.2.1
label | 76808785-44a3-5a29-83b3-536b56adcb80 |  | note | Requirement - NOC Renewals Manager to authorise stabilising to proceed
label | a1f4567b-9747-59d9-a4f0-bdaac697aba6 |  | note | Frequency - Each section of stabilising
label | 4befd905-e0f4-5135-8beb-a827b97bd33c |  | note | Hold Point
label | eb5fe7b9-8b5d-5fa1-a917-c60a1518893e |  | note | Responsibility - NOC Renewals Manager
label | 92550c83-f7dd-5b80-bb10-25ff3dcfa84b |  | note | Check the depth of mill & take photos
text | e59a881b-0369-54ac-9898-13661160402f |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Cement Content Testing - Spreading of lime and/or cement
label | 65086f2a-28f3-5945-bea0-397651fe5003 |  | note | Reference - TNZ B/5:2008 - 7.3
label | 5cc186b1-8bd2-5a81-839a-15a5151d4362 |  | note | Requirement - Mat test: (1 m2 canvas) Within ±0.5 kg/m2 of the specified rate
label | 61aea4f0-f887-512c-8132-650981968d46 |  | note | Frequency - Every 500 m2
label | c1e485e4-9109-5440-80aa-a6ed5fffcf55 |  | note | Verify
label | 1b4f3d9a-c118-54ea-be36-30d1963e2293 |  | note | Responsibility - Site Supervisor / Foreman
label | 1e9a835d-cc3d-5562-a203-3f3de0b3f0dc |  | note | Check the depth of mill & take photos
text | 2268e92e-aadb-535b-a1e7-7dfc320e1bfc |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Stabilised Basecourse - Stabilised Basecourse
label | 1e0ea422-3d1a-5a4a-bffb-8d5e1bd87778 |  | note | Reference - TNZ B/5:2008 - 7.6
label | 35783792-7d95-5c5c-8ce2-83eb333a8206 |  | note | Requirement - Stabilised Basecourse 250mm thick with 1.5% cement
label | 380fee28-6e3a-56c7-a26d-486e3e5578be |  | note | Frequency - Cut depth shall be physically measured at both ends of the stabilising drum at least once every 200m along the cut length of miller run. Maximum variation from the specified depth of cut is –5 mm and +15 mm.
label | 0389a543-f2fa-55f9-b883-d07550f8b20d |  | note | Verify
label | 8415b1fa-9fe0-55ab-92d3-7fe0306f532d |  | note | Responsibility - Site Supervisor / Foreman
label | 0d0a926f-4765-5f87-8a00-c91f577aaf13 |  | note | Check the depth of mill & take photos
text | 82972e8c-01dc-57f0-9e42-947dea4b1f71 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Plateau Density Tests - Acceptance criteria for stabilised layer compaction
label | 392c2e3d-a1fc-5e9e-91cd-fdbf17e8b4b4 |  | note | Reference - TNZ B/5:2008 - 7.7.1
label | eb009c6d-9e68-5dc0-ab55-fe7ddca1ccf5 |  | note | Requirement - The Contractor shall undertake plateau density tests for the purpose of determining the target density
label | dbbfbfb2-eca0-5e2c-9dd8-f6602786df06 |  | note | Frequency - One OWC/MDD test per 5000 m2.
label | 15276118-4e6a-5c04-97a4-87dccfd068ff |  | note | Hold Point
label | fae2dbeb-be66-54ff-80ec-087e23ccc013 |  | note | Responsibility - Site Supervisor/ Project Engineer/ NOC Renewals Manager
label | 58f58e85-a757-561d-ae85-38671c9ff198 |  | note | Check the depth of mill & take photos
text | c835372a-7fd4-5d11-9ce0-75b37866061d |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Compaction Testing - Nuclear Density Test
label | 55e32469-1cb4-5564-9afa-6b0e61a058c4 |  | note | Reference - TNZ B/5:2008 - 7.7.1
label | bf8b18a8-99ec-5608-a969-b1c04325807d |  | note | Requirement - Base MDD - Average ≥ 98% - Minimum ≥ 95%
label | 27c449c6-2946-5dc5-b8bf-9a2e60c37a0d |  | note | Frequency - 1 test every 20 lineal metres
label | 77e848bc-99ad-52a3-912a-afb7bdfcd312 |  | note | Hold Point
label | e73554d6-874d-57c2-85a7-3e1a797aadb2 |  | note | Responsibility - Project Engineer / NOC Renewals Manager
label | 6a7de6ef-9eaf-5cdf-8d15-9e66d006a7ab |  | note | Check the depth of mill & take photos
text | 1bb0d2cf-1d37-50d9-a25d-c82a458fdf4d |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Acceptance - Acceptance of Basecourse - visual inspection of surface
label | 161d659f-42ca-5969-8940-d2f17574e5fa |  | note | Reference - TNZ B/5:2008-7.8
label | 84582e2c-09a7-550f-a21d-244081dd844b |  | note | Requirement - No Chipseal to be placed until acceptance of Basecourse layer by Engineer
label | 9a925655-36d9-5b3e-9bdb-9c3fa91f6032 |  | note | Frequency - Per Lot
label | 1a7e3559-cbca-5dfc-9f37-079953c83115 |  | note | Hold Point
label | 8febacf5-6ee7-5485-aa51-d1f6ff6be3eb |  | note | Responsibility - Site Supervisor / NOC Renewals Manager
label | dbe95412-a317-52ee-be46-bb7d7e1ac739 |  | note | Check the depth of mill & take photos
text | fc21cc0b-075f-532c-bbae-a91f15dfaa90 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Basecourse Acceptance - Degree of saturation (DOS)
label | 02e48476-2942-5511-9363-8cecd28f0e82 |  | note | Reference - TNZ B/5:2008
label | 0ec47a73-02e9-5083-a730-b6f064da742d |  | note | Requirement - < 60% (or 80% on consultation with the pavement designer)
label | 950c1bd1-5310-54da-abad-4bace284c77b |  | note | Frequency - 5 (five) randomly selected areas
label | 863a5cbe-4a83-54b3-ad97-06b3ac22a66c |  | note | Hold Point
label | 4fc9e627-09af-59c5-96d1-7d3dba68806b |  | note | Responsibility - Project Engineer / NOC Renewals Manager
label | ff84aa51-533f-5293-9c94-26f33319b4db |  | note | Check the depth of mill & take photos
text | c7d63bde-e61d-5834-bc76-0305c159d0d7 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Chip - Check chip in stockpile
label | 6681ec68-914a-5e97-960e-fb4221f4da0c |  | note | Requirement - confirm size, quantity, cleanliness
label | 25f6dc1f-70aa-5e0b-bb83-5ac997884037 |  | note | Frequency - Per Lot
label | 1baa4fae-2489-593f-aa4d-d2769aa4ec91 |  | note | Hold Point
label | 82a0ef6e-efcd-57a9-85f6-3f3363c829f8 |  | note | Responsibility - Project Engineer / NOC Renewals Manager
label | 25a8ce95-9ebf-580c-83b5-3bc019bdb411 |  | note | Check the depth of mill & take photos
text | c1f89f67-a033-5de2-a614-edaad0552cdf |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Sealing - Pre-surveyed seal area –
label | 5fa59d03-9be9-5ae9-9d5a-8340e4d021ea |  | note | Requirement - Prior to first coat, confirm seal extent and get confirmation from Renewals Manager
label | 0416de7d-a28e-5507-95ac-6acb99f1c8d8 |  | note | Frequency - Per Lot
label | 7418619b-1a6c-5507-bddb-b181d32c4724 |  | note | Hold Point
label | eb84af04-0432-5036-8d5a-7ead98ea9803 |  | note | Responsibility - Project Engineer / NOC Renewals Manager
label | 5f8df036-33f7-5978-9804-03880d2c6e0f |  | note | Check the depth of mill & take photos
text | 9e640543-72f9-5bbe-bd19-54c7069f2f63 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checklist-flat |  |  | checklist | Basecourse Overlay & Stabilise - SH2 Norsewood AWPT 2022 |  |  |  |  | Yes | Basecourse Overlay & Stabilise - SH2 Norsewood AWPT 2022 | 6330bbbb-bda1-4214-a7b5-6d66cd7e0add
checkpoint-status |  |  | checkpoint | Material-Approval of M4 AP40 Material for basecourse
label | 678edded-8a36-5307-bb0f-9337316c8817 |  | note | Reference-TNZ M/4: 2006
label | c5c6c063-ea49-5340-9aa1-8ab02c2ecb70 |  | note | Requirement-Quarry Material Test Results to meet standards and specification
label | bb741fe7-14db-5574-a5cb-935af04a14ea |  | note | Frequency-1 Test Every 10,000m3
label | 62710243-47b8-5aba-a166-2340e8f07a5f |  | note | Responsibility-Project Manager/Project Engineer
label | 3a9e2672-21fc-5575-8526-9cbe13454a58 |  | note | Verify
checkpoint-status |  |  | checkpoint | Material-Approval of AP65 Material for shoulder & subbase
label | ebf76144-e81f-5093-a997-d270fa865660 |  | note | Reference-AP65:2006
label | 097fdd50-b241-5033-942b-82d3ca617355 |  | note | Requirement-Quarry Material Test Results to meet standards and specification
label | 8aa01305-79ad-56d5-9ac8-ff9444ea5d2d |  | note | Frequency-1 Test Every 10,000m3
label | d9a47a38-2e65-536d-9ead-7091c2dc1c99 |  | note | Responsibility-Project Manager/Project Engineer
label | 19ad4a94-5fc2-5cda-be8e-c0542482e480 |  | note | Verify
checkpoint-status |  |  | checkpoint | Material-UCS testing to confirm cement %
label | 7e8ba5e0-410e-5618-868b-381e25d904ce |  | note | Reference-Chapter 7 of AustStab (AustStab 2015).
label | 17ab7de4-b9a5-54aa-8c70-579823eb07c6 |  | note | Requirement-Test representative aggregate samples at 1%, 2% and 3% to determine optimum cement content
label | bb0594a4-5df2-5629-95c6-ee974b1f2c07 |  | note | Frequency-Per Lot
label | a81a17df-d236-527d-ab69-cb739ec15908 |  | note | Responsibility-NOC Renewals Manager
label | b751a062-9c72-5c4e-bc0d-3f4a0eb5a6d6 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Shoulder-Approval of excavated surface before backfill
label | 9970b567-9e19-5e9d-86cd-986b84587fe3 |  | note | Requirement-Based on site conditions
label | cf33d8c8-71cc-5993-bcdb-f4a49cb6c65d |  | note | Frequency-As required.
label | 02a92d27-86ae-5cf8-a625-ac5b7dd1c1d0 |  | note | Responsibility-Site Supervisor / Project Manager / Project Engineer
label | 40b3dcca-6e74-5f14-9940-831974441ef6 |  | note | Verify
checkpoint-status |  |  | checkpoint | Shoulder-Backfill & compact shoulder
label | e2d86e75-b892-5cff-87fe-db19d1694d53 |  | note | Requirement-Basic compaction & efficient material usage
label | 08a9533a-e85e-5af1-b9b8-59cf93e6443f |  | note | Frequency-As required.
label | c7bb52a6-43b5-587a-a1b5-21160fa2258d |  | note | Responsibility-Project Manager / Project Engineer
label | d9f26d9b-2a2b-575f-8622-3694a4b5d501 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Drainage-Driveway culverts, manholes etc
label | 0741004c-bbed-5954-ade7-44c70b2077f3 |  | note | Requirement-As directed by NOC Renewal Manager
label | 8daf6507-3763-5fb5-9057-e82db05ec415 |  | note | Frequency-On-Site confirmation
label | f1119653-29a3-5c9a-b1a9-7be6b70a55bf |  | note | Responsibility-Site Supervisor/ NOC Renewals Manager
label | a91833f1-8585-53ca-a82d-5735e3c4a484 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Existing Seal Surface Removal-Saw cut existing road surface and remove
label | fb47f9cb-c1d7-53bb-a64b-782cbff0b4df |  | note | Requirement-Peel off existing road surface layer
label | cbe41ac8-d0e7-5301-921c-cb8fade8d129 |  | note | Frequency-As required. To be agree with NOC Renewals Manager
label | 4f5c8a7c-3154-5c72-94e2-624646886dfd |  | note | Responsibility-Site Supervisor/ NOC Renewals Manager
label | 024c8364-5765-5cca-b559-cd701327f2e8 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Pavement Dig-outs to 160 mm-Excavate only to approved level
label | f4f85b62-a9aa-5010-963a-ed2ee368b75f |  | note | Requirement-Mark-out & excavate as directed by NOC
label | d8e94ff2-5529-5c08-b751-d9b717dfb594 |  | note | Frequency-On-Site confirmation
label | 0fbc409f-2bc3-5ef4-9342-4d39e3dce795 |  | note | Responsibility-Site Supervisor/ NOC Renewals Manager
label | f93af69a-f53c-506c-8c47-a040f5268516 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Tie-In-Excavate & backfill
label | c9a77ef4-392c-5b5a-961d-085c5a811e13 |  | note | Requirement-Mark-out, excavate & backfill as directed by NOC
label | 8ae9c47d-5492-5312-874c-4b0d40165f69 |  | note | Frequency-As required. To be agree with NOC Renewals Manager
label | 314b3a4f-543f-5ec2-b8ea-49a31628be45 |  | note | Responsibility-Site Supervisor/ NOC Renewals Manager
label | 9a68729e-dc91-503b-afce-c3b8249fd6b1 |  | note | Verify
checkpoint-status |  |  | checkpoint | Approval to stabilise subbase -Acceptance of subbase layer
label | aeb95a65-b026-51ef-9d6f-2e7fa0115888 |  | note | Reference-TNZ B/5:2008 - 7.2.1
label | b1664902-f9ec-5470-a992-e290fc36d8af |  | note | Requirement-NOC Renewals Manager to authorise stabilising to proceed
label | 502a4908-d05d-5756-88c5-96d798ab19ae |  | note | Frequency-Each section of stabilising
label | 11db115b-e7d8-5da2-bb5c-3537ce920af1 |  | note | Responsibility-NOC Renewals Manager
label | 593ec05d-847e-5a06-bbd8-91416703b0d3 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Cement Content Testing-Spreading of lime and/or cement
label | 4c870c09-3042-5c39-ac62-d7d8ba1cc0dc |  | note | Reference-TNZ B/5:2008 - 7.3
label | 3622ad6c-fa0d-5efd-a8f3-3ac851314114 |  | note | Requirement-Mat test: (1 m2 canvas) Within ±0.5 kg/m2 of the specified rate
label | 365d502e-2dd1-5168-a190-2b740c4adfac |  | note | Frequency-Every 500 m2
label | 85bb649b-5299-56db-9cd7-c6835d981d81 |  | note | Responsibility-Site Supervisor / Foreman
label | ff821ac1-9824-56e7-813d-90daa785492d |  | note | Comments-Check the weight of cement & take photos
label | 85b4c670-0d25-5fd5-9e6b-cd8fde6165b1 |  | note | Verify
checkpoint-status |  |  | checkpoint | Stabilised Subbase-Stabilised Subbase
label | 5fcbf413-f892-525a-bdae-7bedc01e30a2 |  | note | Reference-TNZ B/5:2008 - 7.6
label | a980854a-5f10-5b81-b19d-062c1ea8a21d |  | note | Requirement-Stabilised subbase 200mm thick with 5% cement
label | e8158307-e453-554a-b75c-420e40ceca4c |  | note | Frequency-Cut depth shall be physically measured at both ends of the stabilising drum at least once every 200m along the cut length of miller run. Maximum variation from the specified depth of cut is –5 mm and +15 mm.
label | b2429cce-5502-5511-b3a7-4497b8c4442b |  | note | Responsibility-Site Supervisor / Foreman
label | d0e46d0d-7c23-5ec1-a35c-6156d688ce91 |  | note | Comments-Check the depth of mill & take photos
label | e80c8744-8aad-5d9a-9c14-4d5fc3b097b5 |  | note | Verify
checkpoint-status |  |  | checkpoint | Plateau Density Tests -Acceptance criteria for stabilised layer compaction
label | 2f0e95fc-ae66-52f6-a35e-4509fe5aa47d |  | note | Reference-TNZ B/5:2008 - 7.7.1
label | cd09e194-8280-58b9-b648-83c27c10ac15 |  | note | Requirement-The Contractor shall undertake plateau density tests for the purpose of determining the target density
label | 44aef223-8eb6-5e53-a45d-0c9d8a234234 |  | note | Frequency-One OWC/MDD test per 5000 m2.
label | 0ba15cf0-4cd7-52ba-b079-fb8d02a63369 |  | note | Responsibility-Site Supervisor/ Project Engineer/ NOC Renewals Manager
label | a380a9f2-9b0d-521b-8a0e-17afa841c6c6 |  | note | Comments-During construction, the agreed maximum dry density (MDD) for the stabilised material shall be determined by the Contractor and the Engineer using the test data obtained from the laboratory testing before construction, and the in-situ plateau density during construction.
label | 22c128a6-7186-549c-9cd8-4d98b17d62df |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Compaction Testing-Nuclear Density Test
label | e57e9ad0-18a8-5e1f-aad7-d788b2bb1405 |  | note | Reference-TNZ B/5:2008 - 7.7.1
label | df432347-2c33-5fc9-b6db-f7ddcf90510d |  | note | Requirement-Base MDD - Average ≥ 98% - Minimum ≥ 95%
label | d5082f5c-be9f-5d3c-b0b5-309521383a0b |  | note | Frequency-1 test every 20 lineal metres
label | bd124494-30f4-5092-9f26-2fc83f896f42 |  | note | Responsibility-Project Engineer / NOC Renewals Manager
label | 4cff8c89-57a1-5bb7-b6dc-953fba882a4e |  | note | Comments-Engineer has to sent the results to NOC Renewal Manager for approval
label | 3e965a9b-a94d-516e-9018-431bb6bde0fa |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Subbase Acceptance-Acceptance of subbase - visual inspection of surface
label | d67084a5-2ce5-523a-82f6-acc708b47f87 |  | note | Reference-TNZ B/5:2008-7.8
label | a5a3698c-0c02-5526-b157-117801e6ea55 |  | note | Requirement-No Basecourse layer to be place until approval of subbase by Engineer
label | b3c6e1f8-15bb-5d0d-b586-87c770d9157f |  | note | Frequency-Per Lot
label | 4942260f-3b62-5106-a21f-79efafdeb8bd |  | note | Responsibility-Site Supervisor / NOC Renewals Manager
label | b2b51c71-b465-557d-8067-b6805e909f53 |  | note | Comments-Supervisor has to contact NOC Renewal Manager to approve the final basecourse.
label | 796950e5-e49e-53ee-bfdb-ca74129ca0ed |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Subbase Acceptance-Degree of saturation (DOS)
label | c7624b05-5b1f-5ff0-ae55-be6183f5a6fd |  | note | Reference-TNZ B/5:2008
label | 03f41089-32f5-5d52-a4ba-221d65e89b67 |  | note | Requirement-< 60% (or 80% on consultation with the pavement designer)
label | 2b5343f5-2ba0-5bc0-b226-ca29dc62cdf7 |  | note | Frequency-5 (five) randomly selected areas
label | e3a5252b-bea9-59ef-b95e-774bd81d4616 |  | note | Responsibility-Project Engineer / NOC Renewals Manager
label | 113da1a1-d279-57d9-8ba8-28990555a2a6 |  | note | Comments-Pavement layer compaction test results may be used for this purpose where the Engineer is satisfied that the water content has not had a chance to rise between testing and sealing. (i.e. it has not rained or additional watering has not been applied to the pavement).
label | c3f31699-8452-5e24-b423-23ca3546893c |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Basecourse layer-Place Basecourse layer to design level
label | 0f30ef66-67d9-5569-b60b-b77b0f7f7cfc |  | note | Reference-TNZ B/5:2008 - 7.3, 7.7 , 7.8
label | 4b4f4ee9-9f3c-50f7-a7c8-f8c21169d840 |  | note | Requirement-160mm thick M4 AP40 (average depth)
label | 7aa32033-8ab5-5098-8cdc-3c76a0c0bb9c |  | note | Frequency-Each Lot of Basecourse. Confirm with Survey Manager
label | e3553473-410e-5a09-b245-c09fc37aac07 |  | note | Responsibility-Site Supervisor / Project Manager / Project Engineer/Survey Manager
label | 40a60371-703a-5e2d-adae-a4b282592dee |  | note | Verify
checkpoint-status |  |  | checkpoint | Approval to stabilise basecourse-Acceptance of basecourse layer
label | f7b1ed42-788a-532b-ac79-6198948a14c4 |  | note | Reference-TNZ B/5:2008 - 7.2.1
label | c218323b-f419-5006-95a2-6280cfb4be85 |  | note | Requirement-NOC Renewals Manager to authorise stabilising to proceed
label | b4d6d72e-57f6-5a53-9099-ac69ebadbb3e |  | note | Frequency-Each section of stabilising
label | 800afeeb-98bd-5267-a319-3d9646b03f05 |  | note | Responsibility-NOC Renewals Manager
label | ca46e421-f9d7-540f-b952-b475185e9110 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Cement Content Testing-Spreading of lime and/or cement
label | e2fd4e12-4a34-5bba-8461-422777a7f5cc |  | note | Reference-TNZ B/5:2008 - 7.3
label | 05590cf5-3730-5796-b430-1b9123f34736 |  | note | Requirement-Mat test: (1 m2 canvas) Within ±0.5 kg/m2 of the specified rate
label | 92b73ede-b379-53be-a057-83dec7a74055 |  | note | Frequency-Every 500 m2
label | 1711a722-2496-5492-9c5e-5a5d3a4bd422 |  | note | Responsibility-Site Supervisor / Foreman
label | 696e16a1-d495-599b-8a9b-2820d13bca2b |  | note | Comments-Check the weight of cement & take photos
label | 68ce9d48-1621-545b-a95b-32ff85bf7405 |  | note | Verify
checkpoint-status |  |  | checkpoint | Stabilised Basecourse-Stabilised Basecourse
label | 7049349f-0ea4-5fe5-b430-9790afcbb020 |  | note | Reference-TNZ B/5:2008 - 7.6
label | da096d0f-a231-58f1-a2c8-b3a4ce04b46a |  | note | Requirement-Stabilised Basecourse 160mm thick with 1.5% cement
label | 70c93e56-e381-5009-9bd3-46b0cde4e645 |  | note | Frequency-Cut depth shall be physically measured at both ends of the stabilising drum at least once every 200m along the cut length of miller run. Maximum variation from the specified depth of cut is –5 mm and +15 mm.
label | 9c1c21dc-dc3d-5b05-87fd-53a9cdf1d603 |  | note | Responsibility-Site Supervisor / Foreman
label | 1591cce6-f08b-5731-91b6-5cbe2a46c571 |  | note | Comments-Check the depth of mill & take photos
label | 69335aec-9966-52de-a0f1-5600021f0a4e |  | note | Verify
checkpoint-status |  |  | checkpoint | Plateau Density Tests -Acceptance criteria for stabilised layer compaction
label | 86fc3d5e-5244-5986-889f-2792a9d8a3fa |  | note | Reference-TNZ B/5:2008 - 7.7.1
label | d15f66b8-cbdf-52c0-88e5-741a6cf1cef6 |  | note | Requirement-The Contractor shall undertake plateau density tests for the purpose of determining the target density
label | bb29a87a-2c74-5e24-9a49-b01798e36d4e |  | note | Frequency-One OWC/MDD test per 5000 m2.
label | 4ed03c17-c018-52d4-af56-0dc06deb5416 |  | note | Responsibility-Site Supervisor/ Project Engineer/ NOC Renewals Manager
label | c19505ef-4340-5a94-9dfb-20a673129239 |  | note | Comments-During construction, the agreed maximum dry density (MDD) for the stabilised material shall be determined by the Contractor and the Engineer using the test data obtained from the laboratory testing before construction, and the in-situ plateau density during construction.
label | f2fedd6f-d2a1-5076-b570-7c2e0a8e94f2 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Compaction Testing-Nuclear Density Test
label | 5a32d458-ab91-5894-88fd-89309b27bc32 |  | note | Reference-TNZ B/5:2008 - 7.7.1
label | 2b889467-fd08-599d-b3f1-97ce67756a2b |  | note | Requirement-Base MDD - Average ≥ 98% - Minimum ≥ 95%
label | ada781ab-6884-5977-b805-13a8b335c1c5 |  | note | Frequency-1 test every 20 lineal metres
label | ea07b38a-3e29-57ef-8cef-1e6a4c00530c |  | note | Responsibility-Project Engineer / NOC Renewals Manager
label | 39bcfef8-49fe-5848-a702-83d17de42604 |  | note | Comments-Engineer has to sent the results to NOC Renewal Manager for approval
label | 5533c47e-5f5c-58c7-b363-f0be185d010a |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Acceptance-Acceptance of Basecourse - visual inspection of surface
label | 30b90996-179c-5334-85df-c1fff2f7e064 |  | note | Reference-TNZ B/5:2008-7.8
label | 18ca9bbb-3aa2-5462-bbf7-3877eb220284 |  | note | Requirement-No Chipseal to be placed until acceptance of Basecourse layer by Engineer
label | ffb644e5-6e4b-5818-b9b4-91d24479552c |  | note | Frequency-Per Lot
label | 197a3759-2ba6-5b8a-aea7-a9d0c3e5d4ce |  | note | Responsibility-Site Supervisor / NOC Renewals Manager
label | fd2b8b0a-0514-5440-a699-70fc2f8eabb7 |  | note | Comments-Supervisor has to contact NOC Renewal Manager to approve the final basecourse.
label | 5c8b96af-184c-578a-b622-5970d68a3aed |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Basecourse Acceptance-Degree of saturation (DOS)
label | dbf17b8e-d95f-5a2e-afed-fa24821a90a6 |  | note | Reference-TNZ B/5:2008
label | 0a7e6846-d578-5eed-8501-8e3bedb84de0 |  | note | Requirement-< 60% (or 80% on consultation with the pavement designer)
label | 1e400a77-3089-5a94-8076-7d47caf0fc58 |  | note | Frequency-5 (five) randomly selected areas
label | a96a4e52-5e65-5601-82bb-b89a1ff48cf3 |  | note | Responsibility-Project Engineer / NOC Renewals Manager
label | 1e23fb24-108e-588a-99c0-0e67891856bf |  | note | Comments-Pavement layer compaction test results may be used for this purpose where the Engineer is satisfied that the water content has not had a chance to rise between testing and sealing. (i.e. it has not rained or additional watering has not been applied to the pavement).
label | 92c1f52e-78ee-59ec-9a0b-19db06aec025 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Chip-Check chip in stockpile
label | c8266574-372f-5d16-967b-633bdec7cbc7 |  | note | Requirement-confirm size, quantity, cleanliness
label | 4543516e-9305-5ee1-9cb7-c6174d9cc9e1 |  | note | Frequency-Per Lot
label | 307256c3-dc2a-5fa8-84df-8f0c5ad0192b |  | note | Responsibility-Project Engineer / NOC Renewals Manager
label | e5b83ce2-16d2-50f5-a571-5abc792f2ff0 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Sealing-Pre-surveyed seal area –
label | 8e338520-64f0-555c-a271-2bef6396ef4d |  | note | Requirement-Prior to first coat, confirm seal extent and get confirmation from Renewals Manager
label | 57a04be7-a0d2-5fb7-99ab-58ebf36ece12 |  | note | Frequency-Per Lot
label | 81a5dc6b-512b-5421-8e60-eb2d26e38922 |  | note | Responsibility-Project Engineer / NOC Renewals Manager
label | 2f9cadee-007d-5e51-81dd-831e3b4c549e |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checklist-flat |  |  | checklist | ITP - Chipseal | itp |  |  |  | Yes | ITP - Chipseal - Cambridge - AWPT | 63c37543-2f9f-45f0-9f03-657f2df2f53d
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | 88d48f32-b685-526a-96ed-8a57a3796e2d |  | note | Reference - NZTA M/6 3.2
label | 54111b46-052e-5d50-baf1-ded45a1625a5 |  | note | Requirement - Crushing Resistance Test
label | 1c142fa0-27c0-59bc-a41d-ee226a426369 |  | note | Frequency - 1 Test
label | 6402fac0-87d1-5057-b10d-3ad06023ec2c |  | note | T
label | 5875a20b-97de-5ef1-8cef-a2a542722506 |  | note | Responsibility - IANZ accredited laboratory
label | bd62d391-1e66-5cf6-b451-31f4a5ede0af |  | note | Check the depth of mill & take photos
text | 9acbb0f6-dab2-5073-bb31-23edadedc660 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | e77d2dc2-bcc7-5df2-8625-8c30b3a1a873 |  | note | Reference - NZTA M/6 3.3
label | b1ef996c-6e93-50d4-ba61-1f057e04c8e6 |  | note | Requirement - Weathering Quality Index Test
label | cb919bcb-5c1a-5952-b87c-8471f7833964 |  | note | Frequency - 1 Test
label | 99f9093d-0c22-58c8-be87-329ba7ff0af0 |  | note | T
label | 9c86ffdd-f1fe-5d2b-ba8c-47f162172984 |  | note | Responsibility - IANZ accredited laboratory
label | 9a837db9-fbd0-5ddf-bd92-f4a6b4ec95ea |  | note | Check the depth of mill & take photos
text | 4d4fa1a9-fb44-51ea-b5b1-da2421b38386 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | 9f3a8ec2-8187-5463-af21-a5cb1b5e285b |  | note | Reference - NZTA M/6 3.5
label | 1fbcf92c-09df-5576-8133-4ebee7839f68 |  | note | Requirement - Polished Stone Value Test
label | 97eff5c0-0c4c-5250-bfde-0b6396edbf77 |  | note | Frequency - 1 Test
label | 39829f13-a89e-55ee-9d6a-cdbc1d5a6d23 |  | note | T
label | b0a47395-8053-5ad6-a3a9-d2df85884527 |  | note | Responsibility - Accredit PSV testing laboratory
label | 2a01323e-eef9-58be-9915-3bbe90ee3036 |  | note | Check the depth of mill & take photos
text | 66dbca11-ab52-582e-b5f7-7e8ae7f0cf57 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | 0031ae33-3c98-57fe-aa0f-bb4244d18d5c |  | note | Reference - NZTA M/6 4.1.1
label | 46a90149-5cac-5eac-b43e-74c22b2834d0 |  | note | Requirement - Cleanliness Test
label | 42b55649-358c-51b3-a000-4e4ef4d564ed |  | note | Frequency - 1 Test
label | 0454d5af-d60b-5074-b2c0-c5baf60cc160 |  | note | T
label | 47ee7dff-443b-545d-9a3d-e98e07f23389 |  | note | Responsibility - IANZ accredited laboratory
label | 8a5b9854-aeaa-5546-8284-2d962b7b4632 |  | note | Check the depth of mill & take photos
text | 0f81a0b1-3438-5e37-a255-c8a921e63f59 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Material - Bitumen
label | 7d834cae-5195-527b-a9bd-7f16e2e863d2 |  | note | Reference - NZTA M/1 Table 1
label | 8d9e0ab0-85d7-5da2-9a4d-225c37afb744 |  | note | Requirement - Confirm viscosity of bitumen
label | cf669ac1-7f12-543b-99e1-9892983b44fb |  | note | Frequency - 1 Test
label | 00b9be24-dc4c-5c1b-a2c1-84978fda8bd9 |  | note | T
label | de7b2284-d088-5ed0-85ba-134676d9911b |  | note | Responsibility - IANZ accredited laboratory
label | 51010f1c-3efb-507f-886a-2d4f3423b42b |  | note | Check the depth of mill & take photos
text | 5b49f79b-d82c-564f-8eab-2278935c9369 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | 90eee2a5-a443-59eb-a765-677a6e1fdd29 |  | note | Reference -
label | 8a1044fc-38bf-52d9-a996-a6b391d0a0ca |  | note | Requirement - Confirm site measurements
label | 8bbbe8bb-93af-5d04-a674-b7e2e4da91f9 |  | note | Frequency - Before sealing to take place
label | 1845a5f0-8878-5c9c-b5c4-4a25d63ff7bd |  | note | H
label | b12e4994-6d74-570b-a7c7-91ac4402b6ad |  | note | Responsibility - Sealing Manager / Supervisor
label | 2e4181e2-0c3b-52d5-8540-0629bb0ff3e9 |  | note | Check the depth of mill & take photos
text | 7fcfb243-e543-5dff-bcc8-452ab9fd853a |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | ccf6a7b7-c846-5a02-91b6-eee0dcfb529e |  | note | Reference -
label | f8ad6f88-71af-5620-a835-0159b9e5e1c9 |  | note | Requirement - Confirm stockpile area and correct grade of chip
label | 3100d3c0-ea41-56d6-a9cf-6772928a83cd |  | note | Frequency - Before sealing to take place
label | d7f1cfc5-330c-57a2-9bf8-37bd5634601f |  | note | H
label | 48dfa054-880f-58ab-8073-b3a274654b3e |  | note | Responsibility - Sealing Manager / Supervisor
label | ae9c1338-8bac-5934-bd0b-dc1831404609 |  | note | Check the depth of mill & take photos
text | f7bc3a64-51d2-5120-8454-f98e6de06939 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Material - Bitumen
label | 7f64e58b-e5a6-58cc-907e-5bc964750264 |  | note | Reference - NZTA M/1 Table 1
label | f1c830d6-709c-50e1-87c0-66aebdaf8ce9 |  | note | Requirement - Confirm penetration grade of bitumen
label | f1c81a94-4966-560a-b8e5-490dd8d8dc02 |  | note | Frequency - 1 Test
label | 1c7eedfe-e474-58a1-ad72-46e3d7da1241 |  | note | T
label | b4d853a3-edc2-52dc-8917-8d447745b1d6 |  | note | Responsibility - IANZ accredited laboratory
label | 35f73835-9e1e-5431-a555-e5f038b70b4d |  | note | Check the depth of mill & take photos
text | 30c8dc9b-7134-5aee-a875-94350e97b1cc |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Material - Bitumen
label | 808fefd6-db03-5c85-afeb-952b7c83cfbd |  | note | Reference - TNZ P/3 : 1996
label | b5eaa268-c5fd-50da-8a0f-e75446bbea52 |  | note | Requirement - Spray bitumen, then place chip and roll – refer design for chipseal grade
label | efd4f6ee-d2aa-5ea2-97c0-cd1d131fc976 |  | note | Frequency - 1 Test
label | df657ac3-cda0-5dad-a4c5-0630c5efde71 |  | note | H
label | 70531b4a-c3af-570c-b445-a37aa1daa308 |  | note | Responsibility - Sealing Supervisor
label | 6443d9a5-820d-5733-a39c-b23b66dcd0ad |  | note | Check the depth of mill & take photos
text | 2bcf46bd-2ce1-5303-8647-03e20855f53c |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | e9f628b5-b124-5270-8b4a-292d5673e126 |  | note | Reference - TNZ P/3 : 1996
label | bb4e06ad-1cbe-5bef-a1f9-4c8c1b3ac803 |  | note | Requirement - Removal of loose chip
label | 94f2a10b-68f9-5c4f-ae73-54d3ba21e15d |  | note | Frequency - As per document
label | 919ddad9-cd50-54f2-8200-6d6749bd22f6 |  | note | I
label | 9d09da7e-6257-5bd0-829d-983f9a0abb52 |  | note | Responsibility - Sealing Supervisor
label | 91d3ddf3-0372-593a-809d-5f7cf63be5df |  | note | Check the depth of mill & take photos
text | db679c9f-02c5-5def-987b-6c33e05f2b93 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | - Line Marking
label | ccf46006-0289-55ee-b64c-a85cb3fd55ee |  | note | Reference - TNZ P/12
label | 3f26c855-9bdd-5717-9b9e-a37122f19237 |  | note | Requirement - Pavement markers/line marking
label | e422e35b-2813-5009-81ee-919e9d6c9d3c |  | note | Frequency - As per document
label | 1d2109da-eea4-5e69-812a-0f293cd3bdec |  | note | I
label | 760a8c6d-8b9a-58ae-b1f7-e60002469c0f |  | note | Responsibility - Supervisor
label | f04addb8-65cb-5123-afd5-c24f6c2e5e48 |  | note | Check the depth of mill & take photos
text | 864795a3-d6b2-51e6-86b6-697405fe1bf2 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | - Data
label | e1c63df0-c911-50ec-a25d-c47c5383c2dc |  | note | Reference - CMP Document
label | 25742902-cea0-5145-ba81-91c4b6f92159 |  | note | Requirement - Collection of RAMM data
label | b38e8ec6-697b-59a9-ae22-1d8c5b05905c |  | note | Frequency - As per CMP Document
label | 37f23a90-0017-59ab-9eef-66e956bd389d |  | note | H
label | 5ce828a6-d6b8-5a9a-9ade-d02000191bbe |  | note | Responsibility - Supervisor
label | 9f606aeb-0f6b-5852-bb79-f0de9ed8e710 |  | note | Check the depth of mill & take photos
text | 4288d0fe-8287-54bd-972e-2ef18c352db4 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checklist-flat |  |  | checklist | ITP - Section A&B Construction | itp |  |  |  | Yes | ITP - Section A&B Construction - Hunterville - AWPT | 7b8fe016-7e7b-4676-81af-7d804517ae1a
checkpoint-status |  |  | checkpoint | Material - Approval of AP65 Material for base course
label | 98e4ee6c-01d9-5463-a14d-5bce88d7ecd1 |  | note | Reference - TNZ M/4: 2006
label | 6bf3d926-3ae1-5755-a53a-ce5de00d7ffa |  | note | Requirement - Quarry Material Test Results to meet standards and specification
label | d217c488-8386-5751-afdf-23d8a2baf3ea |  | note | Frequency - 1 Test Every 10,000m3
label | b2cf7f68-a6a5-5642-84ff-ff057ef0134f |  | note | Verify
label | 1add8e1c-e177-5acc-a8d8-49d2993ea0d4 |  | note | Responsibility - Project Manager/Project Engineer
text | 7d223c23-6963-5652-b31f-930389203895 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Mill-out - Excavate only to approved level
label | 60b4e58d-8661-5673-8256-7a9b26f199c6 |  | note | Requirement - Mark-out & excavate as directed by NOC
label | 7cdfa078-362f-5bcc-9370-521a86fb42e7 |  | note | Frequency - On-Site confirmation
label | 1f0918de-5fbd-59ef-993c-e14aafa027ad |  | note | Hold Point
label | ddd6ea56-9158-5526-a598-a58075ced629 |  | note | Responsibility - Site Supervisor/ NOC Renewals Manager
text | 0923c122-2762-5d90-bcdb-1d1b1c700ee8 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Tie-In - Excavate & backfill
label | 5d645793-9aae-501b-a04d-2a8818947b3a |  | note | Requirement - Mark-out, excavate & backfill as directed by NOC
label | 2289895f-ecbe-5c9a-af4f-43dac239b977 |  | note | Frequency - As required. To be agree with NOC Renewals Manager
label | 75619370-658e-5166-b776-580298fe1257 |  | note | Verify
label | 85b1c279-b323-5dfc-97ae-92f2eba11c08 |  | note | Responsibility - Site Supervisor/ NOC Renewals Manager
text | d9c8200e-f67a-5d5d-84ab-028d456b2ebd |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Base Course layer - Place Base Course layer to design level
label | 4f5cb0ea-92b3-526e-964e-2c9f0d19aa14 |  | note | Reference - TNZ B/5:2008 - 7.3, 7.7 , 7.8
label | e1f40f4a-b56c-565c-8d33-6f333fdf2fb2 |  | note | Requirement - 160mm thick M4 AP40 (average depth)
label | bd98835e-d43a-521e-939d-23fcd81bde24 |  | note | Frequency - Each Lot of Base Course. Confirm with Survey Manager
label | 0ad98cbe-c4c5-50ff-a4c6-7d9260e37cfc |  | note | Verify
label | f33329e4-0309-5e8f-b815-f1ec67b81b7f |  | note | Responsibility - Site Supervisor / Project Manager / Project Engineer/Survey Manager
text | 90086bc2-51b8-5d39-a6ad-caf5147e273f |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Approval to stabilise new Base Course - Acceptance of Base Course layer
label | de15426e-34a6-5c1f-9bf2-f140c86faff9 |  | note | Reference - TNZ B/5:2008 - 7.2.1
label | 50588467-f6fc-5c7c-8b0a-3075148e8213 |  | note | Requirement - NOC Renewals Manager to authorise stabilising to proceed
label | c9df14d4-6a6d-544b-b2f7-1f3b0bd51dd0 |  | note | Frequency - Each section of stabilising
label | d0befd12-aa71-5deb-a0bb-4daafba52274 |  | note | Hold Point
label | 3faf82b7-c3df-5c35-b01b-568ca2d6421e |  | note | Responsibility - NOC Renewals Manager
text | 5cff6e15-b1b8-57df-a2da-6097bd776fd7 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Cement Content Testing - Spreading of lime and/or cement
label | 2e51f3bf-35ba-54f9-a8fc-cde19d3f847c |  | note | Reference - TNZ B/5:2008 - 7.3
label | e2b2f414-2aeb-5030-baa3-d0a99d6f096d |  | note | Requirement - Mat test: (1 m2 canvas) Within ±0.5 kg/m2 of the specified rate
label | e1d74a12-50fc-5aac-bdfb-1ff79060a2ae |  | note | Frequency - Every 500 m2
label | 9dad3495-7b8f-5fa9-ac8a-d1d8c17efc1c |  | note | Verify
label | b4c9f106-410e-52db-b268-76796d0b60d0 |  | note | Responsibility - Site Supervisor / Foreman
text | fbabdc01-d469-5175-9524-4956ec3ffb0c |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Stabilised Base Course - Stabilised Base Course
label | 9d73fd35-39aa-5fd6-be75-6ef06ada7d55 |  | note | Reference - TNZ B/5:2008 - 7.6
label | 656d1244-aba3-5281-a99a-951096f20fce |  | note | Requirement - Stabilised Base Course 180mm thick with 1.5% cement
label | cfa172ca-7dbf-501b-afa3-06eb37d30f52 |  | note | Frequency - Cut depth shall be physically measured at both ends of the stabilising drum at least once every 200m along the cut length of miller run. Maximum variation from the specified depth of cut is –5 mm and +15 mm.
label | d1496c3b-4f66-5329-9edb-ee0aa2181f72 |  | note | Verify
label | 1f999fac-324b-5494-96c4-959b49978225 |  | note | Responsibility - Site Supervisor / Foreman
text | 363fb374-472e-59ea-bbcb-882763fca3cf |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Plateau Density Tests - Acceptance criteria for stabilised layer compaction
label | 32894f31-d486-5fd9-ba2a-54809d4beb0e |  | note | Reference - TNZ B/5:2008 - 7.7.1
label | d017bfb7-40ec-50a1-b512-5e5398ef2add |  | note | Requirement - The Contractor shall undertake plateau density tests for the purpose of determining the target density
label | 198633a9-6d5d-5c52-bdbd-cee64fa29343 |  | note | Frequency - One OWC/MDD test per 5000 m2.
label | 1092cef1-5e01-5b8d-b68f-1421149c0af6 |  | note | Hold Point
label | 7ac8679b-4f02-50c0-8c4d-3871ea5cfe11 |  | note | Responsibility - Site Supervisor/ Project Engineer/ NOC Renewals Manager
text | 2c5fe1c8-5e3a-5e73-863f-a5b6b63c95af |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Compaction Testing - Nuclear Density Test
label | bb0398d9-ba7f-5803-8391-1e9dafeabec6 |  | note | Reference - TNZ B/5:2008 - 7.7.1
label | 1371a592-28b2-5a6b-849c-41c0d5dc7922 |  | note | Requirement - Base MDD - Average ≥ 98% - Minimum ≥ 95%
label | 7ef8056b-09e8-5386-9c40-7d8ccb18fa1f |  | note | Frequency - 1 test every 20 lineal metres
label | 78ffa8a2-73ec-57a7-9b2c-f5728accd0fc |  | note | Hold Point
label | 35dfbaea-43af-5a82-b6d1-08716d50d17b |  | note | Responsibility - Project Engineer / NOC Renewals Manager
text | f7bc6a49-8b55-5c4e-9144-4c443488b7df |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Acceptance - Acceptance of Base Course - visual inspection of surface
label | d2b5ffa8-a985-56d5-938e-9058913eacae |  | note | Reference - TNZ B/5:2008-7.8
label | 91180956-736c-528a-b448-059a77303ca4 |  | note | Requirement - No Chipseal to be placed until acceptance of Base Course layer by Engineer
label | 5e8590e9-a5cd-5db9-babd-79adbdae6e86 |  | note | Frequency - Per Lot
label | eb96657f-3c02-5b78-9480-8802de78261d |  | note | Hold Point
label | ecca508d-99e1-58d6-8083-9e18dc991260 |  | note | Responsibility - Site Supervisor / NOC Renewals Manager
text | 49b1ed4f-38a1-5603-997c-4971c14410d9 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Base Course Acceptance - Degree of saturation (DOS)
label | a7409579-7d97-50d5-afc9-3f66c0d9daaa |  | note | Reference - TNZ B/5:2008
label | 4566008c-9fa5-5dc3-8178-731fcd331faa |  | note | Requirement - < 60% (or 80% on consultation with the pavement designer)
label | 930671a0-fd92-5b77-b465-246b72744632 |  | note | Frequency - 5 (five) randomly selected areas
label | 9c8c3e89-b38a-5ccf-82bb-d66e434b7425 |  | note | Hold Point
label | 5b24ae8b-fd24-5786-9f8c-f28d78253165 |  | note | Responsibility - Project Engineer / NOC Renewals Manager
text | 5cf90dd5-eefe-5907-a9fd-df4365c57633 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checklist-flat |  |  | checklist | ITP - Construction |  |  |  |  | Yes | ITP - Construction | ab753393-75f9-441e-aa2d-ff0fc3deb968
checkpoint-status |  |  | checkpoint | Material - Approval of M4 AP40 Material for basecourse
label | e3f65560-8fe0-5ff5-bc35-bdf6c747c728 |  | note | Reference - TNZ M/4: 2006
label | 6bd056fa-ac35-5eba-b2ba-182d3e7e23eb |  | note | Requirement - Quarry Material Test Results to meet standards and specification
label | c86e3ae0-f85c-548d-a72f-9640cbf34673 |  | note | Frequency - 1 Test Every 10,000m3
label | 144f7972-3745-5b96-844c-bb3bbde679b0 |  | note | Hold Points - Verify
label | 09735abc-f93c-5c56-abfe-2ce39b6e12f5 |  | note | Responsibility - Project Manager/Project Engineer
checkpoint-status |  |  | checkpoint | Material - Approval of AP65 Material for shoulder & subbase
label | 0b6638c3-3511-5b55-b0df-a93cc71be66b |  | note | Reference - AP65:2006
label | 6ad88e42-f4ad-5005-868d-4eb6a9040bef |  | note | Requirement - Quarry Material Test Results to meet standards and specification
label | 1f21aa1a-a5e7-5204-ac0c-4bbac4c968ab |  | note | Frequency - 1 Test Every 10,000m3
label | 90d00d7b-d845-5e1c-8b51-2bb25b34bec6 |  | note | Hold Points - Verify
label | 5194596d-9dd3-5a73-9c5f-85b284304df6 |  | note | Responsibility - Project Manager/Project Engineer
checkpoint-status |  |  | checkpoint | Material - UCS testing to confirm cement %
label | ce1ea16f-9ff4-50f6-9095-edad6053415d |  | note | Reference - Chapter 7 of AustStab (AustStab 2015).
label | e6d4d735-bf2f-5a53-8cc4-ef28988f7522 |  | note | Requirement - Test representative aggregate samples at 1%, 2% and 3% to determine optimum cement content
label | 21d4db96-3f05-5921-b37f-6d8ed699653d |  | note | Frequency - Per Lot
label | 0ca72e9a-f8b6-5cef-90b1-69f03050aa67 |  | note | Hold Points - Hold Point
label | ae05af96-b403-53f0-b648-8210cc54d25a |  | note | Responsibility - NOC Renewals Manager
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Shoulder - Approval of excavated surface before backfill
label | d91f5964-6e8a-5ce0-8322-72886aa244bc |  | note | Requirement - Based on site conditions
label | ca8f860e-7c33-583e-a763-919fd74f1a1f |  | note | Frequency - As required.
label | 9cfeb01a-abd8-51ed-aa87-d4d6e58d8629 |  | note | Hold Points - Verify
label | defe092d-fdf4-5596-82a5-0ca898ba445e |  | note | Responsibility - Site Supervisor / Project Manager / Project Engineer
checkpoint-status |  |  | checkpoint | Shoulder - Backfill & compact shoulder
label | 5233e27c-084a-5ec2-af10-156bab565bbe |  | note | Requirement - Basic compaction & efficient material usage
label | 5ffcb350-6034-590a-b8fb-c5331e4b6270 |  | note | Frequency - As required.
label | 536a4b5d-d752-58d4-89c1-262b1e01cfac |  | note | Hold Points - Hold Point
label | 66ad9710-06f5-5492-b145-4d87613f7c7f |  | note | Responsibility - Project Manager / Project Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Drainage - Driveway culverts, manholes etc
label | 0a9072e0-0ce8-591b-a584-d4e52d042d57 |  | note | Requirement - As directed by NOC Renewal Manager
label | 83a25fc9-4506-5545-9d1f-f87e2335603d |  | note | Frequency - On-Site confirmation
label | 9347a6a7-d1fc-54c2-8cb8-25c8f90bbee8 |  | note | Hold Points - Hold Point
label | 8e61f107-a533-5bfd-84a0-f81f795a2719 |  | note | Responsibility - Site Supervisor/ NOC Renewals Manager
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Pavement Dig-outs (if required) - Excavate & backfill
label | fa37f5d3-46f4-5f5d-88a2-7847a8949eb0 |  | note | Requirement - Mark-out, excavate & backfill as directed by NOC
label | fb1f2b05-e022-52b1-91b7-a077781ecd6f |  | note | Frequency - On-Site confirmation
label | 688638c9-4e1c-5bb5-b763-0b32424e6063 |  | note | Hold Points - Hold Point
label | 16dc5f3a-fac9-5ab8-aaa2-4bac4b9e070c |  | note | Responsibility - Site Supervisor/ NOC Renewals Manager
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Tie-In - Excavate & backfill
label | 2326cba5-29d0-5ba0-b09d-5b2d49a63fa6 |  | note | Requirement - Mark-out, excavate & backfill as directed by NOC
label | 5261e8a8-6515-58ed-9a75-8b0e540e8199 |  | note | Frequency - As required. To be agree with NOC Renewals Manager
label | 8332d47c-b3a0-5927-b177-648ded88cedf |  | note | Hold Points - Verify
label | d7799bad-a404-5504-94db-9354e68e22ca |  | note | Responsibility - Site Supervisor/ NOC Renewals Manager
checkpoint-status |  |  | checkpoint | Existing Seal Surface Preparation - Rip existing surface
label | 3e2d3ca7-a7cc-5c7e-bf61-e78af827ef72 |  | note | Requirement - Rip existing seal along ruts with grader tines
label | a31a9516-0dca-50a7-9828-1a359d08cc18 |  | note | Frequency - As required. To be agree with NOC Renewals Manager
label | 5cf0c43a-72be-5f9b-a782-1db3bb32efe2 |  | note | Hold Points - Hold Point
label | 4cb90b14-31c9-5c4f-983f-517939a64ed8 |  | note | Responsibility - Site Supervisor/ NOC Renewals Manager
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Basecourse layer - Place Basecourse to design level
label | cba40b87-2632-5f71-9a66-d33ea5fb6100 |  | note | Reference - TNZ B/5:2008 - 7.3, 7.7 , 7.8
label | 008b2dfa-6db5-5d09-9b24-9b61e4926680 |  | note | Requirement - 150mm thick AP40 (average depth)
label | 3d44da64-8353-5b3e-84f4-8b5e5bcc614f |  | note | Frequency - Each Lot of Basecourse. Confirm with Survey Manager
label | 7cd789ac-6c33-5b08-bff3-7fd26c9723ff |  | note | Hold Points - Verify
label | 81ce6951-03dc-5114-bb27-8ad3242d9122 |  | note | Responsibility - Site Supervisor / Project Manager / Project Engineer/Survey Manager
checkpoint-status |  |  | checkpoint | Approval to stabilise - Acceptance of Basecourse layer
label | 320ea207-e375-56f3-b7df-ff9cad1043fb |  | note | Reference - TNZ B/5:2008 - 7.2.1
label | 975524ad-cdeb-53fb-a310-8a6080775859 |  | note | Requirement - NOC Renewals Manager to authorise stabilising to proceed
label | 2901e680-42a4-572c-9ad4-9fa06d5a2e36 |  | note | Frequency - Each section of stabilising
label | ca59051e-845d-5aea-935b-28aad994d649 |  | note | Hold Points - Hold Point
label | 853b5219-8e19-574a-97b7-4c51dc137c4b |  | note | Responsibility - NOC Renewals Manager
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Cement Content Testing - Spreading of lime and/or cement
label | 80a44ea3-fd1b-5f4a-8da5-63f30f818de5 |  | note | Reference - TNZ B/5:2008 - 7.3
label | 4627dc87-5906-546b-ab24-f305824d47c6 |  | note | Requirement - Mat test: (1 m2 canvas) Within ±0.5 kg/m2 of the specified rate
label | ac9019e2-026e-5906-b23e-f3c5d22ea2a4 |  | note | Frequency - Every 500 m2
label | 9b49eb8b-4fb4-5194-a55f-f999f367f306 |  | note | Hold Points - Verify
label | e226e278-cf68-5b76-98fb-1d88b9dd421a |  | note | Responsibility - Site Supervisor / Foreman
label | 80c3e3be-8ccc-5b5f-a238-c2f435dd0eff |  | note | Comments - Check the weight of cement & take photos
checkpoint-status |  |  | checkpoint | Stabilised Basecourse - Stabilised Basecourse
label | 5bd30c73-02d5-5a06-9a07-dc6c45de92c3 |  | note | Reference - TNZ B/5:2008 - 7.6
label | ef22b241-86ad-538c-928f-d1f14036241a |  | note | Requirement - Stabilised Basecourse 200mm thick with required (TBC by testing) cement
label | f4ae50a0-e411-5023-95ee-832d07d3db15 |  | note | Frequency - Cut depth shall be physically measured at both ends of the stabilising drum at least once every 200m along the cut length of miller run. Maximum variation from the specified depth of cut is –5 mm and +15 mm.
label | c8cb3ba3-d123-5369-8f15-cf6d54ab0c4e |  | note | Hold Points - Verify
label | 1193cdd2-b6ff-5850-85c3-9fc8ec70fd7c |  | note | Responsibility - Site Supervisor / Foreman
label | de54060c-5d9c-56e8-a1c0-0fbaa7b2c7bf |  | note | Comments - Check the depth of mill & take photos
checkpoint-status |  |  | checkpoint | Plateau Density Tests - Acceptance criteria for stabilised layer compaction
label | e13e6434-8854-54c3-b550-ba70114b985c |  | note | Reference - TNZ B/5:2008 - 7.7.1
label | 7d4ab006-5d2d-5172-9ab3-32c2e22320c2 |  | note | Requirement - The Contractor shall undertake plateau density tests for the purpose of determining the target density
label | c227f3d9-2e50-57a6-8ef7-2417502d55da |  | note | Frequency - One OWC/MDD test per 5000 m2.
label | 9880194e-0068-5a18-b96f-dd9ff359437b |  | note | Hold Points - Hold Point
label | 33214aad-26aa-5ee6-9e65-d1b1d9935797 |  | note | Responsibility - Site Supervisor/ Project Engineer/ NOC Renewals Manager
label | 90ade832-868e-564b-9882-4b1960f8f833 |  | note | Comments - During construction, the agreed maximum dry density (MDD) for the stabilised material shall be determined by the Contractor and the Engineer using the test data obtained from the laboratory testing before construction, and the in-situ plateau density during construction.
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Compaction Testing - Nuclear Density Test
label | e61df563-1890-5350-be19-a52d2d7d3656 |  | note | Reference - TNZ B/5:2008 - 7.7.1
label | bd994af8-4fc3-58fa-861f-ca2b77f24e9a |  | note | Requirement - Base MDD - Average ≥ 98% - Minimum ≥ 95%
label | 36576468-da25-596d-b943-296d5c6be184 |  | note | Frequency - 1 test every 20 lineal metres
label | 76797a9b-7a78-55be-9dbd-c6eec47ecad0 |  | note | Hold Points - Hold Point
label | 98c13cef-77a6-5cf9-9147-bf1d1b16cead |  | note | Responsibility - Project Engineer / NOC Renewals Manager
label | f2234475-7ece-567a-ab98-e1a0f91a77ad |  | note | Comments - Engineer has to sent the results to NOC Renewal Manager for approval
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Basecourse Acceptance - Acceptance of Basecourse - visual inspection of surface
label | b5f6fc3c-9cbe-5718-a60b-14603cd698f8 |  | note | Reference - TNZ B/5:2008-7.8
label | a719a929-6603-50ca-87fe-392d6fa87e19 |  | note | Requirement - No Chipseal to be placed until acceptance of Basecourse layer by Engineer
label | 00993cad-a2ed-5623-98c0-1a41f6a30fcd |  | note | Frequency - Per Lot
label | 37c49473-3b48-5564-826b-b5c3f63eec5f |  | note | Hold Points - Hold Point
label | 865339db-7a96-5d02-b69a-1207d4ebf9c4 |  | note | Responsibility - Site Supervisor / NOC Renewals Manager
label | 957dbabc-7f6a-545c-8cf5-d40370ded3b2 |  | note | Comments - Supervisor has to contact NOC Renewal Manager to approve the final basecourse.
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Basecourse Acceptance - Degree of saturation (DOS)
label | 7df2fad4-cb91-5a20-ad1a-5f1a18d5c696 |  | note | Reference - TNZ B/5:2008
label | 189d9c59-a814-5990-b251-b0042c7a0290 |  | note | Requirement - < 60% (or 80% on consultation with the pavement designer)
label | e0beb958-1aac-572f-95d3-e07581783bc4 |  | note | Frequency - 5 (five) randomly selected areas
label | 0e3840e4-1c8a-5ae3-869c-53d3184460db |  | note | Hold Points - Hold Point
label | df95f121-ef9c-574e-896b-36da1eda53be |  | note | Responsibility - Project Engineer / NOC Renewals Manager
label | 59142771-e29b-53c9-8e5d-b29d04bdb7d6 |  | note | Comments - Pavement layer compaction test results may be used for this purpose where the Engineer is satisfied that the water content has not had a chance to rise between testing and sealing. (i.e. it has not rained or additional watering has not been applied to the pavement).
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Works Completed and conforming
text | 067a947c-c5b5-56ba-b91d-ee9d863a324a |  | textbox | Authorised By:
text | b1303db8-d533-50f6-aadb-faaef75dfceb |  | textbox | Date:
label | c441a77e-bba6-5b1e-8efd-dd99aff47f17 |  | note | Ensure All relevant documents attached to Inspection Test Plan for Area of Works completed.
checklist-flat |  |  | checklist | Basecourse Overlay & Stabilise - SH2 MANGATERA AWPT |  |  |  |  | Yes | Basecourse Overlay & Stabilise - SH2 MANGATERA AWPT | bc682904-b476-43d1-955b-d2dc9eeb7b82
checkpoint-status |  |  | checkpoint | Material-Approval of M4 AP40 Material for basecourse
label | faa78c4b-551c-5a89-80d3-5f2a758ba569 |  | note | Reference-TNZ M/4: 2006
label | f72330ca-f818-5f7a-99bf-927d87df4a5e |  | note | Requirement-Quarry Material Test Results to meet standards and specification
label | bb47a04d-5d44-5934-94b5-9e10b154738c |  | note | Frequency-1 Test Every 10,000m3
label | b5ed9813-4fa9-5381-8f15-b360a8b77a3b |  | note | Responsibility-Project Manager/Project Engineer
label | 86287f8f-6941-589a-b5b7-34e6f9c82208 |  | note | Verify
checkpoint-status |  |  | checkpoint | Material-Approval of AP65 Material for shoulder & subbase
label | 280ec085-1af1-5a4c-a527-f038878964ac |  | note | Reference-AP65:2006
label | 2e54c134-00c1-54af-adf2-fb6a6fa6764e |  | note | Requirement-Quarry Material Test Results to meet standards and specification
label | c71bda8e-3e78-5af6-a596-ef841d92c34e |  | note | Frequency-1 Test Every 10,000m3
label | d737f3df-8d3a-5f38-801d-4744b248f796 |  | note | Responsibility-Project Manager/Project Engineer
label | c2a83413-9918-5cf4-b1a4-1a409feac2b7 |  | note | Verify
checkpoint-status |  |  | checkpoint | Material-UCS testing to confirm cement %
label | 210fc8eb-cd61-57f6-9034-6469bbe1580f |  | note | Reference-Chapter 7 of AustStab (AustStab 2015).
label | 37575282-fa64-5d16-bc56-636eb3664577 |  | note | Requirement-Test representative aggregate samples at 1%, 2% and 3% to determine optimum cement content
label | 755ccafb-c912-50c9-ac8b-7338f5c22f79 |  | note | Frequency-Per Lot
label | 132ab17b-627f-5c73-9cb1-6ec4b032939c |  | note | Responsibility-NOC Renewals Manager
label | a6312893-5862-5c3b-8023-4a322147c72e |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Shoulder-Approval of excavated surface before backfill
label | adf2a597-7892-5191-a9dc-ba26375b1765 |  | note | Requirement-Based on site conditions
label | d5420441-88c1-5d3a-88f2-d16376b63f5a |  | note | Frequency-As required.
label | a1113abf-d94d-5695-aaea-bda47a43d08c |  | note | Responsibility-Site Supervisor / Project Manager / Project Engineer
label | e755f0c4-2d2c-56bc-bfd6-8bc9f22b1761 |  | note | Verify
checkpoint-status |  |  | checkpoint | Shoulder-Backfill & compact shoulder
label | d28d6c00-1fa1-595d-85f8-50ffde849841 |  | note | Requirement-Basic compaction & efficient material usage
label | 6537b3f2-cdc7-5d8e-8daf-e7e85107a460 |  | note | Frequency-As required.
label | 3f7f0cdc-bc1b-5f78-943a-5687b6a95bd4 |  | note | Responsibility-Project Manager / Project Engineer
label | 1d1d63b3-1540-5a9b-aee9-015a35bc080c |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Drainage-Driveway culverts, manholes etc
label | f8abfd0c-4dd2-5f6f-b00d-9a368a24b260 |  | note | Requirement-As directed by NOC Renewal Manager
label | 9bb97a40-7ba1-533b-8711-2ea7bc0193ee |  | note | Frequency-On-Site confirmation
label | c64493dd-b3f7-5ea2-bac8-be837b5ec879 |  | note | Responsibility-Site Supervisor/ NOC Renewals Manager
label | 6e7257c4-9d04-5e20-b7ca-a8c0636d8c01 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Existing Seal Surface Removal-Saw cut existing road surface and remove
label | 0be2f4d7-0579-5a0d-adc7-3bacb6f3dedf |  | note | Requirement-Peel off existing road surface layer
label | e187cd6b-12a3-5ed9-b83f-40e35cac29a2 |  | note | Frequency-As required. To be agree with NOC Renewals Manager
label | c5c9f8b5-e138-5199-9585-a8db7975a51c |  | note | Responsibility-Site Supervisor/ NOC Renewals Manager
label | 9eace683-fe2d-5748-881a-d80688eacee2 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Pavement Dig-outs to 160 mm-Excavate only to approved level
label | c8319eeb-bf5d-5bf2-b627-3cc790d9b1ed |  | note | Requirement-Mark-out & excavate as directed by NOC
label | dbc1ec35-2697-5ae9-9b1a-fb86ee5994db |  | note | Frequency-On-Site confirmation
label | 16e67b20-f82c-5a0f-85a7-1f1f169ac6d3 |  | note | Responsibility-Site Supervisor/ NOC Renewals Manager
label | dd7c59f6-9b37-52ec-b379-8fd8ea56ca73 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Tie-In-Excavate & backfill
label | a8f7a496-9b2c-5c00-beb1-ce7560fa0360 |  | note | Requirement-Mark-out, excavate & backfill as directed by NOC
label | c18ec7ea-48a4-5dfe-a567-82c6e63c436a |  | note | Frequency-As required. To be agree with NOC Renewals Manager
label | e72e448a-b657-51c6-b7de-84adf28ab2b8 |  | note | Responsibility-Site Supervisor/ NOC Renewals Manager
label | feca18dd-f352-529c-a547-c0b52915a918 |  | note | Verify
checkpoint-status |  |  | checkpoint | Approval to stabilise subbase -Acceptance of subbase layer
label | f03b4246-fb17-50ca-abf5-130981e190c2 |  | note | Reference-TNZ B/5:2008 - 7.2.1
label | 3ed6cbdc-df18-50bb-b002-b4f39f930182 |  | note | Requirement-NOC Renewals Manager to authorise stabilising to proceed
label | 79475b35-a8ed-5de0-a409-87c75a5f2daa |  | note | Frequency-Each section of stabilising
label | a6d9a521-4423-5eb9-8977-aff96c270e0e |  | note | Responsibility-NOC Renewals Manager
label | e8ecdc37-5c9f-5577-a648-bf7c9140a4a2 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Cement Content Testing-Spreading of lime and/or cement
label | 8880c41c-5b18-5476-878c-ab6f2cdcbd98 |  | note | Reference-TNZ B/5:2008 - 7.3
label | 3fdd17c2-7b21-5062-99b6-4ffa6ef9e463 |  | note | Requirement-Mat test: (1 m2 canvas) Within ±0.5 kg/m2 of the specified rate
label | 3a8854a5-3698-5375-bdbc-bc9e4017f65b |  | note | Frequency-Every 500 m2
label | 1de89a52-8c99-5624-9ceb-33fe0371058a |  | note | Responsibility-Site Supervisor / Foreman
label | c79b93d3-6672-5330-b4c9-f2229cfa61b2 |  | note | Comments-Check the weight of cement & take photos
label | d383ff2a-87b7-5cd4-9a8d-428d8125e0d6 |  | note | Verify
checkpoint-status |  |  | checkpoint | Stabilised Subbase-Stabilised Subbase
label | 58823aaa-6e02-55f6-baf7-6cc1ebafce13 |  | note | Reference-TNZ B/5:2008 - 7.6
label | 2eac5b7f-965f-5d1e-b894-700acbff552c |  | note | Requirement-Stabilised subbase 200mm thick with 5% cement
label | d6ea60f2-e68f-54fb-b326-544c6cce72cc |  | note | Frequency-Cut depth shall be physically measured at both ends of the stabilising drum at least once every 200m along the cut length of miller run. Maximum variation from the specified depth of cut is –5 mm and +15 mm.
label | d446afed-5fad-5b70-964b-d4eaaef5df36 |  | note | Responsibility-Site Supervisor / Foreman
label | d310883c-5696-5363-8882-065fcce5357c |  | note | Comments-Check the depth of mill & take photos
label | 85c54f0c-fb85-5c06-bedc-09af4c65d20c |  | note | Verify
checkpoint-status |  |  | checkpoint | Plateau Density Tests -Acceptance criteria for stabilised layer compaction
label | 26412f5c-6ee4-57d8-b99d-21a4218c3f04 |  | note | Reference-TNZ B/5:2008 - 7.7.1
label | 48d3ef1e-0cca-504c-90de-1f785b6b3479 |  | note | Requirement-The Contractor shall undertake plateau density tests for the purpose of determining the target density
label | 7a7b472a-0b9e-5f4d-9ec5-8bd438013792 |  | note | Frequency-One OWC/MDD test per 5000 m2.
label | 86a3421d-81ee-5813-a5f5-7ea211c5daed |  | note | Responsibility-Site Supervisor/ Project Engineer/ NOC Renewals Manager
label | 2509f0a7-0881-5412-9bc4-e9c3afa45197 |  | note | Comments-During construction, the agreed maximum dry density (MDD) for the stabilised material shall be determined by the Contractor and the Engineer using the test data obtained from the laboratory testing before construction, and the in-situ plateau density during construction.
label | 40101100-8f4a-5ff3-ae38-79efdd26cb65 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Compaction Testing-Nuclear Density Test
label | 94f66e4d-1853-513c-b2f6-6ba8f635047e |  | note | Reference-TNZ B/5:2008 - 7.7.1
label | 440f7308-8cae-590b-9e9a-5fbd63650ec5 |  | note | Requirement-Base MDD - Average ≥ 98% - Minimum ≥ 95%
label | 889cdbd1-d521-56d7-a2c7-474f494a71a1 |  | note | Frequency-1 test every 20 lineal metres
label | f337e100-fab6-57a0-998a-e2f32565f3c1 |  | note | Responsibility-Project Engineer / NOC Renewals Manager
label | 56da5996-df1c-5ae1-bd53-80792917d6b7 |  | note | Comments-Engineer has to sent the results to NOC Renewal Manager for approval
label | 67a989c9-8ecb-5db1-a2c3-fbba164fd393 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Subbase Acceptance-Acceptance of subbase - visual inspection of surface
label | fdad8020-c3b0-5a82-a9a6-39110dbe4e42 |  | note | Reference-TNZ B/5:2008-7.8
label | c27f3f7b-b827-53cd-a090-d6b208a07cfc |  | note | Requirement-No Basecourse layer to be place until approval of subbase by Engineer
label | b13974bf-9ba9-5fc4-afdf-e712eba9cb9b |  | note | Frequency-Per Lot
label | 28fc7b4d-1cbb-548d-9baa-671936cf646c |  | note | Responsibility-Site Supervisor / NOC Renewals Manager
label | d8af588f-88c8-550d-8957-4ded63a54af4 |  | note | Comments-Supervisor has to contact NOC Renewal Manager to approve the final basecourse.
label | 2bbffb8b-b29e-582e-913f-66211e3e7ce0 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Subbase Acceptance-Degree of saturation (DOS)
label | e8192ed2-64f4-55ef-96ba-83b639fed2b7 |  | note | Reference-TNZ B/5:2008
label | 79e7d580-e75a-5155-8697-82cca0de8bf0 |  | note | Requirement-< 60% (or 80% on consultation with the pavement designer)
label | 4ce53bfd-2cd9-5d7e-8320-566691ef9ad3 |  | note | Frequency-5 (five) randomly selected areas
label | fb8759b7-72b0-500f-a8c8-147c89d64aec |  | note | Responsibility-Project Engineer / NOC Renewals Manager
label | d0c02df8-bd97-521d-8443-f5a19d2318f3 |  | note | Comments-Pavement layer compaction test results may be used for this purpose where the Engineer is satisfied that the water content has not had a chance to rise between testing and sealing. (i.e. it has not rained or additional watering has not been applied to the pavement).
label | 9a14690a-5ebb-50ed-8768-f6a974637cd1 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Basecourse layer-Place Basecourse layer to design level
label | b21de673-8f0d-57f7-88e3-e6ed2cf2bddc |  | note | Reference-TNZ B/5:2008 - 7.3, 7.7 , 7.8
label | 9077c884-77b6-5ec8-bf7e-3be2e4a2cf64 |  | note | Requirement-160mm thick M4 AP40 (average depth)
label | 320dee77-20e3-5db4-9554-5bbda4a5455f |  | note | Frequency-Each Lot of Basecourse. Confirm with Survey Manager
label | 8430b3c5-b986-5489-872c-cd5178ebdde7 |  | note | Responsibility-Site Supervisor / Project Manager / Project Engineer/Survey Manager
label | 06c1b1ba-08fb-5ec0-90d4-4b51254f0f78 |  | note | Verify
checkpoint-status |  |  | checkpoint | Approval to stabilise basecourse-Acceptance of basecourse layer
label | ae6b2a28-1e7e-5298-b942-54b232ac24b7 |  | note | Reference-TNZ B/5:2008 - 7.2.1
label | eac88e37-03e3-5190-926b-c1a63ac6103c |  | note | Requirement-NOC Renewals Manager to authorise stabilising to proceed
label | 77c6b289-d2eb-5c9e-912a-36c3ac5a73a7 |  | note | Frequency-Each section of stabilising
label | 9b1a0c53-1a79-5b4a-878a-6c1182e4ee35 |  | note | Responsibility-NOC Renewals Manager
label | fa87c63b-1b0e-566c-8ab4-e78e0d965aa8 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Cement Content Testing-Spreading of lime and/or cement
label | 20320ad5-18da-58a0-9879-8d692adb9535 |  | note | Reference-TNZ B/5:2008 - 7.3
label | 226d644e-075b-5e06-a8b6-b76768084161 |  | note | Requirement-Mat test: (1 m2 canvas) Within ±0.5 kg/m2 of the specified rate
label | f62a39f8-c000-587e-b128-8e2dd7e3afff |  | note | Frequency-Every 500 m2
label | 2a3d0559-f5ff-55b3-bdd7-8807e09e27b0 |  | note | Responsibility-Site Supervisor / Foreman
label | e4568d0e-30a7-55d1-8b05-8c86ac4b13bf |  | note | Comments-Check the weight of cement & take photos
label | 843c1443-077c-517f-ab03-0e21b31a2a48 |  | note | Verify
checkpoint-status |  |  | checkpoint | Stabilised Basecourse-Stabilised Basecourse
label | 1cbb7c6d-d978-5f7e-9501-c5fc75f6d593 |  | note | Reference-TNZ B/5:2008 - 7.6
label | 75588c44-5078-51d2-9f95-f0692b36b1d2 |  | note | Requirement-Stabilised Basecourse 160mm thick with 1.5% cement
label | c8fcd05a-faba-569e-be6b-655a4b53d56a |  | note | Frequency-Cut depth shall be physically measured at both ends of the stabilising drum at least once every 200m along the cut length of miller run. Maximum variation from the specified depth of cut is –5 mm and +15 mm.
label | caea1889-d1fb-5db2-855d-84953d2ec4ec |  | note | Responsibility-Site Supervisor / Foreman
label | 26793ebc-6b32-53a7-9f7c-ccc06ce5ec76 |  | note | Comments-Check the depth of mill & take photos
label | ffc44da6-550f-5f70-9f27-fa867a37cb2e |  | note | Verify
checkpoint-status |  |  | checkpoint | Plateau Density Tests -Acceptance criteria for stabilised layer compaction
label | ac0251f3-1227-539c-999b-4983ec01dafd |  | note | Reference-TNZ B/5:2008 - 7.7.1
label | a758b1ac-7529-524b-b192-f60e8c372259 |  | note | Requirement-The Contractor shall undertake plateau density tests for the purpose of determining the target density
label | 24143676-666b-5041-86f5-396afcb964aa |  | note | Frequency-One OWC/MDD test per 5000 m2.
label | 64ada7a4-ccc3-59d3-9a21-5de1b0a6cfde |  | note | Responsibility-Site Supervisor/ Project Engineer/ NOC Renewals Manager
label | 155b6b63-ef9e-515d-81d3-3bac7f4a5ca9 |  | note | Comments-During construction, the agreed maximum dry density (MDD) for the stabilised material shall be determined by the Contractor and the Engineer using the test data obtained from the laboratory testing before construction, and the in-situ plateau density during construction.
label | 1686e10f-d5e5-579f-a98a-13df062863e2 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Compaction Testing-Nuclear Density Test
label | beb0566c-9d9c-5acc-9ed0-31a008610627 |  | note | Reference-TNZ B/5:2008 - 7.7.1
label | c33e1299-3909-52d6-ba34-1a7ba7430b96 |  | note | Requirement-Base MDD - Average ≥ 98% - Minimum ≥ 95%
label | 6695da04-a8b9-5a67-8be6-939c040ea9b8 |  | note | Frequency-1 test every 20 lineal metres
label | da0b615d-df94-5042-9987-55fffd3ad36e |  | note | Responsibility-Project Engineer / NOC Renewals Manager
label | 25ea87f3-ce78-5f28-9672-60af3afa3b7c |  | note | Comments-Engineer has to sent the results to NOC Renewal Manager for approval
label | 72aad878-5d26-578c-b165-e55274ea3bd1 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Acceptance-Acceptance of Basecourse - visual inspection of surface
label | 33a8a2af-641c-52e5-9573-76393915596b |  | note | Reference-TNZ B/5:2008-7.8
label | 5adfabc3-f04c-5268-a2c8-10be3e7e5f0e |  | note | Requirement-No Chipseal to be placed until acceptance of Basecourse layer by Engineer
label | 1a579f4c-6d50-564c-bbd4-8a6fa2dd905f |  | note | Frequency-Per Lot
label | 641ee068-5def-5eea-99e1-1b2274b525b3 |  | note | Responsibility-Site Supervisor / NOC Renewals Manager
label | 3b35a79d-7d6d-54e0-90c4-2ebb80f5db58 |  | note | Comments-Supervisor has to contact NOC Renewal Manager to approve the final basecourse.
label | 73d596a4-34ac-53b7-a103-26914c4527ec |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Basecourse Acceptance-Degree of saturation (DOS)
label | 622b77fb-823e-55f9-8b8d-0ebeabb432d3 |  | note | Reference-TNZ B/5:2008
label | 5ceeaa2e-1c07-53ee-a838-e2862ba69d19 |  | note | Requirement-< 60% (or 80% on consultation with the pavement designer)
label | f2c517f0-259f-57ca-ac4f-f76c87def0ec |  | note | Frequency-5 (five) randomly selected areas
label | 19adeead-440b-55a6-83ef-ab4862c04987 |  | note | Responsibility-Project Engineer / NOC Renewals Manager
label | 071c64b7-3622-5954-be21-97786eefe97a |  | note | Comments-Pavement layer compaction test results may be used for this purpose where the Engineer is satisfied that the water content has not had a chance to rise between testing and sealing. (i.e. it has not rained or additional watering has not been applied to the pavement).
label | a6d373c9-4fe1-57d9-a387-a847252c2d41 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Chip-Check chip in stockpile
label | a6f02d5e-64e4-517c-8c03-8987abace04d |  | note | Requirement-confirm size, quantity, cleanliness
label | 24a1d710-86ce-5df6-99b2-cee9e3a0b485 |  | note | Frequency-Per Lot
label | 15a6867c-0508-561f-b48d-62b6854048e4 |  | note | Responsibility-Project Engineer / NOC Renewals Manager
label | d1966610-487c-55f7-a299-5b567c39c030 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Sealing-Pre-surveyed seal area –
label | b8a68852-1323-5c7a-a669-d01b3891a9f0 |  | note | Requirement-Prior to first coat, confirm seal extent and get confirmation from Renewals Manager
label | 5ced465e-09a8-5431-85b1-7846df73fe5d |  | note | Frequency-Per Lot
label | e2793a00-4e2a-51cf-bfe7-fc717222c0fb |  | note | Responsibility-Project Engineer / NOC Renewals Manager
label | 7b86f010-aece-5c0f-b94b-eb3b15134609 |  | note | Hold Point
holdpoint |  |  | signoff | Hold Point
checklist-flat |  |  | checklist | ITP - Sealing | itp |  |  |  | Yes | ITP - Sealing - Hunterville - AWPT | c1eff8c9-88da-4b3b-94b6-d5b87fac0c94
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | adacb70b-a20e-504c-84b5-2d4b17957b78 |  | note | Reference - NZTA M/6 3.2
label | 7cbc5eeb-b764-5a72-a04e-bdfc738694e5 |  | note | Requirement - Crushing Resistance Test
label | 8a4b95b2-264b-5f07-ad9a-da5dac8ec09b |  | note | Frequency - 1 Test
label | b291e205-d080-554a-bc49-a9d7554d174d |  | note | T
label | 980ffdc6-0a63-5d33-9e13-a26efe010c58 |  | note | Responsibility - IANZ accredited laboratory
text | 5bf4cf5c-5e10-562a-aa0e-3b05451a634b |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | 144fa5f7-03bf-5e03-8e96-73990fce40b5 |  | note | Reference - NZTA M/6 3.3
label | 86336d86-5bcd-5e6e-8d43-dcfe101fa769 |  | note | Requirement - Weathering Quality Index Test
label | 9f1955ff-9bd1-561a-a3bb-a968f3220a69 |  | note | Frequency - 1 Test
label | e5819c54-016b-59df-898f-3501c934c4c4 |  | note | T
label | 87a4f427-7a2b-5edb-bf42-3afcfee12701 |  | note | Responsibility - IANZ accredited laboratory
text | a04fcac3-bf9e-5801-8495-8be81daf43b9 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | 99f3ae9c-1a24-59b2-9210-4a40ca8f1279 |  | note | Reference - NZTA M/6 3.5
label | e0edc4ff-f289-519b-b78d-900c676461f4 |  | note | Requirement - Polished Stone Value Test
label | c24daf37-2f95-5463-8954-0ae88210f6ff |  | note | Frequency - 1 Test
label | 6e0bc7b1-6704-5a69-af57-93b1c4649a38 |  | note | T
label | bda6a50a-d025-585b-8584-789473cb1acb |  | note | Responsibility - Accredit PSV testing laboratory
text | 3ea71b11-4fc6-5e28-9ef6-823e68527d1a |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | fc43a8b4-15c4-5adb-bcb5-b953bbb07a47 |  | note | Reference - NZTA M/6 4.1.1
label | a737457b-b1ea-5243-ae1e-4b5b3c04938e |  | note | Requirement - Cleanliness Test
label | a225a582-2e94-5749-a856-bd36377a3833 |  | note | Frequency - 1 Test
label | ae12ad2f-e21f-55cb-820a-653ef78a856d |  | note | T
label | 5c445bea-b5ac-5a6c-b3fe-bcbf27ae45ce |  | note | Responsibility - IANZ accredited laboratory
text | 3fd97d52-6720-5c9d-9ee8-cc5685a0c181 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Material - Bitumen
label | de934813-d2da-5464-a7e1-27bd1c0ebc5f |  | note | Reference - NZTA M/1 Table 1
label | 4537a262-533c-5996-8925-52cae7530d5a |  | note | Requirement - Confirm viscosity of bitumen
label | 6bba1f08-6ece-5d3b-9639-c4a9ce9c40bd |  | note | Frequency - 1 Test
label | dc17746b-fd79-5a04-80f0-c48b181646b3 |  | note | T
label | 51e17304-b9de-595a-8974-6b833b204d3b |  | note | Responsibility - IANZ accredited laboratory
text | d4fd386a-fcd3-5c6d-9379-31ede0ee0b9b |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | 23c6b8ab-adb6-5bcb-b526-808c10194217 |  | note | Requirement - Confirm site measurements
label | f8d3109f-e2cd-522c-a3e6-fc545961fee1 |  | note | Frequency - Before sealing to take place
label | 303d7b4f-47e2-515a-8e15-345e782ef66e |  | note | H
label | 02af65ba-7192-5973-a286-091692556346 |  | note | Responsibility - Sealing Manager / Supervisor
text | e468a9d1-7c03-5138-8663-3b9940910fbb |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | a20bb694-8c25-5300-8ee9-771df88ac318 |  | note | Requirement - Confirm stockpile area and correct grade of chip
label | 7c237dad-dcb1-5e8a-8981-9e3750ea4715 |  | note | Frequency - Before sealing to take place
label | c5ce51eb-d32a-54e8-883a-6c0517ccb9a8 |  | note | H
label | 133bd5b6-6362-5e9c-8898-27d26153cb82 |  | note | Responsibility - Sealing Manager / Supervisor
text | 9d3ec7ee-d361-5c66-bd6d-82860c55cf8d |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Material - Bitumen
label | 54bb6f1e-3374-53c2-925f-19fdac8eae89 |  | note | Reference - NZTA M/1 Table 1
label | 7e63c763-b932-5e20-94a2-1965c96fe032 |  | note | Requirement - Confirm penetration grade of bitumen
label | f71f2415-34b3-5761-8a11-d936eda10dc4 |  | note | Frequency - 1 Test
label | f6cd9b1c-afc0-5111-b1da-8177e5b1ef9f |  | note | T
label | 80387dbd-4bbf-5ca1-ba2b-fe076455a8e5 |  | note | Responsibility - IANZ accredited laboratory
text | 95ff04ad-a19e-5425-8a54-2100e28ddc3f |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Material - Bitumen
label | 58119221-96cd-58f5-80ec-f441dd5905b0 |  | note | Reference - TNZ P/3 : 1996
label | 3af9db9f-a6a6-5402-aac4-5d8b589d65ed |  | note | Requirement - Spray bitumen, then place chip and roll – refer design for chip seal grade
label | 940a2464-dc91-53a1-85a5-73fc81e0bb55 |  | note | Frequency - 1 Test
label | 707b41a4-260a-55f0-bc7b-6c91d37253da |  | note | H
label | d6f7722b-363d-5a46-b10c-86c615b9a9e4 |  | note | Responsibility - Sealing Supervisor
text | fb4f52a7-2fc9-5e16-a198-19b7b1499583 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Material - Sealing Chip
label | e57b7867-5745-5ca3-8a0a-579b5868f288 |  | note | Reference - TNZ P/3 : 1996
label | a8871023-91d1-558b-9e91-08bb798d8206 |  | note | Requirement - Removal of loose chip
label | 63b87182-685e-57ac-960b-35c7fe3e021c |  | note | Frequency - As per document
label | aa2d4f10-4e77-5121-862f-b54ebbeca8df |  | note | I
label | 6a9c195d-ee8e-5b70-b0e0-4196498f7872 |  | note | Responsibility - Sealing Supervisor
text | a9540ed1-c629-56b1-837b-09240073bdb3 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Line Marking
label | f0306a81-420e-5070-85a4-c7de1b5ce335 |  | note | Reference - TNZ P/12
label | 7b047496-01e4-51ad-af1e-4a0109671992 |  | note | Requirement - Pavement markers/line marking
label | 90b2477c-a3e3-5601-b472-5cd677e10f4d |  | note | Frequency - As per document
label | bb49f601-c202-5612-9973-da9c6ef9c525 |  | note | I
label | c7b1fe07-5038-5f39-ae72-eede5fe40879 |  | note | Responsibility - Supervisor
text | 065d589a-6785-55c3-92a5-d9c19ea6f077 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Data
label | bedf4b6b-fa96-589e-804d-f50356ce8ee2 |  | note | Reference - CMP Document
label | b97af639-36b2-5aae-9101-2ae6ebb84631 |  | note | Requirement - Collection of RAMM data
label | 593f18a2-f4e3-5c92-9123-77766814fa93 |  | note | Frequency - As per CMP Document
label | 52ffb407-ff36-517c-8ee3-3003d89e5591 |  | note | H
label | acf86faa-7037-5b7e-839e-03df79cfc137 |  | note | Responsibility - Supervisor
text | 0a7f1279-8806-58a5-9a36-56f6c99abb8e |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT
checklist-flat |  |  | checklist | Chip Resealing |  |  |  |  | Yes | Chip Resealing | f4344deb-7e81-4e1c-b2c5-3230c0be1129
checkpoint-status |  |  | checkpoint | Chipseal Designs
label | 5376e8b7-299a-5f4c-addb-1a30c715bef9 |  | note | Controlling Documents-MWNOC15 Design Report, Chipsealing in NZ, NZTA P/17
label | 20793a11-299d-5d0f-973f-652867afa596 |  | note | Acceptance Criteria-Client Approval
label | 402d62f3-16cf-5703-9f08-2a0f0c618a42 |  | note | Method-Review
label | 5f0bcc31-c184-5cb8-8075-b1423c8ee437 |  | note | Frequency-Annual
label | aa3695e0-e3f2-592f-a8b1-12234de45635 |  | note | Responsible Person-Surfacing Project Manager
label | b92f079a-a21f-5da5-9b0f-25b51f4827c7 |  | note | Verifying Document-MWNOC15 Design Report Acceptance
label | 520ae1b6-470c-534a-928d-97ded54f439f |  | note | Conduct Test-Higgins
label | 8a974063-ba8d-5a59-b0ab-78dd01917ee1 |  | note | Produce Record-Higgins
label | 505e2d0b-d057-554c-82e5-066306256008 |  | note | Approval of Inspection-Client Rep
label | aed1a2d0-def6-5128-89d4-2aad12e505a6 |  | note | Inspection Point-N
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Finalise Sprayrate
label | 9400fb00-0a2d-559d-b21f-815f1339b47c |  | note | Controlling Documents-MWNOC15 Design Report, Chipsealing in NZ, NZTA P/17
label | bb7b7362-b8c2-56ce-a91f-22329bd0bb56 |  | note | Acceptance Criteria-N/A
label | 6a797745-3093-5a2b-ab3f-73613e0ab2e4 |  | note | Method-Review
label | ce53a1a3-040e-5dda-a0bb-740d8a95b636 |  | note | Frequency-Per Site
label | 12959909-227b-5d5c-a5f0-eca4ae71ee75 |  | note | Responsible Person-Surfacing Project Manager / Sealing Foreman
label | 18608834-94d8-59b1-8d34-5ad0a2a6fa71 |  | note | Verifying Document-Site/Spray Instruction
label | 4c2bccca-feb2-5bfb-9277-a8b39e87abae |  | note | Conduct Test-Higgins
label | a77c43e6-0e66-5f9a-882d-389fbf1ee284 |  | note | Produce Record-Higgins
label | 9600ee87-7890-5ef2-aaf6-59bf6d1ee88b |  | note | Approval of Inspection-Higgins
label | ae2ab70e-19ee-53c4-860f-8d5833327d90 |  | note | Inspection Point-Y
checkpoint-status |  |  | checkpoint | Check weather
label | e1adc206-e3b8-5c41-96f5-5223e0de7232 |  | note | Controlling Documents-N/A
label | 94a2f9da-cc18-57c6-8f15-2ec44de78e2a |  | note | Acceptance Criteria-Not foggy or raining or wet surface. Base Temp ≥ 10ºC and rising. No rain forecast in next 24 hours
label | e50a6869-4434-5d31-818f-f0589fd03623 |  | note | Method-Weather Forecast
label | 1af93634-2c20-5e27-bab2-b9b00fa1f9f6 |  | note | Frequency-Prior to starting
label | c0a80ad0-bdc0-59a2-8026-dca5b81a14da |  | note | Responsible Person-Surfacing Project Manager / Sealing Foreman
label | 1424bc80-8d6c-50ca-8c11-332f963ddc25 |  | note | Verifying Document-Daily Report, Chip Sealing Quality and Site Record
label | de2af923-94ad-5c59-9b16-dae480573152 |  | note | Conduct Test-Higgins
label | 78d3a821-b12c-5238-a6ab-77a1c0a03d72 |  | note | Produce Record-Higgins
label | 9ef21546-10c3-58be-9ecf-8819f4580b0c |  | note | Approval of Inspection-Higgins
label | 37a7fa72-6d9d-5ccd-9515-aebbf657f440 |  | note | Inspection Point-Y
checkpoint-status |  |  | checkpoint | Ensure Limits of site are marked
label | 4ae27d67-2b2a-5cf9-a834-4b32b4a12ce3 |  | note | Controlling Documents-MWNOC Design Report
label | b789eb80-ecd1-5ed5-86cf-876bd6e7abe2 |  | note | Acceptance Criteria-Visual Inspection
label | 55d049ed-cb5f-5b2a-bdd2-52ced7565abd |  | note | Method-Visual
label | 7616dd7b-043b-528a-aa2c-c7738f39f3cf |  | note | Frequency-Prior to start Sealing
label | 266c8516-6681-57ee-8931-0e5324a2b1de |  | note | Responsible Person-Surfacing Supervisor
label | 404a22e7-ed00-5338-9df5-e2909c93c2f2 |  | note | Verifying Document-Chip Sealing Quality and Site Record
label | 095a06d1-97cb-57e3-a3f2-61e386bdd4f1 |  | note | Conduct Test-Higgins
label | 90ba1f11-fd0e-5d34-8b21-d0143e10a16e |  | note | Produce Record-Higgins
label | acfb1a51-455f-5b27-b54f-daa668ef4375 |  | note | Approval of Inspection-Higgins
label | abe85368-b31b-5705-9280-39e2d9cec3da |  | note | Inspection Point-Y
checkpoint-status |  |  | checkpoint | Establish TTM
label | edc79499-1d23-5b4f-ae9c-23eaf5ecbee8 |  | note | Controlling Documents-TMP
label | 948279ae-8ed6-521f-b6b1-8920ce811f41 |  | note | Acceptance Criteria-Comply with TMP
label | cddbc955-3eab-5540-bb96-93a9b749dfc7 |  | note | Method-Visual
label | d0c750f7-8581-5470-889f-a6e91238be1b |  | note | Frequency-Per Site
label | 6e0d5eca-9586-5495-b2cd-1479804413f8 |  | note | Responsible Person-Traffic Safe STMS, Sealing Supervisor
label | eac5697d-590c-5f91-adc9-1c0b2f51c552 |  | note | Verifying Document-Daily Diary / STMS Record
label | 7ffe6e14-a1de-59a5-833a-9dcbd1105c1f |  | note | Conduct Test-Higgins
label | 151304d8-2756-517e-887f-13bcf1704c85 |  | note | Produce Record-Higgins
label | ebcffa91-b36c-58fd-a80b-70ba0c2c9338 |  | note | Approval of Inspection-Higgins
label | ae4a4436-34ae-5b29-93f1-3a2a9be90f1e |  | note | Inspection Point-Y
checkpoint-status |  |  | checkpoint | Sweep surface clean of deleterious material
label | 1ac6aa10-903c-5d77-a563-064f58c25833 |  | note | Controlling Documents-P/17
label | 68c03d69-360b-5ca1-9385-bc677624d373 |  | note | Acceptance Criteria-Visual Inspection
label | 90231f4e-d80c-5b80-bbf9-1c117cf9c7b5 |  | note | Method-Tractor Broom
label | c1d436b5-c727-536b-8b66-a098f4d966a9 |  | note | Frequency-Each site, prior to start of sealing
label | 2364103c-1ea2-5627-95d8-ba64d2a11c74 |  | note | Responsible Person-Surfacing Supervisor
label | 430feba7-dfc3-5b39-8c85-90a931c03538 |  | note | Verifying Document-Chip Sealing Quality and Site Record
label | cc638cc2-db61-5114-a211-7e6e3a94443a |  | note | Conduct Test-Higgins
label | 0bc8187c-3595-5619-82a1-00680a9ebaff |  | note | Produce Record-Higgins
label | f97617a6-a074-5663-94d7-aca28a49c40e |  | note | Approval of Inspection-Higgins
label | d933289c-c9d3-5fcf-aef0-faffd23a01c9 |  | note | Inspection Point-Y
checkpoint-status |  |  | checkpoint | Confirm correct treatment(s) and chip
label | c5709762-7984-5046-9339-84605dce169d |  | note | Controlling Documents-MWNOC15 Design Report
label | 2533d017-a39f-517e-8c6d-5bbf938db65c |  | note | Acceptance Criteria-Details/chip correct
label | eab6e820-c992-5cf1-bb9a-18b75d8a92bd |  | note | Method-Visual
label | 81c23994-5ac8-58dc-b3ef-8f72c61cb89c |  | note | Frequency-Per Site
label | bee6b749-8a4b-59af-ab7b-1712cdffff06 |  | note | Responsible Person-Surfacing Supervisor
label | d144af56-2238-5365-a7ea-fc162600ec7d |  | note | Verifying Document-Chip Sealing Quality and Site Record
label | 07f5fd3b-9453-5f8d-a492-dc78cf5b6c19 |  | note | Conduct Test-Higgins
label | ee8a61be-9162-5556-8810-16be927bdc83 |  | note | Produce Record-Higgins
label | 29ddb555-e364-56ed-b888-240faffdf730 |  | note | Approval of Inspection-Higgins
label | 119f3a4a-86c0-5f73-8b55-cedc40f8a2b6 |  | note | Inspection Point-Y
checkpoint-status |  |  | checkpoint | Cutback Bitumen Blend
label | 67a0107b-e3af-518a-a8f1-ce62f433dfe0 |  | note | Controlling Documents-RNZ 9803_0513
label | 34f252e8-41df-5d17-ad0f-d9d0d97c4e51 |  | note | Acceptance Criteria-+/- 2PPH Cutter, +ve for Adhesion agent presence
label | f23f7cc8-d820-5816-9bae-347468d7258e |  | note | Method-Sample and test
label | e2bf1005-14dc-5495-9be3-675e78ad328e |  | note | Frequency-1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
label | 098b4532-02a2-5456-8951-067ea77e1e52 |  | note | Responsible Person-Surfacing Project Manager, Surfacing Supervisor
label | 9ce69a69-5a65-5b23-be4b-419bed6dd828 |  | note | Verifying Document-IANZ Report's
label | 9022301c-eb27-5aa9-8664-821a96f43411 |  | note | Conduct Test-Higgins
label | 52e8f83a-67be-58b7-9e22-b956d4e2f893 |  | note | Produce Record-Higgins
label | c46bd5fd-d0b6-5286-823d-83d5a72d66b4 |  | note | Approval of Inspection-Higgins
label | 428c6d6d-2a2a-5eb5-9bcd-eff7b765a09a |  | note | Inspection Point-Y
checkpoint-status |  |  | checkpoint | Bitumen Application Rate
label | 5ce2ebb3-acc9-599b-ada3-0bc474ec94e6 |  | note | Controlling Documents-E/2 Certificate, Seal Design / Spray Instruction
label | 76438bcc-2942-55e9-85c3-289247cb5228 |  | note | Acceptance Criteria-Current E/2 Certificate, +/- 4% per Spray Run
label | c8fb11f8-aacd-58cc-abb1-317acc7fed61 |  | note | Method-Test, Review
label | 0413bac0-f389-5e3e-84e3-953d31afa6d6 |  | note | Frequency-Per Sprayer, per Site
label | 4795804a-2ab4-57c5-b7f9-f751d68d4e77 |  | note | Responsible Person-Surfacing Project Manager, Surfacing Supervisor
label | f21c13d0-07a9-5a93-a909-76b55d95d266 |  | note | Verifying Document-E/2 Certificate. Spray Sheets
label | aa932409-7278-562f-84f2-ff432517a8b6 |  | note | Conduct Test-Higgins
label | d0129d11-be01-5ef1-bac7-68f6543dad03 |  | note | Produce Record-Higgins
label | c8c3d35a-d697-54d0-8f22-f00a5aa381b0 |  | note | Approval of Inspection-Higgins
label | ae2f4129-c873-5de4-ac6e-3a3eebdea764 |  | note | Inspection Point-Y
checkpoint-status |  |  | checkpoint | Chip Application Rates
label | 0c05a889-8c73-59fd-9cff-39a0d40df9ad |  | note | Controlling Documents-Chipsealing in NewZealand
label | f34c77ed-a047-5a47-b226-45964ee027ea |  | note | Acceptance Criteria-As per Chipping Guide
label | 611f174c-ba9a-5f2d-bf71-04902c71016c |  | note | Method-Record
label | 22365ad7-f453-5d6e-8d0a-d11d81477a1f |  | note | Frequency-Daily
label | c9d233b7-f844-5abc-997b-43ea5740eb8a |  | note | Responsible Person-Surfacing Supervisor
label | 3e1267c7-32dc-586f-a73d-1f102707f01c |  | note | Verifying Document-Chip application check sheet. Chip Sealing Quality and Site Record
label | 4fce12be-2242-5a88-a94c-10b51dbcae7e |  | note | Conduct Test-Higgins
label | 25725c00-bb9d-5f07-a5c7-119b171fa582 |  | note | Produce Record-Higgins
label | 9e4b295b-698d-557a-afd8-65db8ed78e9c |  | note | Approval of Inspection-Higgins
label | 340ed227-ba60-51a1-9e9e-70c54fe99ca9 |  | note | Inspection Point-Y
checkpoint-status |  |  | checkpoint | Rolling
label | 6ba35563-6179-564e-94f1-8d164b8449ea |  | note | Controlling Documents-Chipsealing in NewZealand
label | 488ae5a5-a1ae-5ae8-a815-a6f92e86adec |  | note | Acceptance Criteria-Mimimum as per CS in NZ - Bit volume / 3600
label | 8552cb24-ff5c-5b9f-84e4-7edfe91fda63 |  | note | Method-Record
label | d9041fec-fd18-5d94-b109-ba720ca26746 |  | note | Frequency-Per Site
label | fc9e9755-a7cb-51d0-a9a9-8758599d786e |  | note | Responsible Person-Surfacing Supervisor
label | 8dfd2b14-85b7-5636-be49-044d652371db |  | note | Verifying Document-Chip Sealing Quality and Site Record
label | 114380b1-f64b-5289-ae76-d364a843f3cc |  | note | Conduct Test-Higgins
label | 4244b48c-d74e-58f9-8d32-238898d11810 |  | note | Produce Record-Higgins
label | 99cdbee3-85cf-575c-b99e-3e2df5a26b98 |  | note | Approval of Inspection-Higgins
label | 2f11133a-7abc-5e1b-a1d7-28c19e891d84 |  | note | Inspection Point-Y
checkpoint-status |  |  | checkpoint | Cleanup
label | 923e8eb7-d142-54c6-a92e-5e100b72a144 |  | note | Controlling Documents-Chipsealing in NewZealand
label | 301b07fc-6f66-56a9-8f15-d2c60baf4c63 |  | note | Acceptance Criteria-Site including adjacent surfaces free of loose chip
label | b352efbf-1253-5e27-9c95-03c11ac9f83a |  | note | Method-Visual
label | 4f7b5fb7-48ef-552d-80b8-ae0c5e991944 |  | note | Frequency-Per Site
label | 9f28ad6d-6b8a-5fbd-9c3c-098ff4180018 |  | note | Responsible Person-Surfacing Supervisor
label | ca881813-9620-5ecf-8d05-f9b307e82455 |  | note | Verifying Document-Chip Sealing Quality and Site Record
label | 41e8e14d-0c1c-5664-a009-3bd51a7c8c72 |  | note | Conduct Test-Higgins
label | f596eb9c-cd19-5c82-ae43-c9cf435a3587 |  | note | Produce Record-Higgins
label | 669fa92e-e57a-5258-9fe1-6e44bd13ed0a |  | note | Approval of Inspection-Higgins
label | 5baf0156-c1a9-5303-a355-2f7e9d217e40 |  | note | Inspection Point-Y
checkpoint-status |  |  | checkpoint | Removal of TTM
label | 89656fd4-42a6-5a16-b5ff-aa916dfbd821 |  | note | Controlling Documents-TMP
label | 4fd9184a-7e9d-58e9-bd69-75577607dab2 |  | note | Acceptance Criteria-Comply with TMP
label | fb39ebdb-433a-5954-836f-ea22251d0466 |  | note | Method-Record
label | af961c24-e86c-5009-b234-2c4de828f3f2 |  | note | Frequency-Per Site
label | 38c86c83-7e6b-52c4-861a-95e1ae9df6ab |  | note | Responsible Person-Traffic Safe STMS, Site Supervisor
label | 4417f679-6d0f-58d6-b00d-04a4cddecde8 |  | note | Verifying Document-STMS Record
label | e5bdc5c8-2fff-5965-93d7-1299ce01b4c7 |  | note | Conduct Test-Higgins
label | e98113b5-9456-5d1a-a704-be206af97f73 |  | note | Produce Record-Higgins
label | 1ac0c07a-0051-55c5-82c7-69d1362393c1 |  | note | Approval of Inspection-Higgins
label | 1a067746-f011-5be6-acd9-5cde0bb9a933 |  | note | Inspection Point-Y
checkpoint-status |  |  | checkpoint | Resurfacing Construction Completion report
label | de42c0b6-7458-583e-abcc-360ad70e0a0c |  | note | Controlling Documents-NOC; MS 6.1.3
label | 6529ecd3-b088-5802-92fd-9d6cedfa6f15 |  | note | Acceptance Criteria-Comply with Requirement of NOC MS 6.1.3
label | 9ee9b4fa-996b-5df7-993c-c4b5a735c470 |  | note | Method-Record
label | a192516b-3923-5897-8fef-8042b7d5eb11 |  | note | Frequency-Per Site
label | 5ae8c784-ea73-52e4-94eb-351c4d716965 |  | note | Responsible Person-Resurfacing Construction Completion report
label | 9435ae64-20a3-59f3-9a2f-7f14a995ba08 |  | note | Verifying Document-STMS Record
label | 0480b112-aed4-5db5-a4ed-4139d5514684 |  | note | Conduct Test-Higgins
label | 297cd57e-e689-5e26-b107-9b4a84106d86 |  | note | Produce Record-Higgins
label | 0bd947ec-7917-50fc-9875-982c113fa16d |  | note | Approval of Inspection-Higgins
label | e72a668d-0d69-545d-9945-9fb0ed232051 |  | note | Inspection Point-Y
checkpoint-status |  |  | checkpoint | Chipseal Post-Verification Testing and Report
label | ce2f74d2-f1e9-5268-8790-8af5c7adc151 |  | note | Controlling Documents-NOC; MS 6.1.3
label | 569c4f82-d005-5449-b04f-9e3f3cfbb9c6 |  | note | Acceptance Criteria-Comply with Requirement of NOC MS 6.1.3
label | 2e075a9b-a530-5bf1-a882-c2cb2e12791d |  | note | Method-Record
label | dfa47794-2627-50a7-9e92-147c37ed73ca |  | note | Frequency-Per Site
label | 610f6d17-e5f7-5ee1-b61c-daf973eab643 |  | note | Responsible Person-Surfacing Manager
label | 5acc3a59-2622-51be-a948-08d0ecd0a067 |  | note | Verifying Document-Chipseal Post-Verification Testing and Report
label | f286cd3b-0396-5e13-8769-59f26f5689e0 |  | note | Conduct Test-Higgins
label | 58042553-c07e-5e9c-89df-c007239266a0 |  | note | Produce Record-Higgins
label | fdaf9a0d-a282-596d-8122-750db69b6590 |  | note | Approval of Inspection-Higgins
label | 3fc6c421-fc18-5f2f-8bfe-3d1c1c69b3bf |  | note | Inspection Point-Y
checklist-flat |  |  | checklist | Basecourse Overlay & Stabilise |  |  |  |  | Yes | Basecourse Overlay & Stabilise - SH2 MANAWATU HILL AWPT - 2015 | f57fc7f1-1b6e-400a-89d1-94a03fb109e8
checkpoint-status |  |  | checkpoint | Material - Approval of M4 AP40 Material for Base Course
label | 86ec15d9-8c03-53bc-97db-b3cd49544bed |  | note | Reference - TNZ M/4: 2006
label | 10039f09-2c34-58bb-adf4-931b91bcae4f |  | note | Requirement - Quarry Material Test Results to meet standards and specification
label | 1fce7184-ed89-5e7c-920f-d60e771f62c7 |  | note | Frequency - 1 Test Every 10,000m3
label | ed21b343-cc46-5a9b-8b36-8dcbfbde7088 |  | note | Hold Points - Verify
label | c44d0672-f5ea-52e4-a63a-ba6e404cbcee |  | note | Responsibility - Project Manager/Project Engineer
text | f9e982b4-847d-520c-b38e-c5cf28a9c269 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Drainage - Driveway culverts
label | 4bd57213-6441-5ecd-a66a-067b5620563f |  | note | Requirement - As directed by NOC Renewal Manager
label | 01b88014-a6ea-5fae-a8aa-314f7e578a15 |  | note | Frequency - On-Site confirmation
label | 6643240d-94fb-5ac5-9044-a8027ea0f2e4 |  | note | Hold Points - Hold Point
label | 90b613db-6a12-590e-ba94-82d567eea30b |  | note | Responsibility - Site Supervisor/ NOC Renewals Manager
text | aa33aea2-084e-5e17-9514-28a63c72f85f |  | textbox | Date:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Drainage - Sub-soil drain
label | 042bcd81-5a1b-5c9b-8e09-1e70595ce85b |  | note | Requirement - As per the approved construction drawing
label | e90dc02d-3d56-5833-930b-fe02e51c5f8e |  | note | Frequency - every 50m check the depth of backfill with peametal & hardfill with GAP40/65
label | 167b03ef-e8fb-5781-b1f9-6a739ad83e1b |  | note | Hold Points - Verify
label | 9cedf786-e523-53df-a961-558937d9fc97 |  | note | Responsibility - Site Supervisor / Foreman
text | 5324659f-f844-5672-b08b-910b14d7d759 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Pavement Dig-outs to 160 mm - Excavate only to approved level
label | 4f44dc7e-1b5d-5ec4-918f-397b3978b6b9 |  | note | Requirement - Mark-out & excavate as directed by NOC
label | 78bee811-dab5-50e7-97ac-32f75442b507 |  | note | Frequency - On-Site confirmation
label | 7eb2971d-628c-55ae-85c4-3ee1c1a2c5ec |  | note | Hold Points - Hold Point
label | 49dd2010-0bc3-5788-8598-75f38a38acf3 |  | note | Responsibility - Site Supervisor/ NOC Renewals Manager
text | ec5cb638-b5c9-5069-8b60-d8a27fb22e90 |  | textbox | Date:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Tie-In - Excavate & backfill
label | 0eb3322e-4a42-576d-8f43-54ef304e5b5d |  | note | Requirement - Mark-out, excavate & backfill as directed by NOC
label | 4a584d01-6490-5a00-bf93-db18e832230c |  | note | Frequency - As required. To be agree with NOC Renewals Manager
label | 7a85319a-4a22-5219-a3c1-cc567000a7ca |  | note | Hold Points - Verify
label | acdbefac-b092-5ab2-876f-e64326d83a3c |  | note | Responsibility - Site Supervisor/ NOC Renewals Manager
text | e4386c23-d30c-56a7-a80a-808c59a0eb78 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Approval to stabilise subbase - Acceptance of subbase layer
label | dac301ae-8c36-575e-84d7-2b16fbf4381f |  | note | Reference - TNZ B/5:2008 - 7.2.1
label | 6fd2ae99-c76f-503d-8d1c-6be79099dd4f |  | note | Requirement - NOC Renewals Manager to authorise stabilising to proceed
label | 217f852e-4d4e-5502-a9ac-d156d68268cc |  | note | Frequency - Each section of stabilising
label | 0fce43d6-0de6-58da-b8ac-c1a14dfb3507 |  | note | Hold Points - Hold Point
label | e0b82eed-0778-5f64-bd62-f3994f8c9858 |  | note | Responsibility - NOC Renewals Manager
text | b263e4ff-5c65-5a7f-81bc-9869a9c51656 |  | textbox | Date:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Cement Content Testing - Spreading of lime and/or cement
label | 4791b463-d586-58fa-9ecd-97415f451af6 |  | note | Reference - TNZ B/5:2008 - 7.3
label | eafb4cb3-997a-5512-b850-5cd04f01b076 |  | note | Requirement - Mat test: (1 m2 canvas) Within ±0.5 kg/m2 of the specified rate
label | 76bf8376-9d35-5db7-9da8-4914d5d05a97 |  | note | Frequency - Every 500 m2
label | 802216dd-a483-5df2-9920-1212fd25c4a6 |  | note | Hold Points - Verify
label | 1615db1e-df2a-5df6-ac94-dba03df87915 |  | note | Responsibility - Site Supervisor / Foreman
text | 4d067434-98b1-5f96-8762-d25d5e45c6cd |  | textbox | Date:
label | c1b2999f-eb1b-5c79-b633-783eb6a979b9 |  | note | Comments: Check the weight of cement & take photos
checkpoint-status |  |  | checkpoint | Stabilised Subbase - Stabilised Subbase
label | ef7373cc-8a02-5dc7-ab5a-007fd6bdea4d |  | note | Reference - TNZ B/5:2008 - 7.6
label | 9cfca023-cf74-5532-be2f-6890b113fd3c |  | note | Requirement - Stabilised subbase 250mm thick with 5% cement
label | e3266a92-8fb8-55b4-9998-daeb65c7c86b |  | note | Frequency - Cut depth shall be physically measured at both ends of the stabilising drum at least once every 200m along the cut length of miller run. Maximum variation from the specified depth of cut is –5 mm and +15 mm.
label | 5773be43-36d4-5b24-a449-5f4dc2a22ed1 |  | note | Hold Points - Verify
label | f93b7146-ae5b-5a19-91d7-6adc5cffb351 |  | note | Responsibility - Site Supervisor / Foreman
text | 7f785d73-1225-5385-8e7f-08666031b16d |  | textbox | Date:
label | 0925250e-12db-5ee5-b5d1-a1ab26b8aeaa |  | note | Comments: Check the depth of mill & take photos
checkpoint-status |  |  | checkpoint | Plateau Density Tests - Acceptance criteria for stabilised layer compaction
label | 27e39e14-be8c-56ee-8577-456707983642 |  | note | Reference - TNZ B/5:2008 - 7.7.1
label | c3298e2f-71e4-539a-af94-87d92540586b |  | note | Requirement - The Contractor shall undertake plateau density tests for the purpose of determining the target density
label | 68ebbdaa-8c67-5498-84b8-1f17472b8be2 |  | note | Frequency - One OWC/MDD test per 5000 m2.
label | 7e2665b6-6d61-5732-987f-ab92f3633e9c |  | note | Hold Points - Hold Point
label | 25f66232-e10f-5a01-bbce-68094c74dd67 |  | note | Responsibility - Site Supervisor/ Project Engineer/ NOC Renewals Manager
text | 262b4750-aeb2-5086-8104-37c11240481b |  | textbox | Date:
label | ffb10b01-f8f8-53a7-a205-0aadd6dd9b6a |  | note | Comments: During construction, the agreed maximum dry density (MDD) for the stabilised material shall be determined by the Contractor and the Engineer using the test data obtained from the laboratory testing before construction, and the in-situ plateau density during construction.
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Compaction Testing - Nuclear Density Test
label | 2b2dfd09-e7be-5583-b5f0-4203ddefe575 |  | note | Reference - TNZ B/5:2008 - 7.7.1
label | 77224827-574c-5a02-a176-335aae3cbf93 |  | note | Requirement - Base MDD - Average ≥ 98% - Minimum ≥ 95%
label | c6037ac5-248e-5e4f-bfde-d214a6c252f3 |  | note | Frequency - 1 test every 20 lineal metres
label | fa1ff6c9-2874-5ebc-be55-563be8b600bf |  | note | Hold Points - Hold Point
label | a0333403-0580-5bdf-8c2a-0d59cab567db |  | note | Responsibility - Project Engineer / NOC Renewals Manager
text | 1cc36818-87b6-5c15-9ec1-ab5d9e9a79b2 |  | textbox | Date:
label | 3d70a8a4-5410-5704-9545-352bc1ee3dbc |  | note | Comments: Engineer has to sent the results to NOC Renewal Manager for approval
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Subbase Acceptance - Acceptance of subbase - visual inspection of surface
label | cbe84af7-4e21-573d-862f-992c43d6ad4f |  | note | Reference - TNZ B/5:2008-7.8
label | b7718962-5aad-52fe-85ed-21fe82d8095d |  | note | Requirement - No Base Course layer to be place until approval of subbase by Engineer
label | 3f0c8261-f14f-52b6-820c-eec6381097bc |  | note | Frequency - Per Lot
label | 25ab0497-1087-5c4e-bb8b-ca17ab5f1d56 |  | note | Hold Points - Hold Point
label | ca067bc3-5752-5db8-b3e4-a62fa8d27dda |  | note | Responsibility - Site Supervisor / NOC Renewals Manager
text | 2b2b8cdc-8ff4-5acc-9f78-e05d679e5e86 |  | textbox | Date:
label | 9404fb28-aecb-56bc-ac13-ad05cadb3e45 |  | note | Comments: Supervisor has to contact NOC Renewal Manager to approve the final Base Course.
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Subbase Acceptance - Degree of saturation (DOS)
label | 0d560e85-e521-5456-bfc2-492237aea3e9 |  | note | Reference - TNZ B/5:2008
label | 2fdb69af-5f3c-593c-9c05-55b4bef4503b |  | note | Requirement - < 60% (or 80% on consultation with the pavement designer)
label | efa335ee-7a33-58b7-a02c-bd2c1daf5f54 |  | note | Frequency - 5 (five) randomly selected areas
label | 5180b5c5-c4c6-5a4d-92e8-96c6e03fe17f |  | note | Hold Points - Hold Point
label | c79f32c0-3592-5639-93fa-7b61862385bd |  | note | Responsibility - Project Engineer / NOC Renewals Manager
text | 6320fb7e-0f16-529f-aeb9-eb554b980396 |  | textbox | Date:
label | 0487966f-a3ee-539c-a0ec-33308c77d690 |  | note | Comments: Pavement layer compaction test results may be used for this purpose where the Engineer is satisfied that the water content has not had a chance to rise between testing and sealing. (i.e. it has not rained or additional watering has not been applied to the pavement).
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Base Course layer - Place Base Course layer to design level
label | c6d278b7-bdc1-5591-84bd-8e47c5a3a012 |  | note | Reference - TNZ B/5:2008 - 7.3, 7.7 , 7.8
label | d6dfd1be-3003-5c02-b199-e8aadb88942d |  | note | Requirement - 160mm thick M4 AP40 (average depth)
label | 305d0655-120e-5aa6-89b3-27027c6fc32a |  | note | Frequency - Each Lot of Base Course. Confirm with Survey Manager
label | 67c5bee0-b751-52bb-a2cb-0da38bf7a43b |  | note | Hold Points - Verify
label | dc484785-51ba-548b-8a5a-b289385e751c |  | note | Responsibility - Site Supervisor / Project Manager / Project Engineer/Survey Manager
text | 584ba75e-4f77-5238-9ae6-d1c2b3109b42 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Approval to stabilise Base Course - Acceptance of Base Course layer
label | 05843d7f-a977-54d9-a9cc-7fdbe67acd48 |  | note | Reference - TNZ B/5:2008 - 7.2.1
label | 32a1fb3c-8bba-54f4-bcef-b0dae2f2c84b |  | note | Requirement - NOC Renewals Manager to authorise stabilising to proceed
label | a74a2c83-09e6-505b-8d1d-0351db8d3fe6 |  | note | Frequency - Each section of stabilising
label | 44de3b4f-5a78-550a-a8f0-7e8f4dfd4e16 |  | note | Hold Points - Hold Point
label | b45aca0d-ab77-5539-9af9-2ac1d35ffd9a |  | note | Responsibility - NOC Renewals Manager
text | c4025443-9b01-5f40-8069-96a76d16ea21 |  | textbox | Date:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Cement Content Testing - Spreading of lime and/or cement
label | 11df3c14-8c10-5a56-b2cd-6195946c4b79 |  | note | Reference - TNZ B/5:2008 - 7.3
label | 1aa07f5c-46f1-57e9-9a47-96264b1851c9 |  | note | Requirement - Mat test: (1 m2 canvas) Within ±0.5 kg/m2 of the specified rate
label | 5a6ecf24-e77f-5af5-becc-e1f259db6962 |  | note | Frequency - Every 500 m2
label | 4e7e7052-f79b-5680-90e9-065b82e8c682 |  | note | Hold Points - Verify
label | bf54de5f-f86a-5fc7-ba00-3d7516c60a31 |  | note | Responsibility - Site Supervisor / Foreman
text | b7d0820c-c040-5f9f-8208-5f79cb256605 |  | textbox | Date:
label | fe58de76-bd70-5b68-b974-37d5ddb754ba |  | note | Comments: Check the weight of cement & take photos
checkpoint-status |  |  | checkpoint | Stabilised Base Course - Stabilised Base Course
label | d4276108-4c4d-5356-af20-374847216df4 |  | note | Reference - TNZ B/5:2008 - 7.6
label | 575d7e08-d680-5a1a-a003-2a90eb12a612 |  | note | Requirement - Stabilised Base Course 180mm thick with 1.5% cement
label | 1241cdf9-407d-50a2-a89c-3ab9089102fd |  | note | Frequency - Cut depth shall be physically measured at both ends of the stabilising drum at least once every 200m along the cut length of miller run. Maximum variation from the specified depth of cut is –5 mm and +15 mm.
label | 15690069-587b-5c29-b739-24acb0453f53 |  | note | Hold Points - Verify
label | 94f78356-716d-5562-853c-6498a089a129 |  | note | Responsibility - Site Supervisor / Foreman
text | 7fba6af0-ed1d-52b0-96a3-f51ee1b09fd7 |  | textbox | Date:
label | 3d544af3-2089-54c0-8df0-6a2e683bb494 |  | note | Comments: Check the depth of mill & take photos
checkpoint-status |  |  | checkpoint | Plateau Density Tests - Acceptance criteria for stabilised layer compaction
label | 3be4ff75-300f-5c6d-a719-c03759341415 |  | note | Reference - TNZ B/5:2008 - 7.7.1
label | 372c824c-7e43-5c5e-baef-c2033e43f114 |  | note | Requirement - The Contractor shall undertake plateau density tests for the purpose of determining the target density
label | 7a8bfded-aace-5569-8650-7911ff1c29f7 |  | note | Frequency - One OWC/MDD test per 5000 m2.
label | a09b747f-e981-5415-9a0f-2478b3bffdb5 |  | note | Hold Points - Hold Point
label | ce3f28d8-24dd-5139-ad4f-8b88a4af3367 |  | note | Responsibility - Site Supervisor/ Project Engineer/ NOC Renewals Manager
text | 9442ba6e-ca43-55cb-ad5a-b90946112e1e |  | textbox | Date:
label | 26c58505-71fc-573f-bf41-e1865545b780 |  | note | Comments: During construction, the agreed maximum dry density (MDD) for the stabilised material shall be determined by the Contractor and the Engineer using the test data obtained from the laboratory testing before construction, and the in-situ plateau density during construction.
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Compaction Testing - Nuclear Density Test
label | 34307d3d-0877-51c1-8cb3-8d324c3cb42c |  | note | Reference - TNZ B/5:2008 - 7.7.1
label | 18b59836-2746-58ac-98fb-3f47a7025c01 |  | note | Requirement - Base MDD - Average ≥ 98% - Minimum ≥ 95%
label | 8ba419d0-5893-5101-89fc-ab4aaae3a28f |  | note | Frequency - 1 test every 20 lineal metres
label | c7fe7d7d-5bbc-5f75-8127-0b956cbd405c |  | note | Hold Points - Hold Point
label | 862749da-becb-53e7-9f48-8748cd119f2a |  | note | Responsibility - Project Engineer / NOC Renewals Manager
text | f33d39a3-b4c9-5fcb-b53d-b5bb222c4685 |  | textbox | Date:
label | 0f0a4da6-6af1-5523-bc23-49ed1f24523a |  | note | Comments: Engineer has to sent the results to NOC Renewal Manager for approval
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Acceptance - Acceptance of Base Course - visual inspection of surface
label | 007729d0-a96e-5e0f-90cf-0afd1fa82568 |  | note | Reference - TNZ B/5:2008-7.8
label | 1ff63d5f-6071-5fe7-8a69-60dfbce6f3bf |  | note | Requirement - No Chipseal to be placed until acceptance of Base Course layer by Engineer
label | 5cd2ee31-ef26-5807-ba72-defcaac8b867 |  | note | Frequency - Per Lot
label | 52dc0d1a-1d04-5c3c-90c8-10fe9cce4a30 |  | note | Hold Points - Hold Point
label | 97a16b1c-2880-5142-a4c4-b158c53c9879 |  | note | Responsibility - Site Supervisor / NOC Renewals Manager
text | 279982ce-1129-5132-ae89-6817c5d95330 |  | textbox | Date:
label | 9c0623fb-407d-5a6d-8932-ab15d24760be |  | note | Comments: Supervisor has to contact NOC Renewal Manager to approve the final Base Course.
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Base Course Acceptance - Degree of saturation (DOS)
label | 1f7926cd-ddc6-51d3-a8f5-e79b2704391e |  | note | Reference - TNZ B/5:2008
label | e948fd09-546e-5d9a-9e89-4b3271fb1ffd |  | note | Requirement - < 60% (or 80% on consultation with the pavement designer)
label | 5a50a532-d33f-522d-9a8d-fb36b2886b01 |  | note | Frequency - 5 (five) randomly selected areas
label | 3605273e-e576-5552-9b4d-f3f6450d5708 |  | note | Hold Points - Hold Point
label | 18d6139b-85ae-587e-a0b7-11266aeebe78 |  | note | Responsibility - Project Engineer / NOC Renewals Manager
text | 5673ccce-cfd5-58b6-bd3e-411ce95020f3 |  | textbox | Date:
label | 45e49777-5d06-5061-b465-37e0fb484b48 |  | note | Comments: Pavement layer compaction test results may be used for this purpose where the Engineer is satisfied that the water content has not had a chance to rise between testing and sealing. (i.e. it has not rained or additional watering has not been applied to the pavement).
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Chip - Check chip in stockpile
label | aabe156c-5dba-5eba-b6b7-5a6c61b24ac5 |  | note | Requirement - confirm size, quantity, cleanliness
label | 539b0ad2-d7e1-5da5-90af-f13035eefcc1 |  | note | Frequency - Per Lot
label | f198d7df-302b-57f7-b922-9d2e08d98be4 |  | note | Hold Points - Hold Point
label | b6a10332-2516-54ba-8f04-2e3123715910 |  | note | Responsibility - Project Engineer / NOC Renewals Manager
text | 6f1a0794-52ad-5fab-9702-0839ae40b829 |  | textbox | Date:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Sealing - Pre-surveyed seal area –
label | 87a13044-17e9-589a-bbc1-93d0b3d35454 |  | note | Requirement - Prior to first coat, confirm seal extent and get confirmation from Renewals Manager
label | 384bf43c-bd69-5efd-b385-e7f77ccadc5d |  | note | Frequency - Per Lot
label | df137c1b-a735-56d7-b14a-9766e7a8a332 |  | note | Hold Points - Hold Point
label | ae48d9c1-d542-564b-97da-40d7357a38fa |  | note | Responsibility - Project Engineer / NOC Renewals Manager
text | 20cca707-5ed7-55d5-b9b9-b65be2deafb0 |  | textbox | Date:
holdpoint |  |  | signoff | HOLDPOINT