## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - Resurfacing | itp |  |  |  | Yes | ITP - Resurfacing | 0c05b808-e201-4bdf-84eb-579cbac4dfae
checkpoint-group |  |  | section | 1.0 Pre-Work
checkpoint-status |  |  | checkpoint | Approved JMF for Strengthening Repairs Mix (if required)
label | a024d5bf-f658-5fef-b961-28b8d5df27c9 |  | note | H
label | e364ef62-4351-57e6-a174-dffa3841e902 |  | note | Reference or Specification - Design Report
label | 42c6de4a-ab86-5728-91b0-cdfcb66daf07 |  | note | Method/Test Required - Confirm approved JMF dates in Design Report
label | 5e53a8a0-a384-5d8e-92f0-6bd8dc927f54 |  | note | How Often? Each site
label | 11797eff-8b58-5aea-82db-953342a862e6 |  | note | Records Required - Copy of Approved Design Report
label | 72e36507-5cc8-56c4-b8cc-95c8d17c7c66 |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Approved JMF for Pre-Level Mix (if required)
label | bd0de5a3-35d9-5d76-ae8c-5604bb0d4e2b |  | note | H
label | 31ecc9ff-eaa1-5b2d-a830-41a25af4c631 |  | note | Reference or Specification - Design Report
label | 52c82ad5-8530-5855-b0b7-58754e038b84 |  | note | Method/Test Required - Confirm approved JMF dates in Design Report
label | 306105f2-f518-50e0-94d1-bb99b13fbb12 |  | note | How Often? Each site
label | b3b7f7a6-69dc-5eb3-a6ab-388f31d3dcb2 |  | note | Records Required - Copy of Approved Design Report
label | 8b4695bf-751e-506f-a301-fe2cc9a4ccbd |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Approved JMF for Wearing Course Mix
label | 2d1d30e5-fdc3-58ed-93bc-fa6a48bf5186 |  | note | H
label | ef841a8e-9a69-5343-9569-3c8139f7bdf5 |  | note | Reference or Specification - Design Report
label | 1b15bbf7-d9fb-59d7-b70c-ea2af5e78a2c |  | note | Method/Test Required - Confirm approved JMF dates in Design Report
label | fc6c5a33-33d2-55b6-9a3e-2055513c7749 |  | note | How Often? Each site
label | acc3c24c-dddb-573c-8efb-541a308b1ca9 |  | note | Records Required - Copy of Approved Design Report
label | e44bf0cd-919e-5b74-aa9c-1c9987ae2112 |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Approved Design Report
label | edc29671-0081-5025-adde-2c04770d063a |  | note | H
label | 9a8de062-8699-53d1-8494-582705b4b093 |  | note | Reference or Specification - Design Report
label | 67f99758-af06-5964-a5d3-1a409ed4756c |  | note | Method/Test Required - Confirm document on-site
label | 0525ef29-5f63-563a-8cc6-2cb38cf5dbe3 |  | note | How Often? Each site
label | 3c266a68-0af5-5684-acd6-2f26dd28a4ae |  | note | Records Required - Copy of Approved Design Report
label | 908114db-b506-567c-9f68-8c63be168677 |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Treatment of affected Service Covers (to be raised or protected)
label | 710fbe1a-4660-5342-bef8-8bd11702488d |  | note | H
label | dbc19095-6061-5eaf-800e-2bcb6419bb3e |  | note | Reference or Specification - Job sheet
label | 248f68cd-018e-52f8-b95a-95f72ac7fecb |  | note | Method/Test Required - Confirm plan in place
label | e03befc2-16aa-58e3-8b20-b4eb3e332877 |  | note | How Often? Each site
label | 8f77222b-8aae-5e00-9d13-573e6c52e82d |  | note | Records Required - Job Sheet record
label | 4aae8d2f-479f-5588-9300-47a92f5f00af |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Stakeholder Management Requirements met
label | 0d54bf7b-18b7-5c10-91f1-7092030f3b5c |  | note | H
label | d1bcf89c-9b88-5860-8acd-a72321ae418c |  | note | Reference or Specification - CSCMP
label | 4e9d0bbc-8aa6-5cb1-8fdb-7d508848e002 |  | note | Method/Test Required - Confirm requirements followed
label | b1d88f2e-5ae3-5e2f-994c-476ca97c741d |  | note | How Often? Each site
label | 9089b33b-6eb4-524b-b035-d4e6e3d00677 |  | note | Records Required - Copy of stakeholder notification / Photographs of VMS Boards
label | 2ea41c7f-c4da-5ca0-bb62-25f817d0ba15 |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work
label | 64fd45e4-931a-578f-8134-bfe6b9e251ad |  | note | H
label | 8aa0376f-8bb1-5c6d-b6cc-b3a69b7860d5 |  | note | Reference or Specification - QMP
label | bf2c01e2-bd45-5821-82b3-b3d7f29cde6e |  | note | Method/Test Required - Brief all team members on day’s work plan
label | daf638d6-5f22-5040-b4d3-e3fab006d752 |  | note | How Often? Each site
label | 1e261f7d-e13d-5489-b821-1bd8898ac3b0 |  | note | Records Required - Daily diary
label | 57f412d5-eff5-593b-93ea-215b23dbac3f |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Confirm if any environmental protection is required
label | 6983ca34-b2c2-576d-9cb1-e6b64b6643d0 |  | note | H
label | 9cd11dd0-b0fb-5549-89c4-ea1de0490827 |  | note | Reference or Specification - ESMP
label | b0772333-20e0-5ce4-a6c3-b52f85ade6d7 |  | note | Method/Test Required - Record decision
label | 57105e6c-f176-5b9c-b0dc-4c23042f12b9 |  | note | How Often? Each site
label | 19b70933-bd00-58d5-a729-425f4f07cbe6 |  | note | Records Required - Job Sheet record
label | a761e08c-0065-5f2c-b3eb-0fba114561b3 |  | note | Responsibility - Project Manager
checkpoint-group |  |  | section | 2.0 Site set up
checkpoint-status |  |  | checkpoint | Ambient Conditions - Pavement Surface Temp ≥ 5ºC (Intermediate or structural layers) and ≥ 10ºC (wearing course) and forecast to rise
label | a218bc71-e55d-5256-80fa-51b4831d99a1 |  | note | H
label | 71794d7c-885c-57c2-828b-7414205b5023 |  | note | Reference or Specification - NZTA M10: 2020 9.5.2
label | f7a1a9b3-902d-5ae9-a94c-1e518bffa820 |  | note | Method/Test Required - Temperature Gun Check
label | 8c2ee2d4-8f5f-5c1b-8b30-da5659f73406 |  | note | How Often? Each site
label | 31f43ee9-46b6-5845-b601-ed88f410270a |  | note | Records Required - Job Sheet record
label | b2173da3-af73-5963-9917-d8a6df38ce20 |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | Job start, identify risks and controls, communicated to team
label | 4021c400-06a5-5e94-8d9c-d07b038cff1d |  | note | H
label | 882b1917-29d7-5268-a477-c8b81572ea0f |  | note | Reference or Specification - HSMP
label | aa2ef453-245c-52e1-8d6b-b9735af3912a |  | note | Method/Test Required - Record all risks and controls on Hazard ID following Team discussion
label | e4ff66a6-0c3c-5d83-8051-42d8a9ffccc3 |  | note | How Often? Each site
label | 59a87781-6a2f-58b4-aad6-865a810d5c2d |  | note | Records Required - Hazard ID form
label | 67e336a7-3065-50dd-8aea-52a74229b4bc |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | Establish traffic management to plan
label | 8469f5b3-635a-58fb-8527-dc23cbd36b5e |  | note | H
label | 00013edf-637e-5ba7-a624-a690299f94d6 |  | note | Reference or Specification - TMP
label | c371d0b7-4bd7-5d32-9a69-3e52bdf4a2a7 |  | note | Method/Test Required - Site audit post set up
label | 98f7b843-9691-5dd7-84ff-916b9d7eb951 |  | note | How Often? Each site
label | 87b1bc71-9d9d-549c-85d6-2c7ce2b4ea0a |  | note | Records Required - TTM diary
label | be974457-091b-5142-b056-45ab0c88965c |  | note | Responsibility - STMS
checkpoint-status |  |  | checkpoint | Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report
label | aadfcf2d-0c7e-5f7c-b099-a7168f769741 |  | note | H
label | 47ee3127-0e20-57f3-bd55-b15452b074ed |  | note | Reference or Specification - Design Report
label | 7601c67a-bf59-5c53-91b1-7eec29eaadfd |  | note | Method/Test Required - Record as-built site dimensions
label | 78e00f28-112b-509b-a65b-1cd7553934dc |  | note | How Often? Each site
label | 4fd12504-f8d1-5742-86b0-6930cdfcbc52 |  | note | Records Required - Job Sheet record
label | 3cd4b21c-6de5-5433-97e5-0f3449ba0cba |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | Identification of Services; Service Plans on Site; Shallow Services Marked
label | 8b129944-425c-57b2-b803-a69d85358a8c |  | note | H
label | a7c018a6-1636-5fa2-a4c9-f4bee9f35925 |  | note | Reference or Specification - SOP
label | 14a9088b-2b78-50f2-8aca-39cd4abf14be |  | note | Method/Test Required - Confirm document on-site / Visual check
label | 48d54a18-bb10-546b-b197-e25eae48fb47 |  | note | How Often? Each site
label | 2dcfe7de-1356-5019-9d74-185a08b90037 |  | note | Records Required - Job Sheet record
label | 6bd0e704-36ee-58c2-957c-384e5ca72a48 |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | Record & photograph environmental protection measures installed
label | b9f38abb-d3f3-507c-bf56-2da72bdaaf08 |  | note | I
label | 8ec32a6d-267e-5fec-a34e-29af503337ef |  | note | Reference or Specification - ESMP
label | a3316ea7-c36c-562b-a5a2-f1904f6051b9 |  | note | Method/Test Required - Record temporary measures
label | 737a5eab-c11e-5580-80ae-cd34db1963a1 |  | note | How Often? Each site
label | ccca5baa-a6a8-5c7b-af13-e89c4b574883 |  | note | Records Required - Job Sheet record & photograph
label | 4e50a391-f7ac-53cf-9a3c-7710ba04214e |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-group |  |  | section | 3.0 Milling (If Required)
checkpoint-status |  |  | checkpoint | Milling undertaken to correct depth - +/- 5mm nominal thickness
label | ae345f90-0eff-54ec-bf27-b35628f8da66 |  | note | I
label | 1ad4c0b2-f1fd-5028-8675-eaad8dad8544 |  | note | Reference or Specification - Design Report
label | b51e0643-67a4-54e2-97ab-2f839a69a3f7 |  | note | Method/Test Required - Dip checks
label | 93b6ab96-beaf-5317-b7f1-bf69feab55ff |  | note | How Often? Per site
label | 608fb053-5435-588c-b3a2-959857305bf1 |  | note | Records Required - Job Sheet record
label | 8a1d2ac0-fa48-5d95-bdae-c03188e56b83 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-status |  |  | checkpoint | Exposed Basecourse waterproofed / levelled
label | 5c76162b-407f-53af-b93a-bc66c80f2891 |  | note | I
label | 059ae904-d765-5347-b410-6fbf09a45051 |  | note | Reference or Specification - QMP
label | d52444ce-52af-58af-913f-fc04a96a29c9 |  | note | Method/Test Required - Acceptable / Unacceptable
label | 41f3a8d7-045f-5044-8dbc-28d7633d71cb |  | note | How Often? Per site
label | 3790c320-8dba-5cf0-a4e6-dafd03ee5722 |  | note | Records Required - Job Sheet record
label | de836c3a-b2fe-528c-9281-00336bb8ed6f |  | note | Responsibility - Site Supervisor
checkpoint-group |  |  | section | 4.0 Membrane (If Required)
checkpoint-status |  |  | checkpoint | Application as per Design Requirements (Chip size / binder application rate)
label | 77c4e6e3-c922-5bd4-af83-f4a3c183691c |  | note | I
label | 3585ce3c-1228-5fe7-ab93-4113f949a556 |  | note | Reference or Specification - Design Report
label | a79787e0-44b3-5d84-8bf2-d7394424ea19 |  | note | Method/Test Required - Spray Sheet/s
label | c7ef2cc8-6dfc-5b8d-84a3-a6d23133cc8a |  | note | How Often? Per site
label | da49fd37-99bc-5375-8219-635cf53f46b1 |  | note | Records Required - Job Sheet record
label | 3af54cc0-2135-529b-a9cd-62005fba4093 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-group |  |  | section | 5.0 Strengthening Repairs (If Required)
checkpoint-status |  |  | checkpoint | Delivery temperature - +/- 30 degrees from recommended mixing temperature
label | 71767c44-f82c-53ae-ae54-3c2f5590da27 |  | note | T
label | 0abf82fc-4765-59c9-8020-211438418388 |  | note | Reference or Specification - NZTA M10: 2020 Notes
label | 72ecc88c-0ee1-5c6c-b77f-25bdef779571 |  | note | Method/Test Required - Temperature Gun Check - Acceptable/Unacceptable
label | bca8b1e7-5a46-5eeb-bd61-82bec2c4c41a |  | note | How Often? Per load
label | 920705e4-fcc1-55d8-a989-22da0364c107 |  | note | Records Required - Job Sheet record
label | 3228344f-bbeb-5ac8-aa94-5f9748dcc20d |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | Structural Asphalt Layer Thickness - Each Layer >55mm with ±10mm nominal thickness
label | e8aea0df-4864-500a-877b-19c29dfe1ebd |  | note | T
label | 654f8385-66a8-59c4-be59-ea86a93e7d44 |  | note | Reference or Specification - NZTA M10 2020 10.1 & Table 3.1
label | 5ba93131-127a-53fa-8ad7-e70cc57dbbbe |  | note | Method/Test Required - Dip checks during paving process / Cores
label | b4b9c305-b0f2-5fe6-831b-c509ba4bcad3 |  | note | How Often? One test per patch & / or One test per 300m2
label | 6be51e52-6d26-5b89-8972-a880ee0e2273 |  | note | Records Required - Job Sheet record & photograph
label | fe815bac-9dbb-5b2e-a77e-2b01f0d7d1e5 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-status |  |  | checkpoint | Compaction and Air Voids
label | 8d845ac8-b683-557e-b81c-ec1b221462a5 |  | note | T
label | bd220764-0f71-567d-a104-82f3d7ef88b8 |  | note | Reference or Specification - Paving SOP
label | 932e2f8a-6d17-5cd4-a298-cd6dab0c974d |  | note | Method/Test Required - NDM for Quality Control Only
label | f64cf966-0187-5009-88d9-bb91c736f964 |  | note | How Often? One test per patch & / or One test per 50m2
label | f44acc37-218b-5199-9ee1-ff7b4e0f10d6 |  | note | Records Required - Job Sheet record & photograph
label | b4293d48-6a69-5265-a926-94643af1847f |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-group |  |  | section | 6.0 Pre-Levelling (If Required)
checkpoint-status |  |  | checkpoint | Delivery Temperature - +10 / -30 degrees from recommended mixing temperature
label | 2f935b92-cab4-56b8-b938-8dc2e0c83564 |  | note | T
label | 95af440d-2ce6-51d1-ab59-40e6ea34221a |  | note | Reference or Specification - NZTA M10: 2020 Notes
label | 1c3264ab-49f7-5f22-bd53-daa497b0e0a8 |  | note | Method/Test Required - Temperature Gun Check
label | 66020f9f-7ea6-538b-95ad-784551725cf7 |  | note | How Often? Per load
label | 56276078-b7c1-5a36-9254-5fa8950a5231 |  | note | Records Required - Job Sheet record
label | 8fb4ce29-e44d-585e-a0a4-abe56b3c508f |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | -5mm / +5mm below bottom of the nominal thickness of wearing course specified in Design Report
label | fc3b1ea9-5f5e-53f1-bded-3b8af6464f21 |  | note | T
label | 1ebe8233-e48a-5d26-a7b3-1f7fc823a6fd |  | note | Reference or Specification - Design Report
label | eec83eb0-6336-59e6-9a55-6624c1748660 |  | note | Method/Test Required - Dip checks during paving process / Cores
label | f248f09e-6c05-57ab-bcc2-f197dbe24e6c |  | note | How Often? Every 15m
label | 894be55f-03c4-52f2-b779-bae2c48dc0e7 |  | note | Records Required - Stringline Sheet record & photograph
label | 70250237-2273-5b24-af9e-371c6338b3c4 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-group |  |  | section | 7.0 Wearing Course
checkpoint-status |  |  | checkpoint | Delivery temperature - +10 / -30 degrees from recommended mixing temperature
label | 034ec8af-239d-5219-b698-512f7925a877 |  | note | T
label | 9100d542-a078-59e1-bf95-ac1a598725ae |  | note | Reference or Specification - NZTA M10: 2020 Notes
label | f2bac618-8542-5000-ac46-63c0156017ed |  | note | Method/Test Required - Temperature Gun Check
label | be65913b-6484-5288-8741-333ca8f59982 |  | note | How Often? Per load
label | b64aa7fe-e938-5b48-a5ee-3b4530ee11a3 |  | note | Records Required - Job Sheet record
label | 5a0ec909-1225-5054-96cf-1a2aeed6a1dc |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | -5mm / +10mm nominal thickness specified in Design Report; If applicable all mix is not more than 5mm above lip of channel unless specified otherwise in the Design Report
label | 5cc7baf4-a9d9-5cb0-9714-99e5d8c6b014 |  | note | T
label | 3cac3ed8-4113-527b-b17d-605e9bab203e |  | note | Reference or Specification - NZTA M10:2020 10.1 & NZTA M10:2020 Notes Table 3.3 & 3.4 or NZTA M27:2020 10.2 & NZTA M27:2020 Notes Table 3.1
label | c5a0f3f9-7a2e-5581-86bb-f8c077a05695 |  | note | Method/Test Required - Dip checks during paving process / Stringline Sheet
label | 7da525e2-ee86-52b8-b83a-6ba2dbb46ac6 |  | note | How Often? Every 15m
label | d7182a45-ae75-5f79-9b05-e6c46dbe1753 |  | note | Records Required - Stringline Sheet record & photograph
label | 6f2851b8-eb1f-5eb5-8539-0d3ab40985a8 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-status |  |  | checkpoint | Compaction and Air Voids (1)
label | e465c2de-6f21-5129-a6e0-f18de1972740 |  | note | Mat density air voids (+3 and -2) and joint density air voids (+5 and -2) as noted on JMF with the offset (1)
label | 0126481f-929e-539d-82a6-9044b0fa0ca9 |  | note | T
label | 17cc965c-8db2-5ec0-ae46-b28d98c04fb9 |  | note | Reference or Specification - NZTA M10: 2020 Table 9.2 + ASTM D3203 or NZTA M27: 2020 Table 9.2
label | 302c3f17-36c8-5c80-9341-f62001f61ce8 |  | note | Method/Test Required - 150mm Diameter Cores where: 1. >30 tonnes 2. >=35mm lift thickness
label | 0d44b042-5e7a-5a56-97c2-b9907796b746 |  | note | 100mm Diameter Cores where: 1. >30 tonnes, 2. >=35mm and <40mm lift thickness
label | a06e17de-4dcc-5047-865d-4498c33b3a4d |  | note | NDM (only where accepted by the Engineer in writing along with the testing plan.)
label | 100f68ab-a18a-54a2-9ce0-136585299e39 |  | note | How Often? Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot
label | 5bf5998b-1834-57f9-8747-5da5c79f261a |  | note | Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint.
label | 1650fc6a-2be1-5c1f-bb1d-9a8229ef4175 |  | note | NDM (only where accepted by then Engineer as per agreed testing plan.)
label | 0949a7b3-4ae0-53f6-90fa-1fc8ef7c53d2 |  | note | Records Required - IANZ Accredited Laboratory
label | e84b0c10-0db5-51e4-b7e8-a5bdd2f7e68e |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-status |  |  | checkpoint | Compaction and Air Voids
label | dc284615-fffa-5d61-9235-22b093a922d0 |  | note | Mat density air voids (+3 and -2) and joint density air voids (+5 and -2) as noted on JMF with the offset
label | 0f4b9117-dfd2-59d4-91ac-07eb1de41ff4 |  | note | T
label | 22ad0ba4-eb0c-5949-9779-f14744602ac5 |  | note | Reference or Specification - NZTA M10: 2020 Table 9.2 + ASTM D3203 or NZTA M27: 2020 Table 9.2
label | 80ba996b-b67d-5f77-8cee-d739e502a567 |  | note | Method/Test Required - NDM for Quality Control Only
label | 7135f617-94ca-5c77-9c2a-1438e72285a4 |  | note | How Often? Every 20m alternating wheel tracks
label | d2b42f29-d51f-5bb2-b6cb-43a9b74f9c8c |  | note | Records Required - Job sheet Record
label | 30f9af8e-24fa-56db-ac79-5e319c6bf7a3 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-status |  |  | checkpoint | Post construction surface condition
label | 8aae2568-db9c-58d4-946f-31768d41f769 |  | note | I
label | ab0e793d-bc32-5bcf-95c6-3acc22c0fbfa |  | note | Reference or Specification - Design
label | 2a45cbb7-d581-58d3-b85f-652b8863039b |  | note | Method/Test Required - Acceptable / Unacceptable
label | 6406bc41-3b55-5746-bdce-2c248000107e |  | note | How Often? Per site
label | badd7ae5-535e-55ee-abd8-58a291213dc4 |  | note | Records Required - Job Sheet record
label | 5be45680-004d-5745-a63c-d848807f7e52 |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | Supervisor to provide an update regarding site completion per shift
label | d18dbc40-ae48-5506-aedc-d2025ae74fd4 |  | note | H
label | d96db665-1dbc-52cc-a7a8-08996551a6bb |  | note | Reference or Specification - Design
label | 2d5d81c9-b367-5809-b66c-75a0c7882a92 |  | note | Method/Test Required - Acceptable / Unacceptable
label | 12cf9243-3b5d-57ef-8d3a-e0111f43f602 |  | note | How Often? Per site
label | e6c94a81-647b-5868-9065-eda96ef99f99 |  | note | Records Required - Email
label | aa8095bd-0af6-50b7-be62-ae30bc570835 |  | note | Responsibility - Site Supervisor
checkpoint-group |  |  | section | 8.0 Post-Construction
checkpoint-status |  |  | checkpoint | Linemarking and RRPM Reinstated - Matches previous linemarking - within 48 hours of sealing
label | 276c4070-065b-58e8-b0ed-ec1cacfad2c1 |  | note | H
label | 6c775cf3-09ad-510a-9dbc-a5ef8d9074ae |  | note | Reference or Specification - MOTSAM
label | adf24853-2a36-52da-b5a8-49f11159e1e1 |  | note | Method/Test Required - Visual check
label | b6f0f724-ac56-5d0f-aeaf-20ab57d863ec |  | note | How Often? Per site
label | 720943af-1620-5350-a123-ca47bccef389 |  | note | Records Required - Job Sheet record & photograph
label | c7b23b90-d661-5c5a-8418-48f8c96314ed |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | As-Built records – structural patches
label | b213a621-f913-596c-9cba-d7d9452b438e |  | note | H
label | 27e69a79-8d4b-59cf-a17c-6993fc809625 |  | note | Reference or Specification - Design
label | f778d81a-8d7f-563a-ba93-b3a838781a29 |  | note | Method/Test Required - Record as-built patch dimensions & RPs
label | 9bb096ea-0b68-589a-8e5b-f6a0e73a9e70 |  | note | How Often? Per site
label | 9136c19c-e96c-54e6-8b7f-e6e19194324e |  | note | Records Required - Job Sheet record & photograph
label | 4c2a6563-9d29-5da7-870b-0947cb12fbda |  | note | Responsibility - Project Manager / Site QA
checkpoint-status |  |  | checkpoint | Collect RAMM data
label | 236e5223-565e-5328-8a00-632a506f800d |  | note | H
label | df6a6c88-8eac-5558-8aaf-38077654b1ac |  | note | Reference or Specification - Comply with Waka Kotahi format
label | 12c58364-c9bc-5188-92b1-00bbe5bbbeaf |  | note | Method/Test Required - Correct data supplied
label | 81c2d116-3581-578c-9c5c-ee3631f66259 |  | note | How Often? Per site
label | 258d48e8-09cf-5664-bab7-61565c904ec7 |  | note | Records Required - Job Sheet record + As-Builts + photographs
label | f866fc1e-6c44-5139-8bcb-3bd25d8f15d3 |  | note | Responsibility - Project Manager / Site QA
checkpoint-status |  |  | checkpoint | Compaction as per sample test results
label | c854b44b-c518-598d-835b-40bf46157533 |  | note | H
label | 708bf1db-fb4f-52a3-875c-af86b98c2c0b |  | note | Reference or Specification - JMF Design Compaction
label | 39a0d584-7acb-59f8-b315-8ca549ea49d7 |  | note | Method/Test Required - Mean ≥95% ; Minimum ≥92%
label | bd1cb603-c943-5a6d-9b96-6a2810eb77d6 |  | note | How Often? Every 20m alternating wheel tracks
label | b894ebc0-9b61-5dd4-b853-0a16e9a4d608 |  | note | Records Required - Post-Verification Testing and Report from IANZ Accredited Lab
label | babe7679-a432-55e2-ab5e-1e63a06aceae |  | note | Responsibility - Project Manager
checkpoint-group |  |  | section | 9.0 Out Of Season Paving
checkpoint-status |  |  | checkpoint | Out of Season Paving
label | 0d51bf43-6893-5c3a-9c5e-027f04280995 |  | note | H
label | 4658e4ed-9a7d-57b2-b8f1-6cba318165f3 |  | note | Reference or Specification - Winter Surfacing Site Note
label | 52bc802f-dccc-5fb4-8baa-0fd7c1aaa970 |  | note | Method/Test Required - Waka Kotahi Approval
label | ddee7209-9809-5f68-81c7-4666e828b102 |  | note | How Often? Per Applicable Site
label | 6215828f-6cd8-5805-abcd-2400248f2f7b |  | note | Records Required - Copy of Waka Kotahi Approval on-site
label | 76bf9296-e53d-5934-8046-a7200521c0f5 |  | note | Responsibility - Project Manager / Site Supervisor
checkpoint-status |  |  | checkpoint | Dispatching Temperature compliance
label | 9678b7de-938e-55b3-82bf-177bc34d4876 |  | note | T
label | 6327801f-b381-5c8a-bc83-5b1712ae1b0c |  | note | Reference or Specification - NZTA M10: 2020 Notes - Table 3.3
label | 6d8afae5-5703-58a6-84d8-80b70a183a5a |  | note | Method/Test Required - As per Table N4.1: NZTA M/10: 2014
label | 22b39d05-3224-56c1-8727-fe47b78e8305 |  | note | How Often? Per Load
label | 95cd50ca-71a4-5363-9b23-9a80d5e4090f |  | note | Records Required - Job Sheet record
label | 00c4a9ef-ef66-527b-8711-00779aa455ef |  | note | Responsibility - Asphalt Plant Manager
checkpoint-status |  |  | checkpoint | Arrival and Compaction Temperature: 110-170°C - To be recorded when mix is tipped into the paver.
label | 11581603-8f10-521c-95e2-8da3d428a56d |  | note | Manager to be notified if temperature falls below:
label | f63ac43c-99c6-5597-82d4-e07820f48050 |  | note | SMA9.5 134°C
label | 503a7a21-5538-5245-bdb7-df622df3c95f |  | note | SMA12.5 134°C
label | 39051b0f-ed35-5b0a-a901-525fe19be802 |  | note | SMA11 134°C
label | e8ff068a-74f6-5f2c-9a86-055d1cbf2ede |  | note | AC20 145°C
label | fc78f837-a50f-57ea-a6f6-583ee0aeae54 |  | note | AC14 142°C
label | bcbf1fed-ce07-56bd-8592-cd5a24bf367b |  | note | If temperature falls below 110°C mix will not be used
label | d40c32c8-d5c6-5ba9-841b-040fd6f3cb6e |  | note | T
label | 48ca8ee7-21ef-58c0-b185-70bf92e51f8b |  | note | Reference or Specification - NZTA M10: 2020 Notes - Table 3.3
label | f4370d87-df9d-563c-a3ec-3ebb213cb501 |  | note | Method/Test Required - Temperature Gun, Acceptable / Unacceptable
label | 91d48dfe-4f08-58b6-b546-bc6834c7491d |  | note | How Often? Per Load
label | eba3f0d2-0131-5a95-9b8f-6cc707425524 |  | note | Records Required - Job Sheet record
label | d7d0b4b2-64c5-5a19-978f-883b6914455c |  | note | Responsibility - Site Supervisor / Site QA
checklist-flat |  |  | checklist | Approved Design Report |  |  |  |  | Yes | Approved Design Report | 1d76fe4b-c6d5-4545-af6f-aba212fefc25
checkpoint-status |  |  | checkpoint | Approved Design Report
checklist-sectioned |  |  | checklist | ITP - 2 coat Grade 3/5 Chipseal - SH57 Currins | itp |  |  |  | Yes | ITP - 2 coat Grade 3/5 Chipseal - SH57 Currins | 1d970553-2cc1-42f4-91ca-0b08a08dc793
checkpoint-group |  |  | section | Sealing
checkpoint-status |  |  | checkpoint | 2.1.1 - Seal Design
label | 2df67408-2f70-50b2-a964-a1477940e917 |  | note | Detail of Activity - Seal design outlining all design assumptions
label | 7b3a50ad-36ef-54a5-8c9b-a189db27a009 |  | note | Action (Hold, Monitor, Witness) - H
label | f3bdc2ac-1963-5f03-84b2-65508081d02a |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per seal application type
label | b08a4d03-a468-5b8f-a4ca-575763edea63 |  | note | Inspection / Test method - Review
label | e9c9895e-037c-56db-a0f4-6c18125c84b7 |  | note | Acceptance Criteria - New Zealand Chip Sealing Handbook
label | 8a554607-f0b0-56af-8d1f-390671225f7c |  | note | Record documents - Seal design in contractor's site folder
label | 5a05add4-efcb-51c2-9d77-675e3f4f2e26 |  | note | Responsibility - Designer / Engineer's Rep
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.1.2 - Check raw materials
label | f1010946-f080-5cb0-8183-2db5bfd34a73 |  | note | Detail of Activity - Sealing Aggregates
label | e7616124-c1fd-587b-a046-aa0121fa7f32 |  | note | Action (Hold, Monitor, Witness) - M
label | 33850043-7a0e-518f-a670-6db29bc72e32 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per source stockpile
label | 5fe040ca-bfb9-5135-8f08-c9b6b1fab682 |  | note | Inspection / Test method - Source Properties
label | 70a6e181-86bc-5582-8773-4c78c8fb53c5 |  | note | Acceptance Criteria - NZTA M06 / RNZ 9805:2009
label | 7b3dc073-51ec-5def-85b3-9138c0f6fc68 |  | note | Record documents - Certificate in contractor's site folder
label | 24d14665-a898-5014-beeb-8fbead5a27d4 |  | note | Responsibility - Contractor
label | dd8749ae-c308-5661-8f1c-95e54f0c7bad |  | note | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint-status |  |  | checkpoint | 2.1.3 - Check raw materials
label | 37d438bd-0e49-5e2f-bcb3-24a2df4798c4 |  | note | Detail of Activity - Sealing Aggregates
label | 7245254f-842d-57f4-b29f-802dcb8d9cac |  | note | Action (Hold, Monitor, Witness) - M
label | 71c505dd-3dc5-52ba-ae73-2acebf54a546 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per source stockpile
label | c6af8fe5-3638-5a25-ae22-5123fd86504d |  | note | Inspection / Test method - Production Properties
label | f89d0daf-fda3-50ef-9b5a-1d683d9df5f0 |  | note | Acceptance Criteria - NZTA M06 / RNZ 9805:2009
label | 318b029b-3f0f-5a5b-9074-fd56b6777e08 |  | note | Record documents - Certificate in contractor's site folder
label | 881b5eb1-79f0-54cf-aa19-3579ed3efb04 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 2.1.4 - Check raw materials
label | 2052cf9a-31ae-57c1-9d52-a4f8160df52e |  | note | Detail of Activity - Adhesion Agents
label | 68e04123-3955-5808-aee1-9874c04c0013 |  | note | Action (Hold, Monitor, Witness) - M
label | 14def79e-2be2-5c26-99b0-80ec130f6ff3 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to use
label | d1830eef-c145-5221-beca-11f4bc3e688e |  | note | Acceptance Criteria - NZTA M06 / NZTA M13
label | ac290e8a-5a27-5bc9-8a26-82af9596a98c |  | note | Record documents - Certificate in contractor's site folder
label | d1f2b57f-4259-55ed-bbf9-40896f89473e |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 2.1.5 - Check raw materials
label | 7395b2e4-7b06-544c-abe5-e35bbdfba29f |  | note | Detail of Activity - Audit samples
label | b76be85e-19bf-5dd5-874b-0ddcb1ff3cba |  | note | Action (Hold, Monitor, Witness) - M
label | 81e376bc-cb1b-5a8a-a3f6-282ac9a55e58 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 20 kg per stockpile
label | e2b0d954-d11f-5eb5-b250-01033fe526aa |  | note | Inspection / Test method - N/A
label | aee74a07-bd9e-5ec8-96ab-710aa818f494 |  | note | Acceptance Criteria - Stored in a sealed plastic bag in a covered environment
label | ae968563-675f-5e72-b1a7-1fda4d567f8e |  | note | Record documents - ITP
label | 47c4f30d-0e07-5a63-a27d-e76a7017012f |  | note | Responsibility - Contractor
label | ae837cb6-68c0-5091-a6c9-fa2618e71065 |  | note | Comments - Retain for testing if required
checkpoint-status |  |  | checkpoint | 2.1.6 - Pre-Seal requirements
label | 21cc663b-77bb-56a1-9d4d-567cd266f929 |  | note | Detail of Activity - Visual inspection of surface to be sealed
label | d703d82a-f9a2-58f4-b022-f74174b41b49 |  | note | Action (Hold, Monitor, Witness) - W
label | d6a41d5f-25e1-54af-9283-b8ebd2c8174e |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) -
label | 68652afb-0989-564c-b02f-c30a5b2762ca |  | note | • per sealing schedule.
label | f9b7dd0f-bf30-50ff-ae80-c9d61fd0dc18 |  | note | • 1 Lot = 1 day's production and < 1500m2
label | 8f76918e-66a7-5861-9710-7ada7a8b9094 |  | note | Inspection / Test method - Visual Inspection
label | b89ddd83-c3a6-51cd-9c0b-17ea32bcada8 |  | note | Acceptance Criteria - NZTA B02
label | d13644b2-db47-5baa-a87d-b0fd8dc419ec |  | note | Record documents - Contractor's site diary
label | 38a07686-a464-5dec-b74a-7c9cb01786aa |  | note | Responsibility - Engineers Rep
label | b6c7afd7-eb82-5e58-aa6e-b2273b438268 |  | note | Comments - The surface finish, line and level is checked by Engineer's Rep. immediately prior to sealing
checkpoint-status |  |  | checkpoint | 2.1.7 - Pre-Seal requirements
label | 37e8404d-d81e-5d55-82b2-2a6fbe251c26 |  | note | Detail of Activity - Dry back Moisture Content
label | 636510aa-36ac-57db-a5f2-7687038f9401 |  | note | Action (Hold, Monitor, Witness) - H
label | eb155def-84a7-51d1-a7fd-29ac187551f1 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 9 per Lot
label | 590f7a6a-b821-5aeb-8eb1-dfdb09a23490 |  | note | Inspection / Test method - NZS 4407.4.2.1
label | 5a589a63-49f0-5044-8f75-9a925f71de65 |  | note | Acceptance Criteria - DOS ≤ 80% preferably ≤ 70%
label | b343c504-8415-5d87-87ff-104f5ef90d71 |  | note | Record documents - IANZ Report
label | a11fe4e4-6606-5123-b843-744d18f5425b |  | note | Responsibility - Contractor
label | d98a60b0-c070-5106-8801-80dedcab866f |  | note | Comments - Only required if pavement widening extends into trafficked lane
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.1.8 - Pre-Seal requirements
label | 4de5f012-7af5-5de8-98ef-f2ff3342386a |  | note | Detail of Activity - Clegg Hammer
label | e5527d85-12b3-5461-9390-8fdc913b7ad5 |  | note | Action (Hold, Monitor, Witness) - M
label | 6026f2e9-58e8-5a60-9cf0-3e60d40b1f11 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) -
label | e9eb13b0-e782-5e84-8a11-0b1769626d9f |  | note | • 1 CIV per 10m
label | 7eb967b9-a252-5219-bb14-718a95b860af |  | note | • 1 Lot < 300m
label | 8f1089b6-26a8-53f6-bab0-d0b93c55175d |  | note | Inspection / Test method - Clegg Impact Value Test
label | 837c37ce-2d1d-57ab-aced-a69beaf2eedf |  | note | Acceptance Criteria -
label | edae6469-a5d8-5ae3-a170-6570264fdebb |  | note | • Average CIV > 40
label | 30436cc1-3018-572d-8d56-065c5714febe |  | note | • Min. CIV > 35
label | b4fcaab3-ef90-5818-9d5e-837c9a8ae12f |  | note | Record documents - Contractor's CIV form appended to Contractor's daily diary
label | 1c627627-2e44-5bd7-bfaa-4744c0b74187 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 2.1.9 - Sealing
label | d8152139-a71c-5494-968a-c194b30e0e98 |  | note | Detail of Activity - Bitumen / Bitumen Emulsion for Chip Sealing
label | 2d815d53-eece-5d1e-a41c-3bd8fd6653d9 |  | note | Action (Hold, Monitor, Witness) - M
label | 99f11a0b-74ee-5bc2-802d-257ea0ef8db3 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 2 samples per distributor
label | 825653a3-5873-5f0e-90d5-e8019fa65c26 |  | note | Inspection / Test method - Penetration grade testing
label | b29793e7-2c34-5c03-8400-35bc104f6af6 |  | note | Acceptance Criteria - NZTA M01 - Tables 1, 2, 3 and 5
label | 7208ee82-a58a-5b74-9718-fe02452a498c |  | note | Record documents - Certificate in contractor's site folder
label | 4b1e8525-e04a-55ff-b19a-c302edd6a487 |  | note | Responsibility - Contractor
label | bba0f173-894c-5546-9e0b-276a6584cec3 |  | note | Comments - Sampling as per ASTM D140 or equivalent
checkpoint-status |  |  | checkpoint | 2.1.10 - Sealing
label | fd121110-e5c7-5b72-8959-7fb83ac42f6b |  | note | Detail of Activity - Bitumen / Bitumen Emulsion for Chip Sealing
label | c7550462-b2b2-5c41-9e28-a02d1003608f |  | note | Action (Hold, Monitor, Witness) - M
label | e52bcc04-d024-5f5a-986d-2eabb9031c8a |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 2 samples per distributor
label | 22d9f82a-9012-557e-a618-f821e811899f |  | note | Inspection / Test method - Durability
label | 6c79a697-ae12-5ce5-8b52-dc2b89efe7f5 |  | note | Acceptance Criteria - NZTA M01 - Table 5
label | 828bc5cb-0636-558d-9318-cb11ef7fcd36 |  | note | Record documents - Certificate in contractor's site folder
label | afbe450c-6aa0-5e20-acb6-90550dfb411f |  | note | Responsibility - Contractor
label | 2343945a-ba0a-5417-85bd-660730977486 |  | note | Comments - Refer notes in clause 5 of NZTA M01
checkpoint-status |  |  | checkpoint | 2.1.11 - Sealing
label | f6aa3e50-95a6-5197-ac58-c1582902bc02 |  | note | Detail of Activity - Spraying Temperature (Bitumen only)
label | 79d081a7-e411-5c2c-9620-d198cff5c82b |  | note | Action (Hold, Monitor, Witness) - W
label | 8c1b57c3-4515-58a8-b9c9-d72b15d07252 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Ongoing with non-going heat sensing gauge
label | 23547079-962a-58c0-ac0c-0d70e393c1e5 |  | note | Inspection / Test method - Non-contact heat sensing gun
label | 214ede4b-6ffc-5620-9975-0331563b38cb |  | note | Acceptance Criteria - NZTA P03 - Table 2
label | 34e01367-68b1-5d03-bac4-82e8f9e77083 |  | note | Record documents - ITP
label | 97e5b10c-7405-59d2-a543-9e9146616d3d |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 2.1.12 - Sealing
label | 60f3090f-a18a-56c7-9a58-3efea25f3030 |  | note | Detail of Activity - Residual Bitumen Application Rate
label | 8feb95a9-38c2-552f-ad6a-261035fb93ee |  | note | Action (Hold, Monitor, Witness) - M
label | e77cfccb-1fe4-5f8e-b47a-98471760077e |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Reconcile day's production
label | e63940ef-cc66-5793-84cd-d354739cb942 |  | note | Inspection / Test method - Dockets vs Area
label | 76fb2c2c-7f62-5d9f-a477-00523a8ba4e6 |  | note | Acceptance Criteria - ± 0.1 L/m2
label | 106e6c17-3fd0-5b22-bc51-1879acb74291 |  | note | Record documents - Site diary
label | a07bf76a-ed0b-5e21-90f5-b5553ed01e6b |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 2.1.13 - Non-conforming results
label | 16eed891-fa7a-54ec-b6bf-8d9fcb044fa1 |  | note | Detail of Activity - Assessment of all test results for conformity
label | e7137de5-20a1-5a49-a500-0e6c5fd0cbd5 |  | note | Action (Hold, Monitor, Witness) - H
label | dff10531-59e2-5eaa-a000-486283b0b3a5 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each Lot
label | cf197bd0-f661-56d3-a608-c7e8819bef78 |  | note | Inspection / Test method - Site Inspection
label | ac797bad-3696-5f27-b65b-2e6200919e15 |  | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | 3b4ca18a-d4c9-58c2-99fd-2a8cbb8bc243 |  | note | Record documents - NCR
label | cf2a4100-ffd3-588e-bcbf-c2c09b906520 |  | note | Responsibility - Engineer's Rep
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
text | 4817bf51-3e78-5cb8-92b6-284380fa0a17 |  | textbox | Contractor's Rep Name:
text | c0990b34-5144-594b-a0b8-4f8d00d9d581 |  | textbox | Engineer's Rep. Name:
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | Production and Testing ITPs |  |  |  |  | Yes | Production and Testing ITPs | 21a70bf6-59b2-46e5-8f4b-6bddde70f403
checkpoint-status |  |  | checkpoint | Production and Testing ITPs
checklist-sectioned |  |  | checklist | ITP - In-Situ Modified Basecourse - SH57 Currins | itp |  |  |  | Yes | ITP - In-Situ Modified Basecourse - SH57 Currins | 507ad19c-e81d-40db-8af7-54cbfdd2dcd6
checkpoint-group |  |  | section | 1.1. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING
checkpoint-status |  |  | checkpoint | 1.1.1 - M4 AP40 Basecourse Aggregates used for overlay
label | a0f40560-0a17-5b7b-81c9-f4b0551193f0 |  | note | Detail of Activity - Quality of Fines, either PI or SE or CI
label | 7ab50908-4597-5d2e-88b2-5bc096b79ac0 |  | note | Action (Hold, Monitor, Witness) - H / M*
label | 4bae6fd0-a355-5de6-826e-1c9e127bc915 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m2
label | 23abaec1-8408-5957-b2dc-70b6bc1f6991 |  | note | Inspection / Test method -
label | e290c5b1-2b8b-5a6f-923d-0f13927bbbb7 |  | note | • NZS4407:3.4 - PI
label | 211a6a6c-8d97-535c-9afc-d68e5fc855b5 |  | note | • NZS4407:3.5 - CI
label | bb2171e8-14f9-5d23-93ed-81bf576d9c45 |  | note | • NZS4407:3.6 - SE
label | 2526a163-fa4a-5403-9ba8-595d4e15f7ed |  | note | Acceptance Criteria -
label | a6c0330a-8f51-5a77-bbb3-f40189964cb0 |  | note | • PI ≤ 5
label | 1c5f2fe5-7aa8-5d3d-89aa-5e1600386d18 |  | note | • CI ≤ 3
label | aedfd603-eb4f-5f72-93d8-450310d3e43f |  | note | • SE ≥ 40
label | d1ff526d-9882-5efe-8349-541d2445dbc4 |  | note | Record documents - IANZ Report
label | 11e980bb-352b-5756-9af1-65f012cd6613 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.1.2 - Notes:
label | 21768900-a6e4-5774-8328-0be1f829df8c |  | note | Detail of Activity - Broken Faces Content
label | f36241ca-d06d-5517-af46-099ef4c68759 |  | note | Action (Hold, Monitor, Witness) - H / M*
label | 805c48fd-e56c-5570-be5d-e268bd99ab7f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m2
label | a29eb2e5-5d5b-5753-a982-4dc48f55a908 |  | note | Inspection / Test method - NZS4407:3.14
label | 937b030e-9113-5e62-b93f-725141e4e34e |  | note | Acceptance Criteria - ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm
label | 0b265c50-97ea-5b07-8dfd-6e9099a6b727 |  | note | Record documents - IANZ Report
label | ed554e56-6598-5855-ac46-9cef3de9a0cb |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.1.3 - H = Hold point up to approval of Optimisation Testing
label | 69fbf006-2888-50bf-8752-b5f7d7e20b2e |  | note | Detail of Activity - Particle Size Distribution
label | 99a94484-c723-5003-9528-e0db2bf19e72 |  | note | Action (Hold, Monitor, Witness) - H / M*
label | 8fb0eb65-bb9b-5573-b7af-fd5e76288053 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m2
label | c483966e-4d72-5b09-bb66-7e87946649da |  | note | Inspection / Test method - NZS4407:3.8.1
label | 49a78f59-4ee5-59ca-875f-e88339a80ced |  | note | Acceptance Criteria - Check if 50:50 blend of average existing (from TPs) and NZTA M/4 AP40 will meet the FBS grading.
label | a9e5bada-5022-5b3b-bde6-138c995479f0 |  | note | Record documents - Report using IANZ Reports for AP40 and TP PSDs
label | a6e59463-f90c-594b-9d49-149adc25cec4 |  | note | Responsibility - Contractor to provide analysis
label | b1129bf5-fb06-58fc-a50a-ca8fc0eb1dad |  | note | Comments - Designer to advise if "average" blend is acceptable.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.1.4 - Optimisation of Stabilizing Agent
label | 21321cd8-cd11-5955-862d-0a44526d9188 |  | note | Detail of Activity - Indirect Tensile Strength, ITS
label | 5e9bfeac-ea02-5022-802c-f594a730cc09 |  | note | Action (Hold, Monitor, Witness) - H
label | 5cea8c0b-29cc-591c-83ec-db8f8b3fba7d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Optimisation test per aggregate type
label | a44f380a-b00c-5861-98b6-384f49fb6e88 |  | note | Inspection / Test method - NZTA T/19: 2020
label | c21fe904-1a77-5dde-a0b4-eb35f11ea61a |  | note | Acceptance Criteria -
label | 8bc577d3-1966-5e84-a21c-a4cbdae830e7 |  | note | • Dry ITS: 175kPa to 400 kPa
label | f37f1a43-1135-5df9-8ed6-44191f2e2e4d |  | note | • Soaked ITS: 150 kPa to 350 kPa
label | 5e0a3213-038a-500a-b35e-87fb7c706565 |  | note | • TSR ≥ 70%
label | c658192d-443d-571b-9c44-ebdf437a3ac9 |  | note | Record documents - IANZ Report
label | 2d81651c-a6a4-5bd2-bc09-61d0b50ae681 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.1.5 - Optimisation of Stabilizing Agent
label | ac75f0d3-9136-5519-afb4-b7c5eecddb6c |  | note | Detail of Activity - Modified Maximum Dry Density
label | db744449-0b10-5486-8b2d-3bfe87559208 |  | note | Action (Hold, Monitor, Witness) - M
label | 87b62da0-d5ea-5da1-89c8-d3f3c1a74fd4 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - At Optimised Binder selection
label | 75cb1856-b8da-595f-903d-170a2b7b8ba1 |  | note | Inspection / Test method - NZS 4402.4.1.3
label | 2c448ce8-2e8b-5c4e-96a7-237fffd58201 |  | note | Acceptance Criteria - To determine target density
label | 10afe83b-ead0-5959-b442-10eb8ef4e063 |  | note | Record documents - IANZ Report
label | dbde554c-6427-52b6-8e33-054ea730afa9 |  | note | Responsibility - Contractor
label | 6ff89101-177e-50eb-a8f8-2ae6e4213aff |  | note | Comments - Required before Stabilisation comences
checkpoint-group |  |  | section | 1.2. BEFORE STABILISATION COMENCES
checkpoint-status |  |  | checkpoint | 1.2.1 - Setout section
label | 9086294a-7eee-592f-931b-89a256f53a75 |  | note | Detail of Activity - Install offset pegs; record centreline, edge line or mark out stabilisation extents from existing line marking
label | f84e04d6-44b1-5bc7-8bc7-05ada5ec450c |  | note | Action (Hold, Monitor, Witness) - M
label | e9390d45-802d-50b4-b9af-3656fb9403aa |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to each section
label | e402805c-4ebd-5f21-99ad-579bb6892773 |  | note | Inspection / Test method - Survey
label | 00992958-3d05-51f9-87e6-41fa28fc26ae |  | note | Acceptance Criteria - Document existing furniture
label | 43fa920d-fcc1-5b05-b8c7-bb8575e1948c |  | note | Record documents - Electronic survey files
label | 11a782da-4869-5a3f-aa20-717d31dc3b03 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.2.2 - Production Plan
label | 1fcdefd2-4519-5105-a5c2-d3837f51f063 |  | note | Detail of Activity - Plan showing cut lines and sequencing of works
label | a3973b28-5576-5925-a43b-a3dffaa5fea9 |  | note | Action (Hold, Monitor, Witness) - M
label | 5fc3863a-1ca9-5387-8767-ab62e41a2909 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to each section
label | 0ce75a7f-7c35-52f7-aebd-9bfce180b0b9 |  | note | Inspection / Test method - Daily Report
label | 6fd0c65a-3dbb-57b1-8ff4-307181cd1301 |  | note | Acceptance Criteria - Points covered in NZTA B/5
label | 28372ae6-7b4c-5a42-8b2e-2752b3837b77 |  | note | Record documents - Daily Production Plan
label | 5259cb69-d529-5cf2-86f2-a8a22bb85bea |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.2.3 - Weather conditions
label | fbb64c8a-a7b8-594f-ab36-350b3b921c42 |  | note | Detail of Activity -
label | 1b916cbf-271a-5992-bc38-4e2a5c605135 |  | note | • Ambient Temperature (C&L)
label | e0443012-c114-59a7-8b2e-d75efdcb87e7 |  | note | • Material to be stabilised (BE&FBS)
label | e755a130-3fbf-5b8d-a5db-65cd574ec356 |  | note | Action (Hold, Monitor, Witness) - M
label | a892f6eb-65b4-5b52-81ca-701235101bc3 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to spreading
label | c6d863c9-b9b2-5e5a-be47-4f17bed9edb9 |  | note | Inspection / Test method - Measurement
label | e61785c5-c482-5c57-b5cc-505a2fe3e36c |  | note | Acceptance Criteria -
label | f3a66e6c-c427-54cb-9659-29f069db8851 |  | note | • Ambient Temperatures:
label | 41ae7b68-d1af-540b-8c2f-23ecb6a2bdf9 |  | note | ○ Cement: > 5°C, Lime: > 10°C
label | 632bf3b2-252f-50c2-8790-1654387177ce |  | note | • Material after stabilisation:
label | d4c9ad9a-077a-5c9e-bf20-6d6ad04b012a |  | note | ○ BE: > 20°C, FB: > 20°C
label | b4e19239-ab5c-5954-a134-900fed64d32e |  | note | Record documents - Daily work Log
label | bf454e45-cfa7-5845-99bf-1a59a4ae4b13 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.2.4 - Weather conditions
label | c702be5c-1ccd-5468-a6cb-079a786d9d35 |  | note | Detail of Activity - Wind
label | 00c672f9-3f07-595d-8408-8aad928ad437 |  | note | Action (Hold, Monitor, Witness) - M
label | eb50c16e-8757-5517-80c4-5dbcb51ce0ab |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to spreading cement or lime
label | 88a43050-c88a-5724-bc35-c5b9c3ed2653 |  | note | Inspection / Test method - Local weather stations
label | 69faac68-7e85-50e4-aa7d-921b7c2e4d8e |  | note | Acceptance Criteria - Wind speed < 25 km/hr
label | 4438b374-3299-5fde-a0a9-47dcdf5760be |  | note | Record documents - Daily work Log
label | ae97cb62-de07-5328-994e-1e470d7891c9 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.2.5 - Weather conditions
label | 6a93beba-f427-54ab-a54b-39032c51cfc1 |  | note | Detail of Activity - Rain
label | 249b7225-db58-5730-98c3-ccf6595c7602 |  | note | Action (Hold, Monitor, Witness) - M
label | d6d125d1-7cde-5ab0-aadc-6de69660d07d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to spreading cement or lime
label | 75c33a25-a18a-590a-aa6b-602847738294 |  | note | Inspection / Test method - Local weather stations
label | 24545f17-77d6-5e29-a16e-22cd94b6fff7 |  | note | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
label | e1b9c46c-e437-5685-ba7e-ecc97368e043 |  | note | Record documents - Daily work Log
label | 39a7a2d8-ff91-5ecd-b9c0-52a09b011fec |  | note | Responsibility - Contractor
checkpoint-group |  |  | section | 1.3. STABILISATION OPERATION
checkpoint-status |  |  | checkpoint | 1.3.1 - Stabilizing Agent
label | 9bb0b9fd-d1fd-537a-8732-13e7d8f3f53b |  | note | Detail of Activity - Cement, GP
label | a4127419-88b1-597a-b06e-2e61f811cf42 |  | note | Action (Hold, Monitor, Witness) - M
label | d43b6cf4-bd8a-5023-8a39-9a652e6da254 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Batch
label | 9ad9016d-6295-55c0-b1e8-70b4dd794708 |  | note | Inspection / Test method - NZS 3122
label | 8ceea5b1-c696-5b79-8813-c4b683781819 |  | note | Acceptance Criteria - Conform to Specification
label | 5c33ca0f-3760-5288-9cca-d5aabf60f486 |  | note | Record documents - Certificate in contractor's site folder
label | 3365413c-e11c-5d4d-ac5f-2c372690c240 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.2 - Spreading of powdered stabilising agent (Cement)
label | 0d781566-5106-584b-b164-6cdebe7d5513 |  | note | Detail of Activity - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
label | f0e0ba13-fa3d-5de3-8b6f-65929e0760c2 |  | note | Action (Hold, Monitor, Witness) - M
label | b71ed8ca-53de-522b-bf5c-3190e8411d1d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) -
label | 664f553f-8ebb-534b-a342-65ea02f7cba8 |  | note | • every 400 m2
label | dc6ef7e7-7921-5515-bca9-b6f1364f18bf |  | note | • every 150m for a 2.4m width
label | f1e5ac4e-e5bf-5c22-a5db-18fd2badd4ba |  | note | Inspection / Test method - Weigh mat or tray
label | 74e8f06a-c1bf-5120-ba26-888b4138eceb |  | note | Acceptance Criteria - ± 5% of specified rate
label | e684353f-dd2d-5934-8844-3529f43fb50d |  | note | Record documents - Daily work Log
label | abf4da09-c479-5d33-9e10-fd39492af9e6 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.3 - Spreading of powdered stabilising agent (Cement)
label | af89d128-3219-52b3-8c6a-767f82464c34 |  | note | Detail of Activity - Compare area spread with weight used for each spreader load
label | ea059744-9218-56c4-abdb-03d969281927 |  | note | Action (Hold, Monitor, Witness) - M
label | 7d4426f1-fa67-5bd5-a940-015a29b25a7b |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On-going measurement by computer/load cells
label | be2971c8-a8be-5ceb-b1b6-be26a59d4bec |  | note | Inspection / Test method - Measurement each run
label | e761760f-c0ca-5a2a-a457-5385cd8b0527 |  | note | Acceptance Criteria - ± 2.5% of specified rate
label | 70515047-daa5-52f4-ba28-4200e9c0b83f |  | note | Record documents - Daily work Log
label | c480518a-84e4-5f4f-8782-0c31fb97c25b |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.4 - Injection & Mixing of Water
label | f6181b51-0739-5ab4-9096-c96b72bac72b |  | note | Detail of Activity - In-situ Stabilisation process
label | d668f389-4bef-510e-9b0f-7e2941ec45bd |  | note | Action (Hold, Monitor, Witness) - M
label | c41528ca-9103-55ce-baa5-7abff4e5cd3b |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On-going visual assessment
label | 140041d2-2cf5-5450-a244-c88f43a3ad6b |  | note | Inspection / Test method - Visual and hand squeeze test
label | 5cef0907-293d-54f9-91e9-ee7b23b3b46c |  | note | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
label | 01f96cdf-a7d5-56a3-8bc2-586ce8498b59 |  | note | Record documents - Daily work Log
label | 4b40ec98-fd6b-5055-b82c-f31deb7e8240 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.5 - Depth of stabilisation
label | 166a3f17-eec7-5feb-b103-e9ecbbbd705d |  | note | Detail of Activity - Depth of stabilisation
label | 058ffc6f-7604-5053-9eb2-3f83359f0929 |  | note | Action (Hold, Monitor, Witness) - M
label | c02112b1-c312-5692-a251-cdb95362cb5d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Every 200m
label | 35961bd6-2c68-5d53-bf07-d172ee7e55f3 |  | note | Inspection / Test method - Measurement
label | 0b574c47-9725-54a0-9413-21835f69a98f |  | note | Acceptance Criteria - +15mm / -5mm from specified depth
label | 33d7a60c-794d-5cf7-bd50-2210d28c5327 |  | note | Record documents - Daily work Log
label | ea2fd70b-bdfa-5a2e-8c9f-d4eff72de5b4 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.6 - Compaction
label | 6862553f-79b3-54a6-ab4f-61342d3392bb |  | note | Detail of Activity - Plateau Density Test
label | 4c9ad607-206c-557b-b6ba-1dc7e06886c8 |  | note | Action (Hold, Monitor, Witness) - W
label | 3cb20350-90db-5bf9-9706-12ab8667e0eb |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On first day and then 1 per 20,000m2 unless material or anvil conditions change
label | 55a7acaa-a902-55cb-8877-2279fd4f1c71 |  | note | Inspection / Test method - Draft NZTA T/24
label | a03794fd-a073-59f0-a301-5e4824191e2c |  | note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern
label | ae1227d4-f0cb-5fb2-b436-eea0344f7711 |  | note | Record documents - Daily work Log
label | 30a757b5-69a2-5644-be97-5b6ad1b3ef0c |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.7 - Compaction
label | 8d69840b-9f4d-5c19-819b-f2e68e26bca8 |  | note | Detail of Activity - Maximum Dry Density
label | 7475556c-e69c-5480-9782-b87717b9bf6b |  | note | Action (Hold, Monitor, Witness) - M
label | cd77c425-1879-5236-ad5c-18f87851a07f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per day up to 3,000 m2, 1 per 2,000m2 thereafter
label | b19def9a-5311-5359-b819-c9a0e05918e7 |  | note | Inspection / Test method - NZS 4402.4.1.3
label | 50b4a619-d868-5f31-bcff-14f93857b2aa |  | note | Acceptance Criteria - For analysis of DoC
label | 865ea762-1e77-5fa3-96ca-07522a6cf8bb |  | note | Record documents - IANZ Report
label | 63a09c17-acb6-582f-b5e5-29998160005b |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.8 - Compaction
label | d03a2fa4-b0b6-5a8f-b7f1-47466ddb3828 |  | note | Detail of Activity - Degree of Compaction
label | 16126cf7-25d2-5381-a07d-f36ba7a088d1 |  | note | Action (Hold, Monitor, Witness) - H
label | 3239ea27-a611-5b21-9370-a3f8fbe0c924 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 5 per 1,000m2
label | c548965a-00e7-5179-b694-9232f690aaf3 |  | note | Inspection / Test method - NZS 4407.4.2.1 (to 100mm and 200mm) and NZS 4407.4.2.2
label | 4dbc75b7-bb40-54df-800f-bba67c900e52 |  | note | Acceptance Criteria -
label | 43fab17c-e656-5b0d-8928-84710069b812 |  | note | • Average DoC ≥ 98%
label | 714e87a5-539c-550f-98f6-d6510f2e7893 |  | note | • Minimum DoC ≥ 95%
label | ad6e7fc2-4510-55a9-b8fb-ce9d0828d6ed |  | note | • Refer NZTA T/23
label | 3e5b2b45-cf8e-5497-b2b3-08ccaf39d78b |  | note | Record documents - IANZ Report
label | dbe9cbff-a698-5376-a884-c2431afae4bc |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.9 - Finished Pavement
label | b2dc1057-a2de-54e1-8f38-d68b12520d21 |  | note | Detail of Activity - Crossfall
label | a0e5ffe4-0ba8-5165-a0b5-bad7c3ae07a1 |  | note | Action (Hold, Monitor, Witness) - H
label | e0d019d0-96c9-5a56-8e1b-124c99acb67a |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | 232ca06b-a5e7-5914-89fd-15d06cd58d12 |  | note | Inspection / Test method - Measurement
label | 037eed60-5de3-53e8-95e1-e74dccbd2b85 |  | note | Acceptance Criteria -
label | 5ebc5b18-bc2d-54e4-862d-788e841e2efa |  | note | • ± 0.5% of specified crossfall measure
label | d0bbca46-1fb6-5b99-b835-ab3e9894e5f2 |  | note | • 2m apart
label | f2b39e08-5a62-5871-a1fe-ee9e0166caa3 |  | note | Record documents - Survey
label | 89bbe27b-6823-528a-bee3-76bbe528ef97 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.10 - Finished Pavement
label | b4816df1-d1ba-59ad-adf9-1f12a5792e46 |  | note | Detail of Activity - Stabilised width
label | e03baf78-ad07-5402-9967-8cfbd67def91 |  | note | Action (Hold, Monitor, Witness) - H
label | 5dfbd482-ecca-5c0d-9891-7dcb45b84871 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 every 20m
label | e1a3528a-bd9b-5180-897b-e838a0c5ab4c |  | note | Inspection / Test method - Measurement
label | 89c5e087-34ea-50fd-b88b-adecf2688efb |  | note | Acceptance Criteria - –20mm, +100mm
label | 3b1e7fda-4fc9-5638-bb1f-27afe27b1fcc |  | note | Record documents - Survey
label | 7cbcbf5f-c57f-54ef-8c2a-3049cfc52a04 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.11 - Finished Pavement
label | 6de110a2-83e1-5fc6-a9e0-318e28e8a3b7 |  | note | Detail of Activity - Surface Shape
label | d4dea0e3-b3d3-5cb5-94e6-0b953ae6b63d |  | note | Action (Hold, Monitor, Witness) - H
label | a69dd4ab-4572-5bad-976a-cacea5250b5f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | 61084b50-2ad1-50fe-affb-425a1d649750 |  | note | Inspection / Test method - Measurement
label | 3b6a6e1d-91cb-5c08-9787-1c30519c5206 |  | note | Acceptance Criteria - < 10mm using 3m straight edge
label | 9495f3bc-a45d-5708-8962-80809d2591e7 |  | note | Record documents - Survey
label | bd8f6e45-521d-5d61-a4a2-3c47b6ab0d89 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.12 - Finished Pavement
label | 0302adc9-a52a-5dc7-97f0-2ab09743f383 |  | note | Detail of Activity - Surface Levels
label | d116b80e-5431-5b25-9d27-09aefb0fa8bc |  | note | Action (Hold, Monitor, Witness) - H
label | 2fa5fbe7-ba31-5bc1-b850-5181b3b4a171 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | bbea6dac-695b-59e4-9d66-7b38238544c5 |  | note | Inspection / Test method - Measurement
label | 3d95e03c-36ef-5107-bebe-317ecfbedf36 |  | note | Acceptance Criteria - –5mm, +15mm
label | 10909c26-4e0e-5e38-a68f-5f934d2b1278 |  | note | Record documents - Survey
label | 70554b7c-a40d-59fa-bf3c-e0ea8d129bb6 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.13 - Finished Pavement
label | de73fd1c-c994-56e8-811f-ffbc5815c3dc |  | note | Detail of Activity - Surface Finish
label | 8577fdba-6d8d-52e8-9efe-6b07311730e9 |  | note | Action (Hold, Monitor, Witness) - H
label | 38bd6197-ac33-5de8-800e-3d3a4b29a8a9 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Lot
label | a8603014-af05-5953-a577-4eba24669d89 |  | note | Inspection / Test method - Visual
label | c0540b91-487f-5a58-bedf-fa42b4b30a9c |  | note | Acceptance Criteria -
label | 86638d7c-4dae-5628-9356-16ad012efbb3 |  | note | • 1. Larger aggregate held in pace with a matrix of smaller aggregate
label | 52b90272-5cec-5e6e-96b5-e8c9f8bc7490 |  | note | • 2. Smaller aggregate held in place by fine material
label | c5263c08-baa7-5e45-a87e-b1b9f99b58d0 |  | note | • 3. matrix does not displace under normal trafficking and/or sweeping
label | 69d63ef8-277a-5a65-bd95-bea390447144 |  | note | Record documents - Survey
label | 310d9741-3bcd-5c8a-8391-c20fc1abea3b |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.14 - Finished Pavement
label | 4c262d11-6748-57cc-a96f-606dcde459d7 |  | note | Detail of Activity - Degree of Saturation, DOS
label | 79de9af5-12cd-52d8-a8df-b58f7ff3eb0c |  | note | Action (Hold, Monitor, Witness) - H
label | 7f2c17be-6576-5bb0-b31e-4d76cbbb0477 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 5 per Lot
label | 7f019470-0b87-56f8-be9f-137c0260d47c |  | note | Inspection / Test method - Measurement
label | 7d6e7445-f784-5eac-90ba-c1129e3ee1a7 |  | note | Acceptance Criteria - DOS ≤ 80%
label | 1e20895e-0d6b-50c0-bfee-00b94edb1fdb |  | note | Record documents - IANZ report
label | 4157325b-301e-5b15-8331-ecd9bd295cc6 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 1.4. FINAL SIGN OFF
checkpoint-status |  |  | checkpoint | 1.4.1 - Non-conforming results
label | 18be759c-9da5-5d01-8f6f-03051487ab6c |  | note | Detail of Activity - Assessment of all test results for conformity
label | 682f55ad-06de-580f-97f0-e61061b3bfad |  | note | Action (Hold, Monitor, Witness) - H
label | 03e7f799-f7ea-5b47-ae51-07db8b37b28f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each Lot
label | d869c73d-6452-55e1-9f4b-d85d7d380241 |  | note | Inspection / Test method - Site Inspection
label | ed16ff9c-428d-5651-bbb7-bd9713e2033a |  | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | 43852aad-9c90-5d77-947e-58f24c947bdd |  | note | Record documents - NCR
label | 7015fb33-23d0-5930-98ee-63e89049d63e |  | note | Responsibility - Engineer's Rep
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
text | 71abb37b-4848-5b79-8bbb-b4999dd0c459 |  | textbox | Contractor's Rep Name:
text | 3a8e30e7-4b97-5566-bc43-55a37ac3c27b |  | textbox | Engineer's Rep. Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - 2 coat Grade 3/5 Chipseal - Stewart Rd | itp |  |  |  | Yes | ITP - 2 coat Grade 3/5 Chipseal - Stewart Rd | 53767a7f-c130-48d9-8d6d-cb76152731d2
checkpoint-group |  |  | section | Sealing
checkpoint-status |  |  | checkpoint | 2.1.1 - Seal Design
label | 3d856a39-6dba-51e7-b8a7-591e8965a70a |  | note | Detail of Activity - Seal design outlining all design assumptions
label | 6a1c6277-e663-508e-a0f1-3ce4abb5a423 |  | note | Action (Hold, Monitor, Witness) - H
label | ac09a691-a3c5-5b2b-8eb6-b9cf5573c9b6 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per seal application type
label | 4cab376b-2a1c-5f9b-a948-d1295223ec1f |  | note | Inspection / Test method - Review
label | db1dcb73-d522-510b-a8d4-d23260f794e3 |  | note | Acceptance Criteria - New Zealand Chip Sealing Handbook
label | 1a4c7224-9709-54fb-b63d-bbbc15c08471 |  | note | Record documents - Seal design in contractor's site folder
label | 2386506e-b2cc-5c72-a4fb-93e647b3c68d |  | note | Responsibility - Designer / Engineer's Rep
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.1.2 - Check raw materials
label | 7ea7ff04-f4ba-5778-b9c7-8e21d2af2590 |  | note | Detail of Activity - Sealing Aggregates
label | f9d59d3b-5f81-5e9f-a218-bbecf105c168 |  | note | Action (Hold, Monitor, Witness) - M
label | a8c6170c-1abc-5df9-aa0d-3e601d36110d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per source stockpile
label | 26afa4ff-20e1-5447-aefe-58686caceabb |  | note | Inspection / Test method - Source Properties
label | b9bc7889-e8c0-5157-af6e-f236c34a0331 |  | note | Acceptance Criteria - NZTA M06 / RNZ 9805:2009
label | 9829d0ed-99ad-50c0-90b7-8e06d6be4227 |  | note | Record documents - Certificate in contractor's site folder
label | 5d543e06-9c0f-5549-8d9d-8cafabde4c2a |  | note | Responsibility - Contractor
label | c1a16aa6-1103-5c28-a062-823a7aae920a |  | note | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint-status |  |  | checkpoint | 2.1.3 - Check raw materials
label | 937e9ada-0ded-559a-8f32-43ea6df0bc9e |  | note | Detail of Activity - Sealing Aggregates
label | 44be4f2b-1cc3-57ad-8446-731a8c848a3f |  | note | Action (Hold, Monitor, Witness) - M
label | 8c168e49-c5a5-5199-ab8f-53524f0632b9 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per source stockpile
label | 30dae0cf-c408-5e39-a471-ad043043e59e |  | note | Inspection / Test method - Production Properties
label | a1d15648-4d5e-5564-9cad-40902a75a87d |  | note | Acceptance Criteria - NZTA M06 / RNZ 9805:2009
label | 309bede3-4065-5494-a67f-3de9ff598434 |  | note | Record documents - Certificate in contractor's site folder
label | c0a14fce-f612-5050-9165-87049b7371c8 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 2.1.4 - Check raw materials
label | 7258c02b-cf0e-5541-8d56-0060c4ba645f |  | note | Detail of Activity - Adhesion Agents
label | 1fc22c9c-98be-5d54-a498-03a7d0e97cc0 |  | note | Action (Hold, Monitor, Witness) - M
label | 354cea8f-d239-5b9b-a4a3-75139233867e |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to use
label | dc7fcf76-ed7c-5334-be95-cdd96e961042 |  | note | Acceptance Criteria - NZTA M06 / NZTA M13
label | 2152094c-f056-5ccb-9274-7e2d01057641 |  | note | Record documents - Certificate in contractor's site folder
label | 3f18ad68-d897-5fcd-a585-f67c120d4d28 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 2.1.5 - Check raw materials
label | 446f81b5-d53c-5925-a905-1a6b07b50dd3 |  | note | Detail of Activity - Audit samples
label | 2c93e278-002e-5b91-a9af-c8767752a11c |  | note | Action (Hold, Monitor, Witness) - M
label | 9d14c5a4-b427-5aeb-8de7-1bc194d4e2d5 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 20 kg per stockpile
label | e77fbe70-2d5a-57b9-8922-cfab0ef50ab7 |  | note | Inspection / Test method - N/A
label | 25748de3-12e6-5de9-a49f-8e039b425c79 |  | note | Acceptance Criteria - Stored in a sealed plastic bag in a covered environment
label | 8f264bdf-3c55-532d-a3f3-aa9bbc5fa6c4 |  | note | Record documents - ITP
label | 55ee9fce-fe88-5725-9aa1-baa52e6a7a08 |  | note | Responsibility - Contractor
label | 27d5c994-7ffd-556e-b3c0-2f05d4151414 |  | note | Comments - Retain for testing if required
checkpoint-status |  |  | checkpoint | 2.1.6 - Pre-Seal requirements
label | a2f8725f-aa5e-5345-9473-86505eac6116 |  | note | Detail of Activity - Visual inspection of surface to be sealed
label | 1c8c6246-5b15-52de-8c4e-8298afd8c203 |  | note | Action (Hold, Monitor, Witness) - W
label | 0d64bd3c-10c0-5211-8ca4-8eab14a5b5b0 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) -
label | 74dc5e02-c97b-5967-a01a-f246e952e070 |  | note | • per sealing schedule.
label | 221268e9-e44b-5626-bbd2-f17cdc3023bd |  | note | • 1 Lot = 1 day's production and < 1500m2
label | 4a5e662e-6beb-5bc8-a33a-e0b618c7fe41 |  | note | Inspection / Test method - Visual Inspection
label | 47449f33-3de7-5f53-9217-0a3b0668d563 |  | note | Acceptance Criteria - NZTA B02
label | 166a1a65-f78b-508c-add4-f7a551f8ddb9 |  | note | Record documents - Contractor's site diary
label | bfcb4e71-a46e-54b9-ba8d-ae111d1e5cfc |  | note | Responsibility - Engineers Rep
label | c35f32c8-37bb-5426-91e6-fdab177936fa |  | note | Comments - The surface finish, line and level is checked by Engineer's Rep. immediately prior to sealing
checkpoint-status |  |  | checkpoint | 2.1.7 - Pre-Seal requirements
label | 6266074f-3563-5529-8993-caa17aa88138 |  | note | Detail of Activity - Dry back Moisture Content
label | f0c7f838-47f5-56ce-99d0-f23bd7d28355 |  | note | Action (Hold, Monitor, Witness) - H
label | 29081bcb-4390-5e6a-bc8b-aa6e6d41ba36 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 9 per Lot
label | e69188d9-21b5-5393-bfbf-758a3ed4c725 |  | note | Inspection / Test method - NZS 4407.4.2.1
label | dc9ab94a-1946-5704-804f-217b55d5a7ab |  | note | Acceptance Criteria - DOS ≤ 80% preferably ≤ 70%
label | cab04cdb-df2f-5078-b60b-19fdb8c32ef4 |  | note | Record documents - IANZ Report
label | 10980561-8b81-582a-9d08-692762b16f7c |  | note | Responsibility - Contractor
label | 76393ea5-9939-50b1-8d5b-04f087872517 |  | note | Comments - Only required if pavement widening extends into trafficked lane
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.1.8 - Pre-Seal requirements
label | 255bdca4-d498-5820-88e8-09c8d0db86b5 |  | note | Detail of Activity - Clegg Hammer
label | b25bb833-fee4-5a28-b061-92e1bb3b270b |  | note | Action (Hold, Monitor, Witness) - M
label | e0467de4-509b-52ed-bd9c-f1613bffd2e8 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) -
label | ae7ce465-62ed-59a0-9b8f-cd2fcc634cb3 |  | note | • 1 CIV per 10m
label | b1dc6343-f120-5ab9-a198-bcb6af38ff76 |  | note | • 1 Lot < 300m
label | 9052668c-5516-5e95-b002-d52ef7572eb6 |  | note | Inspection / Test method - Clegg Impact Value Test
label | 93b09f38-f920-5690-9801-7ee00490771a |  | note | Acceptance Criteria -
label | 72b1f114-d940-5414-9fce-050ba72a4228 |  | note | • Average CIV > 40
label | fec23cd9-fb34-5994-bf0f-dc2394264ff1 |  | note | • Min. CIV > 35
label | 363305e7-e13e-51c1-8e92-39f961f99411 |  | note | Record documents - Contractor's CIV form appended to Contractor's daily diary
label | 1fbac1a1-77ac-5b56-b4a3-f60d2bc605ca |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 2.1.9 - Sealing
label | 44904108-6fc4-5c36-8bf1-9a4c6b84fc0c |  | note | Detail of Activity - Bitumen / Bitumen Emulsion for Chip Sealing
label | 1b2ec9d8-e81f-5b6c-8cc2-11e6ed9b2852 |  | note | Action (Hold, Monitor, Witness) - M
label | 2f2415fd-6a80-5cd2-90b7-64944f5cf709 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 2 samples per distributor
label | 0803cff9-a75b-543b-bd01-a7f35b196fba |  | note | Inspection / Test method - Penetration grade testing
label | 58af68ee-e1d4-572f-b667-e2b60bbae50a |  | note | Acceptance Criteria - NZTA M01 - Tables 1, 2, 3 and 5
label | 88f586f1-1b8a-5b13-9ae7-5f794884eaf6 |  | note | Record documents - Certificate in contractor's site folder
label | 80e97bc9-d9be-50ca-be16-af6e896c0226 |  | note | Responsibility - Contractor
label | cedd6382-a1a4-55f1-bf5a-a1edcc1b886e |  | note | Comments - Sampling as per ASTM D140 or equivalent
checkpoint-status |  |  | checkpoint | 2.1.10 - Sealing
label | 44bbe471-3d80-5ccb-b54c-6fdf447fa4b5 |  | note | Detail of Activity - Bitumen / Bitumen Emulsion for Chip Sealing
label | bfbf94b2-3132-5919-8cb4-ccbd8a7733ee |  | note | Action (Hold, Monitor, Witness) - M
label | 5320c12b-2f16-5ef0-b9b3-e8d0cc26941c |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 2 samples per distributor
label | 8396be47-c681-5e52-a27f-c6c40611da3e |  | note | Inspection / Test method - Durability
label | de9ba566-efd8-5401-a425-f21f8454268a |  | note | Acceptance Criteria - NZTA M01 - Table 5
label | 04a9e0cd-1833-51a4-b36d-f68bb291c209 |  | note | Record documents - Certificate in contractor's site folder
label | 393483ca-7e3b-5ec0-9075-90ae2fff84ff |  | note | Responsibility - Contractor
label | fc5e1050-4a5d-5c02-b4a2-df8ace474941 |  | note | Comments - Refer notes in clause 5 of NZTA M01
checkpoint-status |  |  | checkpoint | 2.1.11 - Sealing
label | b2bd624a-a65b-52ef-9321-1dc1b24c29c7 |  | note | Detail of Activity - Spraying Temperature (Bitumen only)
label | e31d28b1-3c13-5098-a11f-3931cb500eb6 |  | note | Action (Hold, Monitor, Witness) - W
label | c177b5e6-0175-563b-8762-9c8e7f29394e |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Ongoing with non-going heat sensing gauge
label | ef2b16c6-97e4-5f8a-9a12-bd3586c28d22 |  | note | Inspection / Test method - Non-contact heat sensing gun
label | 7903ffbd-8d1d-5273-bf50-0d44f05015ba |  | note | Acceptance Criteria - NZTA P03 - Table 2
label | ee8a52bf-8286-5414-838c-3bb9df62b0d7 |  | note | Record documents - ITP
label | 49daad0f-408b-506d-a26b-bf42bab00b91 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 2.1.12 - Sealing
label | d1b45369-ea51-531f-b4d5-b81bc9a4275b |  | note | Detail of Activity - Residual Bitumen Application Rate
label | 9074c9a9-ad4a-533b-bffe-71a3dae09ced |  | note | Action (Hold, Monitor, Witness) - M
label | 5f01247e-ba03-504c-96c4-5ba04c87e1a7 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Reconcile day's production
label | e43e9bc0-b03b-5cc7-83db-5e0cc5fd3b97 |  | note | Inspection / Test method - Dockets vs Area
label | 811361ed-5558-580e-8123-c8ed55982251 |  | note | Acceptance Criteria - ± 0.1 L/m2
label | 4841444e-4ce0-55da-ae12-50e55638d6c6 |  | note | Record documents - Site diary
label | a378ddab-ad5c-509f-ba78-1ede1d08a4cc |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 2.1.13 - Non-conforming results
label | f25c08a3-523d-51f6-8090-e5f5caf8b163 |  | note | Detail of Activity - Assessment of all test results for conformity
label | 9f2c1fc3-1ab0-5e1b-8774-30b1c2ffddcf |  | note | Action (Hold, Monitor, Witness) - H
label | c62952ad-5415-504c-9fdf-5fe95cf78982 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each Lot
label | 8f3d3a74-66a7-5903-9f5b-78f69e07d59e |  | note | Inspection / Test method - Site Inspection
label | 5183498e-c37a-52d1-835c-82124886cd3a |  | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | 3643220b-4a81-52a2-81e5-6694d8531761 |  | note | Record documents - NCR
label | eadccb12-f379-5580-ab79-83f634e1f80a |  | note | Responsibility - Engineer's Rep
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
text | 9c2471fa-5545-54f0-b244-fb273b756f82 |  | textbox | Contractor's Rep Name:
text | 06768db3-1bfd-58b7-8c86-f2019295fadf |  | textbox | Engineer's Rep. Name:
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | Verified Program |  |  |  |  | Yes | Verified Program | a3ce49c5-a4d1-42f2-95c4-acf61bdfbb16
checkpoint-status |  |  | checkpoint | Verified Program
checklist-sectioned |  |  | checklist | ITP - In-Situ Modified Basecourse - Stewart Rd | itp |  |  |  | Yes | ITP - In-Situ Modified Basecourse - Stewart Rd | a8c7ffcb-ca09-4639-af48-43b55882e3a8
checkpoint-group |  |  | section | 1.1. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING
checkpoint-status |  |  | checkpoint | 1.1.1 - M4 AP40 Basecourse Aggregates used for overlay
label | c5a3b9ae-d2cc-58bf-a0f4-5780fddb1608 |  | note | Detail of Activity - Quality of Fines, either PI or SE or CI
label | 27e5d721-003e-531b-a674-3f8428470ce2 |  | note | Action (Hold, Monitor, Witness) - H / M*
label | 74ada4e2-7762-5431-a494-3a91caae4ccd |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m2
label | 79bb4603-9cf5-5caa-9fc5-e87595e9ec81 |  | note | Inspection / Test method -
label | 49ddb3ff-7f15-5f97-b542-3239450c81d0 |  | note | • NZS4407:3.4 - PI
label | 7a9a7437-01b4-5132-af08-83691ffdda40 |  | note | • NZS4407:3.5 - CI
label | df13aa4f-2433-5c41-a5a6-445aa97a1c7f |  | note | • NZS4407:3.6 - SE
label | 19898240-d52c-5fbf-a5e2-56c6a2e4bfea |  | note | Acceptance Criteria -
label | bbcb57e3-5b16-5227-b1f0-37a268e2578b |  | note | • PI ≤ 5
label | 45b4f489-1d43-5188-9b23-1be3aa9fc43d |  | note | • CI ≤ 3
label | 0e4b2e10-9f2f-5a11-8903-438175b9044d |  | note | • SE ≥ 40
label | e99d6840-d09e-5ab8-a068-d990c5821f68 |  | note | Record documents - IANZ Report
label | 8572d916-51e0-534c-abff-389a73883db4 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.1.2 - Notes:
label | dcd7f41f-7ab8-5909-9d8a-ea2245aa1595 |  | note | Detail of Activity - Broken Faces Content
label | c1f0e7e6-9f92-512e-bae5-4db45d28eda2 |  | note | Action (Hold, Monitor, Witness) - H / M*
label | 796b3be2-2784-52bc-bb1f-1755604c0a32 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m2
label | 1812f6f4-42a8-534c-a6f8-88827e26c4df |  | note | Inspection / Test method - NZS4407:3.14
label | 7f436e93-320f-5f96-9399-7bb0df0d947c |  | note | Acceptance Criteria - ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm
label | 7c3fa528-98c3-5018-8772-0e5750d2e7b3 |  | note | Record documents - IANZ Report
label | ee2c9b72-af1f-5e70-ab58-0ab0263b3695 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.1.3 - H = Hold point up to approval of Optimisation Testing
label | c81f1b51-fcb2-5b44-b722-aaa0c4a38718 |  | note | Detail of Activity - Particle Size Distribution
label | 11d78d46-21ee-5062-b1f8-13280baafa81 |  | note | Action (Hold, Monitor, Witness) - H / M*
label | 7c2f2349-9e92-59dd-965f-ee5ae614cfc6 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m2
label | 66de6d7a-86de-540b-81df-ae59aa5b1378 |  | note | Inspection / Test method - NZS4407:3.8.1
label | dd75278f-6312-52b2-b67f-472e119e31a8 |  | note | Acceptance Criteria - Check if 50:50 blend of average existing (from TPs) and NZTA M/4 AP40 will meet the FBS grading.
label | 8bab098b-5dd5-5dab-a14e-6ddd55a5834a |  | note | Record documents - Report using IANZ Reports for AP40 and TP PSDs
label | a0bfb161-0c82-5440-ad8c-07d9b7ff6836 |  | note | Responsibility - Contractor to provide analysis
label | 085e1801-9299-56e9-9f46-389f8806719c |  | note | Comments - Designer to advise if "average" blend is acceptable.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.1.4 - Optimisation of Stabilizing Agent
label | 3e1b5ba8-0028-549f-b7fe-8b41c5146be5 |  | note | Detail of Activity - Indirect Tensile Strength, ITS
label | 47cc19c1-1d0a-5fdb-b6d2-f60563da65f0 |  | note | Action (Hold, Monitor, Witness) - H
label | 44acb877-c2d5-57ab-a662-ccf548767441 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Optimisation test per aggregate type
label | 567e0794-aab9-590f-86d4-45b116168bdf |  | note | Inspection / Test method - NZTA T/19: 2020
label | c2677f3c-2224-50f0-b7f3-dae5b3e36707 |  | note | Acceptance Criteria -
label | d31ee003-297f-5294-8639-2045df8ffaec |  | note | • Dry ITS: 175kPa to 400 kPa
label | 214fa3b5-7e8e-5b6b-946c-a1e3b6f3689d |  | note | • Soaked ITS: 150 kPa to 350 kPa
label | 2c92a8fd-d807-5c97-9f03-2af23d14a662 |  | note | • TSR ≥ 70%
label | ae689301-80ef-532a-9cb1-e906372ebde3 |  | note | Record documents - IANZ Report
label | 1f71842d-3f05-5b8d-8297-25008a8bba02 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.1.5 - Optimisation of Stabilizing Agent
label | c68efdf5-08ad-519d-9aa0-5f8f3099631b |  | note | Detail of Activity - Modified Maximum Dry Density
label | fdec2a64-ede8-517d-a9c4-47d177fc51be |  | note | Action (Hold, Monitor, Witness) - M
label | 91670f33-d0ef-5dd3-82b6-468e99ffb7a0 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - At Optimised Binder selection
label | a5d7f7b2-0df1-5c22-bffd-4359bdf54a14 |  | note | Inspection / Test method - NZS 4402.4.1.3
label | 18c45df8-63bf-5857-9a1a-ca94d13e2481 |  | note | Acceptance Criteria - To determine target density
label | a4f8d09a-0342-50dc-8956-95a39ab63650 |  | note | Record documents - IANZ Report
label | 1723fbb0-f590-5673-9701-c230691dff7d |  | note | Responsibility - Contractor
label | 600d056e-0e98-5406-aca2-bac285ac5eaa |  | note | Comments - Required before Stabilisation comences
checkpoint-group |  |  | section | 1.2. BEFORE STABILISATION COMENCES
checkpoint-status |  |  | checkpoint | 1.2.1 - Setout section
label | abe6a4cb-64a3-591c-bb08-e38b39a61970 |  | note | Detail of Activity - Install offset pegs; record centreline, edge line or mark out stabilisation extents from existing line marking
label | f78a46e6-991d-52fc-9238-7d9deaf98d9f |  | note | Action (Hold, Monitor, Witness) - M
label | d107d944-2096-5b41-a8d4-d503c7d6872b |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to each section
label | 1cfb6a91-acb6-5fd2-a69d-739ef5aad063 |  | note | Inspection / Test method - Survey
label | daaec00e-a34e-5258-8bc2-fa6544b47344 |  | note | Acceptance Criteria - Document existing furniture
label | ab93e0dc-9945-5cf7-8513-0e534bd61732 |  | note | Record documents - Electronic survey files
label | 2a970e5a-a623-5054-912e-1730b51a7c9b |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.2.2 - Production Plan
label | 535f1fa6-e65e-5d6c-b2d8-38495f75d9a7 |  | note | Detail of Activity - Plan showing cut lines and sequencing of works
label | 215a7ba4-3910-5d11-93e2-8a25d8fb3438 |  | note | Action (Hold, Monitor, Witness) - M
label | 8ae3ac7f-d235-5a3f-b7d7-45ddc76c8c0b |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to each section
label | 957fd461-53ff-555d-bfb0-34685c71f506 |  | note | Inspection / Test method - Daily Report
label | b305dbaa-ebb8-5b50-a9ce-f2cc7c4cc5ed |  | note | Acceptance Criteria - Points covered in NZTA B/5
label | 0dbf10c5-19a9-5867-aba0-56b643fe38d9 |  | note | Record documents - Daily Production Plan
label | e03756ce-9b72-5e87-a5b4-dad6300de998 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.2.3 - Weather conditions
label | f79f95ff-8465-5181-840f-da8651e33750 |  | note | Detail of Activity -
label | f12697dc-0a00-5423-aa3b-957c1bcd8f6b |  | note | • Ambient Temperature (C&L)
label | 6fb7f957-42f2-5534-af4e-fac543c0ee6e |  | note | • Material to be stabilised (BE&FBS)
label | 590f12f1-6867-5e8d-92f1-7626bfb0ba43 |  | note | Action (Hold, Monitor, Witness) - M
label | 23a16c63-c479-507d-add7-e58d0bda3a96 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to spreading
label | 93169655-d52b-5d52-a454-ac91cca264f9 |  | note | Inspection / Test method - Measurement
label | 271c7b00-7646-5e1d-a048-87dd69201476 |  | note | Acceptance Criteria -
label | 4065533b-29a2-53d7-9e41-e6c93ad5b56f |  | note | • Ambient Temperatures:
label | 653bcd71-7a6f-526c-a746-9c727eb3246a |  | note | ○ Cement: > 5°C, Lime: > 10°C
label | dc4050c1-2ca4-5657-ae48-bac4366a550a |  | note | • Material after stabilisation:
label | 802eba46-38e4-50ca-8b62-4bcf9bb79092 |  | note | ○ BE: > 20°C, FB: > 20°C
label | bdf57025-c02f-51b8-931b-80b1cd00e07c |  | note | Record documents - Daily work Log
label | 9271c85c-0231-5e2d-9cfd-f5c0fc9f907f |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.2.4 - Weather conditions
label | fde07fd9-8863-5049-804e-23325747212b |  | note | Detail of Activity - Wind
label | 9a0a55ec-f9ed-5173-a415-86acc2993583 |  | note | Action (Hold, Monitor, Witness) - M
label | e9a8c0dc-4d4f-5bc9-a794-46881bf70074 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to spreading cement or lime
label | 15d4611d-7660-5013-8071-f04d3937fe4a |  | note | Inspection / Test method - Local weather stations
label | 53a4ecca-498d-512c-ad6e-2e9bc5a5bef2 |  | note | Acceptance Criteria - Wind speed < 25 km/hr
label | c2a1b6af-94ab-58e6-a3cc-b607ad253dad |  | note | Record documents - Daily work Log
label | 0581acf5-3162-551f-ba37-c5bb061efcda |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.2.5 - Weather conditions
label | 001d28e8-28b0-5137-a36b-d1e219e03d12 |  | note | Detail of Activity - Rain
label | 0279f478-59c1-5c44-a7d6-caf4c9c8b80c |  | note | Action (Hold, Monitor, Witness) - M
label | 14ccff7c-297c-50b3-acc5-676fedea47a8 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to spreading cement or lime
label | 793f94ad-b098-5bef-aec3-8d0cb1c8bc01 |  | note | Inspection / Test method - Local weather stations
label | 41e1bcff-abbb-5555-8bb9-dd433777a9a6 |  | note | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
label | f906513d-32e7-5602-9a7c-ffcb96f5ed1c |  | note | Record documents - Daily work Log
label | 9fa72d79-6e95-51e4-bd5d-44d8a169bd0f |  | note | Responsibility - Contractor
checkpoint-group |  |  | section | 1.3. STABILISATION OPERATION
checkpoint-status |  |  | checkpoint | 1.3.1 - Stabilizing Agent
label | c67b682f-b103-5569-baba-d226735db2b1 |  | note | Detail of Activity - Cement, GP
label | e06ebeba-1a33-56e1-9511-4b0a5fe08b91 |  | note | Action (Hold, Monitor, Witness) - M
label | da0e22fb-0d2f-517d-a0c9-e17b2229273a |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Batch
label | 7c87c35d-8103-542e-aa5d-4e287ea809bc |  | note | Inspection / Test method - NZS 3122
label | 15b1b548-639a-5836-9be4-a42ee78763e9 |  | note | Acceptance Criteria - Conform to Specification
label | 368e39bb-243e-5d60-9b30-50d7eb0c7a07 |  | note | Record documents - Certificate in contractor's site folder
label | aab3565c-0373-5275-872d-9b22bbd71926 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.2 - Spreading of powdered stabilising agent (Cement)
label | e10b4d1c-47df-5263-bb7e-b9199d2f2e5d |  | note | Detail of Activity - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
label | 2cf9ea93-4f25-5d93-9110-d3a12b4ae04d |  | note | Action (Hold, Monitor, Witness) - M
label | 8fe3bc33-1675-5534-ab80-239e0cdbd5bd |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) -
label | c18f9abb-12be-5736-8e65-7606ab59fcb9 |  | note | • every 400 m2
label | a50a812a-0d13-57b0-b738-25f6d951dd2d |  | note | • every 150m for a 2.4m width
label | 62346d11-f256-52db-b1ed-322bec173c96 |  | note | Inspection / Test method - Weigh mat or tray
label | bdfddb9a-e1e1-5e59-afb9-56d4effc581a |  | note | Acceptance Criteria - ± 5% of specified rate
label | 6db81312-add2-5d65-a44e-4b55d66fcfcb |  | note | Record documents - Daily work Log
label | 5f1fbc2f-1e16-5764-80d5-13f49ac5d6c0 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.3 - Spreading of powdered stabilising agent (Cement)
label | 0d1508a8-a9d6-5255-ab9f-18116245337b |  | note | Detail of Activity - Compare area spread with weight used for each spreader load
label | f2b004a3-3f54-5482-acfd-87bcb7e7522c |  | note | Action (Hold, Monitor, Witness) - M
label | 1f9de0c3-9b79-50a6-9f96-e18d2858218c |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On-going measurement by computer/load cells
label | a86cfda8-cba6-5aec-b00c-4fd0fe7a2325 |  | note | Inspection / Test method - Measurement each run
label | d9a6928f-586e-5fc1-9b6a-874bb368723b |  | note | Acceptance Criteria - ± 2.5% of specified rate
label | 41d027ea-0efb-5133-b9fa-35fde9ee92d4 |  | note | Record documents - Daily work Log
label | ae2f36be-3160-5169-83ca-6d1106ee75dc |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.4 - Injection & Mixing of Water
label | 2f597f6b-d28f-5300-b62b-8c83c8347688 |  | note | Detail of Activity - In-situ Stabilisation process
label | cfbe0f03-acb8-5d6d-8124-48af3c9a3a9d |  | note | Action (Hold, Monitor, Witness) - M
label | 6268fe55-901c-5a1c-af15-0db83093072f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On-going visual assessment
label | fb313aae-182d-551b-8754-35c6bf8785c3 |  | note | Inspection / Test method - Visual and hand squeeze test
label | d2affa1f-73cc-5486-9039-ebb0501a335a |  | note | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
label | ead48d84-1f98-57ca-8006-e0949f2745e5 |  | note | Record documents - Daily work Log
label | e7cb8311-6bb0-5b7c-a488-e7d3abfbe15e |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.5 - Depth of stabilisation
label | c0097621-d127-58d2-9d68-72917f83a722 |  | note | Detail of Activity - Depth of stabilisation
label | 0e70337f-a563-5c91-8402-650c9c46e4b6 |  | note | Action (Hold, Monitor, Witness) - M
label | 4a910f2e-1194-5a94-8342-a482af35fa44 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Every 200m
label | 06197805-11e1-5d1d-82c5-ab84afd30d4a |  | note | Inspection / Test method - Measurement
label | 6699476d-4d20-535e-affe-20531700b677 |  | note | Acceptance Criteria - +15mm / -5mm from specified depth
label | 3550e73f-6371-579e-8fd7-ee1ac1c96029 |  | note | Record documents - Daily work Log
label | 7383d51a-af06-550b-879f-8315a11e1d16 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.6 - Compaction
label | 9ce29f0a-fd45-538f-8909-2b2ed5b7b369 |  | note | Detail of Activity - Plateau Density Test
label | d2dbfccb-5c92-5fe9-abe0-bcca80406398 |  | note | Action (Hold, Monitor, Witness) - W
label | 3e9e2002-95f1-58d3-a308-39ece79a27dc |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On first day and then 1 per 20,000m2 unless material or anvil conditions change
label | 2bef695f-880c-5445-8575-576d2cb3012f |  | note | Inspection / Test method - Draft NZTA T/24
label | 00911a47-0553-59e5-9421-2368c8b99179 |  | note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern
label | 1ada63fb-a6f6-50b0-a182-7a1c5dd8bb39 |  | note | Record documents - Daily work Log
label | 41311582-2c38-58e1-bdbc-47f079200b4a |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.7 - Compaction
label | 688e9e9f-5608-581c-ad01-d026f2675cf1 |  | note | Detail of Activity - Maximum Dry Density
label | d676a213-9989-552c-af90-7490e247e64e |  | note | Action (Hold, Monitor, Witness) - M
label | 7076befa-c07b-5d98-a71b-19e0acd6500a |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per day up to 3,000 m2, 1 per 2,000m2 thereafter
label | e97e3e7c-e73e-514c-8f78-120997490d97 |  | note | Inspection / Test method - NZS 4402.4.1.3
label | 2bd503c9-89ef-52ff-b88b-5931aa37667e |  | note | Acceptance Criteria - For analysis of DoC
label | 46bfa0f1-e0fc-5923-8b3e-e77824f9b568 |  | note | Record documents - IANZ Report
label | 9cca3442-6520-55d7-85ff-3aceed34af64 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.8 - Compaction
label | 659a421a-1ff3-5c84-9a09-8962db5a21ff |  | note | Detail of Activity - Degree of Compaction
label | 2c498ae3-e84d-52c4-9900-36a83a1a1780 |  | note | Action (Hold, Monitor, Witness) - H
label | 41b89b83-a182-5d6f-bc34-4d63c0cbb664 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 5 per 1,000m2
label | 99f5314b-0565-5bde-8e83-7acd5798d7dd |  | note | Inspection / Test method - NZS 4407.4.2.1 (to 100mm and 200mm) and NZS 4407.4.2.2
label | 3c013383-56a3-59c1-8e52-8467fd3fe316 |  | note | Acceptance Criteria -
label | 830fdfa2-8a9b-586a-a493-2bf7cab42017 |  | note | • Average DoC ≥ 98%
label | f494dec6-0467-5821-9996-b8b740be9c3c |  | note | • Minimum DoC ≥ 95%
label | 83f98d5f-5811-525b-a4a8-b85aa0e9da29 |  | note | • Refer NZTA T/23
label | 1de79b60-768f-530f-9d63-72affada2dae |  | note | Record documents - IANZ Report
label | e4320b66-acd0-5bd3-af55-5465fe495cf9 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.9 - Finished Pavement
label | 74f16a5f-cc7d-5015-9c3d-8a48029fdf3a |  | note | Detail of Activity - Crossfall
label | eaf5d473-1c56-5db0-9bfa-0bb2f80fc162 |  | note | Action (Hold, Monitor, Witness) - H
label | ff632619-9620-5191-801a-8fb38061297b |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | fa7d04b5-2e9f-5391-a0d6-4bd637e585a1 |  | note | Inspection / Test method - Measurement
label | 95f3968e-08dc-5ead-a00c-3563dee24acc |  | note | Acceptance Criteria -
label | 35f14337-7cfe-5fc0-8275-25d82206eabb |  | note | • ± 0.5% of specified crossfall measure
label | 96ac3893-33a6-5da9-b5e5-e245f4ab1b07 |  | note | • 2m apart
label | b7810d2b-64d1-5444-8417-c7b2ab76aec3 |  | note | Record documents - Survey
label | 250b94d9-36b5-511d-8a47-a377013f2031 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.10 - Finished Pavement
label | ea3406dd-835a-5f40-81ae-617c7d1e5b52 |  | note | Detail of Activity - Stabilised width
label | 4585f8f5-936a-5e81-a2f5-8a31f03cbb3a |  | note | Action (Hold, Monitor, Witness) - H
label | cc84ba76-9c9c-5578-80d6-22c96360ba6c |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 every 20m
label | 88a1c9cc-21dc-561b-a23e-a9e6cd4fa76b |  | note | Inspection / Test method - Measurement
label | a2948c76-991c-5e45-a095-ee8c3192611c |  | note | Acceptance Criteria - –20mm, +100mm
label | 8ed8632f-f84e-502e-9bdb-68d66fe8ad01 |  | note | Record documents - Survey
label | 23460091-7a27-5f7f-b190-14618f896ac4 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.11 - Finished Pavement
label | ef583fe7-b0c5-5249-b728-c5532330c4d7 |  | note | Detail of Activity - Surface Shape
label | 356af275-625b-513d-b8be-9309f15866ab |  | note | Action (Hold, Monitor, Witness) - H
label | c4a616f0-b865-53fa-a45d-7f20b4f1b05c |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | c38cf4cc-3067-59b3-bbbf-b89290b59a6f |  | note | Inspection / Test method - Measurement
label | 8a924303-ffe2-5424-8ae7-553dbc151b79 |  | note | Acceptance Criteria - < 10mm using 3m straight edge
label | 45a3e983-dbee-5d42-adc5-671e3dd9d429 |  | note | Record documents - Survey
label | 2de253bf-b92a-5ef6-82dd-ac0a584ea705 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.12 - Finished Pavement
label | 71ba1394-a362-59d8-9d09-9aba29d8602d |  | note | Detail of Activity - Surface Levels
label | 47e848b5-173f-51b4-8953-58178e266e74 |  | note | Action (Hold, Monitor, Witness) - H
label | 6b00afc4-934b-5d05-b61b-8d19ed33e033 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | f146fc13-1d8b-5197-84b8-552aebb75b22 |  | note | Inspection / Test method - Measurement
label | 3454da9e-7bab-587a-a5b1-a30b35ce6479 |  | note | Acceptance Criteria - –5mm, +15mm
label | b4f6801a-b836-5ef5-91ec-1014b8aa3de3 |  | note | Record documents - Survey
label | 1a6537dd-146a-5d99-970c-e17a4ae5ded1 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.13 - Finished Pavement
label | fbfe061e-cd37-5e4e-b55e-250a3c7e46ed |  | note | Detail of Activity - Surface Finish
label | 7b134992-10aa-5d05-9e04-4d5785825a4a |  | note | Action (Hold, Monitor, Witness) - H
label | 1987cda5-6689-500f-894d-d49e9826b9a9 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Lot
label | 9c8748b7-d1f3-5cfc-91a5-7e7c63682cbe |  | note | Inspection / Test method - Visual
label | 0dc4bda9-72f0-5c08-98c3-a3b1ab8575c1 |  | note | Acceptance Criteria -
label | 935805f7-a557-505c-9edd-fe4fc28dfd39 |  | note | • 1. Larger aggregate held in pace with a matrix of smaller aggregate
label | 94d15648-5891-5b48-bea2-537d18f14cad |  | note | • 2. Smaller aggregate held in place by fine material
label | 4bcf866d-435b-5e59-abf3-a4867b8af612 |  | note | • 3. matrix does not displace under normal trafficking and/or sweeping
label | 2235436c-782f-54ad-accc-abaa21d39f42 |  | note | Record documents - Survey
label | 113ab1b0-28e6-57df-869c-af34245a1334 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.14 - Finished Pavement
label | 5fe4675d-3fc5-5581-8c67-4776432a0f10 |  | note | Detail of Activity - Degree of Saturation, DOS
label | 56ff4b43-794e-5091-9ba7-f87fc8525fd6 |  | note | Action (Hold, Monitor, Witness) - H
label | 5694ebed-38b5-5e29-aa46-4704e2f564f7 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 5 per Lot
label | 29c51104-16f1-5fd5-bc71-d8e68b22855b |  | note | Inspection / Test method - Measurement
label | 836b0807-d810-5ad6-8c6f-810cbc1a5bec |  | note | Acceptance Criteria - DOS ≤ 80%
label | ec853ed8-d08a-583c-b577-039981c141aa |  | note | Record documents - IANZ report
label | f05b7274-2f17-546d-b79b-444521a4d134 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 1.4. FINAL SIGN OFF
checkpoint-status |  |  | checkpoint | 1.4.1 - Non-conforming results
label | 0b937d23-e651-555a-9050-d4d5d3894cf4 |  | note | Detail of Activity - Assessment of all test results for conformity
label | 3328a907-ee5a-5e11-b8e7-9a98cb83faf7 |  | note | Action (Hold, Monitor, Witness) - H
label | e0781e2f-13c8-5791-8695-7bc18600e934 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each Lot
label | 47ecc7e5-7457-51de-b2b1-e5938c79dc9c |  | note | Inspection / Test method - Site Inspection
label | 87388793-e97c-5bc5-bce4-3057467a5f67 |  | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | ef054bdb-7fa4-50c3-850c-2686a02ece53 |  | note | Record documents - NCR
label | 9c8ce558-87de-50e4-b02a-d83878e56374 |  | note | Responsibility - Engineer's Rep
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
text | 0c9945f3-de28-5e39-a015-9bd8639545ed |  | textbox | Contractor's Rep Name:
text | 2bcb8431-66f4-58d2-8429-9f8d79033f10 |  | textbox | Engineer's Rep. Name:
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | Approved JMF |  |  |  |  | Yes | Approved JMF | b8eb8d25-6b00-4555-88b1-fd1d5c217015
checkpoint-status |  |  | checkpoint | Approved JMF
checklist-flat |  |  | checklist | QMP |  |  |  |  | Yes | QMP | dd354f9d-68fb-42bb-bddc-cadbbf7b50ae
checkpoint-status |  |  | checkpoint | QMP
checklist-sectioned |  |  | checklist | ITP - Resurfacing Physical Works | itp |  |  |  | Yes | ITP - Resurfacing Physical Works | f274d162-1111-4b65-a06d-9e233337d589
checkpoint-group |  |  | section | 1.0 Pre-Works (Off Site)
checkpoint-status |  |  | checkpoint | Stakeholder Management Requirements met
label | c08cb13d-9e49-59e2-ad59-94b168ce8ad6 |  | note | H
label | 3b12b52e-31ec-5aee-85b6-ab4ef912816b |  | note | Reference or Specification: CSCMP
label | e4dc1cbd-d6a8-5680-86be-c3d6bd07b275 |  | note | Method/Test required: Confirm requirements followed
label | c2b966a1-86ec-59a8-93c9-2ed53fb74705 |  | note | How Often? Each site
label | 08a26410-6dc2-543a-8972-08449855f484 |  | note | Records Required: Copy of stakeholder notification / Photographs of VMS Boards
label | 066f6311-387f-5f33-a780-590e6f3134d8 |  | note | Responsibility: Project Manager / Renewals Manager
checkpoint-status |  |  | checkpoint | Confirm if any environmental protection is required
label | 971d9448-790a-5c5e-8c14-20493e256d70 |  | note | I
label | ecf5fc0b-5bbb-564a-b066-a2c6a43106ba |  | note | Reference or Specification: ESMP
label | 5fb24899-cab6-5fd8-bb7d-258366e8b6e3 |  | note | Method/Test required: Record decision
label | 83929edd-ab76-55d0-b458-1b6e08cd6208 |  | note | How Often? Each site
label | 159e5291-65c1-5c4a-bb2d-79b73c1cd9ae |  | note | Records Required: Pre-seal Inspection Form
label | 6d6744e3-a36a-5130-bf0d-90b88d41cd45 |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work
label | cab2f218-55f3-576b-bbd8-b636bd55f51a |  | note | H
label | 2c9a061f-b160-5a9a-aee7-ff089d756e25 |  | note | Reference or Specification: QMP
label | 8702332d-fa44-5cf9-8386-467ff8d6e1b3 |  | note | Method/Test required: Brief all team members on day’s work plan
label | 05d926ec-a2e1-5365-badd-e16a72c520e8 |  | note | How Often? Each site
label | a73f014b-331d-5dda-9e5b-23adcb0f4f06 |  | note | Records Required: Pre-seal Inspection Form
label | 31010a48-c20f-5d87-8fd9-89ea69f15523 |  | note | Responsibility: Project Manager
checkpoint-group |  |  | section | 2.0 Pre-Construction (On Site)
checkpoint-status |  |  | checkpoint | Job start, identify risks and controls, communicated to team
label | ed3e3263-ab8f-50fe-8fc4-6ad96b58e8d2 |  | note | H
label | 0c7a220d-7ec0-5137-8462-7456b51771a8 |  | note | Reference or Specification: HSMP
label | 57ca6e5d-df73-5038-82b6-091a51afaf02 |  | note | Method/Test required: Record all risks and controls on Hazard ID following Team discussion
label | fccdc83d-10f9-500a-8dc7-b740e46111ee |  | note | How Often? Each site
label | b448dbab-4db5-5f83-93b3-a75de792ab18 |  | note | Records Required: Hazard ID form
label | c2278d7d-7949-5e7b-8726-c70f4c3db9fd |  | note | Responsibility: Site Foreperson
checkpoint-status |  |  | checkpoint | Establish traffic management to plan
label | 8714ca26-491f-589f-94b3-07792a0ae4cf |  | note | H
label | bdf63531-4232-5f3a-b730-cb5fb89f0700 |  | note | Reference or Specification: TMP
label | 6090db3e-ab1b-5310-8b09-43056b34d4a7 |  | note | Method/Test required: Site audit post set up
label | 38f39c06-880c-52e2-8fe6-4b564db3e523 |  | note | How Often? Each site
label | 06dce2f0-6953-5396-81d9-247aa46ed401 |  | note | Records Required: TTM Diary
label | 6e705f8a-c956-5d0c-9e89-3ccb2ae2656d |  | note | Responsibility: STMS
checkpoint-status |  |  | checkpoint | Confirm site is on approved programme
label | 356dc010-695b-51d1-b448-8c8640a178ed |  | note | H
label | adaebcfe-9b5d-5223-bfc5-c6d81f52f900 |  | note | Reference or Specification: Approved Programme
label | 5b48b5ce-91b3-5622-aaf7-a8f393213e51 |  | note | Method/Test required: Record as-built site dimensions
label | 2fbbdaac-1ec9-56f7-a001-55c98a2adc61 |  | note | How Often? Each Site
label | 032da9ab-8f44-5737-bd6e-c6bf191f72f9 |  | note | Records Required: Pre-seal Inspection Form
label | 01415539-90ac-5f22-87f8-5915d3fad37d |  | note | Responsibility: Site Foreperson
checkpoint-status |  |  | checkpoint | Confirm site extents (i.e. Check what is marked on the road matches the job sheet / programme details
label | fa242c1a-ee96-5966-beb5-987fd6e0673b |  | note | H
label | dc190d69-61ba-5aec-aa7c-3eed789d2769 |  | note | Reference or Specification: Approved Programme
label | 7859af46-eb90-5ff5-87b3-d145dca77238 |  | note | Method/Test required: Record as-built site dimensions
label | 22013b16-842b-5ad6-a9c0-d8b8ca74f831 |  | note | How Often? Each Site
label | 2194e34d-2a34-540d-90cb-485ecda5e4ed |  | note | Records Required: Pre-seal Inspection Form
label | b56c3d0b-52eb-5dcb-ac93-9faa6fc32270 |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Stockpiled sealing chip is clean and suitable for sealing
label | 4c5ccadf-21ed-5afd-a2b1-1c5f2cd2ec9d |  | note | H
label | ac33631e-f3df-54f7-956f-39bfe53473a8 |  | note | Reference or Specification: QMP
label | 9c16ffc8-bfaf-54d4-80c1-cbf7b5bc31c1 |  | note | Method/Test required: Acceptable/Unacceptable
label | b21e78ea-6053-5bde-ad13-cd5fdefeb658 |  | note | How Often? Each Stockpile
label | d1fa07df-14fc-5a04-b6ab-5fdbc80208f2 |  | note | Records Required: Pre-seal Inspection Form & Photograph
label | 6e7f6c92-a042-502c-8536-5d5198d83aa4 |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Stockpiled sealing chip is the same grade(s) as specified in the chipseal design
label | adc328e4-4488-5497-b967-874698d3912c |  | note | H
label | bc3e32fc-7358-53a2-acbd-446489e8e716 |  | note | Reference or Specification: QMP
label | e43a771f-8787-5412-90a9-1d3f5bdc001b |  | note | Method/Test required: Acceptable/Unacceptable
label | 91f623a4-23ac-5719-9e30-8da077bc75c8 |  | note | How Often? Each Stockpile
label | d8030933-31df-506b-b957-93c36d76bd4d |  | note | Records Required: Pre-seal Inspection Form
label | fa0c3b6d-dbf2-5225-a21a-38a9af1a6005 |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Record & photograph environmental protection measures installed
label | 836dd4ff-794e-588a-a2e7-60d34d368ffc |  | note | I
label | 17c8be83-cc75-5218-984e-9fe88a44932e |  | note | Reference or Specification: ESMP
label | 3d24421a-8152-5d4b-bb2b-e63c96e93fa7 |  | note | Method/Test required: Record temporary measures
label | 3e8b0da1-354b-5fc0-8f57-239cd324b6fc |  | note | How Often? Each site
label | 62bf1251-4901-5c35-a90e-745e941a0f39 |  | note | Records Required: Pre-seal Inspection Form & Photograph
label | bafc99c0-996e-5544-afab-279a67c4ac3d |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Binder application rate
label | f4b7d316-b474-5699-a1ef-cb2ad823b1de |  | note | T
label | c17843a6-6868-5f97-be44-ce09052546e5 |  | note | Reference or Specification: Seal Design / Spraying Instructions
label | b38621dd-35c8-5d4f-8f7d-044ee707276f |  | note | Method/Test required: Confirm seal design requirements from programme
label | ba716bfe-3c88-55b2-a8fd-c7c9b220241b |  | note | How Often? Per site
label | eafcf87e-8abe-5d9d-95d9-ab7746665f94 |  | note | Records Required: Spray Sheet
label | 73498d67-f034-54b1-8108-ed40b7a15aab |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Pre-Sealing surface condition
label | 68800705-7367-57c8-8adb-3d3804e7cd39 |  | note | I
label | 2c01666e-8a3e-5e19-bf77-968f60918412 |  | note | Reference or Specification: QMP
label | d040eeb9-0a21-5eb6-9da1-edea597daa49 |  | note | Method/Test required: Acceptable/Unacceptable
label | ff467823-36a1-533a-9558-9fbdea334904 |  | note | How Often? Per Site
label | 029aae0b-42c1-5f8b-9243-88476579b765 |  | note | Records Required: Pre-seal Inspection Form & Photograph
label | 64cded00-dbbd-5e52-bf18-3778adb1f0d8 |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-group |  |  | section | 3.0 Construction
checkpoint-status |  |  | checkpoint | Start spraying Temp >10°C
label | 3455178c-b1b3-53fc-8e3e-7d2dd502aed9 |  | note | T
label | 12792e9f-3792-5e60-a343-4de1cccaca30 |  | note | Reference or Specification: NZTA P/17
label | b24280b0-8720-5992-b876-4dae87bbf1cd |  | note | Method/Test required: Start >10°C
label | 66090e48-1d3e-5e94-a23f-a55b59f1bda7 |  | note | How Often? Per site
label | ac7e8f63-53ad-50a7-ba77-59e71999dded |  | note | Records Required: Spray Sheet
label | d62125b1-47a5-5b8f-bca0-e10f7bfc0d10 |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Binder application variation
label | 51a9ee41-f922-5110-8a67-553d2c7c5b26 |  | note | T
label | e302f42f-f614-5f88-bfb1-f97d31658af4 |  | note | Reference or Specification: NZTA P/17
label | aa13106f-8de3-56b2-9fc7-88b170a9a256 |  | note | Method/Test required: +/- 4% (spray rate) ; '+/- 50l (tank dip)
label | c941fd2d-c3fe-5c2d-8870-19a81fb50282 |  | note | How Often? Per site
label | 51afd765-c49e-5752-aace-d3131c409c0b |  | note | Records Required: Spray Sheet
label | 501d59a9-6349-5d97-a2ac-f7b699c545ea |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Sealing chip application
label | 96b35556-02b7-5cf2-a767-06f7147898f5 |  | note | I
label | 7ed78178-1491-53b2-bc20-3dc5f43914db |  | note | Reference or Specification: NZTA P/17
label | 8c2971af-4768-5102-96a4-0a4363f3d4bd |  | note | Method/Test required: Full and even coverage of sprayed area
label | 409b5bc4-88fd-5e84-9a14-68d5493a89e1 |  | note | How Often? Per site
label | a32b3d7d-0328-5840-bdcf-b9d9aa35cb0d |  | note | Records Required: Post-seal Inspection Form
label | 7c941a85-06e6-5a8d-8d3c-2c7bdddbc354 |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | PTR Rolling pattern
label | 718ec91f-bf34-57ef-8ff0-14bdc0ba297e |  | note | I
label | 0b73a4b0-d9e5-5c2f-8621-e466d2579031 |  | note | Reference or Specification: NZTA P/17
label | 3067aa4d-0e35-5008-bac0-2422375c286c |  | note | Method/Test required: Initial rolling completed along with traffic-rolling under controlled TTM
label | 4b541f4e-5d33-59fd-9489-e21d9ae77fac |  | note | How Often? Per Site
label | ab0e9510-34f2-5c8a-880e-10694494b8e2 |  | note | Records Required: Post-seal Inspection Form
label | 73f40a7c-9e20-5eac-85fa-600333d733c7 |  | note | Responsibility: Site Foreperson
checkpoint-status |  |  | checkpoint | Traffickating
label | a354eb97-be53-5f16-9e9d-a3ca262247f1 |  | note | I
label | 0ed00319-1bf2-5d00-b23a-d376d14b8671 |  | note | Reference or Specification: Chapter 11 - Chipsealing in NZ
label | af51c0ae-d08c-5d70-ab7f-db50cbd31e18 |  | note | Method/Test required: Initial rolling completed along with traffic-rolling under controlled TTM
label | 347dcf6a-dae5-50f1-8386-7c1b46f1a47a |  | note | How Often? Per Site
label | 062bf474-a580-5972-8109-e8d7c45f5489 |  | note | Records Required: Post-seal Inspection Form
label | 6d19197e-64b5-54f5-85fb-3c10331022f6 |  | note | Responsibility: Site Foreperson / STMS
checkpoint-status |  |  | checkpoint | Tagging for line marking
label | 94e7237f-6240-5700-a597-ab976687bd99 |  | note | I
label | 128ec509-418e-5d68-93f0-89fe72e89f74 |  | note | Reference or Specification: Chapter 11 - Chipsealing in NZ
label | c48be04c-a7a6-5e66-88c2-f7fa501eba69 |  | note | Method/Test required: Pre-seal Visual check
label | 01a00db9-d282-58cf-ac93-0e9a8db02758 |  | note | How Often? Per site
label | 72844bda-2c3c-5a51-9436-f36f02e19271 |  | note | Records Required: Post-seal Inspection Form
label | dfef43b4-317c-5445-bd75-634481c07aaa |  | note | Responsibility: Site Foreperson
checkpoint-status |  |  | checkpoint | Post-Sealing Surfacing Condition
label | 2bb923f3-8096-5fc0-877a-624aaf3dfd66 |  | note | I
label | a835d131-d034-5893-bc5c-49b5ed40700e |  | note | Reference or Specification: QMP
label | e9633b1d-3288-57d4-a707-9bdd3ed69022 |  | note | Method/Test required: Visual check
label | 15708480-458d-5404-91e5-f8bf99d8b1b1 |  | note | How Often? Per site
label | 10665b6e-f3b9-5d27-895e-424a73995706 |  | note | Records Required: Post-seal Inspection Form & Photograph
label | 4203b00e-35ad-5659-839d-b27e8f7c7fcb |  | note | Responsibility: Site Foreperson
checkpoint-group |  |  | section | 4.0 Post-Construction
checkpoint-status |  |  | checkpoint | Linemarking and RRPM Reinstated, Matches previous linemarking - within 48 hours of sealing
label | 90134ff9-0d93-5ecd-b1c3-57c59c9a8319 |  | note | H
label | 7abfea83-c67e-57b5-bc1f-e8fff36ade5f |  | note | Reference or Specification: MOTSAM
label | 326ebd8a-8fe2-578c-be67-29b0a9c48f69 |  | note | Method/Test required: Visual check
label | d2518b77-5afe-5558-9d8c-7a24224a9960 |  | note | How Often? Per site
label | 2b53f163-3d47-5886-b16b-2ecc6ba14eb9 |  | note | Records Required: Photograph
label | 71ccc7ee-cd09-5b6a-83a1-8affb76c3834 |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Spray Sheet/s Checked & Supplied for Claiming
label | 813ffe25-6e2e-59a0-9d4c-d97a15c893e1 |  | note | H
label | d63617ac-f290-56f8-a465-9b523500386f |  | note | Reference or Specification: QMP
label | eda2ee46-9aa2-57b4-b0f7-c0c724f65b66 |  | note | Method/Test required: Spray sheet data verified against design/programme
label | 7fbe72e3-335b-589d-99be-7c7bc56ddf11 |  | note | How Often? Per site
label | 5fb16359-f2db-596d-b9b3-08c8e7d4d3d2 |  | note | Records Required: Spray Sheet/s
label | 3a7b3b02-5424-5099-99b7-c2a8400d7b4f |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Collect & Upload RAMM data
label | 1f020d08-0af6-5b3b-9251-56ce2affc63f |  | note | H
label | 7e30c5b2-f08e-505c-9e73-47b2c4d60c10 |  | note | Reference or Specification: Comply with Waka Kotahi format
label | 8d1fbbbb-de5e-5428-a4da-4bd7da56294d |  | note | Method/Test required: Correct data supplied
label | a074fbdf-4e5f-55e9-90e1-c1c7e5011ec6 |  | note | How Often? Per site
label | 39828baa-c0c2-5a54-9ec8-a7a80cc1f837 |  | note | Records Required: Spray Sheet/s & Photographs
label | 0217f987-f95a-57d2-b64a-2f746a7003cb |  | note | Responsibility: Renewals Manager
checkpoint-group |  |  | section | 5.0 Out Of Season Sealing
checkpoint-status |  |  | checkpoint | Out of Season Sealing
label | de3d22b9-5604-555b-b5e1-1f4fa5f4a7fe |  | note | H
label | 0aa2ed7c-9522-5589-80db-497c815ee5c8 |  | note | Reference or Specification: Winter Surfacing Site Note
label | 01280e67-dfdb-5140-ab07-8b940d6ed9a4 |  | note | Method/Test required: Waka Kotahi Approval
label | d3314dc4-d643-5cdf-8e3a-c84ad9505c49 |  | note | How Often? Per Applicable Site
label | 8b20eb38-d27e-5114-87bd-34095e7bcbd9 |  | note | Records Required: Copy of Waka Kotahi Approval on-site
label | eda5b432-8e3b-5044-bdcb-6d30bcc86a36 |  | note | Responsibility: Project Manager / Renewals Manager
checklist-sectioned |  |  | checklist | ITP - In-Situ Modified Basecourse | itp |  |  |  | Yes | ITP - In-Situ Modified Basecourse | f6151ead-602b-4989-830d-718cc8efc8bf
checkpoint-group |  |  | section | 1.1. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING
checkpoint-status |  |  | checkpoint | 1.1.1 - M4 AP40 Basecourse Aggregates used for overlay
label | a2dce480-9fc2-5f81-a647-7035df52ce75 |  | note | Detail of Activity - Quality of Fines, either PI or SE or CI
label | b1b936d8-1ffa-5239-90cf-9edbfa8fb11a |  | note | Action (Hold, Monitor, Witness) - H / M*
label | a611944c-29c9-5862-8237-22d684668ee4 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m2
label | b92e18c3-bfc4-5f8a-972f-075b89ac07f0 |  | note | Inspection / Test method -
label | b627e5e9-432e-5b0e-8a66-75a380c0ba44 |  | note | • NZS4407:3.4 - PI
label | 8d9de190-81f1-5a3d-973f-9e562ebf68cd |  | note | • NZS4407:3.5 - CI
label | 5ab7ef0e-a437-51da-b637-3b102f25ab11 |  | note | • NZS4407:3.6 - SE
label | 336a3b4b-7a3e-51ad-9095-12987e2061f5 |  | note | Acceptance Criteria -
label | c105c36d-6bef-5ac4-8b32-fbc529a216fb |  | note | • PI ≤ 5
label | 456f1d41-93b8-5260-a909-6cee46e12af8 |  | note | • CI ≤ 3
label | 4b7474c5-571f-5506-a4cf-118fd5eaccca |  | note | • SE ≥ 40
label | 0380f230-eed8-500f-8548-de1ca544c7cc |  | note | Record documents - IANZ Report
label | ca9060b4-b7fe-5fae-abd2-e3aa4f4d5854 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.1.2 - M4 AP40 Basecourse Aggregates used for overlay
label | 30c05b99-4b8b-5f62-bee3-890ea3085193 |  | note | Detail of Activity - Broken Faces Content
label | 4cfbb4b0-4732-51fe-9702-7b3bf38eef76 |  | note | Action (Hold, Monitor, Witness) - H / M*
label | b4ea7313-fd75-59e4-8f24-4e54174989ff |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m2
label | 721fa480-76e0-5bbd-b84c-94bf6487b79b |  | note | Inspection / Test method - NZS4407:3.14
label | 122520c4-c665-5ffa-8471-a33eaf68f30d |  | note | Acceptance Criteria - ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm
label | d9e4a22c-f91f-580b-b2b4-a4782b7a2f00 |  | note | Record documents - IANZ Report
label | 7e871a27-14db-51f8-9a2d-44c694295483 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.1.3 - M4 AP40 Basecourse Aggregates used for overlay
label | 96b2f746-879c-559f-9a72-20ab24f3821a |  | note | Detail of Activity - Particle Size Distribution
label | ef867c97-d813-5009-b581-670916a3c37e |  | note | Action (Hold, Monitor, Witness) - H / M*
label | e08ccd9a-095c-5029-a586-1ca9197ed04f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m2
label | 6f2703b9-eda3-51eb-8ae4-3cc9b80c5d94 |  | note | Inspection / Test method - NZS4407:3.8.1
label | ea7ccabf-7ffd-55b1-8fb2-b1d3d87f16e2 |  | note | Acceptance Criteria - Check if 50:50 blend of average existing (from TPs) and NZTA M/4 AP40 will meet the FBS grading.
label | a2a34f58-c576-58e5-a3c6-a765769980d1 |  | note | Record documents - Report using IANZ Reports for AP40 and TP PSDs
label | 18168f8a-5179-5aaf-a98a-767ec4717366 |  | note | Responsibility - Contractor to provide analysis
label | 705daec5-d888-5fe2-99e2-6c0e484cabf4 |  | note | Comments - Designer to advise if "average" blend is acceptable.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.1.4 - Optimisation of Stabilizing Agent
label | 5c584f90-3651-58af-9a92-da1e13df942e |  | note | Detail of Activity - Indirect Tensile Strength, ITS
label | 5f63576b-7ecb-55fc-b5c5-20ff549ff5bf |  | note | Action (Hold, Monitor, Witness) - H
label | 5f0e6d9f-d8a8-51ff-bcdd-d23c71d9c5b2 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Optimisation test per aggregate type
label | a745b2c2-714d-526b-98ce-0563f1e37d2b |  | note | Inspection / Test method - NZTA T/19: 2020
label | 54aa0d61-7e86-5c2c-a9e8-79ecfaf27fe9 |  | note | Acceptance Criteria -
label | 57dc34a0-c95e-5e68-90b9-b6f3fb2ac624 |  | note | • Dry ITS: 175kPa to 400 kPa
label | 4dd4670d-1046-5ae9-a022-4a91d2495b6f |  | note | • Soaked ITS: 150 kPa to 350 kPa
label | 1c18c996-b206-58d9-9d51-4624dabf9ab4 |  | note | • TSR ≥ 70%
label | dd8c87a4-c24a-530e-99c1-a5e7a2275cad |  | note | Record documents - IANZ Report
label | 09fce5c0-1a16-5e09-b507-a7e4a0834487 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.1.5 - Optimisation of Stabilizing Agent
label | 06719d42-416d-535f-a042-e73a7a41762b |  | note | Detail of Activity - Modified Maximum Dry Density
label | 2fc9755f-3a62-5a2c-a2e0-f5850c1b36d0 |  | note | Action (Hold, Monitor, Witness) - M
label | 14fba29d-0217-51da-8916-4f56538d5c8f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - At Optimised Binder selection
label | 6ce74db4-3e26-5aad-ba1c-21277d50c0e3 |  | note | Inspection / Test method - NZS 4402.4.1.3
label | 6dc1c3f8-0499-539e-aaea-68dfbef62bd0 |  | note | Acceptance Criteria - To determine target density
label | ab0ba83c-58e3-5625-942b-5e5f5e914b82 |  | note | Record documents - IANZ Report
label | 054f356e-b4a6-5790-942d-fdb7d17ff9a9 |  | note | Responsibility - Contractor
label | ca7f389a-5702-5b14-89a6-22ecf56ee327 |  | note | Comments - Required before Stabilisation comences
checkpoint-group |  |  | section | 1.2. BEFORE STABILISATION COMMENCES
checkpoint-status |  |  | checkpoint | 1.2.1 - Setout section
label | 48df2f87-125b-54d4-aa5b-055fac7f3856 |  | note | Detail of Activity - Install offset pegs; record centreline, edge line or mark out stabilisation extents from existing line marking
label | 77b73f32-c2a8-50a2-b3f3-be3ecee5cf98 |  | note | Action (Hold, Monitor, Witness) - M
label | 3642130f-60a3-544d-b31c-39d3527014d1 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to each section
label | 64cb1343-1e05-5df2-9afe-f7412bec87df |  | note | Inspection / Test method - Survey
label | e22c0715-4a1c-5fc7-a533-c3034bc7bae9 |  | note | Acceptance Criteria - Document existing furniture
label | b44e78e9-8843-58f6-bbd8-707f6c56e6ca |  | note | Record documents - Electronic survey files
label | b6393981-0151-53d9-b7e4-5fcc22b7f0cf |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.2.2 - Production Plan
label | a4194e3b-1b3d-50f4-b0b5-6d0a1d0f4fa1 |  | note | Detail of Activity - Plan showing cut lines and sequencing of works
label | f3ce413a-e358-558b-a14c-b2bcea6124c2 |  | note | Action (Hold, Monitor, Witness) - M
label | a1d88b58-8e05-5c08-b8ad-a1a1b21d1d7f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to each section
label | fabe5781-97a1-5920-a47e-7c80c64c53af |  | note | Inspection / Test method - Daily Report
label | 2bc08a07-161d-5f11-a72c-6201a86839e9 |  | note | Acceptance Criteria - Points covered in NZTA B/5
label | cb2355e1-00ee-55d3-b7d9-afedbedbce49 |  | note | Record documents - Daily Production Plan
label | 21db8bd9-c63c-512b-b827-eb045b3a2c16 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.2.3 - Weather conditions
label | 561c942b-9ab8-557c-86e5-a118c3e5ba17 |  | note | Detail of Activity -
label | 7463dcb9-ea50-58f4-93df-58bf45bb961f |  | note | • Ambient Temperature (C&L)
label | e60c1c95-a320-5675-a03b-936f6cf20d0a |  | note | • Material to be stabilised (BE&FBS)
label | 817689e5-c071-51e6-b137-f1be44c93045 |  | note | Action (Hold, Monitor, Witness) - M
label | e8b612da-8069-5da8-a0fb-8f55a0f341a9 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to spreading
label | 5a72d0dc-e10e-5c18-958d-3e1a9deac4c6 |  | note | Inspection / Test method - Measurement
label | a3822d3c-cb7f-5fc7-be14-25d140ee7c51 |  | note | Acceptance Criteria -
label | 9643a77c-f6bc-5d71-bf8d-7d6a5b91d2de |  | note | • Ambient Temperatures:
label | 9e708a32-23aa-5ae2-9c64-7b1c432ad898 |  | note | ○ Cement: > 5°C, Lime: > 10°C
label | baa6f1ba-3ffe-5272-8bd0-ec420742d222 |  | note | • Material after stabilisation:
label | a47dbccd-1bf2-590f-9cdd-5ba34268bd24 |  | note | ○ BE: > 20°C, FB: > 20°C
label | 76402da8-1138-555f-9cc0-1bdd2691af91 |  | note | Record documents - Daily work Log
label | 6d5ea768-3733-51a9-a965-8db95766142b |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.2.4 - Weather conditions
label | cffb971b-494b-55cd-bb31-fc50b65015c8 |  | note | Detail of Activity - Wind
label | 66dededf-6020-5b15-bc99-e6f659f3929f |  | note | Action (Hold, Monitor, Witness) - M
label | 38ee105c-ec8c-579c-99c8-9bab70ee2c13 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to spreading cement or lime
label | 3a11ef21-0f8b-5282-904d-485d8834065c |  | note | Inspection / Test method - Local weather stations
label | 5560c7a8-880f-52a3-9362-764faf0a5f35 |  | note | Acceptance Criteria - Wind speed < 25 km/hr
label | 249a1c75-cb75-59e2-b5a2-d68caa62f22c |  | note | Record documents - Daily work Log
label | 0dab3150-d9fd-5c65-8ead-c3443727561e |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.2.5 - Weather conditions
label | 51a9fe19-2ecc-5e4c-a56b-caafebfb2c7b |  | note | Detail of Activity - Rain
label | 39e79eb7-4834-5b4a-b95c-2a2fcd1cccb8 |  | note | Action (Hold, Monitor, Witness) - M
label | 04be82fb-eb1b-5ebc-ad67-4db660862ca1 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to spreading cement or lime
label | 112e5c72-1f82-5550-9c52-0e617fa89529 |  | note | Inspection / Test method - Local weather stations
label | edc81fb5-59c4-5681-b617-97bb8c873b26 |  | note | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
label | 9f4d3dc4-a577-54d6-807c-cfbd4a98666f |  | note | Record documents - Daily work Log
label | 80b8b040-a330-5970-b4b8-06b3666f84b0 |  | note | Responsibility - Contractor
checkpoint-group |  |  | section | 1.3. STABILISATION OPERATION
checkpoint-status |  |  | checkpoint | 1.3.1 - Stabilizing Agent
label | e32ce9a3-1f0c-58c1-845c-c3049dd1cbd0 |  | note | Detail of Activity - Cement, GP
label | e2ed33d5-36bc-56bf-b5b2-0d9041562904 |  | note | Action (Hold, Monitor, Witness) - M
label | 97b6ab3b-9f31-5b0e-b93e-adbd662d86d1 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Batch
label | b9cfde23-9d30-55d8-adf3-c8b08e0f5454 |  | note | Inspection / Test method - NZS 3122
label | d8a09495-a3d5-5796-8486-75dd181ee458 |  | note | Acceptance Criteria - Conform to Specification
label | efcb2d09-141c-51c5-b540-88d7f5a89e2d |  | note | Record documents - Certificate in contractor's site folder
label | abf249b2-8a4c-524b-a377-cbf4fc4d4e73 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.2 - Spreading of powdered stabilising agent (Cement)
label | 41810956-5efc-5f56-a9ec-549d11cc307a |  | note | Detail of Activity - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
label | 0805d6a0-abf5-58b8-8869-060442e12486 |  | note | Action (Hold, Monitor, Witness) - M
label | 2612c101-8f81-5598-8e54-b42243c77a12 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) -
label | f0143ead-5902-5054-8201-f8d1249b4ed1 |  | note | • every 400 m2
label | 857534a9-180d-51d4-8843-d2e49bdd0a9c |  | note | • every 150m for a 2.4m width
label | 10620fdb-363b-5846-97ae-935b466eda5c |  | note | Inspection / Test method - Weigh mat or tray
label | 1be7ca24-1117-5b1c-b92f-5344ae03c30c |  | note | Acceptance Criteria - ± 5% of specified rate
label | 49c89af9-ba0e-5167-b137-a63bf37df815 |  | note | Record documents - Daily work Log
label | 3dd23918-904d-5c98-ab89-25a70dc32493 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.3 - Spreading of powdered stabilising agent (Cement)
label | cc40ebcb-2da6-5362-b63d-94f530b34db7 |  | note | Detail of Activity - Compare area spread with weight used for each spreader load
label | 16c0b6e3-3365-517b-b63c-63cd1b2e47db |  | note | Action (Hold, Monitor, Witness) - M
label | 506ad407-3553-5854-88d4-d4d1066a57ee |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On-going measurement by computer/load cells
label | 08662990-4d0c-5e9c-a79f-0d9d6cc58279 |  | note | Inspection / Test method - Measurement each run
label | 34235760-1e51-5cbc-acd7-cb8a19a54ba2 |  | note | Acceptance Criteria - ± 2.5% of specified rate
label | 1a7a43b7-d6eb-573d-9d14-c6d5e5d43dfd |  | note | Record documents - Daily work Log
label | fd62138e-8fcb-5f24-a213-38a77ca7010c |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.4 - Injection & Mixing of Water
label | 874b6ab0-ed1f-53f9-99a5-ddc3b637e86a |  | note | Detail of Activity - In-situ Stabilisation process
label | 60bf38d5-6332-5491-8371-a2cec2ca8cfe |  | note | Action (Hold, Monitor, Witness) - M
label | da2ab1ed-3c6c-56f8-bc23-6b329688b602 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On-going visual assessment
label | adb38fbd-3bf0-5f35-b95b-aa59105178ad |  | note | Inspection / Test method - Visual and hand squeeze test
label | 4ce253b7-f3b7-5b12-9ef8-66cfb8e73858 |  | note | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
label | f38a4fd7-32d8-5ac1-8bb6-df28196dd281 |  | note | Record documents - Daily work Log
label | 3cce5c47-43f2-558e-b9b4-b75114d6b2ad |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.5 - Depth of stabilisation
label | 8581e612-74be-55f6-9059-ee6f2f8a10f0 |  | note | Detail of Activity - Depth of stabilisation
label | be0fd1bc-8841-5cab-af57-272a1f1fb6ab |  | note | Action (Hold, Monitor, Witness) - M
label | 83150ae7-1e79-543b-afb8-ea81dd3c6f08 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Every 200m
label | 48bd0b0b-9134-5386-9ac9-0c3900585113 |  | note | Inspection / Test method - Measurement
label | b8aaec02-34f4-5959-93cf-2ef6834bb5a3 |  | note | Acceptance Criteria - +15mm / -5mm from specified depth
label | 94a2788d-cd33-56f0-aa0e-6f0f1b2f9987 |  | note | Record documents - Daily work Log
label | 21cbed20-8262-5554-8913-4680bb033bb8 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.6 - Compaction
label | 980b181b-44e4-57ff-8b27-b92728713461 |  | note | Detail of Activity - Plateau Density Test
label | 4518e202-cbf3-58a9-af15-bf674c31bf4e |  | note | Action (Hold, Monitor, Witness) - W
label | baea2266-8aa0-5ed8-b5fe-84c1fe6ae7f8 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On first day and then 1 per 20,000m2 unless material or anvil conditions change
label | a88ffce2-acd7-58aa-81ea-2285663be883 |  | note | Inspection / Test method - Draft NZTA T/24
label | dc09b32f-f374-5368-abcf-726035b694a4 |  | note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern
label | 9c28205d-bf1d-5ee6-b601-c9e6aab94956 |  | note | Record documents - Daily work Log
label | d6d4787c-5e91-5097-aed2-7054841d897c |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.7 - Compaction
label | 50060d01-811d-5dfe-b1a2-00e208af9c17 |  | note | Detail of Activity - Maximum Dry Density
label | 0c0e7c9f-f9cb-538d-94cb-d10016984fa1 |  | note | Action (Hold, Monitor, Witness) - M
label | a606678b-8c64-5e44-b489-d183bc6c861e |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per day up to 3,000 m2, 1 per 2,000m2 thereafter
label | 468533d6-04ce-5717-b01c-96dba78da558 |  | note | Inspection / Test method - NZS 4402.4.1.3
label | 4af5b0e6-19ad-50cf-a4f5-a944f50c74c8 |  | note | Acceptance Criteria - For analysis of DoC
label | 11d4ccf3-9106-5ba6-a996-5cfce6ebca64 |  | note | Record documents - IANZ Report
label | b940f415-dc62-5ac7-8211-7bfc2a1c6043 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 1.3.8 - Compaction
label | 9d9c62ed-4491-55b2-964d-b06f84dfd17f |  | note | Detail of Activity - Degree of Compaction
label | 11c14389-4778-5f30-840a-7457a0de7040 |  | note | Action (Hold, Monitor, Witness) - H
label | 315c2d9a-ca7d-5758-8c37-843f3693fdec |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 5 per 1,000m2
label | 73ebe6f8-cac6-5b33-b3b6-4820465920cf |  | note | Inspection / Test method - NZS 4407.4.2.1 (to 100mm and 200mm) and NZS 4407.4.2.2
label | 047a2c6a-1b23-50f3-a9dd-1da16af7ceae |  | note | Acceptance Criteria -
label | ebb52868-71fd-5fb6-b9fb-f8516ce00373 |  | note | • Average DoC ≥ 98%
label | afb070d1-1086-5870-9a69-a1723a0f04eb |  | note | • Minimum DoC ≥ 95%
label | 9a516064-83e0-5b6b-b4d9-4772af83156c |  | note | • Refer NZTA T/23
label | 48d86c87-5da4-582b-8b58-bfdd1ce7beae |  | note | Record documents - IANZ Report
label | ddaaafb4-d235-5d9c-8ba6-f79afee31f2f |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.9 - Finished Pavement
label | 56a284c1-8e6d-5cd6-9955-f114039879aa |  | note | Detail of Activity - Crossfall
label | 235c7cbb-bedd-5ec6-b7f9-8391a447772a |  | note | Action (Hold, Monitor, Witness) - H
label | 522c2b21-ec03-5769-8682-21ad8ebaa57f |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | dbdc2bc5-e5d6-5c9d-b025-bae54bd76bdd |  | note | Inspection / Test method - Measurement
label | da6cc842-49c1-5064-a700-c1a1d3840277 |  | note | Acceptance Criteria -
label | c4884b56-fa6d-560f-9507-3ea17777df41 |  | note | • ± 0.5% of specified crossfall measure
label | f012129a-43b4-5bd4-9ae0-ff1285380019 |  | note | • 2m apart
label | 545272e4-7d0b-5ce5-b89f-a57decf4a4d9 |  | note | Record documents - Survey
label | a432f296-3b92-5149-950d-f69169470258 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.10 - Finished Pavement
label | 334f8889-e3ce-58fb-be67-fd840a9408c4 |  | note | Detail of Activity - Stabilised width
label | d3279935-8a83-5e89-90c2-c22618b316b0 |  | note | Action (Hold, Monitor, Witness) - H
label | 54a491c4-c85d-5d38-b0d2-41d1a6dd3253 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 every 20m
label | 48228546-b795-5bf4-8644-392106b976ce |  | note | Inspection / Test method - Measurement
label | 9877cbe3-6284-546c-90b3-94b21cecbd88 |  | note | Acceptance Criteria - –20mm, +100mm
label | afa57648-26c4-5941-815f-095bb822f982 |  | note | Record documents - Survey
label | a4e1028f-ba92-50e2-a70e-91ff08a39b40 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.11 - Finished Pavement
label | b2d599d9-5b82-52db-9585-a8e16d964b18 |  | note | Detail of Activity - Surface Shape
label | b8e29005-9915-52f2-9b72-6a191833af68 |  | note | Action (Hold, Monitor, Witness) - H
label | 0508c047-2f68-5121-b3ab-ec545afd1147 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | 5826e44f-717e-5133-a181-f79b7eb67165 |  | note | Inspection / Test method - Measurement
label | a8ca189b-765a-5b43-ab30-ad74f9da80c7 |  | note | Acceptance Criteria - < 10mm using 3m straight edge
label | 4f4a0437-a0e6-54b6-9ae6-a3ab96a18e62 |  | note | Record documents - Survey
label | 16b89adf-56ef-513e-95c4-52bc77dc9cc2 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.12 - Finished Pavement
label | b28459b7-a0f2-5022-8285-4cf4bddd9cdf |  | note | Detail of Activity - Surface Levels
label | f0bb3710-aecf-5b8a-ba4c-c405c657fbed |  | note | Action (Hold, Monitor, Witness) - H
label | 8b9082b6-790a-54ae-8235-e01a31479c26 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | bc4415cb-672c-5ffd-ae8a-157ba32f65b9 |  | note | Inspection / Test method - Measurement
label | 7aeceb26-7c5b-5327-8923-40355fa416a4 |  | note | Acceptance Criteria - –5mm, +15mm
label | c804fd40-af20-54ea-a6e3-eb05eac81b38 |  | note | Record documents - Survey
label | a340ac45-c4a9-58ec-8e25-d0596df41562 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.13 - Finished Pavement
label | 0e048703-842d-5cdf-be5f-5db52d8233be |  | note | Detail of Activity - Surface Finish
label | 0b618eca-0e61-5b7c-9c73-0094f62b9f5b |  | note | Action (Hold, Monitor, Witness) - H
label | 44968a50-ca7a-5093-a365-d5cd7ca4ef56 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Lot
label | 0e5cf507-7554-5c2d-bd42-32f505555615 |  | note | Inspection / Test method - Visual
label | 656e4be0-7df2-5dfa-b922-a255291d3025 |  | note | Acceptance Criteria -
label | 444772b3-a495-5aca-8239-161c53de7744 |  | note | • 1. Larger aggregate held in pace with a matrix of smaller aggregate
label | dc6cc4eb-7743-5fc0-99e9-c77456b73fa9 |  | note | • 2. Smaller aggregate held in place by fine material
label | 976e78c7-4fe3-5443-8742-8069c04f2a12 |  | note | • 3. matrix does not displace under normal trafficking and/or sweeping
label | f0543d02-f72f-546c-9bfe-a3fd66723c99 |  | note | Record documents - Survey
label | fa8744fd-cb3c-5c51-b300-e0164e1a8c84 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3.14 - Finished Pavement
label | a0797932-ed0f-5ffb-a59e-eb7e62469af3 |  | note | Detail of Activity - Degree of Saturation, DOS
label | 49a52698-81f9-5437-9e32-fc7f0a7d7ad5 |  | note | Action (Hold, Monitor, Witness) - H
label | 19e86731-2b6b-58f9-a1d9-5d6595080a84 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 5 per Lot
label | beb2aede-97ca-5d76-935d-478e71015e83 |  | note | Inspection / Test method - Measurement
label | 98373453-69b3-5a60-98d3-cb02fb10be7c |  | note | Acceptance Criteria - DOS ≤ 80%
label | 8da331f6-0a81-5504-b3c3-47fda4d7335e |  | note | Record documents - IANZ report
label | 7de6eaf1-8f4a-5899-a893-08e8b652038f |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 1.4. FINAL SIGN OFF
checkpoint-status |  |  | checkpoint | 1.4.1 - Non-conforming results
label | 684936d1-497e-5aa5-b4f2-a667ea14fe5b |  | note | Detail of Activity - Assessment of all test results for conformity
label | 12f701ec-b3c8-5aed-92e0-bd04e179d9f1 |  | note | Action (Hold, Monitor, Witness) - H
label | 90d9ba5e-b42b-5de8-b9b2-425418e72d90 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each Lot
label | fa47a2af-2903-54da-9d3a-0280895fa87a |  | note | Inspection / Test method - Site Inspection
label | cd590e84-a3b5-5674-ac29-57d292ffaf45 |  | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | 3a3c92a8-c2bc-5ba4-b917-f7912c36a2d7 |  | note | Record documents - NCR
label | 8f5a4202-49a9-5c1b-8793-1b81119551fa |  | note | Responsibility - Engineer's Rep
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
text | 3d64bb44-2636-570f-a45a-8db7fe7624d8 |  | textbox | Contractor's Rep Name:
text | 8b3fa54a-c520-510b-8bc4-eab00d330abf |  | textbox | Engineer's Rep. Name:
holdpoint |  |  | signoff | Add Signature