## Earthworks (hidden)
Insert Client Logo here |  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP No: Project # - dd mm yyyy
|  |  |  | Project# and Name: Project # / Project Name |  |  |  |  | Date submitted: dd/mm/yyyy
|  |  |  | Construction Process: Earthworks |  |  |  |  | Prepared By: Design Engineer
Client: | Client | Contractor: Higgins |  | Specification: as referenced |  |  |  |  | Approved By: Project Manager
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) | Inspection / Test method |  |  |  |  | Engineer's Rep | Contractor | Date
1 | SETOUT AND PREPARATION
1.0.1 | Mark out and approve | Set out and mark up of treatment area | H | All earthworks areas | Visual Inspection | N/A | Contractor's site diary | Contractor | Treatment area marked up jointly by Contractor and Eng.Rep.
1.0.2 | Underground services | Identify and positively locate services | H | All earthworks areas | Hydoexcavation | N/A | Drawings | Contractor
1.0.3 | Determine Embankment / Subgrade Strength | Determine bearing strength of subgrade | H | 1 Scala per 20m | NZS 4402.6.5.2 | For design input | IANZ Report | Contractor | Scalas to be carried out to check consistency and determine inferred CBR before placing the subbase material and after placing, shaping and pre-compacting the subbase layer
1.1 | MATERIALS - LAYER
1.11 | Material properties | Bearing Strength | W | 1 Lot < 3,000 m3 | NZS 4402.6.1.1 | CBR ≥ insert value from project specs in here (if applicable) | Contractors site diary | Contractor
1.12 |  | MDD vs OMC | W | 1 Lot < 3,000 m3 | NZS 4402.4.1.1 | N/A | Contractor's site diary | Contractor
1.2 | CONSTRUCTION - LAYER
1.11 | Testing of placed materials | Strength of placed material | W | All earthworks areas 1 lot < 300m2 per 0.5m lift | NZS 4402.6.5.2 | Scala Penetrometer x blows / 100mm | Contractors site diary | Contractor
1.2.1 |  | Proof roll of placed material | W | All earthworks areas per lift | Visual Inspection | No significant visual deformation under the wheel load | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
1.2.2 |  | Density of placed material | W | All earthworks areas 1 lot < 300m2 per 0.5m lift | Nuclear Density Meter | Minimum field density of 92% of maximum dry density (MDD) obtained by standard compaction | Contractor's site diary | Contractor
1.3 | CLOSE OUT SUBBASE LOT
1.3.1 | Non-conforming results | Assessment of all test results for conformity | H | Each Lot | Site Inspection | Reporting of any non-conforming results to Designer via NCR | NCR | Engineer's Rep
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## UBG Subase (hidden)
Insert Client Logo here |  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP No: Project # - dd mm yyyy
|  |  |  | Project# and Name: Project # / Project Name |  |  |  |  | Date submitted: dd/mm/yyyy
|  |  |  | Construction Process: UNBOUND GRANULAR SUBBASE |  |  |  |  | Prepared By: Design Engineer
Client: | Client | Contractor: Higgins |  | Specification: as referenced |  |  |  |  | Approved By: Project Manager
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) | Inspection / Test method |  |  |  |  | Engineer's Rep | Contractor | Date
2 | SETOUT AND PREPARATION
2.0.1 | Mark out and approve | Set out and mark up of treatment area | H | All areas of unbound granular pavement layers | Visual Inspection | N/A | Contractor's site diary | Contractor | Treatment area marked up jointly by Contractor and Eng.Rep.
2.0.2 | Determine Embankment / Subgrade Strength (Pavement Widening) | Determine bearing strength of subgrade | H | 1 Scala per 70 m2 (typically 1 per 10m staggered between lanes) | NZS 4402: 6.5.2 | For design input | IANZ Report | Contractor | By IANZ accredited lab
2.0.3 | Determine subgrade / embankment fill levels | Check top of subgrade / fill levels | M | Every 20m | NZTA Z/16 | No Concrete Channel: -25mm + 5mm with Concrete Channel: -25mm + 5mm | Survey Diary or CAD | Surveyor / contractor
2.1 | MATERIALS - SUBBASE
2.1.1 | Unbound Granular Subbase | Particle Size Distribution (PSD) | M | 1 per source stockpile | NZS 4407: 3.8.1 | NZTA M03 and/or Project Spec. | IANZ Report | Contractor | Test certificate(s) from the loaded stockpile and not more than 3 months old
2.1.2 |  | Quality of Fines | M | 1 per source stockpile | PI - NZS 4407: 3.4 CI - NZS 4407: 3.5 SE - NZS4407: 3.6 | NZTA M03 and/or Project Spec. | IANZ Report | Contractor | Test certificate(s) from the loaded stockpile and not more than 3 months old
2.1.3 |  | Weathering Quality Index | M | 1 per source stockpile | NZS4407: 3.11 | NZTA M03 and/or Project Spec. | IANZ Report | Contractor | Test certificate(s) from the loaded stockpile and not more than 3 months old
2.1.4 |  | Target Density (MDD vs OMC) | M | 1 per source stockpile (1 Lot ≤ 500m3) | NZS4402: 4.1.3 | NZTA M03 and/or Project Spec. | IANZ Report | Contractor | Test certificate(s) from the loaded stockpile and not more than 3 months old
2.1.5 |  | California Bearing ratio (CBR) | M | 1 per source stockpile (1 Lot ≤ 500m3) | NZS 4402: 3.15 | NZTA M03 and/or Project Spec. | IANZ Report | Contractor | Test certificate(s) from the loaded stockpile and not more than 3 months old
2.2 | CONSTRUCTION - SUBBASE
2.2.1 | Unbound Granular Subbase | Check top of subbase levels | M | L, C, R every 20m | NZTA Z/16 | No Concrete Channel: -25mm + 5mm with Concrete Channel: -25mm + 5mm | Survey Diary or CAD | Surveyor / contractor
2.2.2 |  | Crossfall | M | Centre of lanes every 20m | NZTA Z/16 | Within 0.5% of specified crossfall | Survey Diary or CAD | Surveyor / contractor
2.2.3 |  | Degree of Compaction | H | 9 per Lot (1 Lot ≤ 1000m2) | NZS 4407: 4.2.1 | NZTA B02: DoC Mean ≥95%, Min. ≥ 92% | IANZ Report | Contractor | By IANZ accredited lab
2.2.4 |  | Benkelman Beam | H | L, C, R every 20m | NZTA T/1 | Refer Project Specifications | IANZ Report | Contractor
2.3 | CLOSE OUT SUBBASE LOT
2.3.1 | Non-conforming results | Assessment of all test results for conformity | H | Each Lot | Site Inspection | Reporting of any non-conforming results to Designer via NCR | NCR | Engineer's Rep
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## UBG Basecourse (hidden)
Insert Client Logo here |  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP No: Project # - dd mm yyyy
|  |  |  | Project# and Name: Project # / Project Name |  |  |  |  | Date submitted: dd/mm/yyyy
|  |  |  | Construction Process: UNBOUND GRANULAR BASECOURSE |  |  |  |  | Prepared By: Design Engineer
Client: | Client | Contractor: Higgins |  | Specification: as referenced |  |  |  |  | Approved By: Project Manager
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) | Inspection / Test method |  |  |  |  | Engineer's Rep | Contractor | Date
3 | SETOUT AND PREPARATION
3.0.1 | Mark out and approve | Set out and mark up of treatment area | H | All areas of unbound granular pavement layers | Visual Inspection | N/A | Contractor's site diary | Contractor | Treatment area marked up jointly by Contractor and Eng.Rep.
3.0.2 | Determine subbase levels | Check top of subbase levels | M | Every 20m | NZTA Z/16 | No Concrete Channel: -25mm + 5mm with Concrete Channel: -25mm + 5mm | Survey Diary or CAD | Surveyor / contractor
3.1 | MATERIALS - SUBBASE
3.1.1 | Unbound Granular Basecourse | Particle Size Distribution (PSD) | M | 1 per source stockpile | NZS 4407: 3.8.1 | NZTA M04 and/or Project Spec. | IANZ Report | Contractor | Test certificate(s) from the loaded stockpile and not more than 3 months old
3.1.2 |  | Quality of Fines | M | 1 per source stockpile | PI - NZS 4407: 3.4 CI - NZS 4407: 3.5 SE - NZS4407: 3.6 | NZTA M04 and/or Project Spec. | IANZ Report | Contractor | Test certificate(s) from the loaded stockpile and not more than 3 months old
3.1.3 |  | Weathering Quality Index | M | 1 per source stockpile | NZS4407: 3.11 | NZTA M04 and/or Project Spec. | IANZ Report | Contractor | Test certificate(s) from the loaded stockpile and not more than 3 months old
3.1.4 |  | Target Density (MDD vs OMC) | M | 1 per source stockpile (1 Lot ≤ 500m3) | NZS4402: 4.1.3 | NZTA M04 and/or Project Spec. | IANZ Report | Contractor | Test certificate(s) from the loaded stockpile and not more than 3 months old
3.1.5 |  | California Bearing ratio (CBR) | M | 1 per source stockpile (1 Lot ≤ 500m3) | NZS 4402: 3.15 | NZTA M04 and/or Project Spec. | IANZ Report | Contractor | Test certificate(s) from the loaded stockpile and not more than 3 months old
3.2 | CONSTRUCTION - SUBBASE
3.2.1 | Unbound Granular Basecourse | Check top of subbase levels | M | L, C, R every 20m | NZTA Z/16 | No Concrete Channel: -5mm + 15mm with Concrete Channel: - within 1m from channel: -5mm + 5mm - other locations: -5mm + 15mm | Survey Diary or CAD | Surveyor / contractor
3.2.2 |  | Crossfall | M | Centre of lanes every 20m | NZTA Z/16 | Within 0.5% of specified crossfall | Survey Diary or CAD | Surveyor / contractor
3.2.3 |  | Degree of Compaction | H | 9 per Lot (1 Lot ≤ 1000m2) | NZS 4407: 4.2.1 | NZTA B02: DoC Mean ≥98%, Min. ≥ 95% | IANZ Report | Contractor | By IANZ accredited lab
3.2.4 |  | Benkelman Beam | H | L, C, R every 20m | NZTA T/1 | Refer Project Specifications | IANZ Report | Contractor
3.3 | CLOSE OUT BASECOURSE LOT
3.3.1 | Non-conforming results | Assessment of all test results for conformity | H | Each Lot | Site Inspection | Reporting of any non-conforming results to Designer via NCR | NCR | Engineer's Rep
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## Stabilised Pavement Layer
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP No: Project GP0718 - dd mm yyyy
|  |  |  | Project# and Name: GP0718 - NOC AWPTs 2023-24 |  |  |  |  | Date submitted: dd/mm/yyyy
|  |  |  | Construction Process: Modified Granular Layer - Cement Stabilised Pavement |  |  |  |  | Prepared By: Design Engineer
Client: | NZTA | Contractor: Higgins |  | Specification: as referenced |  |  |  |  | Approved By: Kyle Goodman
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) | Inspection / Test method |  |  |  |  | Engineer's Rep | Contractor | Date
4 | SETOUT AND PREPARATION
4.0.1 | Mark out and approve | Set out and record existing line markling within the treatment area | H | All areas of unbound granular pavement layers | NZTA Z/16 | N/A | Contractor's site diary | Contractor | Treatment area marked up jointly by Contractor and Eng.Rep.
4.0.2 | Level Control | Install offset pegs; record centreline, edge line or mark out stabilisation extents from existing line marking | M | Prior to works | NZTA Z/16 | Document existing furniture | Site Diary | Contractor
4.0.3 | Determine levels of substrate before placing materials | Check top of substrate levels | M | Every 20m | NZTA Z/16 | Subgrade: checkNZTA F/1 and/or project specifications. Subbase: No Concrete Channel: -25mm + 5mm with Concrete Channel: -25mm + 5mm | Survey Diary or CAD | Surveyor / contractor
4.0.4 | Modification Agent(s) Optimisation | Stabilised material strength - ITS | H | 1 Optimisation test per aggregate type | NZTA T/19 | Check Project Specs. Modified materials should be: Dry ITS: 175kPa to 400 kPa Soaked ITS: 150 kPa to 350 kPa | IANZ Report | Client | Must be submitted to the pavement designer for approval at least 5 working days before modification works comence
4.1 | MATERIALS - SUBBASE / BASECOURSE (Delete what is not applicable)
4.1.1 | Check raw materials (whichever applicable) | Cement | M | Per Batch | NZ 3122 |  | Certificate in contractor's site folder | Contractor
4.1.2 |  | Lime | M | Per Batch | NZTA M/15 |  | Certificate in contractor's site folder | Contractor | Test certificates issued to the Engineers Rep at least 10 days prior to sealing
4.1.3 |  | Cement / Lime Supply and Storage Pods | M | Prior to commencement | Document Review | All test certificates with supply and storage pods | Certificate in contractor's site folder | Contractor
4.1.4 |  | Bitumen for Stabilisation (FBS or BE) | M | Per Batch | NZTA M/01 and visual foaming at test nozzle | Pen 80/100 Bitumen or Pen 180/200 (if approved) Bitumen able to achieve min 10x expansion and min. 6s half life | Certificate in contractor's site folder | Contractor
4.1.5 |  | Bitumen Supply and Storage Tanks | M | Prior to commencement | Document Review | All test certificates with supply and storage pods | Certificate in contractor's site folder | Contractor | Retain for testing if required
4.1.6 |  | Sub-base Aggregate | M | 1 per source stockpile | USE ITP LABELLED UBG SUBBASE | NZTA M03 / Project Spec | Certificate in contractor's site folder | Contractor | The surface finish, line and level is checked by Engineer's Rep. immediately prior to sealing
4.1.7 |  | Basecourse Aggregates | M | 1 per source stockpile | USE ITP LABELLED UBG BASECOURSE | NZTA M04 / Project Spec | Certificate in contractor's site folder | Contractor
4.2 | CONSTRUCTION - SUBBASE / BASECOURSE (Delete what is not applicable)
4.2.1 | Modified Subbase / Basecourse | Spreading of powdered stabilising agent | M | On-going measurement by computer/load cells | Measurement each run | ± 5% of specified rate | Worksheet | Contractor
4.2.2 |  | Mixing process | M | On-going visual assessment | Visual Inspection | Mixed material free of pockets or streaks. Overlaps and construction joints as per spec | ITP / Daily work Log | Contractor
4.2.3 |  | Bitumen Injection | M | On-going measurement by computer supplemented with tanker dips at the end of each run | Measurement each run | ± 5% of specified rate | Worksheet | Contractor
4.2.4 |  | Depth of stabilisation | M | 9 per Lot | Measurement | +15mm / -5mm from specified depth | Daily work Log | Contractor
4.2.5 |  | Modified Maximum Dry Density | M | 3 per Lot | NZS 4402.4.1.3 | For analysis of DoC | IANZ Report | Contractor | Basecourse only
4.2.6 |  | Degree of Compaction | H | 9 per Lot | NZS 4407.4.2.1 | NZTA B/5: Subbase DoC Mean ≥95%, Miin ≥ 92% Basecourse DOC Mean ≥98%, Min ≥ 95% | IANZ Report | Contractor
4.2.7 |  | Layer Width | H | every 20m | Measurement | ± 10 mm | Survey | Contractor
4.2.8 |  | Surface Shape | H | every 20m | Measurement | < 6mm using 3m straight edge | Worksheet | Contractor
4.2.9 |  | Surface Levels | H | every 20m | NZTA Z/16 | Subbase: No Concrete Channel: -25mm + 5mm with Concrete Channel: -25mm + 5mm Basecourse: No Concrete Channel: -5mm + 15mm with Concrete Channel: - within 1m from channel: -5mm + 5mm - other locations: -5mm + 15mm | Survey | Contractor
4.2.10 |  | Stabilised material strength - ITS | S | 3 soaked ITS + 3 dry ITS per Lot | NZTA T/19 | Modified: Dry ITS: 150kPa to 350 kPa Soaked ITS: 100 kPa to 300 kPa Bound Subbase: Dry ITS > 500 kPa Soaked ITS > 450 kPa | IANZ Report | Contractor
4.2.11 |  | Stabilised material strength - UCS | S | 3 per Lot | NPTG Guide | UCS < 0.75 MPa | IANZ Report | Contractor | If ITS testing is not available
4.3 | CLOSE OUT MODIFIED LAYER LOT
4.3.1 | Non-conforming results | Assessment of all test results for conformity | H | Each Lot | Site Inspection | Reporting of any non-conforming results to Designer via NCR | NCR | Engineer's Rep
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## Bitumen (hidden)
Insert Client Logo here |  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP No: Project # - dd mm yyyy
|  |  |  | Project# and Name: Project # / Project Name |  |  |  |  | Date submitted: dd/mm/yyyy
|  |  |  | Construction Process: Bitumen Manufacture |  |  |  |  | Prepared By: Design Engineer
Client: | Client | Contractor: Higgins |  | Specification: as referenced |  |  |  |  | Approved By: Project Manager
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 200,000L or per bitumen grade used on project, whichever is the greater - RNZ 9803) | Inspection / Test method |  |  |  |  | Engineer's Rep | Contractor | Date
5 | BITUMEN MANUFACTURE (per Grade)
5.0.1 | Penetration | Penetration at 25°C, 100g, five seconds | M | 1 per Lot | ASTM D5 | NZTA M01 - Table 1 | IANZ Report | Contractor | Sampling as per ASTM D140 or equivalent
5.0.2 | Viscosity | Viscosity, PaS at 60°C | M | 1 per Lot | AS 2341.2 or ASTM D2171 | NZTA M01 - Table 1 (if not met then check at 70°C and Table 2) | IANZ Report | Contractor | Sampling as per ASTM D140 or equivalent
5.0.3 |  | Viscosity, mm2/s, at 70°C | M | 1 per Lot | AS 2341.2 or ASTM D2172 | NZTA M01 - Table 2 | IANZ Report | Contractor | Sampling as per ASTM D140 or equivalent
5.0.4 |  | Viscosity, mm2/s, at 135°C | M | 1 per Lot | AS 2341.3 or ASTM D2170 | NZTA M01 - Table 1 | IANZ Report | Contractor | Sampling as per ASTM D140 or equivalent
5.0.5 | Flash Point | Flash Point (Cleveland open cup), °C | M | 1 per Lot | ASTM D92 | NZTA M01 - Table 1 | IANZ Report | Contractor | Sampling as per ASTM D140 or equivalent
5.0.6 | Solubility | Solubility in Trichloroethylene, % or Solubility in Toluene, % | M | 1 per Lot | ASTM D2042 AS 2341.8 | NZTA M01 - Table 1 | IANZ Report | Contractor | Sampling as per ASTM D140 or equivalent
5.0.7 | Penetration | Penetration of RTFOT residue at 25°C, 100g, five seconds | M | 1 per Lot | ASTM D2872 or AS 2341.10 / ASTM D5 | NZTA M01 - Table 1 | IANZ Report | Contractor | Sampling as per ASTM D140 or equivalent
5.0.8 | Ductility | % of original Ductility of RTFOT residue at 25°C, (metres) | M | 1 per Lot | ASTM D2872 or AS 2341.10 / ASTM D113 | NZTA M01 - Table 1 | IANZ Report | Contractor | Sampling as per ASTM D140 or equivalent
5.0.9 | Durability | Durability Test value max (Mpa) at 5°C and 9 Hz. | M | 1 per Lot | TNZ T/13 | NZTA M01 - Table 5 | IANZ Report | Contractor | Sampling as per ASTM D140 or equivalent
5.1 | CLOSE OUT SEALING LOT
5.1.1 | Non-conforming results | Assessment of all test results for conformity | H | Each Lot | Site Inspection | Reporting of any non-conforming results to Designer via NCR | NCR | Engineer's Rep
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## Seal Coat
Insert Client Logo here |  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP No: Project # - dd mm yyyy
|  |  |  | Project# and Name: Project # / Project Name |  |  |  |  | Date submitted: dd/mm/yyyy
|  |  |  | Construction Process: Bituminous Seal Coat |  |  |  |  | Prepared By: Design Engineer
Client: | Client | Contractor: Higgins |  | Specification: as referenced |  |  |  |  | Approved By: Project Manager
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) | Inspection / Test method |  |  |  |  | Engineer's Rep | Contractor | Date
6 | SETOUT AND PREPARATION
6.0.1 | Seal Design | Seal design outlining all design assumptions | H | 1 per seal application type | Project Specification | New Zealand Chip Sealing Handbook | Seal design in contractor's site folder | Designer / Engineer's Rep
6.0.2 | Bitumen Distributer Certification | E2 | M | 1 per annum | CCNZ E2 | Must be operated as per CCNZ E/2 | Record Distributor # | Contractor | Certified Distributor is on the CCNZ website
6.0.3 | Pre-Seal requirements | Visual inspection of surface to be sealed | W | per sealing schedule. 1 Lot = 1 day's production and < 1500m2 | Visual Inspection | NZTA B/2, B/5, B/6, B/7, B/8 or M/10 (whichever is applcable) | Contractor's site diary | Engineers Rep | The surface finish, line and level is checked by Engineer's Rep. immediately prior to sealing
6.0.4 |  | Dry back Moisture Content (if 1st coat) | H | 9 per Lot | NZS 4407.4.2.1 | DOS ≤ 80% preferably ≤ 70% | IANZ Report | Contractor | Only required if pavement widening extends into trafficked lane
6.0.5 |  | Clegg Hammer (if 1st coat) | M | 1 CIV per 10m 1 Lot < 300m | Clegg Impact Value Test | Average CIV > 40 Min. CIV > 35 | Contractor's CIV form appended to Contractor's daily diary | Contractor
6.1 | MATERIALS - PRIOR TO CONSTRUCTION PHASE
6.1.1 | Source Properties (All aggregate) | Crushing Resistance | M | RNZ 9805:2009 | NZS4407: 3.10 | < 10% under load of 230kN | IANZ Report | Contractor | Test certificates issued to the Engineers Rep at least 10 days prior to sealing
6.1.2 |  | Weathering Resistance | M | RNZ 9805:2010 | NZS 4407: 3.11 | AA or BA | IANZ Report | Contractor | Test certificates issued to the Engineers Rep at least 10 days prior to sealing
6.1.3 |  | Weak Particle Test | M | RNZ 9805:2011 | AS 1141.32 - 1995 | Max of 1% of unsound material | IANZ Report | Contractor | Test certificates issued to the Engineers Rep at least 10 days prior to sealing
6.1.4 |  | Polished Stone Value (PSV) | M | 1 per year | BS EN 1097-8:2009 | Lower value of 2 tests (or median value if more than 3 tets are available) ≥ NZTA T/10 and/or project specifications. 2 tests must be < 2 years old | IANZ Report | Contractor | Test certificates issued to the Engineers Rep at least 10 days prior to sealing
6.1.5 | Production Properties Grades 2, 3 and 4 | Cleanness | M | RNZ 9805:2011 | NZS 4407: 3.9 | Gr.2 ≥ 89; Gr.3 ≥ 87; Gr.4 ≥ 85 | IANZ Report | Contractor | Test certificates issued to the Engineers Rep at least 10 days prior to sealing
6.1.6 |  | Size and Shape | M | RNZ 9805:2011 | NZS 4407: 3.13 | NZTA M/6 - Table 2 | IANZ Report | Contractor | Test certificates issued to the Engineers Rep at least 10 days prior to sealing
6.1.7 |  | Broken Faces | M | RNZ 9805:2011 | NZS 4407: 3.14 | ≥ 98% with at least two broken faces | IANZ Report | Contractor | Test certificates issued to the Engineers Rep at least 10 days prior to sealing
6.1.8 | Production Properties Grades 5 & 6 | General Soundness | M | RNZ 9805:2011 | Visual | Clean, tough particles, free of soft, weathered, disintegrtaed or deleterious material. | IANZ Report | Contractor | Test certificates issued to the Engineers Rep at least 10 days prior to sealing
6.1.9 |  | Grading | M | RNZ 9805:2011 | NZS 4407: 3.8 | NZTA M/6 - Table 3 | IANZ Report | Contractor | Test certificates issued to the Engineers Rep at least 10 days prior to sealing
6.1.10 | Bitumen Properties | As per ITP 5 (previous Tab) | M | refer to ITP 5 | Various | Various | Various | Contractor | Test certificates issued to the Engineers Rep at least 10 days prior to sealing
6.2 | CONSTRUCTION
6.2.1 | Bitumen Sample | Audit sample(s) | M | 1 per sprayer | ASTM D140 or AS2008 | N/A | Contractor's site diary | Contractor | Retain for duration of DLP
6.2.2 | Adhesion Agents | Adhesion Agents | M | Prior to use |  | NZTA M/13 | Certificate in contractor's site folder | Contractor | Test certificates issued to the Engineers Rep at least 10 days prior to sealing
6.2.3 | Aggregates | Audit samples | M | 20 kg per stockpile | N/A | Stored in a sealed plastic bag in a covered environment | Contractor's site diary | Contractor | Retain for duration of DLP
6.3 | CONSTRUCTION - 1st Coat as per TNZ P/3
6.3.1 | Bitumen application | Bitumen Spraying Temperature | M | Ongoing with non-going heat sensing gauge | Non-contact heat sensing gun | NZTA P/3 - Table 2 | Contractor's Spray sheet | Contractor
6.3.2 |  | Bitumen Application rate (BAR) | M | Every sprayer run | Dip sprayer | TNZ P/3 | Contractor's Spray sheet | Contractor
6.3.3 | Sealing Aggregate application | Application rate (m2/kg) | M | Continous | Calculation | Refer TNZ P/3 - section 28 | Contractor's site diary | Contractor
6.4 | CLOSE OUT SEALING LOT
6.4.1 | Non-conforming results | Assessment of all test results for conformity | H | Each Lot | Site Inspection | Reporting of any non-conforming results to Designer via NCR | NCR | Engineer's Rep
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## AC Mix Design (hidden)
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP No: Project # - dd mm yyyy
|  |  |  | Project# and Name: Project # / Project Name |  |  |  |  | Date submitted: dd/mm/yyyy
|  |  |  | Construction Process: Asphalt Mix Design |  |  |  |  | Prepared By: Design Engineer
Client: | Client | Contractor: Higgins |  | Specification: as referenced |  |  |  |  | Approved By: Project Manager
Spec. section | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) | Inspection / Test method |  |  |  |  | Engineer's Rep | Contractor | Date
7 | ASPHALT CONSTITUENTS
7.0.1 | Course Aggregates | Crushing resistance | M | 1 per source stockpile | NZS 4407 Test 3.10 | ≥ 200kN [NZTA M/10] | IANZ accredited test cert | Contractor
7.0.2 |  | Weathering Quality Index | M | 1 per source stockpile | NZS 4407 Test 3.11 | AA or BA [NZTA M/10] | IANZ accredited test cert | Contractor
7.0.3 |  | Single Broken Faces | M | 1 per source stockpile | NZS 4407 Test 3.14 | ≥ 98% [NZTA M/10] | IANZ accredited test cert | Contractor
7.0.4 |  | Two Broken Faces | M | 1 per source stockpile | NZS 4407 Test 3.14 | ≥ 60% [NZTA M/10] | IANZ accredited test cert | Contractor
7.0.5 |  | Polished Stone Value (AC14 surfacing only) | M | 1 per source stockpile | BS EN 1097 Part 8 | As per specific contract requirements | IANZ accredited test cert | Contractor
7.0.6 |  | Los Angeles Abrasion Loss | M | 1 per source stockpile | NZS 4407 Test 3.12 | Report Value | IANZ accredited test cert | Contractor
7.0.7 |  | Wet/Dry Strength variation | M | 1 per source stockpile | AS 2558 Part 5 | Report Value | IANZ accredited test cert | Contractor
7.0.8 |  | Water Absorbtion | M | 1 per source stockpile | AS 1141 or ASTM C127 | Report Value | IANZ accredited test cert | Contractor
7.0.9 | Fine Aggregates | Crushing resistance | M | 1 per source stockpile | NZS 4407 Test 3.10 | ≥ 200kN [NZTA M/10] | IANZ accredited test cert | Contractor
7.0.10 |  | Sand Equivalent | M | 1 per source stockpile | NZS 4407 Test 3.6 | ≥ 35 [NZTA M/10] | IANZ accredited test cert | Contractor
7.0.11 |  | Clay Index | M | 1 per source stockpile | NZS 4407 Test 3.5 | ≤ 3 [NZTA M/10] | IANZ accredited test cert | Contractor
7.0.12 |  | Water Absorbtion | M | 1 per source stockpile | AS 1141 or ASTM C127 | Report Value | IANZ accredited test cert | Contractor
7.0.13 |  | Degradation factor | M | 1 per source stockpile | AS 1141.25.3 | Report Value | IANZ accredited test cert | Contractor
7.0.14 | Mineral Filler | Particle Size Distribution | M | 1 per source stockpile | NZS 4407 | Table 2.4 NZTA M/10 | IANZ accredited test cert | Contractor
7.0.15 | Binder | Flash point | M | 1 per batch of bitumen | AASHTO T48 or ASTM D92 | ≥ 230 ⁰C [NZTA M1-A] | IANZ accredited test cert | Contractor
7.0.16 |  | Viscosity at 135 ⁰C | M | 1 per batch of bitumen | AASHTO T316 or ASTM D4402 | ≤ 3 Pa.s [NZTA M1-A] | IANZ accredited test cert | Contractor
7.0.17 |  | G*/sinδ at 64⁰C @ 10 rad/s | M | 1 per batch of bitumen | AASHTO T315 or ASTM D7175 | ≥ 1.00 kPa [NZTA M1-A] | IANZ accredited test cert | Contractor
7.0.18 |  | RTFOF residue: Mass change (+ve and -ve) | M | 1 per batch of bitumen | AASHTO T240 or ASTM D2872 | ≤ 1.00% [NZTA M1-A] | IANZ accredited test cert | Contractor
7.0.19 |  | Jnr3.2 at 64⁰C | M | 1 per batch of bitumen | AASHTO T350 | ≤ 4.5 kPa (S); ≤ 2.0 kPa (H); ≤ 1.0 kPa (V) ≤ 0.5 kPa (E) [NZTA M1-A] | IANZ accredited test cert | Contractor | Glasnevin use H category
7.0.20 |  | Jnr3.2 at 64⁰C | M | 1 per batch of bitumen | AASHTO T350 | Report Value | IANZ accredited test cert | Contractor
7.0.21 |  | PAV residue (aging temp of 100⁰C) G*/sinδ at 28⁰C @ 10 rad/s | M | 1 per batch of bitumen | AASHTO T315 or ASTM D7175 | ≤ 5000 kPa (S); ≤ 6000 kPa (H, V, E) [NZTA m1-A] | IANZ accredited test cert | Contractor | Glasnevin use H category
7.0.22 |  | S at -6⁰C @ 60s | M | 1 per batch of bitumen | AASHTO T313 or ASTM D6648 | ≤ 6000 kPa [NZTA M1-A] | IANZ accredited test cert | Contractor
7.0.23 |  | m-value at -6⁰C @ 60s | M | 1 per batch of bitumen | AASHTO T313 or ASTM D6648 | ≥ 0.300 [NZTA 1-A] | IANZ accredited test cert | Contractor
7.0.24 |  | Failure strain at -6⁰C @ 1.0 mm/min | M | 1 per batch of bitumen | AASHTO T314 or ASTM D6723 | ≥ 1.0% [NZTA m1-A] | IANZ accredited test cert | Contractor
7.1 | ASPHALT MIX DESIGN
7.1.1 | Asphalt mix | Mix design report and JMF | H | 1 per site location | Review | NZTA M/10 | Mix Design report | Contractor | Mix Design report including all testing outlined in this ITP and table 3.10 [NZTA M/10] to be issued to the Engineers Rep at least 7 days prior to paving
7.1.2 |  | Aggregate Particle Size Distribution | H | 1 per site location | NZS 4407 Test 3.8.1 | Table 3.1 NZTA M/10 | IANZ accredited test cert | Contractor
7.1.3 |  | Binder Content | H | 1 per site location |  | Table 3.1 NZTA M/10 | IANZ accredited test cert | Contractor
7.1.4 |  | Target Design Air Voids | H | 1 per site location | Gyratory Servopac or | Table 3.4 [NZTA M/10) Light = 4% Voids 40 cycles Medium, Heavy = 4% Voids 80/120 cycles V.Heavy = 5% Voids 120 cycles | IANZ accredited test cert | Contractor
7.1.5 |  | Target Design Air Voids | H | 1 per site location | Marshall | Table 3.5 [NZTA M/10) | IANZ accredited test cert | Contractor
7.1.6 |  | VMA for DGA mixes | H |  |  | Table 3.6 [NZTA M/10] | IANZ accredited test cert | Contractor
7.1.7 |  | TSR - Tensile Strength Ratio (only for DGA mizes) | H |  |  | ≥ 75% [NZTA M/10] | IANZ accredited test cert | Contractor
7.1.8 |  | Wheel Tracking (only for H and V.H DGA mixes) | H |  | AS2891.2.1; AS 2891.9.2;AG:PT/T220; AG:PT/T231 | ≤ 6.0mm [NZTA M/10] | IANZ accredited test cert | Contractor
7.2 | ASPHALT MIX DESIGN ACCEPTANCE
7.2.1 | Aspahlt Mix Acceptance | Assessment of all test results for conformity | H | For each mix used on the project | Review | Reporting of any non-conforming results to Designer via NCR | NCR | Engineer's Rep
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## AC Placement (hidden)
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP No: Project # - dd mm yyyy
|  |  |  | Project# and Name: Project # / Project Name |  |  |  |  | Date submitted: dd/mm/yyyy
|  |  |  | Construction Process: Asphalt layer(s) |  |  |  |  | Prepared By: Design Engineer
Client: | Client | Contractor: Higgins |  | Specification: as referenced |  |  |  |  | Approved By: Project Manager
Spec. section | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) | Inspection / Test method |  |  |  |  | Engineer's Rep | Contractor | Date
8 | PRE-PAVING INSPECTION
8.0.1 | Pre-paving inspection | Visual inspection of surface to be sealed | W | per paving schedule. 1 Lot = 1 day's production and < 1500m2 | Visual Inspection | If surface is sealed or asphalt then surface must be clean and free of any dust. If surface is unsealed then the surface must be tight (checked by Clegg Hammer) and have a stone mosaic finish for the tack coat and asphalt to stick to. | Contractor's site diary | Engineer's Rep. | The surface finish, line and level is checked by Engineer's Rep. immediately prior to sealing / paving
8.0.2 |  | Dry back Moisture Content | H | 9 per Lot | NZS 4407.4.2.1 | DOS ≤ 80% preferably ≤ 70% | Test Results | Contractor | Only required if substate is a granular or stabilised layer
8.0.3 |  | Clegg Hammer | M | 1 CIV per 10m 1 Lot < 300m | Clegg Impact Value Test | Average CIV > 50 Min. CIV > 40 | Contractor's CIV form appended to Contractor's daily diary | Contractor | Only required if substate is a granular or stabilised layer
8.1 | ASPHALT MIX PRODUCTION
8.1.1 | Manufactured mix | Particle Size Distribution | M | 1 per 200 t at asphalt plant | NZS 4407: 3.8.1 | NZTA M/10 - Table 3.1, 3.2 or 3.3 | IANZ accredited test cert | Contractor
8.1.2 |  | Binder Content | M | 1 per 200 t at asphalt plant |  | NZTA M/10 - Table 3.1, 3.2 or 3.3 | IANZ accredited test cert | Contractor
8.1.3 |  | Max. Specific Gravity | M | 1 per 200 t at asphalt plant | NZS 4407:3.7 |  | IANZ accredited test cert | Contractor
8.1.4 |  | Mix discharge temperature | M | 1 per 200 t at asphalt plant | Infra Red temperature sensor |  | Site Shift Diary | Contractor
8.1.5 |  | Mix Storage time | M | 1 per 200 t at asphalt plant | Watch | As per contractor's Quality Plan | Site Shift Diary | Contractor
8.1.6 |  | Broken Faces (blend fraction coarser than 4.75mm) | M | 1 per 200 t at asphalt plant | NZS4407:3.14 | Table 3.1 NZTA M/10 | IANZ accredited test cert | Contractor
8.1.7 |  | Sand Equivalent (blend fraction passing 4.75mm) | M | 1 per 200 t at asphalt plant | NZS4407:3.6 |  | IANZ accredited test cert | Contractor
8.1.8 |  | Clay Index (blend fraction passing 75 µm) | M | 1 per 200 t at asphalt plant | NZS4407:3.5 |  | IANZ accredited test cert | Contractor
8.1.9 |  | Size and Shape | M | 1 per 200 t at asphalt plant | NZS4407:3.13 |  | IANZ accredited test cert | Contractor
8.2 | PLACING AND COMPACTION
8.2.1 | Tack Coat | Tack Coat / Membrane Seal | M | 1 per Lot | Tanker dip vs area sprayed | Between 0.10 L/m2 and 0.20 L/m2 | Spray sheets | Contractor
8.2.2 | Membrane Seal (if applicable) | Membrane Seal | M | 1 per Lot | Tanker dip vs area sprayed | ≥ 1.0 L/m2 | Spray sheets | Contractor
8.2.3 | Placing | Ambient Air temperature | M | 1 per delivery truck | Thermometer | Record | Site shift diary | Contractor
8.2.4 |  | Placing temperature | M | 1 per delivery truck | Infra Red temperature sensor | Within 15 deg.C of the JMF or the project specification | Site shift diary | Contractor
8.2.5 | Compaction | Mat density | M | 8 per Lot, where a Lot = Total Area / 300 | Cores | NZTA M/10, section 9.8 | IANZ accredited test cert | Contractor
8.2.6 | Compaction | Joint density | M | 1 per 100m of joint with minimum of 3 per Lot, where a Lot = Total Area / 300. | Cores | NZTA M/10, section 9.8 | IANZ accredited test cert | Contractor
8.2.7 | Level |  |  | top of each layer | Survey | max. 10mm above design levels | Site shift diary | Contractor
8.2.8 | Alignment |  |  | top of each layer | Survey | ±50mm from the corresponding point shown on the drawinsg | Survey report | Contractor
8.2.9 | Thickness |  |  | each layer | Cores | Non-Structural layer: Average thickness ≥ specified thickness Structural layer: Average thickness ≥ 90% of specified thickness | IANZ accredited test cert | Contractor
8.2.10 | Ride Quality |  |  | refer contract specifications | IRI | refer contract specifications | IANZ accredited test cert | Contractor
8.3 | ASPHALT PLACEMENT ACCEPTANCE
8.3.1 | Aspahlt Placement Acceptance | Assessment of all test results for conformity | H | For each mix used on the project | Review | Reporting of any non-conforming results to Designer via NCR | NCR | Engineer's Rep
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## Precast or Cast Insitu (hidden)
|  |  |  | Inspection Test Plan |  | Specification: TS Section 507 | Approved |  | Signature
|  |  |  | Contract Name: | NOC AWPTs 2023-24 |  | FCI Engineer
|  |  |  | Procedure: | Box Culvert (Subway) - Precast or Cast Insitu |  | FCI Quality Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Method Statement: |  | (insert contract suffix here) xxxx |  | Compliance with Method Statements and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method | Conformance Criteria | Records | FCC Initials | Design Engineer Initials (Grey if not required) | Date(s)
submission, visual inspection, testing, measure, review
1 | Permits | H | Obtain Permits | As required | Document Review | Permit to Work, PTW # Digging Checklist (incl. marking out & potholing existing services), PTW # Fall Prevention, Notify Worksafe NZ if required. Permit to Work around services (Gas, Power etc) if required. | Permit attached or permit number noted | Site Engineer
2 | Pre-construction sign offs | H | Ensure that Sub-Contract and Supplier Agreements are signed |  | Document Review |  | Subcontract and Supplier Agreements on Aconex | Site Engineer
|  | H | Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS |  | Document Review |  | TMP on Aconex | Site Engineer
|  | H | Ensure all Sub-Contractors and suppliers go through (insert project name) induction |  | Induction | Issued induction stickers and number | JSEA and Pre-starts to safety team | Site Engineer
3 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer | Design Engineer
4 | Installation of Erosion and Sediment Controls | H | Ensure that Erosion & Sediment Control ITP & Checksheets have been completed and submitted to the Territorial Authority | Prior to commencement | Document Review | Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence | FCI-QMC-TMP-000014 | Environmental Manager/Site Engineer
|  | M | Monitor effectiveness of the ESCP Controls throughout the construction process |  | Visual Inspection |  | Project ESCP | Site Engineer
5 | Survey Setout | H |  | Prior to commencement | Survey | Consistency with Construction Drawing | Survey reciept | Site Engineer
|  | H | Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations) | Prior to commencement | Survey | Consistency with Construction Drawing | Survey receipt | Site Engineer
6 | Material Compliance | H | Concrete mix design(s) shall be submitted to the Design Engineer in writing at least 2 wks prior to placing concrete and approved before placing concrete | Prior to commencement | Document review |  | Design Engineer Approval | Site Engineer | Design Engineer
|  | H | All concrete delivered to site shall be produced strictly in accordance with the approved mix design | Prior to pouring concrete | Concrete Delivery Dockets |  | Concrete Delivery Dockets | Site Engineer
|  | H | Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade called up on the drawings | Prior to ordering steel | Document review | AS/NZS4671&NZS3109 | Detail Sheets and Mill Certificates | Site Engineer
|  | H | Permit to Work, PTW # Digging Checklist (incl. marking out & potholing existing services), PTW # Fall Prevention, Notify Worksafe NZ if required. Permit to Work around services (Gas, Power etc) if required. | Prior to welding or splicing | Document review |  | Mark Up As Built Drawings | Site Engineer
|  | H | Any reinforcement requiring cutting or bending on site to be approved in writing by the Design Engineer | Prior to cutting or bending on site | Document review |  | Mark Up As Built Drawings | Site Engineer
7 | Foundation Acceptance by Engineer's Rep | H | Approval given by engineer's Rep and Signed off Subgrade Approval Checksheet | Prior to commencement | Inspection by Engineer | Inspection and Acceptance of Structure Foundations | Project checksheet | Site Engineer | Design Engineer
8 | Concrete Pumping Operations | W | Ensure the Permit to Concrete Pump & Pump Operator Checksheet has been completed before concrete pumping commences | Prior to commencement | Document review |  | Project checksheets | Site Engineer
9 | Blinding Concrete | H | Once blinding concrete layer has been completed the Engineer's Rep to inspect and give approval for the rest of the works to commence | Prior to commencement | Inspection by Engineer |  | Sign off this document | Site Engineer | Design Engineer
10 | Cast Insitu Box Culvert | H | If the Box Culvert is Cast Insitu Construction then follow the Insitu Concrete ITP for every Pour that is carried out | Prior to commencement | Inspection by Engineer | QA-6006 - Insitu Concrete Work Instruction, ITP & Checksheets | FCI-QMC-TMP-000020 | Site Engineer | Design Engineer
11 | Precast Panel Box Culvert | H | If the Box Culvert has Precast Panels that are to be erected the follow the 2 x Precast ITP's one for the Precast Panel Construction & Precast Panel Installation | Prior to commencement | Inspection by Engineer | FCI-QMC-0049- Precast Concrete Work Instruction & ITP & FCI-QMC-00XX - Precast Installation Work Instruction & ITP (documents to be developed) | FCI-QMC-TMP-0049 & xxxx | Site Engineer | Design Engineer
12 | Subsoil Drainage | H | If the Box Culvert has a Subsoil Drainage system around it then follow the Subsoil Drainage ITP | Prior to commencement | Inspection by Engineer | FCI-QMC-TMP-0048 - Subsoil Drainage Work Instruction, ITP & Checksheets | FCI-QMC-TMP-0048 | Site Engineer | Design Engineer
13 | Backfill Fill Material Compliance Testing | H | Material to meet specifications dependant on material type selected | Each material used | Document Review | Compliance with requirements noted on bulk fill checksheet | Project checksheet | Site Engineer
|  | H | Fill Construction Material | 1 test per XXXm3 | Lab Testing |  | Lab Test Report | Site Engineer
14 | Filling Operation | W | Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately | Daily | Visual inspection |  |  | Site Engineer
|  | W | Fill placed within 1m the structures shall be placed with care using suitable equipment and shall be placed 100mm thick and shall be 1 lift higher than the level of the surrounding fill | During fill operations next to structures or obstructions | Visual inspection |  | Project checksheet | Site Engineer
15 | Filling Testing Requirements | W | Fill placed in horizontal layers no greater than 250mm and compacted. Site Engineer to instruct lab when and where to carry out testing | 1 test per XXXm3 | Visual inspection and Lab Testing |  | Project checksheet | Site Engineer
16 | Confirm testing requirements met | H | Ensure correct no. of test sets performed for fill testing | At completion of Lot | Document Review | A) No. of days worked:_______ B) No. of 500mm lifts:_________ C) How many 1000m3 fill: ______ Require greater of A or B, and not less than C. | Test results and calculations of fill volume | Site Engineer | Design Engineer
17 | Lot Number QA File | W | Ensure all OFIs are closed and included within QA file | At completion of Lot | Document Review |  |  | Site Engineer
|  | W | The Test Result Spreadsheet, bulk fill checksheets, and Test reports to be included within QA file | At completion of Lot | Document Review |  |  | Site Engineer
|  | W | Delivery Dockets to be included in QA file | At completion of Lot | Document Review |  |  | Site Engineer
18 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date:

## Insitu Concrete (hidden)
|  |  |  | Inspection Test Plan |  | Enter Project Doc No. | Approved |  | Signature
|  |  |  | Contract Name: | (insert contract name here) |  | FCI Engineer
|  |  |  | Procedure: | Insitu Concrete |  | FCI Quality Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Method Statement: |  | (insert contract suffix here) xxxx |  | Compliance with Method Statements and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method | Conformance Criteria | Records | FCC Initials | Design Engineer Initials (Grey if not required) | Date(s)
submission, visual inspection, testing, measure, review
1 | Permits | H | Obtain Permits | As required | Document Review | Permit to Work, PTW # x Fall Prevention Checklist (if applicable). Notify Worksafe NZ if required. Permit to Work around services (Gas, Power etc) if required. | Permit attached or permit number noted | Site Engineer
2 | Pre-construction sign offs | H | Ensure that Sub-Contract and Supplier Agreements are signed |  | Document Review |  | Subcontract and Supplier Agreements on Aconex | Site Engineer
|  | H | Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS |  | Document Review |  | TMP on Aconex | Site Engineer
|  | H | Ensure all Sub-Contractors and suppliers go through (insert project name) induction |  | Induction | Issued induction stickers and number | JSEA and Pre-starts to safety team | Site Engineer
3 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer | Design Engineer
4 | Installation of Erosion and Sediment Controls | H | Ensure that Erosion & Sediment Control ITP & Checksheets have been completed and submitted to the Territorial Authority | Prior to commencement | Document Review | Territorial Authorty has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence | FCI-QMC-TMP-0014 | Environmental Manager/Site Engineer
|  | M | Monitor effectiveness of the ESCP Controls throughout the construction process |  | Visual Inspection |  | Project ESCP | Site Engineer
5 | Survey Setout | H | Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations) | Prior to commencement | Survey | Consistency with Construction Drawing | Survey receipt | Site Engineer
6 | Material Compliance | H | Concrete mix design(s) shall be submitted to the Design Engineer in writing at least 2 wks prior to placing concrete and approved before placing concrete | Prior to commencement | Document review |  | Design Engineer Approval | Site Engineer | Design Engineer
|  | H | All concrete delivered to site shall be produced strictly in accordance with the approved mix design | Prior to pouring concrete | Concrete Delivery Dockets |  | Concrete Delivery Dockets | Site Engineer
|  | H | Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade called up on the drawings | Prior to ordering steel | Document review | AS/NZS4671&NZS3109 | Detail Sheets and Mill Certificates | Site Engineer
|  | H | Any welding or mechanical splicing to be approved in writing by the Design Engineer | Prior to welding or splicing | Document review |  | Mark Up As Built Drawings | Site Engineer
|  | H | Any reinforcement requiring cutting or bending on site to be approved in writing by the Design Engineer | Prior to cutting or bending on site | Document review |  | Mark Up As Built Drawings | Site Engineer
7 | Foundation Acceptance by Engineer's Rep | H | Approval given by engineer's Rep and Signed off Subgrade Approval Checksheet | Prior to commencement | Inspection by Engineer | Inspection and Acceptance of Structure Foundations | Project checksheet | Site Engineer | Design Engineer
8 | Concrete Pumping Operations | W | Ensure the Permit to Concrete Pump & Pump Operator Chekcsheet has been completed before concrete pumping commences | Prior to commencement | Document review |  | Project checksheets | Site Engineer
9 | Blinding Concrete | H | Once blinding concrete layer has been completed the Engineer's Rep to inspect and give approval for the rest of the works to commence | Prior to commencement | Inspection by Engineer |  | Sign off this document | Site Engineer | Design Engineer
10 | Temporary Works (Formwork) | W | Formwork to be constructed to design and set to correct line and level as set out by the surveyor | Daily Visual Inspection | Visual inspection | Concrete Inspection Record | Project checksheet | Site Engineer
|  | H | The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured | Prior to concrete pour | Visual inspection | Concrete Inspection Record | Project checksheet | Site Engineer | Design Engineer
11 | Reinforcing | W | Reinforcing steel shall be handled, placed and fixed as per NZS 3109 | Daily Visual Inspection | Document review | Concrete Inspection Record | Project checksheet | Site Engineer
|  | H | Check for any cast in items and ensure they are fixed correctly | Prior to concrete pour | Visual inspection | Concrete Inspection Record | Project checksheet | Site Engineer
12 | Concrete Pumping Operations | W | Ensure the Permit to Concrete Pump & Pump Operator Chekcsheet has been completed before concrete pumping commences | Prior to commencement | Document review |  | Project checksheets | Site Engineer
13 | Concreting | H | The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required | Prior to concrete pour | Visual inspection |  | Project checksheet | Site Engineer | Design Engineer
|  | H | Concrete dockets checked for correct mix and concrete site testing undertaken. 1 sample set per 10m3, 10-25m3 2 sample sets, 25 to 50m3 3 sample sets | Prior to concrete pour | Test Results | NZS 3104 | Project checksheet | Site Engineer
|  | H | Concrete surfaces shall be F4 or better for formed surfaces and U2 or better for unformed surfaces, Bridge decks U5 (broom) finish | At completion of pour | Visual inspection | Concrete Inspection Record | Project checksheet | Site Engineer
14 | Remove formwork | W | Remove formwork as per the approved work method | At completion of pour | Visual inspection | Concrete Inspection Record | Project checksheet | Site Engineer
15 | Lot Number QA File | W | Ensure all OFIs are closed and included within QA file | At completion of Lot | Document Review |  |  | Site Engineer
|  | W | The Concrete Test Result Spreadsheet and Test reports to be included within QA file | At completion of Lot | Document Review |  |  | Site Engineer
|  | W | Delivery Dockets to be included in QA file | At completion of Lot | Document Review |  |  | Site Engineer
16 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: