## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Sealing - Stabilised Pavement Layer | itp |  |  |  | Yes | ITP - Sealing - Stabilised Pavement Layer - Abattoir Road
section | 4.0. SETOUT AND PREPARATION
checkpoint | 4.0.1 - Mark out and approve
label | Detail of Activity - Set out and record existing line markling within the treatment area
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - All areas of unbound granular pavement layers
label | Inspection / Test method - NZTA Z/16
label | Acceptance Criteria - N/A
label | Record documents - Contractor's site diary
label | Responsibility - Contractor
label | Comments - Treatment area marked up jointly by Contractor and Eng.Rep.
holdpoint | HOLD POINT
checkpoint | 4.0.2 - Level Control
label | Detail of Activity - Install offset pegs; record centreline, edge line or mark out stabilisation extents from existing line marking
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to works
label | Inspection / Test method - NZTA Z/16
label | Acceptance Criteria - Document existing furniture
label | Record documents - Site Diary
label | Responsibility - Contractor
checkpoint | 4.0.3 - Determine levels of substrate before placing materials
label | Detail of Activity - Check top of substrate levels
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Every 20m
label | Inspection / Test method - NZTA Z/16
label | Acceptance Criteria - Subgrade: check NZTA F/1 and/or project specifications.
label | ○ Subbase: No Concrete Channel: -25mm + 5mm with Concrete Channel: -25mm + 5mm
label | Record documents - Survey Diary or CAD
label | Responsibility - Surveyor / contractor
checkpoint | 4.0.4 - Modification Agent(s) Optimisation
label | Detail of Activity - Stabilised material strength - ITS
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Optimisation test per aggregate type
label | Inspection / Test method - NZTA T/19
label | Acceptance Criteria - Check Project Specs.
label | Modified materials should be:
label | Dry ITS: 175kPa to 400 kPa
label | Soaked ITS: 150 kPa to 350 kPa
label | Record documents - IANZ Report
label | Responsibility - Client
label | Comments - Must be submitted to the pavement designer for approval at least 5 working days before modification works comence
holdpoint | HOLD POINT
section | 4.1. MATERIALS - SUBBASE / BASECOURSE
checkpoint | 4.1.1 - Check raw materials (whichever applicable)
label | Detail of Activity - Cement
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Batch
label | Inspection / Test method - NZ 3122
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
checkpoint | 4.1.2 - Check raw materials (whichever applicable)
label | Detail of Activity - Lime
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Batch
label | Inspection / Test method - NZTA M/15
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
label | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint | 4.1.3 - Check raw materials (whichever applicable)
label | Detail of Activity - Cement / Lime Supply and Storage Pods
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to commencement
label | Inspection / Test method - Document Review
label | Acceptance Criteria - All test certificates with supply and storage pods
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
checkpoint | 4.1.4 - Check raw materials (whichever applicable)
label | Detail of Activity - Bitumen for Stabilisation (FBS or BE)
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Batch
label | Inspection / Test method - NZTA M/01 and visual foaming at test nozzle
label | Acceptance Criteria - Pen 80/100 Bitumen or Pen 180/200 (if approved) Bitumen able to achieve min 10x expansion and min. 6s half life
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
checkpoint | 4.1.5 - Check raw materials (whichever applicable)
label | Detail of Activity - Bitumen Supply and Storage Tanks
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to commencement
label | Inspection / Test method - Document Review
label | Acceptance Criteria - All test certificates with supply and storage pods
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
label | Comments - Retain for testing if required
checkpoint | 4.1.6 - Check raw materials (whichever applicable)
label | Detail of Activity - Sub-base Aggregate
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per source stockpile
label | Inspection / Test method - USE ITP LABELLED UBG SUBBASE
label | Acceptance Criteria - NZTA M03 / Project Spec
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
label | Comments - The surface finish, line and level is checked by Engineer's Rep. immediately prior to sealing
checkpoint | 4.1.7 - Check raw materials (whichever applicable)
label | Detail of Activity - Basecourse Aggregates
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per source stockpile
label | Inspection / Test method - USE ITP LABELLED UBG BASECOURSE
label | Acceptance Criteria - NZTA M04 / Project Spec
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
section | 4.2. CONSTRUCTION - SUBBASE / BASECOURSE
checkpoint | 4.2.1 - Modified Subbase / Basecourse
label | Detail of Activity - Spreading of powdered stabilising agent
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On-going measurement by computer/load cells
label | Inspection / Test method - Measurement each run
label | Acceptance Criteria - ± 5% of specified rate
label | Record documents - Worksheet
label | Responsibility - Contractor
checkpoint | 4.2.2 - Modified Subbase / Basecourse
label | Detail of Activity - Mixing process
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On-going visual assessment
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps and construction joints as per spec
label | Record documents - ITP / Daily work Log
label | Responsibility - Contractor
checkpoint | 4.2.3 - Modified Subbase / Basecourse
label | Detail of Activity - Bitumen Injection
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On-going measurement by computer supplemented with tanker dips at the end of each run
label | Inspection / Test method - Measurement each run
label | Acceptance Criteria - ± 5% of specified rate
label | Record documents - Worksheet
label | Responsibility - Contractor
checkpoint | 4.2.4 - Modified Subbase / Basecourse
label | Detail of Activity - Depth of stabilisation
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 9 per Lot
label | Inspection / Test method - Measurement
label | Acceptance Criteria - +15mm / -5mm from specified depth
label | Record documents - Daily work Log
label | Responsibility - Contractor
checkpoint | 4.2.5 - Modified Subbase / Basecourse
label | Detail of Activity - Modified Maximum Dry Density
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 3 per Lot
label | Inspection / Test method - NZS 4402.4.1.3
label | Acceptance Criteria - For analysis of DoC
label | Record documents - IANZ Report
label | Responsibility - Contractor
label | Comments - Basecourse only
checkpoint | 4.2.6 - Modified Subbase / Basecourse
label | Detail of Activity - Degree of Compaction
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 9 per Lot
label | Inspection / Test method - NZS 4407.4.2.1
label | Acceptance Criteria - NZTA B/5:
label | ○ Subbase DoC Mean ≥95%, Miin ≥ 92%
label | ○ Basecourse DOC Mean ≥98%, Min ≥ 95%
label | Record documents - IANZ Report
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 4.2.7 - Modified Subbase / Basecourse
label | Detail of Activity - Layer Width
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - ± 10 mm
label | Record documents - Survey
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 4.2.8 - Modified Subbase / Basecourse
label | Detail of Activity - Surface Shape
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - < 6mm using 3m straight edge
label | Record documents - Worksheet
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 4.2.9 - Modified Subbase / Basecourse
label | Detail of Activity - Surface Levels
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | Inspection / Test method - NZTA Z/16
label | Acceptance Criteria - Subbase:
label | ○ No Concrete Channel: -25mm + 5mm with Concrete Channel: -25mm + 5mm
label | Basecourse:
label | ○ No Concrete Channel: -5mm + 15mm with Concrete Channel:
label | – within 1m from channel: -5mm + 5mm
label | – other locations: -5mm + 15mm
label | Record documents - Survey
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 4.2.10 - Modified Subbase / Basecourse
label | Detail of Activity - Stabilised material strength - ITS
label | Action (Hold, Monitor, Witness) - S
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 3 soaked ITS + 3 dry ITS per Lot
label | Inspection / Test method - NZTA T/19
label | Acceptance Criteria - Modified:
label | ○ Dry ITS: 150kPa to 350 kPa
label | ○ Soaked ITS: 100 kPa to 300 kPa
label | Bound Subbase:
label | ○ Dry ITS > 500 kPa
label | ○ Soaked ITS > 450 kPa
label | Record documents - IANZ Report
label | Responsibility - Contractor
checkpoint | 4.2.11 - Modified Subbase / Basecourse
label | Detail of Activity - Stabilised material strength - UCS
label | Action (Hold, Monitor, Witness) - S
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 3 per Lot
label | Inspection / Test method - NPTG Guide
label | Acceptance Criteria - UCS < 0.75 Mpa
label | Record documents - IANZ Report
label | Responsibility - Contractor
label | Comments - If ITS testing is not available
section | 4.3. CLOSE OUT MODIFIED LAYER LOT
checkpoint | 4.3.1 - Non-conforming results
label | Detail of Activity - Assessment of all test results for conformity
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each Lot
label | Inspection / Test method - Site Inspection
label | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | Record documents - NCR
label | Responsibility - Engineer's Rep
holdpoint | HOLD POINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
signoff | Add Signature
checklist | ITP - Sealing - Bituminous Seal Coat | itp |  |  |  | Yes | ITP - Sealing - Bituminous Seal Coat - Abattoir Road
section | 6.0. SETOUT AND PREPARATION
checkpoint | 6.0.1 - Seal Design
label | Detail of Activity - Seal design outlining all design assumptions
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per seal application type
label | Inspection / Test method - Project Specification
label | Acceptance Criteria - New Zealand Chip Sealing Handbook
label | Record documents - Seal design in contractor's site folder
label | Responsibility - Designer / Engineer's Rep
holdpoint | HOLD POINT
checkpoint | 6.0.2 - Bitumen Distributer Certification
label | Detail of Activity - E2
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per annum
label | Inspection / Test method - CCNZ E2
label | Acceptance Criteria - Must be operated as per CCNZ E/2
label | Record documents - Record Distributor #
label | Responsibility - Contractor
label | Comments - Certified Distributor is on the CCNZ website
checkpoint | 6.0.3 - Pre-Seal requirements
label | Detail of Activity - Visual inspection of surface to be sealed
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - per sealing schedule.1 Lot = 1 day's production and < 1500m2
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - NZTA B/2, B/5, B/6, B/7, B/8 or M/10 (whichever is applcable)
label | Record documents - Contractor's site diary
label | Responsibility - Engineers Rep
label | Comments - The surface finish, line and level is checked by Engineer's Rep. immediately prior to sealing
checkpoint | 6.0.4 - Pre-Seal requirements
label | Detail of Activity - Dry back Moisture Content (if 1st coat)
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 9 per Lot
label | Inspection / Test method - NZS 4407.4.2.1
label | Acceptance Criteria - DOS ≤ 80% preferably ≤ 70%
label | Record documents - IANZ Report
label | Responsibility - Contractor
label | Comments - Only required if pavement widening extends into trafficked lane
holdpoint | HOLD POINT
checkpoint | 6.0.5 - Pre-Seal requirements
label | Detail of Activity - Clegg Hammer (if 1st coat)
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 CIV per 10m, 1 Lot < 300m
label | Inspection / Test method - Clegg Impact Value Test
label | Acceptance Criteria - Average CIV > 40, Min. CIV > 35
label | Record documents - Contractor's CIV form appended to Contractor's daily diary
label | Responsibility - Contractor
section | 6.1. MATERIALS - PRIOR TO CONSTRUCTION PHASE
checkpoint | 6.1.1 - Source Properties (All aggregate)
label | Detail of Activity - Crushing Resistance
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - RNZ 9805:2009
label | Inspection / Test method - NZS4407: 3.10
label | Acceptance Criteria - < 10% under load of 230kN
label | Record documents - IANZ Report
label | Responsibility - Contractor
label | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint | 6.1.2 - Source Properties (All aggregate)
label | Detail of Activity - Weathering Resistance
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - RNZ 9805:2010
label | Inspection / Test method - NZS 4407: 3.11
label | Acceptance Criteria - AA or BA
label | Record documents - IANZ Report
label | Responsibility - Contractor
label | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint | 6.1.3 - Source Properties (All aggregate)
label | Detail of Activity - Weak Particle Test
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - RNZ 9805:2011
label | Inspection / Test method - AS 1141.32 - 1995
label | Acceptance Criteria - Max of 1% of unsound material
label | Record documents - IANZ Report
label | Responsibility - Contractor
label | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint | 6.1.4 - Source Properties (All aggregate)
label | Detail of Activity - Polished Stone Value (PSV)
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per year
label | Inspection / Test method - BS EN 1097-8:2009
label | Acceptance Criteria - Lower value of 2 tests (or median value if more than 3 tets are available) ≥ NZTA T/10 and/or project specifications. 2 tests must be < 2 years old
label | Record documents - IANZ Report
label | Responsibility - Contractor
label | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint | 6.1.5 - Production Properties Grades 2, 3 and 4
label | Detail of Activity - Cleanness
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - RNZ 9805:2011
label | Inspection / Test method - NZS 4407: 3.9
label | Acceptance Criteria - Gr.2 ≥ 89; Gr.3 ≥ 87; Gr.4 ≥ 85
label | Record documents - IANZ Report
label | Responsibility - Contractor
label | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint | 6.1.6 - Production Properties Grades 2, 3 and 4
label | Detail of Activity - Size and Shape
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - RNZ 9805:2011
label | Inspection / Test method - NZS 4407: 3.13
label | Acceptance Criteria - NZTA M/6 - Table 2
label | Record documents - IANZ Report
label | Responsibility - Contractor
label | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint | 6.1.7 - Production Properties Grades 2, 3 and 4
label | Detail of Activity - Broken Faces
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - RNZ 9805:2011
label | Inspection / Test method - NZS 4407: 3.14
label | Acceptance Criteria - ≥ 98% with at least two broken faces
label | Record documents - IANZ Report
label | Responsibility - Contractor
label | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint | 6.1.8 - Production Properties Grades 5 & 6
label | Detail of Activity - General Soundness
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - RNZ 9805:2011
label | Inspection / Test method - Visual
label | Acceptance Criteria - Clean, tough particles, free of soft, weathered, disintegrtaed or deleterious material.
label | Record documents - IANZ Report
label | Responsibility - Contractor
label | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint | 6.1.9 - Production Properties Grades 5 & 6
label | Detail of Activity - Grading
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - RNZ 9805:2011
label | Inspection / Test method - NZS 4407: 3.8
label | Acceptance Criteria - NZTA M/6 - Table 3
label | Record documents - IANZ Report
label | Responsibility - Contractor
label | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint | 6.1.10 - Bitumen Properties
label | Detail of Activity - As per ITP 5 (previous Tab)
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - refer to ITP 5
label | Inspection / Test method - Various
label | Acceptance Criteria - Various
label | Record documents - Various
label | Responsibility - Contractor
label | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
section | 6.2. CONSTRUCTION
checkpoint | 6.2.1 - Bitumen Sample
label | Detail of Activity - Audit sample(s)
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per sprayer
label | Inspection / Test method - ASTM D140 or AS2008
label | Acceptance Criteria - N/A
label | Record documents - Contractor's site diary
label | Responsibility - Contractor
label | Comments - Retain for duration of DLP
checkpoint | 6.2.2 - Adhesion Agents
label | Detail of Activity - Adhesion Agents
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to use
label | Acceptance Criteria - NZTA M/13
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
label | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint | 6.2.3 - Aggregates
label | Detail of Activity - Audit samples
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 20 kg per stockpile
label | Inspection / Test method - N/A
label | Acceptance Criteria - Stored in a sealed plastic bag in a covered environment
label | Record documents - Contractor's site diary
label | Responsibility - Contractor
label | Comments - Retain for duration of DLP
section | 6.3. CONSTRUCTION - 1st Coat as per TNZ P/3
checkpoint | 6.3.1 - Bitumen application
label | Detail of Activity - Bitumen Spraying Temperature
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Ongoing with non-going heat sensing gauge
label | Inspection / Test method - Non-contact heat sensing gun
label | Acceptance Criteria - NZTA P/3 - Table 2
label | Record documents - Contractor's Spray sheet
label | Responsibility - Contractor
checkpoint | 6.3.2 - Bitumen application
label | Detail of Activity - Bitumen Application rate (BAR)
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Every sprayer run
label | Inspection / Test method - Dip sprayer
label | Acceptance Criteria - TNZ P/3
label | Record documents - Contractor's Spray sheet
label | Responsibility - Contractor
checkpoint | 6.3.3 - Sealing Aggregate application
label | Detail of Activity - Application rate (m2/kg)
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Continous
label | Inspection / Test method - Calculation
label | Acceptance Criteria - Refer TNZ P/3 - section 28
label | Record documents - Contractor's site diary
label | Responsibility - Contractor
section | 6.4. CLOSE OUT SEALING LOT
checkpoint | 6.4.1 - Non-conforming results
label | Detail of Activity - Assessment of all test results for conformity
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each Lot
label | Inspection / Test method - Site Inspection
label | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | Record documents - NCR
label | Responsibility - Engineer's Rep
holdpoint | HOLD POINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
signoff | Add Signature