## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | A181 - West Dapto - ITC 009 (ITP009) - Traffic Management |  |  |  |  | Yes | A181 - West Dapto - ITC 009 (ITP009) - Traffic Management | 00740229-cfaa-4784-a5dd-4fbbf9cec275
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | 7b416172-c743-5698-b51b-1cccb59d7cb2 |  | textbox | Lot Opened On
text | 27cca1d6-76e0-507d-b2b1-c08c23ea85c5 |  | textbox | Date of Works
text | 7c2c200b-2e2a-556e-8ce3-e5b927f37868 |  | textbox | Lot Type
text | d47cabcc-7647-5dd4-abc0-782ea42eefa2 |  | textbox | Start Chainage
text | 2405a592-9272-5c7e-95af-f24adea31527 |  | textbox | End Chainage
text | 26cb0821-6b4a-4f65-af4c-94ce45ef1f4d |  | textbox | Offset
text | 2eb15d17-25e1-5044-9808-a87d15b72aa4 |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Preparation Works
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 4fb3d4e8-246f-5fee-834d-c6edcf5cd4de |  | note | REQUIREMENTS / REFERENCE: Project Safety Plan
label | 9d1fc523-4091-55e2-a6bb-a5e478558f7b |  | note | ACCEPTANCE CRITERIA:
label | 4fe561ac-34e0-502a-b2b4-884d3de2dc3d |  | note | • All site personnel inducted (includes environment and cultural)
label | a68e406f-17d4-5265-a471-1f9d18fd0c58 |  | note | • Required Safe Work Method Statements completed and signed
label | 291d0c20-1ce2-5e1f-90b4-e8deeddd5d4d |  | note | • Subcontractor’s safety plan/procedure approved
checkpoint-group |  |  | section | 2 - Environment
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 8fbee629-67f2-5929-8659-f595bd038d2f |  | note | REQUIREMENTS / REFERENCE: Project Environment Plan
label | 1702432a-37a2-5847-a90f-5f5d8192c5c3 |  | note | ACCEPTANCE CRITERIA:
label | c617cfeb-aad7-5395-832b-1a59b8570ece |  | note | • Traffic requirements in place as per Plan
checkpoint-group |  |  | section | 3 - Traffic Management
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 967d24fd-af71-534a-adef-d8c256463277 |  | note | REQUIREMENTS / REFERENCE: 1101 2.1
label | 09d723bd-7290-529f-b246-2b0467d2fd60 |  | note | ACCEPTANCE CRITERIA:
label | 3733dedf-f3cd-5f29-8dd2-98b5528ebdc5 |  | note | • HOLD POINT: Submission of Traffic Management Plan (TMP) to the requirements of section 2.1
text | 37740904-fd8d-572e-8e02-1d89a4250231 |  | textbox | HOLD POINT NUMBER:
text | 4846052c-cfa1-5ca0-9b1d-23de0bbc5856 |  | textbox | DATE SUBMITTED:
text | 6b119d06-10cf-5d7c-9ab1-90ad00eb74ff |  | textbox | SUBMITTED BY:
text | a23d1834-7c04-54c0-bd80-556f5d79241c |  | textbox | SPECIFICATION AND CLAUSE:
text | c3ffabab-42ec-5cdf-ab2f-ad252920f361 |  | textbox | HOLD POINT DESCRIPTION:
text | d1fa22f5-a518-56f5-8fbf-e37cd7502e6b |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 4 - Authority Approvals
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 3f26bb37-83bd-5687-91b2-ecd7a55aa9d8 |  | note | REQUIREMENTS / REFERENCE: 1101 1.5
label | 3d6d284c-3377-5039-b34f-18032273aea1 |  | note | ACCEPTANCE CRITERIA:
label | 13d10303-05c5-589a-9080-72843f9bc3d9 |  | note | • HOLD POINT: Submission of evidence of approvals for temporary traffic arrangements 4 weeks prior to works commencing
text | 9d3acb20-abee-52da-871f-5e9f60ad59c2 |  | textbox | HOLD POINT NUMBER:
text | 998a587d-96f3-52b0-b448-136c640ab7d3 |  | textbox | DATE SUBMITTED:
text | ccc1bc70-ecc4-5322-b230-e023b4389389 |  | textbox | SUBMITTED BY:
text | ec12d840-8f6e-5a0d-98fe-ccbe449d32fa |  | textbox | SPECIFICATION AND CLAUSE:
text | a36c599c-fe8c-58b6-90be-8fa6e08a4d47 |  | textbox | HOLD POINT DESCRIPTION:
text | 77e0746c-9747-597f-9b70-ebf55cce96ec |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 5 - Approval of Speed Zone Changes
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 7cc0e761-4555-5561-a897-482fcef4db6a |  | note | REQUIREMENTS / REFERENCE: 1101 1.5
label | 614f071f-6302-5b78-8816-269cf4cbbb2a |  | note | ACCEPTANCE CRITERIA:
label | 354d34f9-f97d-5554-b2b2-5746e5162fd1 |  | note | • HOLD POINT: Submission of evidence of approvals for changes to speed zoning 5 weeks before implementation
text | aa2978fc-e0e3-5142-bdd5-cd11c6ef44fd |  | textbox | HOLD POINT NUMBER:
text | ddeb4ac7-482f-5cb9-8e18-6da7e1fe2b42 |  | textbox | DATE SUBMITTED:
text | 71cdaab5-9285-53c5-aad8-c91b34608936 |  | textbox | SUBMITTED BY:
text | 47793c52-9402-5662-84be-343ee3174b2f |  | textbox | SPECIFICATION AND CLAUSE:
text | c9a8e898-603a-5644-b328-03028e0c3f9a |  | textbox | HOLD POINT DESCRIPTION:
text | a659ab80-ce19-594c-9e2f-f0e1e972c6ee |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 6 - Construction of Temporary Pavement
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 1020d080-3215-586e-bf71-f61955b277fd |  | note | REQUIREMENTS / REFERENCE: 1101 4.5
label | 6b1e7cb9-8b20-527d-8d23-0aa4c4e463a0 |  | note | ACCEPTANCE CRITERIA:
label | 81cd2b0f-c703-5b19-8027-cde0a7508ecd |  | note | • Permission to construct under traffic: Give 5 days’ notice of before carrying out work.
label | c24f68ec-f4ad-5a32-825c-bac533fede02 |  | note | • WITNESS POINT: Notification of completed temporary pavement construction for inspection 3 days before installation of control devices and signs
text | e94ed0f3-66e3-5f37-ab1f-4d8e3b46b6ed |  | textbox | WITNESS POINT NUMBER:
text | cdb22b57-bcc6-52c4-98b6-f74f1bc6667c |  | textbox | DATE SUBMITTED:
text | 6a317d15-e041-5079-8359-adafa9ee7001 |  | textbox | SUBMITTED BY:
text | dddc6c24-90fd-51db-93ab-2383d20a3c89 |  | textbox | SPECIFICATION AND CLAUSE:
text | 42662463-0e3a-5df9-86b4-29caaf7aaf8a |  | textbox | WITNESS POINT DESCRIPTION:
text | 86fc0479-c007-5aa5-8a1d-d2b36e202953 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 7 - Completed Temporary Roadway
checkpoint-status |  |  | checkpoint | HOLD POINT
label | fb553b62-cd66-5d3e-b726-e7c1eb8eb38c |  | note | REQUIREMENTS / REFERENCE: 1101 4.6
label | 096e3bec-1c1e-5ebb-93d2-a20e866df7e2 |  | note | ACCEPTANCE CRITERIA:
label | 180b4da2-1455-506c-82db-b44a0f66e55c |  | note | • HOLD POINT: Notification of completed temporary roadway inclusive of traffic devices 3 days before opening to traffic. Written approval required to open to traffic
text | 508a87ef-a95d-5cd0-bd2e-d21fd0247ee2 |  | textbox | HOLD POINT NUMBER:
text | 3e001e7d-a082-5055-9451-7f8b29ff8678 |  | textbox | DATE SUBMITTED:
text | 635f0b93-78c1-5614-a5fe-e514a4132bda |  | textbox | SUBMITTED BY:
text | 4efbf10f-e225-552e-9e3c-7b5035e433f5 |  | textbox | SPECIFICATION AND CLAUSE:
text | 67d419a0-ae3c-5c91-9713-4e561defb798 |  | textbox | HOLD POINT DESCRIPTION:
text | 4f5ce39f-04e9-57c1-af36-6d7abaee783f |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 8 - Traffic Control Signs and Devices
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | ffd4dd56-3c64-5632-9829-ca5e79f31fe0 |  | note | REQUIREMENTS / REFERENCE:
label | b7e07ff2-27f0-50d8-8507-f1e657db1094 |  | note | • 1101 1.6
label | 05a8b29b-eb1c-556f-ad7d-c00663d304a8 |  | note | • 1101 4.7
label | 0afdc3d2-8f6e-539c-b16a-186e0fa0859d |  | note | ACCEPTANCE CRITERIA:
label | a603c24a-fd43-541e-9592-835cc8b00ff2 |  | note | • WITNESS POINT: Notification of completed installation of any of the following:
label | 97321a36-4289-5230-823d-d31c648d427c |  | note | o Signs and devices
label | 8a30396f-76c6-528d-b0bf-504debeecd3b |  | note | o Alternative access
label | d327bb5d-db28-5973-b6bf-f4ecbbf2a29c |  | note | o Warning devices installation
label | 1753d6ca-189e-5a1e-85db-22a5f050704e |  | note | • 1 day before opening to traffic
text | 79052a7d-946d-5231-8fef-df3588128ea5 |  | textbox | WITNESS POINT NUMBER:
text | cbeadeee-9966-5cff-ab46-96f262167903 |  | textbox | DATE SUBMITTED:
text | 1490c81d-b700-5739-b814-5e1487c79ffd |  | textbox | SUBMITTED BY:
text | e8c99090-b36d-506f-a9e5-eb03322276b6 |  | textbox | SPECIFICATION AND CLAUSE:
text | 1bd08839-6674-56f9-a8dd-3b0d00b0fd9a |  | textbox | WITNESS POINT DESCRIPTION:
text | cd288c18-5da3-5cea-90c0-102a5926c24b |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 9 - Opening Completed Work
checkpoint-status |  |  | checkpoint | HOLD POINT
label | e06e596b-fa0e-578f-90a7-1160ce078806 |  | note | REQUIREMENTS / REFERENCE: 1101 4.7
label | bc794187-dfb4-5734-8bed-ff21fe2bbc42 |  | note | ACCEPTANCE CRITERIA:
label | bd325e8c-868b-55cd-9050-7663d8b1cdb3 |  | note | • Provide at least 10 working days’ written notice of the date of opening the Works to traffic. Obtain agreement for the procedure for opening including with the local Police.
label | 82e39d69-26b5-5c81-a5fd-55964ad1965e |  | note | • HOLD POINT: Notification of reinstatement of affected area by the works 2 days before opening to traffic
text | 40059ba5-f430-5640-a038-027f16398799 |  | textbox | HOLD POINT NUMBER:
text | db65ffc1-90b7-5925-86c4-6b562b46aa10 |  | textbox | DATE SUBMITTED:
text | 69bae5cc-ee31-5c18-be8d-9118ff82f49a |  | textbox | SUBMITTED BY:
text | df54a6c7-62ef-5d8d-803b-014cd423e411 |  | textbox | SPECIFICATION AND CLAUSE:
text | 57e33359-c8f2-54c6-80cb-ff294f66933c |  | textbox | HOLD POINT DESCRIPTION:
text | a07fb936-212c-50db-b2fa-e7c7d65c8529 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | be551147-195a-5671-9e4f-7a38e5776f9b |  | textbox | Lot Verified By:
text | f63a9db1-bb78-5e15-bf8e-77bd1d09ca84 |  | textbox | Lot Closed Date:
button | 1dcb40e3-b983-5e92-b23c-c856444ca97d |  | button | Submitted to Client | Yes, No, N/A
button | e6e5b83a-6e24-51fe-9ef3-1b5d1c762128 |  | button | Reviewed by Client | Yes, No, N/A
text | 33511ddb-9e0d-5817-b6e8-40bae1503e43 |  | textbox | Submission Comments:
checklist-sectioned |  |  | checklist | A181 - West Dapto - ITC 011 (ITP011) - Signposting |  |  |  |  | Yes | A181 - West Dapto - ITC 011 (ITP011) - Signposting | 22b1e2a1-e2de-491f-8f7d-72629e550eb9
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | 3c3ed247-ef6e-5335-8a95-06e80ecd0a14 |  | textbox | Lot Opened On
text | f91f44c3-d90c-5eb2-ab89-83447df54dfe |  | textbox | Date of Works
text | 9381ad39-97bb-5dd0-8331-e0a2d518cc58 |  | textbox | Lot Type
text | 83067f57-730e-5e8e-9430-1db22751c309 |  | textbox | Start Chainage
text | 8759f006-712e-504e-80d0-37c2e4f19a58 |  | textbox | End Chainage
text | b485e713-4753-4dec-ab24-be15b4c15b6b |  | textbox | Offset
text | b5934028-842c-53ba-a766-f95d1a4d0a3d |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Preparation Works
checkpoint-status |  |  | checkpoint | VERIFICATION
label | e5beac51-9c4b-50e3-bb1f-c044391c6ee4 |  | note | REQUIREMENTS / REFERENCE: Project Safety Plan
label | 084b0f01-613c-5dae-8168-dd80a11e2159 |  | note | ACCEPTANCE CRITERIA:
label | f8b6593e-2a88-5687-9ec4-7fc0a1845d90 |  | note | • All site personnel inducted (includes environment and cultural)
label | dd3cbfbf-9254-5593-af7f-0dffe088125f |  | note | • Required Safe Work Method Statements completed and signed
label | 9abcfea1-04b2-5a1d-8a61-1caf2e1b7047 |  | note | • Subcontractor’s safety plan/procedure approved
checkpoint-group |  |  | section | 2 - Environment
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 0b9eefd6-68f1-58d0-81e6-4c5c8c7714e7 |  | note | REQUIREMENTS / REFERENCE: Project Environment Plan
label | 6551a42e-a711-5d7e-89ad-f182856ef2c8 |  | note | ACCEPTANCE CRITERIA:
label | 557e3371-9304-5e61-9e36-e39e9772a815 |  | note | • Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs.
label | 4b00a97f-d845-5332-8f55-58da706a739e |  | note | • Air quality to be visually monitored for dust etc. as a direct result of construction activities.
checkpoint-group |  |  | section | 3 - Details of Manufacturer and Materials
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 83ef8b30-8192-5990-9a58-b5c4892bc7a6 |  | note | REQUIREMENTS / REFERENCE: 1192 1.4
label | 0d4c00fb-4cec-51b2-a610-32cbe7bc4382 |  | note | ACCEPTANCE CRITERIA:
label | 50293b6d-52dc-5955-a804-8c2ab5a46b71 |  | note | • HOLD POINT: Submit details of sign manufacturer, materials and attachment system 2 weeks before fabrication (HP)
text | d0778585-6611-51d2-8be0-12293bab2253 |  | textbox | HOLD POINT NUMBER:
text | 226c32a3-e266-58ba-b1de-d34a1df764fc |  | textbox | DATE SUBMITTED:
text | 760f0959-9c87-583b-b59f-60ed10ec0103 |  | textbox | SUBMITTED BY:
text | 2a6f7e70-b5ee-50da-8f6d-2fb9e396321d |  | textbox | SPECIFICATION AND CLAUSE:
text | c1f16c34-ffaa-50f6-99f5-9f2a8e7fada6 |  | textbox | HOLD POINT DESCRIPTION:
text | 7d72cb30-3bde-5d4e-9baa-9003677e6409 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 4 - Material Conformance
checkpoint-status |  |  | checkpoint | HOLD POINT
label | b7ea72bd-46dc-5568-b25c-a62d8b18043f |  | note | REQUIREMENTS / REFERENCE: 1192 1.4
label | f7bb49ca-5ce8-5d01-88f1-fe080f438c1e |  | note | ACCEPTANCE CRITERIA:
label | 04506046-987f-5c85-883e-399205761197 |  | note | • HOLD POINT: One week before ordering, submit evidence that sign materials and parts conform to this worksection (HP)
text | 915ffdd7-8823-59d0-95ec-80bfc8a76059 |  | textbox | HOLD POINT NUMBER:
text | 3233d191-ab9e-5e05-837c-ebad9371d089 |  | textbox | DATE SUBMITTED:
text | 89386ee8-a04b-5dd8-83e5-983233073c86 |  | textbox | SUBMITTED BY:
text | adee5129-4e3e-5e45-a11e-0213c7f846a9 |  | textbox | SPECIFICATION AND CLAUSE:
text | e85e69e0-8603-56fe-8fb5-e124ee26f222 |  | textbox | HOLD POINT DESCRIPTION:
text | 72582fd8-356a-5364-b2fc-2a79e9846f49 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 5 - Material Compatibility
checkpoint-status |  |  | checkpoint | HOLD POINT
label | fc2589cf-4b5e-5228-94bc-ebb4c4fa551e |  | note | REQUIREMENTS / REFERENCE: 1192 1.4
label | f4e87b3a-485f-5adf-8003-ac9c4ab4f1e7 |  | note | ACCEPTANCE CRITERIA:
label | dcf15121-1855-5f59-9c5d-f1267865fbe6 |  | note | • HOLD POINT: One week before ordering, submit details of materials and evidence that materials for background and legend are compatible
text | 57e763ae-5632-56cb-a662-4206d71e374b |  | textbox | HOLD POINT NUMBER:
text | df256741-8e71-5d51-a894-f571fde0c8e7 |  | textbox | DATE SUBMITTED:
text | bbcaeaf5-7b18-593e-a9ef-787f9525e3f5 |  | textbox | SUBMITTED BY:
text | b2f73187-3d6c-5acc-85be-cf6f6c38ff3f |  | textbox | SPECIFICATION AND CLAUSE:
text | f26d399e-12e0-5318-b207-1d685b134280 |  | textbox | HOLD POINT DESCRIPTION:
text | 0c47c396-3033-5026-99b9-c954fb19044e |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 6 - Sign Supports Conformance
checkpoint-status |  |  | checkpoint | HOLD POINT
label | da30898b-7c63-57a7-8dd0-216ccbab9a2e |  | note | REQUIREMENTS / REFERENCE: 1192 1.4
label | 331d147d-2655-5ecd-be75-528590f71035 |  | note | ACCEPTANCE CRITERIA:
label | 3d510af2-4774-507f-9eea-2b48d7628ef8 |  | note | • HOLD POINT: One week before ordering, submit evidence that sign supports conform to this worksection
text | 8750c38b-c1a1-500e-8ab0-6c6767d4de6b |  | textbox | HOLD POINT NUMBER:
text | 4f8de92f-ac57-5f61-89c2-dcef03fb27c1 |  | textbox | DATE SUBMITTED:
text | 39dea78f-2814-51ca-9d64-86baa1079d8c |  | textbox | SUBMITTED BY:
text | 4d381db1-28cd-5084-bfd2-eb59d74bd94c |  | textbox | SPECIFICATION AND CLAUSE:
text | 4df85ba6-d842-50e2-a050-1f355055020c |  | textbox | HOLD POINT DESCRIPTION:
text | 2c1addf7-110a-508b-b193-d2bf434b144b |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 7 - Steel Reinforcement Conformance
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 7fa97d26-95bb-5773-bbb4-53fe44966bca |  | note | REQUIREMENTS / REFERENCE: 1192 1.4
label | 6e152607-384b-5a9a-9460-6bfda80859ad |  | note | ACCEPTANCE CRITERIA:
label | 1d5cacf0-c745-5e51-a213-4f72df5ed1e7 |  | note | • HOLD POINT: One week before ordering, submit evidence that steel reinforcement conform to this worksection
text | fed0f4bd-337c-5ebe-a034-d1991230110c |  | textbox | HOLD POINT NUMBER:
text | 65184c48-f177-5822-817c-a51f60066ca6 |  | textbox | DATE SUBMITTED:
text | 4da69ba3-0145-594c-be65-5dc9803b154d |  | textbox | SUBMITTED BY:
text | 8d9422fc-b0c5-5773-a030-438b4da271b9 |  | textbox | SPECIFICATION AND CLAUSE:
text | 67d7473c-d397-5cc6-b225-954ddd130711 |  | textbox | HOLD POINT DESCRIPTION:
text | 9dc682a2-b4a4-51f8-b955-4db1d8a52a11 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 8 - Pre-delivery inspection
checkpoint-status |  |  | checkpoint | HOLD POINT
label | f0405344-a932-5cf7-9280-8951078fd944 |  | note | REQUIREMENTS / REFERENCE: 1192 1.4
label | 7b83dfb7-2eba-50d5-bcd8-8bbef02ab092 |  | note | ACCEPTANCE CRITERIA:
label | c9daca7f-86b0-573c-b7ac-6955acaefdaf |  | note | • HOLD POINT: Fabricated purpose-designed sign structures
text | 0d295f2e-1cab-5e74-9c22-04d9ed083f97 |  | textbox | HOLD POINT NUMBER:
text | cadbef6a-34e2-5852-81cd-4750cc4c22e5 |  | textbox | DATE SUBMITTED:
text | 16af6e27-69e7-541c-ab70-1502bebf1950 |  | textbox | SUBMITTED BY:
text | 52a774c8-9134-59a6-8e4b-a02488f44ddf |  | textbox | SPECIFICATION AND CLAUSE:
text | 0351ff61-17d8-5ec0-97cd-474519cb6c81 |  | textbox | HOLD POINT DESCRIPTION:
text | c92d4973-bf1a-5899-8f05-f42d08989fad |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 9 - Protection of Services
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 7d98939f-f4db-5093-9419-3c50749bd733 |  | note | REQUIREMENTS / REFERENCE: 0310, 0319
label | 3fca288d-2a48-5e79-bf3f-13a80e951118 |  | note | ACCEPTANCE CRITERIA:
label | e6ba8ad2-d060-56a0-bff4-e2dd6e4c9761 |  | note | • HOLD POINT: Locate and protect services from damage 1 week before placing footings and erecting signs
text | 6aedc2b1-6ece-5fbc-a68f-72eda835787e |  | textbox | HOLD POINT NUMBER:
text | 7969a96d-db38-5566-a3ea-bb6364dcf3c9 |  | textbox | DATE SUBMITTED:
text | 3ef4e3bc-4926-5b6d-9b21-f9b5cb61bc9c |  | textbox | SUBMITTED BY:
text | d62f6b85-3afa-580a-b0e3-93804b42d371 |  | textbox | SPECIFICATION AND CLAUSE:
text | 89d1feb1-eb23-57b1-8968-aa7aebd66218 |  | textbox | HOLD POINT DESCRIPTION:
text | 807b716c-ebf2-5f7a-913e-bfcaa65fec4a |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 10 - Inspection of Clearing
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 74c52452-6317-5671-8760-a43c31812d6c |  | note | REQUIREMENTS / REFERENCE: 0310, 0319
label | e3a19715-9d21-538f-81b2-1366e4aa137f |  | note | ACCEPTANCE CRITERIA:
label | 080cb74e-f439-52ab-8816-388639a0bd9c |  | note | • WITNESS POINT: Notice of inspection of clearing 1 day after clearing
text | 54d392c8-50dd-5d42-a9e4-b92b716f973a |  | textbox | WITNESS POINT NUMBER:
text | a100a720-2505-5ac3-b261-bb05e11c6846 |  | textbox | DATE SUBMITTED:
text | 82b321ee-4b90-53a5-8a93-6440f5423e72 |  | textbox | SUBMITTED BY:
text | 9a34dac6-b131-5b63-95f7-48e2de4749b2 |  | textbox | SPECIFICATION AND CLAUSE:
text | 5bf9abce-e219-5750-b31a-0b3e4bc6a5b0 |  | textbox | WITNESS POINT DESCRIPTION:
text | 252a80c6-b137-552f-9a61-40aeb0a20c05 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 11 - Inspect Sign Support Set-out
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 671643dd-6e8d-5dab-ba05-ab264c6763a5 |  | note | REQUIREMENTS / REFERENCE: 0310, 0319
label | 2de0d518-95d2-5dc2-9413-94a8ca8ecda6 |  | note | ACCEPTANCE CRITERIA:
label | e40f8f21-6b34-5ec9-9a74-a0b344397cd6 |  | note | • HOLD POINT: Notice of inspection of sign support structure set-out 1 week before sign erection
text | 0a95edee-2486-5e9b-ac3a-6b7b1863ccdb |  | textbox | HOLD POINT NUMBER:
text | 8c02817f-e28f-5f2c-9c72-6976f0310dbc |  | textbox | DATE SUBMITTED:
text | d3b4c3c1-9960-5421-9764-b8bf4231ed14 |  | textbox | SUBMITTED BY:
text | c18d5381-d7d1-5509-8ee3-7c987d21718e |  | textbox | SPECIFICATION AND CLAUSE:
text | 899dc1c4-f06f-5a34-9335-ce2f6f1fc648 |  | textbox | HOLD POINT DESCRIPTION:
text | 09aec917-ab94-5ba8-aaea-f5bb5a86e953 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 12 - Inspect Footing Excavation
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | f5245a19-18dd-5c35-9109-7bf5a16bb676 |  | note | REQUIREMENTS / REFERENCE: 0310, 0319
label | 1477cd57-6517-569a-bbae-6ab6076865ba |  | note | ACCEPTANCE CRITERIA:
label | ae9e7cbd-2eb2-5b0b-9b05-006a43500d05 |  | note | • WITNESS POINT: Notice of inspection of completed excavation for footings 1 day before placing footings
text | 1d24caa7-b247-5c5b-94eb-ab41aa0a14ea |  | textbox | WITNESS POINT NUMBER:
text | f75eb1c8-b022-5ab8-ad26-2c5ba8365dd3 |  | textbox | DATE SUBMITTED:
text | 323e3fe7-d3f0-501d-b436-f53d813d4ac5 |  | textbox | SUBMITTED BY:
text | 5504562d-df01-5308-a54f-cd5bf2aa6f09 |  | textbox | SPECIFICATION AND CLAUSE:
text | b4721d43-b461-5f7f-8bac-9d346bbeb035 |  | textbox | WITNESS POINT DESCRIPTION:
text | 52ec0dd9-7c7f-5c23-ae1f-cc7640048c08 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 13 - Inspect Footing Reinforcement
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | f710dcf3-5d97-5974-b396-fe7476c898e9 |  | note | REQUIREMENTS / REFERENCE: 0310, 0319
label | d082baf3-b692-5e33-8b9a-eff17ff4bedd |  | note | ACCEPTANCE CRITERIA:
label | 08e81812-9af8-5bcc-904e-9355aeb523a7 |  | note | • WITNESS POINT: Notice of inspection of footings for steel reinforcement
text | 1629ae1d-550f-5d77-a611-8bfe3be8969c |  | textbox | WITNESS POINT NUMBER:
text | 6ae2601b-8c82-57cc-b920-0efb3c976b27 |  | textbox | DATE SUBMITTED:
text | 98657880-cdf9-5a00-8605-1c8662ef2d22 |  | textbox | SUBMITTED BY:
text | 24906208-b537-5154-9f06-a6a0b17b76de |  | textbox | SPECIFICATION AND CLAUSE:
text | cfbd29e0-f217-5596-80f8-316e660f678d |  | textbox | WITNESS POINT DESCRIPTION:
text | 257ee175-b9c9-588b-b238-69a2c3ca1d2d |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 14 - Adjustment of Existing Signs
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | fb9281b7-7297-50a9-b877-b7e840ff6a39 |  | note | REQUIREMENTS / REFERENCE: 1192 3.5
label | faa5f646-882d-51e8-af48-63490fe4a85b |  | note | ACCEPTANCE CRITERIA:
label | 9666eca5-33ad-5b70-af71-dcd893b69004 |  | note | • WITNESS POINT: Notice of inspection of adjusted, relocated or replaced signs
text | 720f21c4-810d-5899-af98-ae4cc6d5b13b |  | textbox | WITNESS POINT NUMBER:
text | b0f2938a-1344-5e79-bc75-9332f48ef5bb |  | textbox | DATE SUBMITTED:
text | 7deb383c-3d74-5409-855b-ca7a47226bdd |  | textbox | SUBMITTED BY:
text | dd946b59-bf8d-5cf0-a7a1-5a5e6ac1b3c9 |  | textbox | SPECIFICATION AND CLAUSE:
text | 9209ce47-cc95-514e-a56c-b83c11cc4cde |  | textbox | WITNESS POINT DESCRIPTION:
text | cb6c2ceb-1870-5d38-9382-55a32ce5e952 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | 3010d85f-691e-5e06-ba05-4c61bccdb8f4 |  | textbox | Lot Verified By:
text | 3e0b1bd0-b34e-5eb1-8d9e-683fb11596a1 |  | textbox | Lot Closed Date:
button | 47401d62-b398-5bb3-85f5-d78bc7923a31 |  | button | Submitted to Client | Yes, No, N/A
button | 589b3eca-d010-5fa8-9632-a68fd46161bd |  | button | Reviewed by Client | Yes, No, N/A
text | 865c8329-1056-5354-a8f8-621efc632c19 |  | textbox | Submission Comments:
checklist-sectioned |  |  | checklist | A181 - West Dapto - ITC 005 (ITP005) - Pre-Commencement |  |  |  |  | Yes | A181 - West Dapto - ITC 005 (ITP005) - Pre-Commencement | 27e368cf-cc9b-42d3-8129-73409b4b6716
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | acde31d2-3b48-5cc0-85ee-d73f0b81c92f |  | textbox | Lot Opened On
text | c020df47-cf68-58f2-a75d-eac85f21d9fa |  | textbox | Date of Works
text | 02c9c3f8-4eee-56de-8d16-e562776b065f |  | textbox | Lot Type
text | 3883931c-5082-587b-bde5-8037a5e7b5cc |  | textbox | Start Chainage
text | 0a1a2195-4bce-5469-a193-929e56029877 |  | textbox | End Chainage
text | 3ccbf33f-ffd8-4e76-ab78-f2ed9ae0a98b |  | textbox | Offset
text | 0dbfa9c9-4d19-561f-bcc2-60a8315c3cdc |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Preparation Works
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 176f0aad-333a-5436-84e3-9a65a4772af8 |  | note | REQUIREMENTS / REFERENCE: Project Safety Plan, Project Environment Plan
label | b891f9e2-a249-586c-a035-779ada84267b |  | note | ACCEPTANCE CRITERIA:
label | 2e68ae08-7fa7-589d-99a4-d3767c062ab2 |  | note | • All site personnel inducted, required SWMS completed and signed, Safety Plan approved
label | 0f5c0325-da3a-51b6-96c1-38387b4425ad |  | note | • ERSED controls installed on site, air quality visually monitored for dust etc due to construction activities, Environment Plan approved
label | c3591120-e408-5208-8290-fe9ff912c1c6 |  | note | • Contact DBYD and complete excavation permit, extent of works set out with survey pegs
checkpoint-group |  |  | section | 2 - Pre-start Documentation
checkpoint-status |  |  | checkpoint | VERIFICATION
label | ee5a23d9-4a56-55b6-bbb6-d4eede03eb5a |  | note | REQUIREMENTS / REFERENCE: Project Specific Specifications
label | 925796b7-5c16-566e-be45-94dd303c9921 |  | note | ACCEPTANCE CRITERIA:
label | 3a06af16-dae5-5ecb-8ac9-cbeb44b203b9 |  | note | • Submit the following as per the Project Specific Specification:
label | 087105f3-3412-5a81-bdbb-e71c6acb4e48 |  | note | o All security required under the Contract
label | 6db26bf7-4311-5b4d-97eb-8a8d05204941 |  | note | o Evidence of all insurance required to be effected and maintained
label | 6f1f00ae-5bff-56c2-8cd7-29dd652ae40c |  | note | o Contract Program
label | 1f1b3f29-5492-55be-be53-02dfa82f52e5 |  | note | o Work Health and Safety Management Plan
label | 539e86bd-e3d0-5747-854a-35a2bc7ade7d |  | note | o Construction Environmental Management Plan
label | af50ed38-d87c-5607-82e9-1c9dd14b6ab0 |  | note | o Quality Management Plan
label | 694a8815-8036-5481-8ba0-e7e951399536 |  | note | o Staging Plan
label | 928cf2ca-f951-53d8-91d7-d79a00553333 |  | note | o Traffic and Pedestrian Management Plan
label | dcaceb94-45e2-5a15-b5d9-6bda2b952186 |  | note | o Dilapidation Report
checkpoint-group |  |  | section | 3 - Site Compound Facility Details
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 9d1d8756-fb89-52b8-9924-e87e79c3f80a |  | note | REQUIREMENTS / REFERENCE: Project Specific Specifications
label | cbf3bc14-b0de-51be-8a62-f2c9e778fc6c |  | note | ACCEPTANCE CRITERIA:
label | 7a5269f1-5f8a-5959-bb7d-b55735f26334 |  | note | • HOLD POINT: Submission of site compound facilities details including location, arrangements and appearance
text | 44ea4cd4-0cab-5ead-903d-084fbe95543f |  | textbox | HOLD POINT NUMBER:
text | 9a79c852-a7f5-52e7-8a5a-191ef6e98583 |  | textbox | DATE SUBMITTED:
text | 4d81e75a-3da6-5fce-8c8c-8a120dc76935 |  | textbox | SUBMITTED BY:
text | 0681c85a-4955-5d88-a69c-5c80dcfd7029 |  | textbox | SPECIFICATION AND CLAUSE:
text | 3a2ffa17-a06d-519f-935e-cf1c5a42871b |  | textbox | HOLD POINT DESCRIPTION:
text | 25df814a-7748-5de3-8cea-aa874d5e5f30 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 4 - Client Accommodation Details
checkpoint-status |  |  | checkpoint | HOLD POINT
label | e12752ad-16b0-5962-be9d-9a4edb531655 |  | note | REQUIREMENTS / REFERENCE: Project Specific Specifications
label | ee076bb0-c12a-51ec-8533-8cf773bdfbab |  | note | ACCEPTANCE CRITERIA:
label | fc279e1a-37eb-57a9-894b-585d37df9776 |  | note | • HOLD POINT: Submission of Client accommodation details including location in relation to dust and noise generating activities, layout of compound, internal layout of buildings, furniture provided, security measures, program for its construction
text | d5af025b-154a-50c3-a36e-cce3727878a6 |  | textbox | HOLD POINT NUMBER:
text | c791444f-02a3-5d5c-bd5f-7f9eb1cc3fc1 |  | textbox | DATE SUBMITTED:
text | c81e30d9-de6a-5e82-865b-ad0daf5b3d5d |  | textbox | SUBMITTED BY:
text | e742faed-5436-5349-8deb-58eebe123d20 |  | textbox | SPECIFICATION AND CLAUSE:
text | 80e90593-c627-582f-8106-4d2094486886 |  | textbox | HOLD POINT DESCRIPTION:
text | 66fa63c3-f62e-5999-9910-04cca96e9e88 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 5 - Environmental Management Plan
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 773cf8b5-4ac8-597a-9600-45aee091e1e1 |  | note | REQUIREMENTS / REFERENCE: 0173
label | 13a27103-ccaf-55ba-a3c6-7eedab8dd430 |  | note | ACCEPTANCE CRITERIA:
label | 6a39d906-d039-5851-ade3-9ebf739d08ed |  | note | • Submit the following as per WCC 0173:
label | b6ee1a8c-cafa-5667-8fbc-7b29fa8e8add |  | note | o Environmental Management Plan (EMP) (HP)
text | 0324399d-6aab-5b84-b843-fd472d9157bb |  | textbox | HOLD POINT NUMBER:
text | 759c71b3-61f6-561a-a50a-ddddd928e577 |  | textbox | DATE SUBMITTED:
text | 8c80e1c6-9c8e-5458-949b-dd6c97762a2e |  | textbox | SUBMITTED BY:
text | 9647f2e9-0adf-546c-baf2-7aa56674956f |  | textbox | SPECIFICATION AND CLAUSE:
text | a963d0be-9137-5dfd-b419-888cea4691dd |  | textbox | HOLD POINT DESCRIPTION:
text | c11e869c-f7a8-53bf-b46e-1bd8c03f6edb |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 6 - Unexpected Finds
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 65cd1165-29eb-5313-ae0e-836f330858ea |  | note | REQUIREMENTS / REFERENCE: 0173
label | 29f3b4d3-f77a-585f-96fb-df657d8a06e2 |  | note | ACCEPTANCE CRITERIA:
label | 629ffb88-cfc0-5259-b8fe-618cc7a873f0 |  | note | • Submit the following as per WCC 0173:
label | ddbd6758-f9e6-5532-82df-f35c260bdb67 |  | note | o Details of any unexpected finds (HP)
text | 510cff7e-1dfb-5a8a-84f3-7b09c8c08d86 |  | textbox | HOLD POINT NUMBER:
text | b7db3a17-42e9-562d-aa5a-ec1dd8f56627 |  | textbox | DATE SUBMITTED:
text | e43db6a2-d78d-543f-ba51-7e948ce7f1b4 |  | textbox | SUBMITTED BY:
text | f3518f27-0fa7-50da-8816-e952b7d13090 |  | textbox | SPECIFICATION AND CLAUSE:
text | 32ed6d4f-d91e-589b-b025-01f6a31865f9 |  | textbox | HOLD POINT DESCRIPTION:
text | fb6d4c3d-a106-57f0-8f6f-ecf7a310916e |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 7 - Non-Conforming Items
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 8f9bd564-c4fc-5438-9a95-ca0adb6d4e5a |  | note | REQUIREMENTS / REFERENCE: 0173
label | 08e9833a-94f0-528d-963d-c5a9d6627261 |  | note | ACCEPTANCE CRITERIA:
label | 5813a6ed-9179-51a1-9edb-9a9d5dc47ead |  | note | • Submit the following as per WCC 0173:
label | 85f0da98-c54e-520f-bde9-41ece9819605 |  | note | o Details of any non-conforming items (HP)
text | 5475cd20-62e4-5422-a8c9-5785a1ec3f96 |  | textbox | HOLD POINT NUMBER:
text | c2ff3f61-ff66-5331-8637-dfc210024984 |  | textbox | DATE SUBMITTED:
text | a455d3e1-5551-534d-b4ac-5d57c9f64850 |  | textbox | SUBMITTED BY:
text | ef5863f8-da36-5be1-a877-dec7fe34639c |  | textbox | SPECIFICATION AND CLAUSE:
text | d5edc995-9c37-500c-a390-6e098746c027 |  | textbox | HOLD POINT DESCRIPTION:
text | 40a59e44-f59b-5b2f-a872-105db98e0426 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 8 - Removal or Rectification of Enviro. Issues
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | cba12058-961e-5d84-95dd-d7bb77f39e2f |  | note | REQUIREMENTS / REFERENCE: 0173
label | bdcf0c7f-1bcd-534b-87ce-79919aa306c8 |  | note | ACCEPTANCE CRITERIA:
label | 095c786a-e4db-5367-8a84-e73bf4663a50 |  | note | • Submit the following as per WCC 0173:
label | 03278215-9e57-5ee4-85ce-863ebe8a65ad |  | note | o Invitation to witness completion of removal or rectification of environmental issues (WP)
text | 390df54a-de72-5882-8199-4521a1a1d157 |  | textbox | WITNESS POINT NUMBER:
text | 829bedcd-9b81-5581-9b75-99151a6d18ba |  | textbox | DATE SUBMITTED:
text | 0b00887a-c8bd-5298-ad98-4916bcdd66eb |  | textbox | SUBMITTED BY:
text | ad7903fd-89fe-5f04-92c9-f10ff87dde64 |  | textbox | SPECIFICATION AND CLAUSE:
text | 748e7b75-a10e-54c5-afe3-eac55c7a871a |  | textbox | WITNESS POINT DESCRIPTION:
text | e3f8c4ef-b21d-5528-99ef-e5bcaa285908 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 9 - Submission of Control Plans
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 8e90f734-09b8-58b1-8a67-1f7717460747 |  | note | REQUIREMENTS / REFERENCE: 0173
label | 5921e60b-eba5-5a12-9774-259f8149faab |  | note | ACCEPTANCE CRITERIA:
label | 810d050f-fb13-586f-8192-dd886576b8a8 |  | note | • Submit the following items as per WCC 0173:
label | 68ef4679-7b08-534d-8af3-b37192df97ed |  | note | o Ground contamination control plan
label | 04aa4265-95fb-58a4-84ae-b4d225ff96bf |  | note | o Air quality control plan
label | ebab7a9f-331a-56e9-a477-d887dc18870f |  | note | o Water quality control plan
label | 428417c0-b6ff-5dbf-9256-b78d348f8f35 |  | note | o Noise and vibration control plan
label | bdb71adb-5f07-51f8-9e3f-982d6b5265d7 |  | note | o Flora and fauna control plan
label | 8b144770-3c01-59a0-94ad-2c4e87c5e6c7 |  | note | o Cultural heritage management plan
label | 7a056620-f234-5afb-a464-8d64cca4b33a |  | note | o Weed management control plan
label | fd47e062-4bae-545b-a799-d678e1aa3a48 |  | note | o Erosion and sediment control
checkpoint-group |  |  | section | 10 - Submit ESCP
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 78b8871d-3aae-5779-b9c6-5672bb1a7aab |  | note | REQUIREMENTS / REFERENCE: 1102
label | 3e770b0a-6b42-5e07-8b87-107aa7cf5cee |  | note | ACCEPTANCE CRITERIA:
label | 473fb76b-918d-56b0-a021-4cc861cfb2d6 |  | note | • HOLD POINT: Submit ESCP as detailed in 1102
text | 6098bc27-749d-5cfd-96d9-44a5f75f2b6e |  | textbox | HOLD POINT NUMBER:
text | 498df652-43ca-538a-a81d-3281c24977a1 |  | textbox | DATE SUBMITTED:
text | 7cff758c-f4eb-5d69-9ec1-3c997319f1e0 |  | textbox | SUBMITTED BY:
text | 0491ccc3-a344-5742-92d3-70fe98bbf508 |  | textbox | SPECIFICATION AND CLAUSE:
text | 4075c7b9-9f05-5395-88b5-ab25658e0ca6 |  | textbox | HOLD POINT DESCRIPTION:
text | 5156c071-559b-5d00-beeb-bd7bd7454531 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 11 - Submit embankment survey
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 116dca58-2e49-5804-9529-9283bc3fd544 |  | note | REQUIREMENTS / REFERENCE: 1102
label | ea2c29cb-6f96-5de6-a097-a1f06907f7a6 |  | note | ACCEPTANCE CRITERIA:
label | 6750bbdc-dc5f-56d4-be95-b44c8e15cfd1 |  | note | • HOLD POINT: Submit a survey of embankments
text | 5b17cf03-659f-5034-9dbd-7fdb7a5f4546 |  | textbox | HOLD POINT NUMBER:
text | 5d029b47-1c71-553b-9147-470965b3229f |  | textbox | DATE SUBMITTED:
text | 05008898-3694-55bc-ae08-64f552aacc8f |  | textbox | SUBMITTED BY:
text | e339d723-bac8-50b2-b0b5-c972685677f1 |  | textbox | SPECIFICATION AND CLAUSE:
text | 037c2d5f-4c30-5dfe-9f09-a121d1a52ebb |  | textbox | HOLD POINT DESCRIPTION:
text | 17254bc8-f058-51c4-81dd-d6f4be1c266d |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 12 - Submit section plans
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 2815ec4e-9bb2-5265-9572-fe8af29f46c8 |  | note | REQUIREMENTS / REFERENCE: 1102
label | 8b9ec037-fbe2-550f-8a66-94c1b01fad8a |  | note | ACCEPTANCE CRITERIA:
label | 3a9023b2-07a5-5bfb-b077-5d0aad98bdca |  | note | • HOLD POINT: Submit section plans
text | 46d501fc-fd32-5add-98af-0b7b1f1123d8 |  | textbox | HOLD POINT NUMBER:
text | 3b53e5bc-2c17-5134-95bd-222776b7e1a2 |  | textbox | DATE SUBMITTED:
text | 7d892727-85ec-572f-8249-d31ea652ee60 |  | textbox | SUBMITTED BY:
text | 3daef1ab-e591-542f-86e8-93caaca77b34 |  | textbox | SPECIFICATION AND CLAUSE:
text | f7d9a28e-67d8-5730-b168-4982b6dcf728 |  | textbox | HOLD POINT DESCRIPTION:
text | 1a00dcf4-4807-51c9-a775-0981d4c45bf5 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 13 - Initial install of sediment controls
checkpoint-status |  |  | checkpoint | HOLD POINT
label | b61138d7-4114-5f13-afe3-12d9e7f14717 |  | note | REQUIREMENTS / REFERENCE: 1102
label | 3842204a-0438-5c3d-acbc-5e204865a691 |  | note | ACCEPTANCE CRITERIA:
label | 78ae8f86-5c9a-5176-b509-5d35f63138ee |  | note | • Give inspection notice for:
label | d46ffaf2-df55-5e42-af9b-c6d160049893 |  | note | o Initial installation of sediment controls (HP)
text | 32c02115-c253-5b41-900a-32bcd4f01588 |  | textbox | HOLD POINT NUMBER:
text | cb447e0c-bf8d-5b03-b04e-24db2d8d8e04 |  | textbox | DATE SUBMITTED:
text | 50723a9e-91e5-54e9-9169-0e701c34cf19 |  | textbox | SUBMITTED BY:
text | a4c6596a-807f-53aa-8d41-b8a28762e031 |  | textbox | SPECIFICATION AND CLAUSE:
text | 7c5d6a71-812a-5c31-92b9-e5491341ce11 |  | textbox | HOLD POINT DESCRIPTION:
text | eae8cb70-3116-5ad9-920b-841d5bc27f36 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 14 - Stockpile protection measures
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 7b93479e-a08c-57e0-afa9-68db08ba5d12 |  | note | REQUIREMENTS / REFERENCE: 1102
label | 590c6347-a5c5-526e-9538-efde4517cd9d |  | note | ACCEPTANCE CRITERIA:
label | 62d756f4-bf80-53ff-b950-d2e384e969d6 |  | note | • Give inspection notice for:
label | 1298e4d9-1a32-5821-b27d-821fe6c71bfc |  | note | o Stockpile protection measures in place (WP)
text | 65f4b3c6-88af-5b56-834b-555740d5b3bb |  | textbox | WITNESS POINT NUMBER:
text | 751ef131-48c5-58f5-be9f-8ab10d138758 |  | textbox | DATE SUBMITTED:
text | ce3eedb4-ad93-511c-9362-95f2da1acb76 |  | textbox | SUBMITTED BY:
text | 5ddc1e06-85ff-5c91-a4cd-d83a5066fa27 |  | textbox | SPECIFICATION AND CLAUSE:
text | 1c9bc8b0-bcb5-513d-8e1b-d2bd867e2058 |  | textbox | WITNESS POINT DESCRIPTION:
text | b1f834d7-c4a0-5a55-a846-989cb2c1bb30 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 15 - Site access and exit vehicle decontam.
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 2f7c638e-94e4-5824-a50e-d2b8b008cd40 |  | note | REQUIREMENTS / REFERENCE: 1102
label | 88ad975b-20be-52f9-9323-2228a0da5a19 |  | note | ACCEPTANCE CRITERIA:
label | 8b1c9c7d-4df4-53ac-a664-92c4359318a2 |  | note | • Give inspection notice for:
label | ff390a53-a7b6-5ebc-9648-e86c1449ef59 |  | note | o Access and exit areas – Decontamination of vehicles (WP)
text | 92651e82-16eb-5a6e-88c0-a47f110d9ef8 |  | textbox | WITNESS POINT NUMBER:
text | 224049d0-27b4-500a-a0d4-2223a3a424c2 |  | textbox | DATE SUBMITTED:
text | 83f183f2-6494-54a6-86ab-e273a8a4e549 |  | textbox | SUBMITTED BY:
text | bf48c8e3-6a84-504f-af9c-4e1c42b9b6ed |  | textbox | SPECIFICATION AND CLAUSE:
text | 55c33abb-28a7-544f-9575-2b4e93758bf2 |  | textbox | WITNESS POINT DESCRIPTION:
text | b38e389a-91a1-503b-970b-ee7e19413c2e |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 16 - Fencing and protection of areas
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 48cbfeae-e5b8-51b4-8211-bc9f3a3623c9 |  | note | REQUIREMENTS / REFERENCE: 1102
label | 5b39082c-7199-5abd-9c23-18fca91f2497 |  | note | ACCEPTANCE CRITERIA:
label | 32d24a7d-4af8-54ef-9835-676d0114dc97 |  | note | • Give inspection notice for:
label | d3b16a62-b89c-55d8-ae6f-f518e254784f |  | note | o Fencing and protection of areas (WP)
text | b8ce5390-8c6d-5e8c-9dd7-ed406a14c8d4 |  | textbox | WITNESS POINT NUMBER:
text | 0257aa83-a9d8-5f0e-bf64-c0d798bf5809 |  | textbox | DATE SUBMITTED:
text | f1399b15-d20d-5ae9-a82d-3f35eafaa789 |  | textbox | SUBMITTED BY:
text | 266ad932-1ea8-592c-8a93-e4b71da29ff2 |  | textbox | SPECIFICATION AND CLAUSE:
text | 94b89846-8222-55c0-ba0d-2365266afd70 |  | textbox | WITNESS POINT DESCRIPTION:
text | e1add999-86ef-5a84-86cc-2034ede2cfe3 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 17 - Construction and lining
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | b290c607-ab3b-5a4e-9389-ec69871aa394 |  | note | REQUIREMENTS / REFERENCE: 1102
label | e55f48ef-1d67-52a4-96cf-9c14eacfe1ad |  | note | ACCEPTANCE CRITERIA:
label | a5295832-147f-5da0-8dbf-1e2cf9fe1949 |  | note | • Give inspection notice for:
label | 66389cdf-75a8-5b32-af23-fd9334995e5c |  | note | o Construction and lining (WP)
text | 24da7ab3-f2f3-5603-b638-db44c08689f0 |  | textbox | WITNESS POINT NUMBER:
text | 9eef68a2-d47b-5f4e-9982-dc58317ca287 |  | textbox | DATE SUBMITTED:
text | c565304d-0d24-56ad-8de7-fcedb120a187 |  | textbox | SUBMITTED BY:
text | 4358814d-1b86-5053-9ade-4ebb2f4b114b |  | textbox | SPECIFICATION AND CLAUSE:
text | 4d251ddb-8c1e-5e79-be85-56999ebc1750 |  | textbox | WITNESS POINT DESCRIPTION:
text | 631559a3-1e6e-5c9f-b598-26de1fcaa915 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 18 - Temporary sediment traps
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 021c708d-819e-59f9-b7f2-85ed55bdeb52 |  | note | REQUIREMENTS / REFERENCE: 1102
label | ff601b55-380a-5878-9251-4c855b9eb07d |  | note | ACCEPTANCE CRITERIA:
label | 066d6c9c-a583-5cc2-aa4c-8e697d85052a |  | note | • Give inspection notice for:
label | eac2368f-b540-5793-8167-d7bf692bfb54 |  | note | o Temporary sediment traps and batter protection (WP)
text | 2d0175ab-ba4b-5ed6-ac78-c1f002e59c1c |  | textbox | WITNESS POINT NUMBER:
text | b49c0ae9-5a3b-5f9f-b13c-988f64e1fc70 |  | textbox | DATE SUBMITTED:
text | 91bff1d4-d8c5-599e-9510-3a3b18e160cb |  | textbox | SUBMITTED BY:
text | 2a79bf25-5e09-5ce0-97ec-cfc3b4624a7d |  | textbox | SPECIFICATION AND CLAUSE:
text | b2f416e6-1d1c-5ed3-9667-9a1712f94306 |  | textbox | WITNESS POINT DESCRIPTION:
text | 266acfd9-d4ff-53c7-a006-62f4db3de650 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 19 - Removal of temporary ERSED controls
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | d207c190-a2e7-58f2-8dc3-30ce13c57005 |  | note | REQUIREMENTS / REFERENCE: 1102
label | 1e54d9c7-db33-5970-93e3-1acceb73c273 |  | note | ACCEPTANCE CRITERIA:
label | 5f4cb74c-13c7-553c-9706-e60f266a32c4 |  | note | • Give inspection notice for:
label | f7293c7e-546b-563a-804e-caa1543d3374 |  | note | o Removal of temporary erosion and sedimentation works (WP)
text | 2add5c67-b608-5940-ba39-3d967140caf9 |  | textbox | WITNESS POINT NUMBER:
text | 13a78d58-a72c-553d-8aca-a227ff30cddc |  | textbox | DATE SUBMITTED:
text | a2c95444-431a-5b9d-bb86-243229fa5857 |  | textbox | SUBMITTED BY:
text | bae2dceb-a7a8-5650-b5b3-1b4b7b9a2c7c |  | textbox | SPECIFICATION AND CLAUSE:
text | 4cf9dbe2-4c75-55e0-8807-f03ae31d34bf |  | textbox | WITNESS POINT DESCRIPTION:
text | 28d6cf18-b5b4-568f-b9da-fff4dbeeef3a |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 20 - Completion of cleaning
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | a0c672d4-5d1a-5b82-9bd1-90cd31ba6fc3 |  | note | REQUIREMENTS / REFERENCE: 1102
label | 91ceeb10-42bf-55bd-aa9d-8b1bf0ee3213 |  | note | ACCEPTANCE CRITERIA:
label | de39fe35-bbf0-50b2-b888-5f6303fe942d |  | note | • Give inspection notice for:
label | fdb3fa98-2e0f-533a-aa46-271a9ab861f6 |  | note | o Completion of cleaning (WP)
text | 9cb5172f-8bef-5563-802d-8e1cda608a55 |  | textbox | WITNESS POINT NUMBER:
text | b7754055-23e8-5e8f-a6ab-27a6c18484d0 |  | textbox | DATE SUBMITTED:
text | 73f46760-7242-5068-9078-9802da4fb143 |  | textbox | SUBMITTED BY:
text | 19d5a05c-b4de-5337-a9b9-c7a11865fe8a |  | textbox | SPECIFICATION AND CLAUSE:
text | 8aa1adbc-3272-58bf-9373-f8a158520b11 |  | textbox | WITNESS POINT DESCRIPTION:
text | 076aa3ee-cf6e-575c-a901-82c9d13dce12 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 21 - Inspection and Test Plans
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 342170a0-6795-579d-bbe4-70444e0fcf90 |  | note | REQUIREMENTS / REFERENCE: Project Specific Specifications
label | 599149c9-29e6-53ed-922e-54a0bd44f13a |  | note | ACCEPTANCE CRITERIA:
label | 6b76b0d5-340e-5db4-bbd5-ce927e7abf04 |  | note | • Submit ITPs two weeks before any work under construction
checkpoint-group |  |  | section | 22 - Protection of Surveyor Marks
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | d6fd84c0-2db5-594b-b432-9351344baaf0 |  | note | REQUIREMENTS / REFERENCE: 0136
label | 11d9cdea-dd99-5fc4-8b02-15757ecd6b92 |  | note | ACCEPTANCE CRITERIA:
label | ba3bdd72-1511-5633-9b10-d92d1854d910 |  | note | • Provide verification that all permanent survey marks have been identified
label | be08c09b-f3d6-5e07-b92f-c0731e17ef40 |  | note | • Preserve survey infrastructure as needed
label | 759160bc-f84f-5083-8805-5fff8cbcb42e |  | note | • WITNESS POINT: Obtain approval and transfer permanent surveyor marks clear of operations
text | 85486ae9-013b-5a61-8115-8f4ce70471b8 |  | textbox | WITNESS POINT NUMBER:
text | d2734243-58d9-512b-b1c3-fc442c1ecd59 |  | textbox | DATE SUBMITTED:
text | f7c1038c-5bfc-5e4b-ae5c-5b57e064c4e3 |  | textbox | SUBMITTED BY:
text | 6f55ebb1-b56e-5d37-a5d6-d51dc78256b5 |  | textbox | SPECIFICATION AND CLAUSE:
text | dd62e57f-2829-506f-9bf4-b0a79274a4ec |  | textbox | WITNESS POINT DESCRIPTION:
text | e82c18e2-18e1-5dc8-911d-a95cb4ee1a82 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 23 - Digital Design Model Discrepancies
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | c38e105d-4c29-534a-affb-f0aa4289e235 |  | note | REQUIREMENTS / REFERENCE: 0136
label | a483ac2e-34c1-5f84-ad8e-1200952ee4a1 |  | note | ACCEPTANCE CRITERIA:
label | fef012e6-40e6-5f8b-b1af-c6304305aa32 |  | note | • WITNESS POINT: Check the digital design model and notify Client of discrepancies between the model and the drawings
text | 714e28f3-7ebd-5306-a86c-3601086c8909 |  | textbox | WITNESS POINT NUMBER:
text | 552c24da-b8b0-5a7c-adb2-e6c2771c104a |  | textbox | DATE SUBMITTED:
text | aa53c178-4e67-5aae-957a-06f5ed5baa1a |  | textbox | SUBMITTED BY:
text | c80a84ef-bc76-549f-b645-89ae1dd6b39b |  | textbox | SPECIFICATION AND CLAUSE:
text | 2ba50e3c-2b9b-5215-983b-958ff5408a85 |  | textbox | WITNESS POINT DESCRIPTION:
text | 86c47b1b-1af5-55eb-8a90-c5cc907ce150 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 24 - Adjoining Property
checkpoint-status |  |  | checkpoint | VERIFICATION
label | ef2d5abe-1967-5307-9a4d-d6eb0c38cac4 |  | note | REQUIREMENTS / REFERENCE: 0136
label | 5fffe418-12c5-509b-a236-9798b01f6a0b |  | note | ACCEPTANCE CRITERIA:
label | 11002b7c-82bb-5005-ae40-15fceb811c24 |  | note | • Submit to owners and occupants of adjoining property written notice of intention to commence work and an outline description of the type and extent of works
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | 4106bad4-3f2e-553c-af55-87faf0eb4762 |  | textbox | Lot Verified By:
text | 7a538252-985e-5abb-8f69-038b2faa4780 |  | textbox | Lot Closed Date:
button | c8ce5239-a38d-57d3-92a7-9e947a07b724 |  | button | Submitted to Client | Yes, No, N/A
button | 6546e41f-3e90-5d93-a910-ae921088ca29 |  | button | Reviewed by Client | Yes, No, N/A
text | 14055c5f-4a60-5282-883a-4b7d9232cc3c |  | textbox | Submission Comments:
checklist-sectioned |  |  | checklist | A181 - West Dapto - ITC 006 (ITP006) - Open Drains |  |  |  |  | Yes | A181 - West Dapto - ITC 006 (ITP006) - Open Drains | 2a50fd99-7630-45d8-81bb-973aacf0a242
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | 6495da2e-b526-5d00-8eed-902aa0fef0f8 |  | textbox | Lot Opened On
text | 082a29d2-d429-5c94-828f-eeddb89bd773 |  | textbox | Date of Works
text | f30ccfc7-beb9-56d1-bb46-c6a3c1c653ef |  | textbox | Lot Type
text | 9e81d2c1-1c4c-56e0-a6bf-c59d42402d93 |  | textbox | Start Chainage
text | 209dfaa9-2bd0-54f4-8892-506f136ee547 |  | textbox | End Chainage
text | 413357f1-8c50-4df6-86e1-2cdf332cc7d2 |  | textbox | Offset
text | 96a81a88-a083-5f74-84d1-6fe8c715f8c1 |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Preparation Works
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 08f05b0f-9838-509a-bd61-bcdf069db4de |  | note | REQUIREMENTS / REFERENCE: Project Safety Plan, Project Environment Plan
label | c21bf410-e7a0-5e1c-b41a-e0be80896360 |  | note | ACCEPTANCE CRITERIA:
label | 57cf1d33-d413-50c8-b4d6-ffe6ce06ce20 |  | note | • All site personnel inducted, required SWMS completed and signed, Safety Plan approved
label | 5ba4e6ec-8c32-5215-8899-d1a67950ec91 |  | note | • ERSED controls installed on site, air quality visually monitored for dust etc due to construction activities, Environment Plan approved
label | ae7f6255-ab10-5de9-bd0b-67c010d22942 |  | note | • Contact DBYD and complete excavation permit, extent of works set out with survey pegs
checkpoint-group |  |  | section | 2 - Road Opening Permit
checkpoint-status |  |  | checkpoint | HOLD POINT
label | d117fa12-d163-57b9-a33b-86af16afac6d |  | note | REQUIREMENTS / REFERENCE: WCC 1121 Annex. 4.1
label | aac68717-f2cc-57e6-93ac-1b41a8e950ab |  | note | ACCEPTANCE CRITERIA:
label | bc3acab4-38c3-5712-ab9d-f88197352034 |  | note | • HOLD POINT: 10 days prior to commencement on site, submit to the Principal, a road opening permit
text | d93b632e-8d63-5633-8947-7add33817d94 |  | textbox | HOLD POINT NUMBER:
text | aa4f8c89-6f0f-53a8-90ec-e15c51452f15 |  | textbox | DATE SUBMITTED:
text | 70df9d0d-21e7-582d-813e-2cf54f514b84 |  | textbox | SUBMITTED BY:
text | b64eb3ca-548f-5e73-ac11-3fa465d75ee3 |  | textbox | SPECIFICATION AND CLAUSE:
text | 7aa7451f-3aeb-5dbb-9aa8-37020424c172 |  | textbox | HOLD POINT DESCRIPTION:
text | 662f8164-05c3-5392-b574-a228c98ddc0b |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 3 - Materials
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 2bf4fd2a-ea00-5912-af51-cf5a1fa720cc |  | note | REQUIREMENTS / REFERENCE: WCC 1121 Cl 2.5
label | 06ae2131-ac55-5221-8cfc-692f3fba29f3 |  | note | ACCEPTANCE CRITERIA:
label | 6745e933-46f9-5605-8e36-c425a25621ce |  | note | • Geotextile material conforms to requirements of Project Drawings and Specifications
label | cd4c3707-b1e9-56d3-aae1-3cb2d6ce11fe |  | note | COMMENTS / ATTACHMENTS: Details of geofabric / geotextile used on site
checkpoint-group |  |  | section | 4 - Temporary Drainage
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 356cd24d-cf29-52c5-a821-dd535aecc76a |  | note | REQUIREMENTS / REFERENCE: WCC 1121 Cl 1.4
label | bfa74792-86d7-5990-8d35-fb8419951819 |  | note | ACCEPTANCE CRITERIA:
label | 0432c1d1-6477-5558-8ff5-0f2c4ee3b0e6 |  | note | • HOLD POINT: Submit details of procedures / devices to maintain effective drainage of the work area during construction, 10 days prior to site commencement
text | cbc52f43-e415-5133-b847-d092bbdef03b |  | textbox | HOLD POINT NUMBER:
text | 671d2f31-0abf-5f73-9a0d-3d5ec550e687 |  | textbox | DATE SUBMITTED:
text | 28fed00b-c09d-5a1b-ae01-69289aedb40a |  | textbox | SUBMITTED BY:
text | 04ac033c-97d5-5056-8005-bc2ed8115b23 |  | textbox | SPECIFICATION AND CLAUSE:
text | 85b2d0e4-a347-511d-9b8d-c0d6e22fb014 |  | textbox | HOLD POINT DESCRIPTION:
text | 60cd3a2c-af35-5143-aa48-d8d9da937659 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 5 - Open Drain Set-out
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 46863df6-3e8c-5d29-a7e3-d7907d533bde |  | note | REQUIREMENTS / REFERENCE: WCC 1121 Annex. 4.1
label | 73611402-da7c-56ca-b61c-6b213561b733 |  | note | ACCEPTANCE CRITERIA:
label | bf7526ba-3b3e-5e80-ad43-2f8d2917f45c |  | note | • HOLD POINT: 5 days prior to set-out of the open drain, submit to the Principal details of any changes to the design of the open drain (if required)
text | 1acc0bcb-6682-5cbf-b63d-56a119c63654 |  | textbox | HOLD POINT NUMBER:
text | d8986dd4-006a-5c55-99a2-03c72a738e02 |  | textbox | DATE SUBMITTED:
text | 4e71bab9-4b0c-5c60-ba43-f02ec9791ff1 |  | textbox | SUBMITTED BY:
text | 02bd158f-efaa-5f2a-a3bc-d26d3a580d5b |  | textbox | SPECIFICATION AND CLAUSE:
text | b3073c75-f675-5cb8-bccf-fd601032115f |  | textbox | HOLD POINT DESCRIPTION:
text | 777dcccb-5701-5610-86b6-22e15708f8b8 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 6 - Set-out of Open Drains
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | daff0efa-e61d-571a-9fb4-4c44c73af341 |  | note | REQUIREMENTS / REFERENCE: WCC 1121 Cl 3.1
label | bc603e68-36b6-5328-965b-9f13f2380c71 |  | note | ACCEPTANCE CRITERIA:
label | 33eca7dc-fa3b-540c-bf75-4b8ba2eba0a2 |  | note | • WITNESS POINT: 3 days prior to set-out, provide a notice of inspection to the Principal
text | f2105c2c-45c7-53d1-be64-9476e7525eaf |  | textbox | WITNESS POINT NUMBER:
text | 34a60990-5e53-5c43-b13e-5559491d785f |  | textbox | DATE SUBMITTED:
text | 80cd742c-7ab2-50c8-b445-f8598da48c93 |  | textbox | SUBMITTED BY:
text | eafc526c-b689-5fb7-a1c9-fd69006d91fb |  | textbox | SPECIFICATION AND CLAUSE:
text | 4a83c898-a18a-58bb-8d71-ff0b584c3378 |  | textbox | WITNESS POINT DESCRIPTION:
text | ba576015-b21c-5822-a539-1fda9efee10a |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 7 - Location of Open Drains
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | d29a90b5-73a3-561f-a136-78d6b6207401 |  | note | REQUIREMENTS / REFERENCE: WCC 1121 Cl 3.2
label | 761f2baa-f239-5665-ab40-4088f2769a12 |  | note | ACCEPTANCE CRITERIA:
label | 0f4d430e-716d-59a9-a2e6-f8f68b655297 |  | note | • WITNESS POINT: 1 day before setting out, provide notice to the Principal of the location of open drains
text | 2c476a48-5b81-565f-a008-f7f5f4c97bad |  | textbox | WITNESS POINT NUMBER:
text | c58131ae-5783-5075-88be-9a44971125da |  | textbox | DATE SUBMITTED:
text | aeda4423-bdbc-5879-a70a-29e5fc9d8217 |  | textbox | SUBMITTED BY:
text | 33624509-3b25-55d3-a0c1-e9b7c67b2b14 |  | textbox | SPECIFICATION AND CLAUSE:
text | 6b762bf3-db5f-535e-8c1b-22b517d79471 |  | textbox | WITNESS POINT DESCRIPTION:
text | c23067a4-36ff-5368-857d-01177b3b66a8 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 8 - Excavation of Open Drains
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | cafb387b-60e3-5ab5-8721-3d5610446022 |  | note | REQUIREMENTS / REFERENCE: WCC 1121 Cl 3.2
label | 83b11783-9cba-5732-a65d-a936427cb7b7 |  | note | ACCEPTANCE CRITERIA:
label | 124fc25b-157c-53ee-81d1-c2d51c46f423 |  | note | • WITNESS POINT: Provide notice to the Principal of the grade of the excavated open drain
text | 4348cd9e-4d74-5ba1-b27e-72d66b73b584 |  | textbox | WITNESS POINT NUMBER:
text | 66ec4edb-a9a7-5e93-ab5f-bcc907714d2a |  | textbox | DATE SUBMITTED:
text | 51f4a2d1-0b96-52f6-a3a3-11a89639b77c |  | textbox | SUBMITTED BY:
text | ca1aa669-5681-5ed0-9892-bb316e48b29d |  | textbox | SPECIFICATION AND CLAUSE:
text | a237082d-633e-5026-a91e-fee2759e57fb |  | textbox | WITNESS POINT DESCRIPTION:
text | a866910b-4d2d-5633-ae8a-0ef0e0f68e1a |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 9 - Excavation below natural channel
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 5719ba49-5cc8-5940-bf91-4961660e8f61 |  | note | REQUIREMENTS / REFERENCE: WCC 1121 Cl 3.2
label | f60fbebf-1f85-5e48-959c-9233565d7ca6 |  | note | ACCEPTANCE CRITERIA:
label | 993fba10-c6d8-5e53-b270-ae4d2e5a3c21 |  | note | • WITNESS POINT: In the event of overexcavation or excavation below the level of the natural channel, backfill with suitable material and compact. Provide notice of the Principal of backfilling with suitable material (if applicable)
text | 163b5739-7cb4-5835-9194-117ea9f0e929 |  | textbox | WITNESS POINT NUMBER:
text | 0b2e0584-555e-5dbd-93d8-d233754a57b2 |  | textbox | DATE SUBMITTED:
text | 697cd21e-4ee7-5768-855c-59c7df1ad4e7 |  | textbox | SUBMITTED BY:
text | 8ee600f2-8c6d-5f48-8ac0-4f7b1293d9c0 |  | textbox | SPECIFICATION AND CLAUSE:
text | 10e9f316-317a-50e0-8119-c1d368d585b4 |  | textbox | WITNESS POINT DESCRIPTION:
text | 6cf58275-d7ff-58e1-b744-c88d0a7858fe |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 10 - Surplus Material
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 56abf469-1b53-5a07-bac6-0b4db98f16b5 |  | note | REQUIREMENTS / REFERENCE: WCC 1121 Cl 3.2
label | 6c8a6dd9-7250-58ff-addb-d1818d02138c |  | note | ACCEPTANCE CRITERIA:
label | 9fd10e8b-71e2-567b-ae6a-071693e1b5aa |  | note | • WITNESS POINT: In the event of surplus material, place excavated material to form embankments to lower side of drains or remove spoil stockpiles as required. Provide notice to the Principal of backfilling with suitable material (if applicable)
text | 54566802-bb36-50a9-849f-2f3cd4650e22 |  | textbox | WITNESS POINT NUMBER:
text | 904b3e04-3f0a-553a-add3-03ceb2fab8ac |  | textbox | DATE SUBMITTED:
text | fa3ca8df-906f-5534-a75c-5e11f11d6d6a |  | textbox | SUBMITTED BY:
text | 6e537a7d-87d1-5fb9-bc24-cb0bb8ea2be0 |  | textbox | SPECIFICATION AND CLAUSE:
text | 04b82a4b-8707-57ab-b575-5846fb0ad43c |  | textbox | WITNESS POINT DESCRIPTION:
text | 4ee31229-18db-5d8b-8ddb-7f43f0c0b8c9 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 11 - Table Drains
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 2ee3b144-847b-5478-9b0d-9ff810bd387c |  | note | REQUIREMENTS / REFERENCE: WCC 1121 Cl 3.3
label | 23f78a6e-0805-5a51-8df9-f50bd0b9f897 |  | note | ACCEPTANCE CRITERIA:
label | dec6f7c8-b723-51eb-a719-ace5e43cee4d |  | note | • WITNESS POINT: Provide notice to the Principal of the location of table drains, swales and depressed medians (if applicable)
text | 142cb578-04a6-5103-9274-8edc23a7f458 |  | textbox | WITNESS POINT NUMBER:
text | 53f6ba7a-8fbd-5499-814e-5ab8a2111345 |  | textbox | DATE SUBMITTED:
text | bc4950a8-f90a-51ca-980d-6ac57efcb73a |  | textbox | SUBMITTED BY:
text | 31fd2788-0f1e-5836-970b-d11438498188 |  | textbox | SPECIFICATION AND CLAUSE:
text | 3d79bad2-3a9c-54ae-85c1-3f5eb8348cb9 |  | textbox | WITNESS POINT DESCRIPTION:
text | 2d64058f-2740-54ee-8471-c00c14c00dfd |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 12 - Compaction
checkpoint-status |  |  | checkpoint | VERIFICATION
label | f75768bf-9fd3-5221-b23e-617af43315c1 |  | note | REQUIREMENTS / REFERENCE: WCC 1121 Cl 3.2
label | 15bc86e5-a6c9-5f95-9a02-0cc0a41428eb |  | note | ACCEPTANCE CRITERIA:
label | 78733fa6-0f25-5a47-ba56-687e78b866fb |  | note | • Compact the excavated material to no less than 95% for standard compactive effort, to AS 1289.5.4.1
label | cefee46d-75ed-57fa-9046-609bcf4a4fc2 |  | note | COMMENTS / ATTACHMENTS: Compaction test results
checkpoint-group |  |  | section | 13 - Completion of Works
checkpoint-status |  |  | checkpoint | VERIFICATION
label | be893376-56d3-53c1-9368-e57a289c24fa |  | note | REQUIREMENTS / REFERENCE: WCC 0257 Cl 3.4
label | e54886f4-dbfe-56fe-8995-492c6df8df7c |  | note | ACCEPTANCE CRITERIA:
label | 9f8f565a-30b0-5373-8d25-850c5080ed88 |  | note | • Spread topsoil, line channel with organic fibre mat or geotextile as per Project Drawings and Specifications
label | 15eef748-4194-5d36-9f39-d8329de7ba45 |  | note | • Complete any vegetation within 7 days of the open drain excavation
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | 999007d0-de7f-5941-b672-c0d7d739459f |  | textbox | Lot Verified By:
text | d61bea69-fd7b-516a-a968-b37fce9363de |  | textbox | Lot Closed Date:
button | 22162097-dd95-5b3c-9a87-ccf82b8539a8 |  | button | Submitted to Client | Yes, No, N/A
button | 75dec717-cdf8-51be-8cc3-b226800a52c5 |  | button | Reviewed by Client | Yes, No, N/A
text | 47628012-edfc-50ec-a367-44bce8bc451d |  | textbox | Submission Comments:
checklist-sectioned |  |  | checklist | A181 - West Dapto - ITC 014 (ITP014) - Utility Adjustments (Water) |  |  |  |  | Yes | A181 - West Dapto - ITC 014 (ITP014) - Utility Adjustments (Water) | 39399160-31dd-48ac-9a34-01562cde3e74
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | de4210a4-e624-51eb-a070-6859a132ec52 |  | textbox | Lot Opened On
text | 1e991505-c1f0-5d4a-a7ca-f0b0c6d9cadc |  | textbox | Date of Works
text | 958762b1-7f38-51b9-a724-86058289f9d5 |  | textbox | Lot Type
text | 38832a4c-4524-5f34-bc5a-423353efeaf4 |  | textbox | Start Chainage
text | 57b8f306-1e89-583b-bb46-984d0258aab5 |  | textbox | End Chainage
text | b371098d-3f30-41e4-99a0-3ab9bc8b6915 |  | textbox | Offset
text | 18516861-d629-5a66-8f66-391579402662 |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Preparation Works
checkpoint-status |  |  | checkpoint | VERIFICATION
label | b01d8209-579a-5f03-94c5-4e45a1a67c0d |  | note | REQUIREMENTS / REFERENCE: Project Safety Plan
label | 864b09a2-96c3-5aa1-a22a-30d564c59a86 |  | note | ACCEPTANCE CRITERIA:
label | 7433cec1-582c-566a-a7e4-e611ecd9b472 |  | note | • All site personnel inducted (includes environment and cultural)
label | e0ec1e52-0474-5a10-82d5-1876f0e82d6f |  | note | • Required Safe Work Method Statements completed and signed
label | ccce9833-ea81-54ac-9dcc-e540a5d2ee34 |  | note | • Subcontractor’s safety plan/procedure approved
checkpoint-group |  |  | section | 2 - Environment
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 48f51c38-2597-54b4-bd27-6005efe85e1e |  | note | REQUIREMENTS / REFERENCE: Project Environment Plan
label | 19091ec0-c8a0-57b0-af7f-1289ebd5f83f |  | note | ACCEPTANCE CRITERIA:
label | aa2b884f-bc69-5978-92ec-bb76dd2bdfce |  | note | • Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs.
label | ea6ffbcb-5323-5146-ad1a-3648b5903646 |  | note | • Air quality to be visually monitored for dust etc. as a direct result of construction activities.
checkpoint-group |  |  | section | 3 - Preparations
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 3b2a7d51-b5a5-54f5-abd5-f65050bfd8a0 |  | note | REQUIREMENTS / REFERENCE: 0223, 1341, 1391 Cl 2
label | 8307b7d2-faa3-55e7-9354-42fbae1ec124 |  | note | ACCEPTANCE CRITERIA:
label | 3656cb6f-e904-52e1-a174-d10509666277 |  | note | • DBYD and service locating completed
label | 0c4b12b0-140a-5f46-b62b-c18666193a4a |  | note | • Water utility design approved and accepted for use
checkpoint-group |  |  | section | 4 - Change Approved Design
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 9eb22eed-bedb-5154-8b43-453d853536d2 |  | note | REQUIREMENTS / REFERENCE: 1341 Cl 1.6
label | 3cf1ed0a-d475-521c-88ab-7e7546568f18 |  | note | ACCEPTANCE CRITERIA:
label | bb465875-6986-5c7a-a590-72efb7e9a512 |  | note | • HOLD POINT: If a change to the approved design alignment is required, submit proposal(s) to adjust alignment or position to the Client at least 3 days prior to excavating trenches
text | 69423b09-50cd-5660-8663-3ff2bc1bfe78 |  | textbox | HOLD POINT NUMBER:
text | ee9e08fd-52d4-5a66-b276-5f2c29583a55 |  | textbox | DATE SUBMITTED:
text | 3ac7e601-e357-5e08-bf6c-e62569adf5b4 |  | textbox | SUBMITTED BY:
text | 79093900-7e3f-55aa-90f9-262aac4775a7 |  | textbox | SPECIFICATION AND CLAUSE:
text | e67c33ae-dc97-578d-8dbf-cb5c65af06b9 |  | textbox | HOLD POINT DESCRIPTION:
text | 9525042f-9aa0-5dee-8b70-6b890adea160 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 5 - Materials
checkpoint-status |  |  | checkpoint | VERIFICATION
label | f4c62b63-8f25-5038-aab8-3abbdd118264 |  | note | REQUIREMENTS / REFERENCE: 1341 Cl 2
label | f68106d1-faed-571a-8808-cd1d8826d5e9 |  | note | ACCEPTANCE CRITERIA:
label | c6cae031-5170-5e1b-8704-7d35180a1c04 |  | note | • Materials comply to requirements of drawings and Project Specifications
checkpoint-group |  |  | section | 6 - Change Trench Excavation
checkpoint-status |  |  | checkpoint | HOLD POINT
label | ea7783ed-abf7-5b6c-854d-6f70471bbe92 |  | note | REQUIREMENTS / REFERENCE: 1341 Cl 1.6
label | 578a1a53-979e-567c-a6aa-5fc58748255a |  | note | ACCEPTANCE CRITERIA:
label | 1310d1c0-1a68-5bd3-9bed-51f966d5c481 |  | note | • HOLD POINT: In the event of unexpected soil conditions, submit details to the Client at least 5 days prior to preparing the trench floor
text | 801ea0d1-77ed-53c7-ac90-3352392b9458 |  | textbox | HOLD POINT NUMBER:
text | 348b00ab-de63-5a8c-8586-8f7d105c964c |  | textbox | DATE SUBMITTED:
text | ba692a0a-ad61-5b59-9687-3eec765574fe |  | textbox | SUBMITTED BY:
text | 0735393f-0643-5806-b20f-cb495221be4c |  | textbox | SPECIFICATION AND CLAUSE:
text | b9b973be-0a07-5a2b-b0a5-eea461a4d59a |  | textbox | HOLD POINT DESCRIPTION:
text | 4a58096b-90e5-5f2d-bb2e-d21fbaa9bf4e |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 7 - Excavation Support Details
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 2ef96fb0-74a4-5305-835d-3cfb42b608c4 |  | note | REQUIREMENTS / REFERENCE: 1341 Cl 3.3
label | 11d6402a-4f13-58a2-a389-0312313e0911 |  | note | ACCEPTANCE CRITERIA:
label | 0d12cbec-f75d-55e4-9093-608bbfc6c499 |  | note | • HOLD POINT: Submit details of excavation support to the Client, including permanent stability proposals, at least 5 days before installing these measures
text | bd3a7600-a327-5f5c-b5c1-06b2ee003b72 |  | textbox | HOLD POINT NUMBER:
text | 8e96ccbf-9734-52bb-8ffb-5cfcc89e37a0 |  | textbox | DATE SUBMITTED:
text | 1d832e66-97bc-5332-ae45-d10686bd4f4a |  | textbox | SUBMITTED BY:
text | 5a183383-bdd0-5814-ad47-b01150f043ea |  | textbox | SPECIFICATION AND CLAUSE:
text | 2b1e247f-4e57-525e-b711-b9c347f557b7 |  | textbox | HOLD POINT DESCRIPTION:
text | e4484f2e-1aa7-5ec4-aa08-b17243e20432 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 8 - Inadequate Supporting Foundation
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | b13596e5-ea09-5d76-a539-b2995a1bac53 |  | note | REQUIREMENTS / REFERENCE: 1341 Cl 3.3
label | ff8305b3-08ff-56ef-b635-5649879a936d |  | note | ACCEPTANCE CRITERIA:
label | b99547a4-b322-557d-98f6-876fe76930f3 |  | note | • WITNESS POINT: In the event of inadequate supporting foundation material in any area, notify the Client at least 5 days before preparing the trench floor (if applicable)
text | 8930cfb8-7af0-5a1b-a5ee-d1b925b259d1 |  | textbox | WITNESS POINT NUMBER:
text | f5e086e2-367c-5442-91bf-41200b94649b |  | textbox | DATE SUBMITTED:
text | 42c9987f-7564-51ec-8752-4a2d34c22c13 |  | textbox | SUBMITTED BY:
text | 6d7a4908-d130-523a-a40c-88a2de873498 |  | textbox | SPECIFICATION AND CLAUSE:
text | 778d34c1-6dac-5f4c-b682-4592fc37cc49 |  | textbox | WITNESS POINT DESCRIPTION:
text | cfde807f-a2ef-5ce0-92ce-5a49f304524e |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 9 - Repair Inadequate Foundation
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 14865445-6b13-506b-b992-f07e6dbbf49a |  | note | REQUIREMENTS / REFERENCE: 1341 Cl 3.3
label | 79fe85e1-fbbb-5008-9dc5-4848d99248fc |  | note | ACCEPTANCE CRITERIA:
label | 1df94d6f-e618-51bc-9b5d-200d0a0587e3 |  | note | • HOLD POINT: In the event of inadequate foundation material, submit proposed details for providing adequate foundation to the Client at least 3 days before preparing the trench floor (if applicable)
text | 310527dd-4fff-5d00-b3d0-02fca2992482 |  | textbox | HOLD POINT NUMBER:
text | 63389d23-f4dd-5f1f-96ff-19cee9516195 |  | textbox | DATE SUBMITTED:
text | 07be72ed-f5b9-5eab-9aea-023ea0264fa0 |  | textbox | SUBMITTED BY:
text | 1adfb059-6542-5ba4-950b-c2d60538f0ad |  | textbox | SPECIFICATION AND CLAUSE:
text | 1afd28bb-cbab-5a86-83bb-2f3f0e2070e6 |  | textbox | HOLD POINT DESCRIPTION:
text | 3495b701-7660-5485-8d00-870778d5c9fa |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 10 - Prepare Trench Floor
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 3d9bc06f-8f1d-5f72-8348-912a1b78971b |  | note | REQUIREMENTS / REFERENCE: 1341 Cl 3.4
label | 41e93398-1675-5738-a28d-63615c7f9d54 |  | note | ACCEPTANCE CRITERIA:
label | 293f3504-5bf4-5e1f-bd7b-eb40ad237975 |  | note | • WITNESS POINT: Provide notice of the completed trench excavation at least 5 days before placement of bedding
label | bd00d12b-d180-5751-9535-7ced89fcc2eb |  | note | COMMENTS / ATTACHMENTS:
label | 955301da-8377-5672-8f51-0feef9360802 |  | note | • Compaction test results
text | 4d51c1e1-8480-5924-a562-f2542d5083c7 |  | textbox | WITNESS POINT NUMBER:
text | 5acf8451-de8e-5935-9cc4-c4b09d6193cf |  | textbox | DATE SUBMITTED:
text | 510c3f17-6ed2-5003-a6e1-a25bf2add24e |  | textbox | SUBMITTED BY:
text | 748304d1-dcc6-53e0-adc7-85f40b07a22d |  | textbox | SPECIFICATION AND CLAUSE:
text | 077f55ef-e39b-5ba0-b063-7e02090563b8 |  | textbox | WITNESS POINT DESCRIPTION:
text | 4f9b8bba-a714-51e8-84bd-68637f89fe43 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 11 - Install Pipe and Fittings
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 85383c50-ca17-5ec3-bda1-5fe9a7908dd9 |  | note | REQUIREMENTS / REFERENCE: 1341 Cl 3.5
label | e6ad819e-e806-58b7-b341-a29ae1d11cc1 |  | note | ACCEPTANCE CRITERIA:
label | fd54c6bb-1673-549c-8ed5-0db7d723c66f |  | note | • HOLD POINT: Submit notice that the pipe laying, jointing and corrosion protection has been completed, at least 2 days prior to the backfilling of the trench
text | ab7a66a8-1dc5-5c9a-9dc7-de2f9405eefe |  | textbox | HOLD POINT NUMBER:
text | 0b36ab17-eb14-5c93-a0c9-4930f4a5e83f |  | textbox | DATE SUBMITTED:
text | 9587e362-c47d-5c1b-8de6-9f2c8d1a3ec1 |  | textbox | SUBMITTED BY:
text | 10ed63bf-4d09-5e76-863e-96c233ad2da9 |  | textbox | SPECIFICATION AND CLAUSE:
text | bc522800-90bb-5817-b684-ceb6dfbadef6 |  | textbox | HOLD POINT DESCRIPTION:
text | 1354eeed-df76-51c6-a7fa-08a0939bc6ea |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 12 - Connect to Existing Main
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 54609a23-a3fc-5a59-974f-bb8ec65d77af |  | note | REQUIREMENTS / REFERENCE: 1341 Cl 3.9
label | dcf50f0c-a680-5b22-a745-6a5d86bfed2c |  | note | ACCEPTANCE CRITERIA:
label | 5627b420-932f-5259-b011-daed1eafe504 |  | note | • WITNESS POINT: Provide notice of connecting to the existing main and charging new main at least 5 days prior to connecting to the existing main (if applicable)
text | 1714a5e3-6e1f-59c3-86a9-82c1da22392b |  | textbox | WITNESS POINT NUMBER:
text | 89b6f6ed-41da-5696-a637-8aaecba33460 |  | textbox | DATE SUBMITTED:
text | 4b9e961d-cb5a-577d-80cb-6e2fa4bb340b |  | textbox | SUBMITTED BY:
text | e86566aa-a851-5eaf-97c1-1306d1cf4be8 |  | textbox | SPECIFICATION AND CLAUSE:
text | c630e3a2-8f8f-5279-b50b-fe53c36c75a9 |  | textbox | WITNESS POINT DESCRIPTION:
text | dd3f697e-ca90-547e-bc65-c9c2b368e79b |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 13 - Damaged Existing Main(s)
checkpoint-status |  |  | checkpoint | HOLD POINT
label | f69e530c-0829-5416-b833-ee02a2bbe37a |  | note | REQUIREMENTS / REFERENCE: 1341 Cl 3.9
label | fb1e41f4-288e-538c-a12c-f0ae821f5047 |  | note | ACCEPTANCE CRITERIA:
label | 126d0ae5-1dbd-59cd-9d7d-60558d43f811 |  | note | • HOLD POINT: In the event of corroded or badly damaged existing water mains, submit notice at least 3 days before connecting to the existing main (if applicable)
text | c91d75e9-197d-54ec-9357-ad6d22b2d37f |  | textbox | HOLD POINT NUMBER:
text | fab7aaee-70f2-5a18-8abe-364902e60667 |  | textbox | DATE SUBMITTED:
text | ff33ee7e-4c36-52ca-9620-88022f08544f |  | textbox | SUBMITTED BY:
text | fd265410-a3d4-5f47-979d-d3d02b96afb4 |  | textbox | SPECIFICATION AND CLAUSE:
text | 969c9128-d748-59a5-8e25-96a9cc1d16a3 |  | textbox | HOLD POINT DESCRIPTION:
text | 2616c502-ff30-550a-9992-ec4c9f7fa80a |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 14 - Backfill Trenches
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 92388b0d-9e52-5449-8219-f5f533342d71 |  | note | REQUIREMENTS / REFERENCE: 1341 Cl 3.10
label | b9110add-e241-5a9e-b20c-b8f6dd67aced |  | note | ACCEPTANCE CRITERIA:
label | 3a69a9c9-37d7-5079-88fe-868e2403b0d2 |  | note | • Do not backfill trench until approval is received for installed works
label | 1ea4c980-83de-58a3-93bf-0e0fbc93233a |  | note | • Backfill in dry weather conditions. Re-use existing surface materials where possible to do so. If not feasible, restore the top surface with grass, concrete, asphalt or paving, as per the approved project drawings
label | 38c20d48-af1b-5910-91d3-8b50e24ca628 |  | note | • Complete compaction testing to Project Specs and drawings, as required
label | a0aa5b70-eddf-5f07-9777-bef81dca1b5b |  | note | COMMENTS / ATTACHMENTS:
label | f2f0ffdc-136d-5be8-b60c-390b7c867f73 |  | note | • Compaction test results
checkpoint-group |  |  | section | 15 - Acceptance Testing
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 28a03e1e-42c4-5230-b359-f588ae1fcd57 |  | note | REQUIREMENTS / REFERENCE: 1341 Cl 3.9
label | e9005300-a728-51bf-9f07-c822c23ed558 |  | note | ACCEPTANCE CRITERIA:
label | 92408136-3112-572c-b09d-4c8e8a25c034 |  | note | • Complete other testing as required, based on WCC 1341 and drawing requirements
label | 0651aab7-ee99-53b4-9584-8fdd7086fea3 |  | note | • WITNESS POINT: Provide notice of the date for acceptance testing being carried out, at least 3 days before starting acceptance testing
label | bee62375-c625-5cb5-a024-42dd053bc0df |  | note | COMMENTS / ATTACHMENTS:
label | a76f125d-0b1b-59d7-9c7b-7ec5ed2c6e88 |  | note | • Test results and documentation
text | a015177d-7731-55d4-ba97-d28bbaa16808 |  | textbox | WITNESS POINT NUMBER:
text | c8d8ca73-b1f5-5650-a6b1-808527e6c4d5 |  | textbox | DATE SUBMITTED:
text | d1dcf748-6c5f-5c5a-b7da-8e53d8214c7d |  | textbox | SUBMITTED BY:
text | 0abfb686-1ccf-50dd-8cc3-1f79993c091f |  | textbox | SPECIFICATION AND CLAUSE:
text | f6d90820-3411-558d-93b0-efb1e1d99491 |  | textbox | WITNESS POINT DESCRIPTION:
text | 27d6032a-c1ae-5120-bb28-87c5559940c4 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 16 - WAE Drawings, Close Out
checkpoint-status |  |  | checkpoint | VERIFICATION
label | deb94147-db28-5198-a8c5-b5e7ae089f72 |  | note | REQUIREMENTS / REFERENCE: 1341 Cl 3.11
label | d6c0c743-0303-5e89-95e5-197124f9655e |  | note | ACCEPTANCE CRITERIA:
label | 88a0cb5e-f20b-5435-9047-35a6fa48e02f |  | note | • Prepare work-as-executed details and operation and maintenance information
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | 5c31d628-ed3c-56db-a8b3-6fd4d9c1d4e4 |  | textbox | Lot Verified By:
text | 2f518b60-8935-5645-9329-ec32818a84d9 |  | textbox | Lot Closed Date:
button | 01f2872d-c38f-5ff3-9652-f6064d8d170b |  | button | Submitted to Client | Yes, No, N/A
button | 0095b9ff-50f7-52a1-9af3-5412ba273db8 |  | button | Reviewed by Client | Yes, No, N/A
text | 6e577194-9d7e-5e95-9c2b-7dd1ff4060a8 |  | textbox | Submission Comments:
checklist-sectioned |  |  | checklist | A181 - West Dapto - ITC 015 (ITP015) - Pavement: HBB, CRS, CRB |  |  |  |  | Yes | A181 - West Dapto - ITC 015 (ITP015) - Pavement: HBB, CRS, CRB | 5573960c-b7bb-4525-9dfb-b0b53d4edbd6
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | 52d9b5f0-8e38-516a-93fc-0a49d5294062 |  | textbox | Lot Opened On
text | 95e89ad3-85e5-5f2f-94fd-497348001441 |  | textbox | Date of Works
text | a81b3c29-86ad-59ad-b152-6f27b47a8a0e |  | textbox | Lot Type
text | f95f859d-7880-5ddf-9757-91ef42bc6f8b |  | textbox | Start Chainage
text | 44eea2c5-ac88-5794-a2db-6a9c15d76dba |  | textbox | End Chainage
text | 8d07a53f-74b4-4829-91d7-fb58a4ccc683 |  | textbox | Offset
text | 7cca9d61-40fa-5bce-bff7-ff216ab7fdfc |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - HBB – Nominated Mix
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 52d9b5f0-8e38-516a-93fc-0a49d5294062 |  | note | REQUIREMENTS / REFERENCE: 1141, 1113
label | 95e89ad3-85e5-5f2f-94fd-497348001441 |  | note | ACCEPTANCE CRITERIA:
label | a81b3c29-86ad-59ad-b152-6f27b47a8a0e |  | note | • HOLD POINT: Submit the following for the nominated mix and materials – Source of supply, and Certificate of Conformance to 1113
text | bf594951-e287-5cd6-af0d-b6a8e58a500d |  | textbox | HOLD POINT NUMBER:
text | 153398b4-49b7-577f-8c84-44cd210bbd5a |  | textbox | DATE SUBMITTED:
text | 3db68198-92a4-55d3-a995-780ec7299858 |  | textbox | SUBMITTED BY:
text | 9f5fe113-a6db-50c3-bdc6-6217eda36bed |  | textbox | SPECIFICATION AND CLAUSE:
text | bd4cb93d-a5b7-58ec-b4fc-5cb9baab224d |  | textbox | HOLD POINT DESCRIPTION:
text | 362b06a3-9ed0-5934-8996-78cd22e63a35 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 2 - HBB – Material Conformance
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 9ad78253-7418-5eab-a6c5-3e34cd62540f |  | note | REQUIREMENTS / REFERENCE: 1141, 1113
label | 556905e7-8d44-50c2-8c6d-1eb3b3157aae |  | note | ACCEPTANCE CRITERIA:
label | 4236c6dc-7453-5c88-89bf-874530948c39 |  | note | • HOLD POINT: Submission of evidence of material conformance
text | bc9a11df-a3b3-59d8-8fbb-3d762f8e608f |  | textbox | HOLD POINT NUMBER:
text | 4f8518a5-0fbd-594f-a60e-45cef3c296c8 |  | textbox | DATE SUBMITTED:
text | bc081a8f-ba78-5810-bc74-b130af908bbf |  | textbox | SUBMITTED BY:
text | bb0b6dfc-a8da-5c7c-b96f-6231d4fcfafb |  | textbox | SPECIFICATION AND CLAUSE:
text | 9a195a2f-28e9-53f1-b276-1120d1ad7176 |  | textbox | HOLD POINT DESCRIPTION:
text | 9f4337ad-7e02-5ab7-9115-78b44d760ded |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 3 - HBB – Delivery Dockets
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | fa6a9d4c-0fdd-5b22-ac5c-0ad83d2c5a96 |  | note | REQUIREMENTS / REFERENCE: 1141, 1113
label | 10ffe57f-81eb-5cd4-8674-44e6ccfd3745 |  | note | ACCEPTANCE CRITERIA:
label | 80d3e34c-2f6d-568d-967b-37d7f64febeb |  | note | • WITNESS POINT: Delivered material loads covered to prevent moisture loss, supply delivery dockets for each truck load upon material arrival
text | 4c3f9790-11b2-5e72-ae84-003a96b42202 |  | textbox | WITNESS POINT NUMBER:
text | 26261248-82a7-5233-a279-cc6d90504efa |  | textbox | DATE SUBMITTED:
text | 98db002c-5a4f-5f1e-8ca9-b05bf3762486 |  | textbox | SUBMITTED BY:
text | 0c8a2a2f-b539-584a-9780-45670a25a641 |  | textbox | SPECIFICATION AND CLAUSE:
text | 4e455883-9245-5b6e-ace0-56ea6df0cbca |  | textbox | WITNESS POINT DESCRIPTION:
text | 6331ac31-c7fa-5746-98b6-7582f12e5bed |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 4 - HBB – Material Inspection
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | e09a6136-0029-58c1-a604-83e8d3891dc3 |  | note | REQUIREMENTS / REFERENCE: 1141, 1113
label | 3b28f7c1-254a-52ec-a14f-cfedcbaf7d03 |  | note | ACCEPTANCE CRITERIA:
label | 78d4e8dd-d805-56ab-9077-8be215416401 |  | note | • WITNESS POINT: Inspection of material upon delivery to site
text | d59536b5-a97d-564d-89c1-5d6fe7299171 |  | textbox | WITNESS POINT NUMBER:
text | 8ea85477-1d2f-5396-8de9-12a4421abbe5 |  | textbox | DATE SUBMITTED:
text | a3566ec0-4462-51fb-96b8-b6bb54b9c7b0 |  | textbox | SUBMITTED BY:
text | b920f510-3dfb-5c8c-98e9-689f09651b9f |  | textbox | SPECIFICATION AND CLAUSE:
text | 7840b962-3188-51c8-94e8-f5e17049122e |  | textbox | WITNESS POINT DESCRIPTION:
text | f827e9f8-f431-522b-9cde-d8c1b4568b33 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 5 - HBB – Trial Section Notification
checkpoint-status |  |  | checkpoint | HOLD POINT
label | e85dc9a1-6d23-5903-9826-d4a79909c561 |  | note | REQUIREMENTS / REFERENCE: 1141, 1113
label | 55d4b2db-f8bd-55cd-a614-3c91dee2414c |  | note | ACCEPTANCE CRITERIA:
label | 53595fcf-ff8d-515f-b3ea-cf63a5cc078d |  | note | • HOLD POINT: Submit details of a Trial Section of HBB placement, two days prior to commencement
text | 54946afe-3779-5f5c-a0d3-42ddf001d740 |  | textbox | HOLD POINT NUMBER:
text | bcc493ff-35be-513c-9175-6f919c2e045a |  | textbox | DATE SUBMITTED:
text | f05f9363-7fa6-5085-af4c-f95781de797e |  | textbox | SUBMITTED BY:
text | cd0d6e46-4824-5325-abad-0b2839303e51 |  | textbox | SPECIFICATION AND CLAUSE:
text | 7c0c0b79-470c-53e5-8c87-4097c16ba6ed |  | textbox | HOLD POINT DESCRIPTION:
text | c28f05c5-3c54-56e8-84f3-9bf246eea9fe |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 6 - HBB – Trial Section Results
checkpoint-status |  |  | checkpoint | HOLD POINT
label | d82d5cc8-e492-54be-8a30-4ad3846d867a |  | note | REQUIREMENTS / REFERENCE: 1141, 1113
label | 56c25b5e-56b0-5809-94eb-0a600219982b |  | note | ACCEPTANCE CRITERIA:
label | aee6010e-75ff-5ece-9d62-b1829d27fabc |  | note | • HOLD POINT: Construct a 50m Trial Section to be incorporated into the finished works, submit trial results a minimum two days prior to commencing the remaining works
text | 5886c6f9-f987-59e0-912a-050f3fd51a64 |  | textbox | HOLD POINT NUMBER:
text | 87ba3afd-b89b-5548-9114-6d090f217433 |  | textbox | DATE SUBMITTED:
text | 3adcd77b-56ab-517c-aff9-9aa3548fe3c1 |  | textbox | SUBMITTED BY:
text | a872afc2-4f4f-540c-a96d-191e12895730 |  | textbox | SPECIFICATION AND CLAUSE:
text | 8012cd11-f00f-57bf-a972-c9390450946d |  | textbox | HOLD POINT DESCRIPTION:
text | 8c87e7bb-4b00-5a47-a973-8741b5fcf4be |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 7 - HBB – Compaction Results
checkpoint-status |  |  | checkpoint | HOLD POINT
label | cc0a9770-ca6b-5e1d-8090-c8017ba0d9ce |  | note | REQUIREMENTS / REFERENCE: 1141, 1113
label | 5cf7ee59-baf2-517d-988c-6a3bd2f23b30 |  | note | ACCEPTANCE CRITERIA:
label | c73e063c-3377-569b-880f-88df143de58d |  | note | • HOLD POINT: Submission of HBB compaction results
text | 171bd323-a0d0-5e6e-82a1-7821bb123b4c |  | textbox | HOLD POINT NUMBER:
text | 75b19440-8de2-5df1-adb7-87737f6c11c6 |  | textbox | DATE SUBMITTED:
text | b52c5d11-918a-59ba-a97e-ebeb2ea96fb4 |  | textbox | SUBMITTED BY:
text | ebbec2cc-d366-50b9-81f6-ead67071dedd |  | textbox | SPECIFICATION AND CLAUSE:
text | 36f32c5d-81c4-5806-96ca-9d8a988cbebf |  | textbox | HOLD POINT DESCRIPTION:
text | 177f8dd7-46dd-5dcb-804b-7a99b40de287 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 8 - HBB – Survey Reports
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 7a4bc01c-eb15-5b0d-b169-aac82ed937c2 |  | note | REQUIREMENTS / REFERENCE: 1141, 1113
label | bd6d053f-660a-5eb7-897e-e24a739395b2 |  | note | ACCEPTANCE CRITERIA:
label | 85ddbc83-d51c-520f-8880-6108bbb23880 |  | note | • HOLD POINT: Submission of the following – Survey report of finished surface levels, Survey report of compacted thickness, Recorded data of straight edge test
text | a52551e1-9721-546c-a39c-16cfce200690 |  | textbox | HOLD POINT NUMBER:
text | d524467b-bfae-518f-92dc-08a26d08c79b |  | textbox | DATE SUBMITTED:
text | 405a746a-30c6-57e2-b458-e3ee6fb6e520 |  | textbox | SUBMITTED BY:
text | 78f808df-568a-5970-8f42-ba820fa1e16c |  | textbox | SPECIFICATION AND CLAUSE:
text | c08986ff-caff-54e3-96dd-b32b10f99156 |  | textbox | HOLD POINT DESCRIPTION:
text | b642102d-c60c-5963-b5aa-ff6bcade9791 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 9 - CR – Material Details
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 7309583b-d36f-53f1-b5fd-2b18e97b0a42 |  | note | REQUIREMENTS / REFERENCE: 1113
label | b5923c72-2155-5ea0-99ba-7bbfe7d6fedf |  | note | ACCEPTANCE CRITERIA:
label | 18300a86-44d9-51bf-ae80-e6eb78e4b215 |  | note | • HOLD POINT: Submit the following for each proposed material ten days before delivery – Source of supply, Blend proportions for blended materials, Test results (NATA)
text | 715c5f63-1d05-586d-992a-cd394140db05 |  | textbox | HOLD POINT NUMBER:
text | 63038bc7-5a18-5082-89c7-c8a7ba1a9d4b |  | textbox | DATE SUBMITTED:
text | e198bb71-f3c4-5682-8159-c8d1b22a693f |  | textbox | SUBMITTED BY:
text | d5eb28b0-605e-55ac-93ec-882cf4c02a43 |  | textbox | SPECIFICATION AND CLAUSE:
text | 095b646d-f304-5d97-a428-f36d93c7984f |  | textbox | HOLD POINT DESCRIPTION:
text | 052a00f8-2f88-5956-a58d-5b108f203339 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 10 - CR – Material Inspection
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 31c0da33-fa81-5362-87d8-4e381db561b0 |  | note | REQUIREMENTS / REFERENCE: 1113
label | ecb42c90-267f-5c12-a9ac-9fb2a270529c |  | note | ACCEPTANCE CRITERIA:
label | 635c2578-b2a0-564f-b416-687df75812fb |  | note | • WITNESS POINT: Inspection of materials at delivery
text | 1b18b320-e3a3-5269-9a1d-dc219719567d |  | textbox | WITNESS POINT NUMBER:
text | 15287abe-69d3-5970-a9fb-70a5b33fc9a9 |  | textbox | DATE SUBMITTED:
text | fd4dc3bc-482d-59ac-b2c6-65552d63d1b3 |  | textbox | SUBMITTED BY:
text | 89f8fba5-6186-5b52-9ca9-1bbab95c0b34 |  | textbox | SPECIFICATION AND CLAUSE:
text | ae030c46-9777-56ee-a85b-a6172e23f798 |  | textbox | WITNESS POINT DESCRIPTION:
text | 9dbb10dd-367d-55c5-b07b-a9a8f097a567 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 11 - CR – Trial Section Results
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 24fd4724-bc6d-5711-981d-ae7de3700b60 |  | note | REQUIREMENTS / REFERENCE: 1113
label | a9799bd4-7034-5e83-83a6-a372a7b4ddd4 |  | note | ACCEPTANCE CRITERIA:
label | da8139bf-a7de-5849-8048-5fd8b26796c0 |  | note | • HOLD POINT: Construct a 50m Trial Section to be incorporated into the finished works, submit trial results a minimum two days prior to commencing the remaining works
text | c20d8f2b-fa32-565e-9f37-22a3e9409476 |  | textbox | HOLD POINT NUMBER:
text | a8bf648c-5863-5f67-9900-dc214a1dbc3a |  | textbox | DATE SUBMITTED:
text | dc2260ce-b0f3-56d9-9d39-0aecc4ca72a4 |  | textbox | SUBMITTED BY:
text | 7925d545-ec7f-5a13-88f4-2d98bac36db2 |  | textbox | SPECIFICATION AND CLAUSE:
text | f1f5028a-7fea-5039-978e-3f1f9a260e81 |  | textbox | HOLD POINT DESCRIPTION:
text | aca29c46-0373-5bc3-b65c-9197caf794d0 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 12 - CR – Survey Reports
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 7872489d-7c70-588b-aff5-5a39bc2fa261 |  | note | REQUIREMENTS / REFERENCE: 1113
label | 217f8619-9ffe-5e2f-bb8c-1f2818d5c832 |  | note | ACCEPTANCE CRITERIA:
label | 04ed10a1-775c-5f79-ae17-50ccc69a8da7 |  | note | • HOLD POINT: Submission of the following – Survey of completed pavement layer, Compaction and Moisture levels, Proof Roll records, Straight edge test records
text | cd1d88f0-25b4-5661-8ff0-213aecb52a0a |  | textbox | HOLD POINT NUMBER:
text | 12a1ef0a-3db7-57cd-bb80-2ab5361b74c1 |  | textbox | DATE SUBMITTED:
text | d5b4d050-e963-535c-a2ae-ba04d374c985 |  | textbox | SUBMITTED BY:
text | fa1425e3-f725-5dcd-b5d4-ba56a17e76d6 |  | textbox | SPECIFICATION AND CLAUSE:
text | b38ed541-b345-5ada-90e8-5a6fcc7fd841 |  | textbox | HOLD POINT DESCRIPTION:
text | bb7e6884-3c37-5cf8-9d10-d603f6395dfa |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | b5e83675-6fc7-53bc-978d-3386f46cdbba |  | textbox | Lot Verified By:
text | 09139bdf-bee1-5cd4-ad9c-3784c1329bd1 |  | textbox | Lot Closed Date:
button | 7943908d-7371-55af-96d9-42cb25de5296 |  | button | Submitted to Client | Yes, No, N/A
button | ddb2f1c6-045e-5cc4-801a-27d6b6b0e3e0 |  | button | Reviewed by Client | Yes, No, N/A
text | 799ce031-4fd5-5e46-8dd5-c3592856dd36 |  | textbox | Submission Comments:
checklist-flat |  |  | checklist | NCR |  |  |  |  | Yes | Add NCR | 624b50a3-8955-4da0-8e0e-af9b76e02408
checkpoint-status |  |  | checkpoint | Non-Conformance Report
label | 37b21765-a0e3-596c-a2cf-cfc265170206 |  | note | Attach NCR form and any relevant documents, photos, etc.
label | 828c050d-f472-5adb-9f21-b46f3850853a |  | note | Issue to Client for their approval and sign off.
text | a8b1507a-5efd-5bf8-a9e9-0b869f77ff5b |  | textbox | NCR Number:
text | c97782d1-0516-52cf-8c27-bdb935db3234 |  | textbox | Lot Number:
text | 9d7fcbe5-e3ab-5d6e-b9fc-b93f780f06ef |  | textbox | NCR Description:
text | bd3456e7-fd21-5f94-8153-1f78892b4324 |  | textbox | NCR Resolution:
holdpoint |  |  | signoff | NCR SIGN OFF
checklist-sectioned |  |  | checklist | A181 - West Dapto - ITC 010 (ITP010) - Concrete Structures |  |  |  |  | Yes | A181 - West Dapto - ITC 010 (ITP010) - Concrete Structures | 766ce0b9-8f58-4381-8053-81c075871518
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | 1a856a64-a317-534d-9408-4816b4d9c434 |  | textbox | Lot Opened On
text | c686d9a8-0817-5280-b993-4441a9445a39 |  | textbox | Date of Works
text | 9ca06b2e-9be2-5ff9-96fc-c3a0664fa08d |  | textbox | Lot Type
text | f4a90c97-4c54-56a8-9e69-73254863327b |  | textbox | Start Chainage
text | 4ea3afcb-ba46-5c91-a62b-c7fb524b8067 |  | textbox | End Chainage
text | 7a8dd859-fb79-4d73-ac97-71ae1935f0e7 |  | textbox | Offset
text | 74a39b3c-1270-5918-9628-3b685979ff10 |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Preparation Works
checkpoint-status |  |  | checkpoint | VERIFICATION
label | aaa6a968-0bb5-5bb9-8c83-1c647a951846 |  | note | REQUIREMENTS / REFERENCE: Project Safety Plan
label | b43aec34-6239-58c0-b8dc-6e64596123bb |  | note | ACCEPTANCE CRITERIA:
label | 5b898e03-09f8-5e0e-aeed-b9730bd52861 |  | note | • All site personnel inducted (includes environment and cultural)
label | 6c97a635-c7dd-5f1f-a214-41ae0b9b318b |  | note | • Required Safe Work Method Statements completed and signed
label | 1edfc079-fe96-5fb7-81ae-4c00588a4e8f |  | note | • Subcontractor’s safety plan/procedure approved
checkpoint-group |  |  | section | 2 - Environment
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 4cdd70b5-231b-5823-8fa3-7222a4c4d138 |  | note | REQUIREMENTS / REFERENCE: Project Environment Plan
label | 6fcf5e2c-9daf-557c-91f5-6cd716494499 |  | note | ACCEPTANCE CRITERIA:
label | 9755195b-be78-5337-ae8f-32d706cc1469 |  | note | • Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs.
label | 71a6d197-4429-5557-90a3-d6814b673037 |  | note | • Air quality to be visually monitored for dust etc. as a direct result of construction activities.
checkpoint-group |  |  | section | 3 - Ground Preparation
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 06adfd58-a776-523f-ac90-053e8662d093 |  | note | REQUIREMENTS / REFERENCE: 0310, 0319
label | e993636e-fbdd-548c-a73b-c3e67e96152a |  | note | ACCEPTANCE CRITERIA:
label | 5e0ed3fa-410b-5208-a644-1d772a5abedf |  | note | • WITNESS POINT: Notice of inspection of base/subgrade before covering 1 day before laying underlay or placing concrete
text | 1b2f1a89-0175-5fbe-b28e-1941da7dcbcd |  | textbox | WITNESS POINT NUMBER:
text | bb1c4a95-fc88-5ed7-a667-7b69fd18f2cc |  | textbox | DATE SUBMITTED:
text | 98fbec25-fbbe-5c0f-9c8a-01822db2ca7e |  | textbox | SUBMITTED BY:
text | 11361dfe-1426-5004-9b50-833f1957d836 |  | textbox | SPECIFICATION AND CLAUSE:
text | e1742148-99d3-589c-8426-d0f344bcf650 |  | textbox | WITNESS POINT DESCRIPTION:
text | af9ba8ee-dab9-53e0-9e1d-d885e32a19eb |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 4 - Formwork Design Certification
checkpoint-status |  |  | checkpoint | HOLD POINT
label | c9dbf0b8-aa9f-5859-9faf-77c2178fc0da |  | note | REQUIREMENTS / REFERENCE: 0310, 0319
label | 9b40d2ad-3089-5215-8ef0-1f25085d6f7b |  | note | ACCEPTANCE CRITERIA:
label | d13200bf-b019-5afe-bbbc-8a01e16ad2f3 |  | note | • HOLD POINT: Formwork design certification 3 days before erecting formwork – for in situ box culverts and retaining walls only
text | 23c8d5aa-0eff-57e3-a384-f8c87a43c30c |  | textbox | HOLD POINT NUMBER:
text | d807b392-70e3-5dd9-9b5e-a62a8c4bbe9a |  | textbox | DATE SUBMITTED:
text | 9abda869-3e31-5139-a4f5-b6ebd2f26f89 |  | textbox | SUBMITTED BY:
text | 89670931-4eeb-5add-a345-4b400671cc37 |  | textbox | SPECIFICATION AND CLAUSE:
text | effa8ea9-5d2b-565c-84dd-0c18e1735db7 |  | textbox | HOLD POINT DESCRIPTION:
text | fcbd3d3d-c30b-5a4f-934b-d59c9a1ea54d |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 5 - Completed Formwork Certification
checkpoint-status |  |  | checkpoint | HOLD POINT
label | f0e66f95-4cd4-5b81-851b-a1df30fb1f54 |  | note | REQUIREMENTS / REFERENCE: 0310, 0319
label | ced85540-b7ce-5f91-82af-3735d739a44f |  | note | ACCEPTANCE CRITERIA:
label | 838f7aaf-5e16-52cd-9ee0-ee5f4eb843ea |  | note | • HOLD POINT: Completed formwork certification 1 day before placing concrete (HP)
text | 42052a7e-8e54-5bc7-994e-db8c261c53c9 |  | textbox | HOLD POINT NUMBER:
text | 372e1277-4bb6-5084-86c0-41c377863b0e |  | textbox | DATE SUBMITTED:
text | d8b390e6-ee54-5787-aa3b-d07966862b03 |  | textbox | SUBMITTED BY:
text | ce5a3f51-fd77-57d4-b835-369ff455255b |  | textbox | SPECIFICATION AND CLAUSE:
text | 56fd58e9-b78e-5623-a933-4f142d52e2f8 |  | textbox | HOLD POINT DESCRIPTION:
text | 91f0c5dd-e21c-53fd-a186-c18f7eb610ac |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 6 - Inspection of Formwork
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 701de48a-888a-5bea-b552-9b4bc62a5c70 |  | note | REQUIREMENTS / REFERENCE: 0310, 0319
label | 0f80f865-dbd8-5dbb-b87d-9f35c8069ba1 |  | note | ACCEPTANCE CRITERIA:
label | cc6e9aa7-cf64-5581-9d8e-48b79cb22e2d |  | note | • WITNESS POINT: Notice of inspection of completed formwork
text | 9a697550-6b48-5bb5-afdb-f8fb8202ca5d |  | textbox | WITNESS POINT NUMBER:
text | 91b79543-e43b-5a7d-8018-fbb830a75988 |  | textbox | DATE SUBMITTED:
text | f5c9969f-e55f-5ffe-bd1d-d1987f95d303 |  | textbox | SUBMITTED BY:
text | ec88d230-7d53-5639-a1c6-218c6333d5ae |  | textbox | SPECIFICATION AND CLAUSE:
text | 64ef5a5a-97cb-5536-8b2e-ce6d0c50bad3 |  | textbox | WITNESS POINT DESCRIPTION:
text | 6d3089ad-398f-566d-99a8-600de29424fc |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 7 - Reinforcement
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | a09ab740-0d7a-50f0-a9da-92c919d0aea9 |  | note | REQUIREMENTS / REFERENCE: 0310, 0319
label | 5dabbf5f-6939-5700-8aaf-0d599152b5fa |  | note | ACCEPTANCE CRITERIA:
label | 96f9d911-c2e1-58ba-a595-b4738bedd022 |  | note | • WITNESS POINT: Notice of inspection of completed reinforcement
text | f8491981-63e8-505c-9ce2-3c7a3b8ae29a |  | textbox | WITNESS POINT NUMBER:
text | 8551fa1b-34cf-5439-82bb-7b7d78a1e2e9 |  | textbox | DATE SUBMITTED:
text | de8b7fee-8c22-5c8b-9e04-def4edfec5f4 |  | textbox | SUBMITTED BY:
text | 4346791c-414a-5d7c-83f9-68f9eeaec5d5 |  | textbox | SPECIFICATION AND CLAUSE:
text | 9a34f808-6213-5c5e-8ebf-a82afe3698f4 |  | textbox | WITNESS POINT DESCRIPTION:
text | 1e03ecd8-98ef-5315-8ccd-93c5f26b0877 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 8 - Machine Mixing Proposal
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 319b123b-0292-56ea-a747-03c4c102a088 |  | note | REQUIREMENTS / REFERENCE: 0310, 0319
label | 7b832b70-012a-5338-821c-3fbb81420433 |  | note | ACCEPTANCE CRITERIA:
label | 670030f5-5432-5c85-820c-9308b7bafcd4 |  | note | • HOLD POINT: Machine mixing: Submit proposals for mixing, placing, finishing, and curing. Include the following where relevant
text | 2efe3c94-c75b-5829-bc33-3a01760ac020 |  | textbox | HOLD POINT NUMBER:
text | 7bf25d10-ee86-5044-946d-cf3b2f6e203d |  | textbox | DATE SUBMITTED:
text | e57aef13-2875-5506-a55c-5880cb413dc8 |  | textbox | SUBMITTED BY:
text | 52b44ef6-18b1-5ee2-8923-93ac24e2fb11 |  | textbox | SPECIFICATION AND CLAUSE:
text | a4580458-c213-550a-a95c-2c229580643d |  | textbox | HOLD POINT DESCRIPTION:
text | ef86e0c3-50a4-5b77-b3bb-29f80d6fb553 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 9 - 95% Strength Before Loading
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 8a92e855-ca8a-5a5d-914b-b85d663c60d6 |  | note | REQUIREMENTS / REFERENCE: 0310, 0319
label | f0fb587d-5acc-5623-a3ba-6e3f63bea613 |  | note | ACCEPTANCE CRITERIA:
label | 5fbf0fde-c189-5614-bbf4-64ca9ae2dc4c |  | note | • HOLD POINT: Submit results to show that concrete has achieved 95% of its design strength 1 day before superimposed load
text | ef6a86b6-aa97-568a-bb99-12878a760f36 |  | textbox | HOLD POINT NUMBER:
text | 19e62329-6915-5210-b091-cc2be3871730 |  | textbox | DATE SUBMITTED:
text | 18f2a01c-ab3e-520e-9664-9ec0d274bb7d |  | textbox | SUBMITTED BY:
text | cf615fa1-b9d4-576f-a5bf-5335bc51cc2b |  | textbox | SPECIFICATION AND CLAUSE:
text | 9aa078b0-e955-5444-ae92-48b1c4ca5abd |  | textbox | HOLD POINT DESCRIPTION:
text | c5247217-3e95-58a6-a21f-21fd818e7b22 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 10 - Concrete
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 7ac537ac-4baf-5edd-9e10-0d229c052c68 |  | note | ACCEPTANCE CRITERIA:
label | d9c9474d-fadf-50fd-816d-d920308f6ba3 |  | note | • Provide concrete delivery dockets, as well as concrete test results, if required
label | e712e369-3e15-51dd-9c47-da671aff9767 |  | note | COMMENTS / ATTACHMENTS:
label | fc0ee542-3f1c-5418-8e9f-c931c238fd72 |  | note | • Concrete dockets and test results
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | a0ecd9eb-72f3-5d3e-914c-73c5c3477524 |  | textbox | Lot Verified By:
text | 44127612-f884-5346-a994-a507e86b5cbd |  | textbox | Lot Closed Date:
button | 5eab0ff0-8f7e-5d69-8b18-6ec9a10e45bb |  | button | Submitted to Client | Yes, No, N/A
button | 97ffabac-d76b-5100-b8ac-a92a72e1b0e7 |  | button | Reviewed by Client | Yes, No, N/A
text | 3749ee07-a0e3-538a-a923-c399bbf908bb |  | textbox | Submission Comments:
checklist-sectioned |  |  | checklist | A181 - West Dapto - ITC 002 (ITP002) - Stormwater & Trench Drains Installation |  |  |  |  | Yes | A181 - West Dapto - ITC 002 (ITP002) - Stormwater & Trench Drains Installation | 7d7e10ad-6388-4048-8843-e1ff1139613e
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | a28e7712-5372-5c89-80c2-87f129aba939 |  | textbox | Lot Opened On
text | 2d92ffbb-3d90-5d8c-b70b-9f826a0b1995 |  | textbox | Date of Works
text | b7bd3b5a-6635-512d-9604-6ce218a12d43 |  | textbox | Lot Type
text | beb41f66-1344-5f14-9194-86f1bfc82978 |  | textbox | Start Chainage
text | a7a358f9-07f9-5826-934d-caa581e22540 |  | textbox | End Chainage
text | 390980a3-f9cd-4157-ac8d-3de7f354d590 |  | textbox | Offset
text | 9cac17e8-e3a5-59ec-b3e3-e3a86eaa478e |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Preparation Works
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 831e856e-a87d-5867-9cfe-2de7f9cf61ca |  | note | REQUIREMENTS / REFERENCE: Project Safety Plan, Project Environment Plan
label | 6f41f4d0-591f-566e-bf1a-bb44822ba2cd |  | note | ACCEPTANCE CRITERIA:
label | ef966e61-a176-5037-a32f-b57dc2df00b5 |  | note | • All site personnel inducted, required SWMS completed and signed, Safety Plan approved
label | f3e2d5eb-c04c-59a1-87e3-c7d5544ffeee |  | note | • ERSED controls installed on site, air quality visually monitored for dust etc due to construction activities, Environment Plan approved
label | 31eeb07e-e5af-500c-912d-661907589402 |  | note | • Contact DBYD and complete excavation permit, extent of works set out with survey pegs
checkpoint-group |  |  | section | 2 - Cert of Conformance (Pipes and Fittings)
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 2461ae44-a820-5f1f-8e04-76388683e880 |  | note | REQUIREMENTS / REFERENCE:
label | 8a139090-fd78-54b7-8ce1-e8eaa96d5d0c |  | note | • AS/NZS 5065
label | fee16d92-d3db-51cb-8536-cf967623e3d1 |  | note | • WCC 1352 Cl 2.3
label | 201b88d5-8f48-5651-a057-8ea3de14d110 |  | note | • WCC 1352 Cl 1.4
label | fe7b4dbe-be2b-563a-852d-e1a963c1ee7e |  | note | ACCEPTANCE CRITERIA:
label | 5394cb06-9e71-5bd9-b494-a799487ec3fe |  | note | • HOLD POINT: Submit certificate of conformance for all pipes and fittings used (if required)
text | 83bc06e0-8f42-5d0c-8545-38997a8b7783 |  | textbox | HOLD POINT NUMBER:
text | a372e80f-5b44-5cc0-a67f-51c08398a14e |  | textbox | DATE SUBMITTED:
text | 8e8ab2e4-bf10-570d-92fa-eaf35aa78fab |  | textbox | SUBMITTED BY:
text | e579302e-509c-53f3-bf7c-a55eebe9b403 |  | textbox | SPECIFICATION AND CLAUSE:
text | c9250b88-a97a-5ecc-be65-1995f11361c0 |  | textbox | HOLD POINT DESCRIPTION:
text | d4cd8d2f-db6b-5013-afde-e5aebeb1f4a6 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 3 - Sample of Pipes and Fittings
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 1286fbdc-9fc4-53d8-98e0-d9a534268c7b |  | note | REQUIREMENTS / REFERENCE: WCC 1352 Cl 1.4
label | 226ae1f0-c117-580e-b4ec-5358091f28c9 |  | note | ACCEPTANCE CRITERIA:
label | f10b6a6f-6e0d-5ad7-b3fa-9f31db27aebb |  | note | • HOLD POINT: Submit sample of pipes and fittings to principal (if required)
text | cd04ae4e-894f-5ae4-ba2f-98a31d5421bd |  | textbox | HOLD POINT NUMBER:
text | 7a3217ad-9242-5505-9351-aac28bd5096b |  | textbox | DATE SUBMITTED:
text | 27beaf99-de5c-50ab-9068-6d302845b668 |  | textbox | SUBMITTED BY:
text | d7b5280e-f5b0-5223-8ab0-5d6bc96043b0 |  | textbox | SPECIFICATION AND CLAUSE:
text | 8290443c-aeba-5b4a-95ed-13f105e935d2 |  | textbox | HOLD POINT DESCRIPTION:
text | 6f57e52d-77a7-53a8-aa3e-65b7f94c1fe7 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 4 - Materials – Precast Concrete Drainage Structures
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 85c46a2c-1f43-541a-ba7c-a387c0c2a420 |  | note | REQUIREMENTS / REFERENCE: WCC 1354 Cl 1.5
label | cdc09153-d30e-50a0-8e4b-df15a4651233 |  | note | ACCEPTANCE CRITERIA:
label | 3c70fdf7-7da6-5f83-b737-b82ba4ed1f61 |  | note | • HOLD POINT: Submission of all quality documents specified in clause 1.5 at least 5 days prior to date of delivery (if required)
text | bce3b2bf-db01-50f6-9e4b-ac5a1efc9519 |  | textbox | HOLD POINT NUMBER:
text | d945c0c3-2d6c-544d-9790-9f686d8e2782 |  | textbox | DATE SUBMITTED:
text | f8147453-7622-59b4-85c7-66ca5d13d263 |  | textbox | SUBMITTED BY:
text | c00fb6f8-cb34-5fc0-9976-71d5e1d22c09 |  | textbox | SPECIFICATION AND CLAUSE:
text | cfe7679b-51ca-54cc-961d-7cc115ab3876 |  | textbox | HOLD POINT DESCRIPTION:
text | 0f658152-2cdb-5aa5-82a5-2375a8f34bc5 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 5 - Changes to Proposed Design
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 4ba973d2-4e44-5eb0-97dd-80cfc656aa4b |  | note | REQUIREMENTS / REFERENCE: WCC 1351 Annex 4.1
label | 05c09356-e9f6-5a46-932d-aa2e7b0368c8 |  | note | ACCEPTANCE CRITERIA:
label | cbfbfafc-bfa1-5c36-bb82-25c55ad96cd1 |  | note | • HOLD POINT: Details of any proposed changes to designed system 5 days before commencement (if required)
text | e832e9be-1ec4-5c29-b6e2-47c136dcd54b |  | textbox | HOLD POINT NUMBER:
text | 47bf86c9-683a-5f04-a7af-c3be1d526ac4 |  | textbox | DATE SUBMITTED:
text | b95752dd-37d2-568a-961e-4ada7285db53 |  | textbox | SUBMITTED BY:
text | 13e4aa46-71d2-59c9-a7f5-0f6d95f525a5 |  | textbox | SPECIFICATION AND CLAUSE:
text | 678927d2-e44b-528e-89e6-39bb6d17da3e |  | textbox | HOLD POINT DESCRIPTION:
text | 147ff555-f820-5135-85a6-bf6cc3f1b25f |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 6 - Set Out of Location Design Levels and Cover
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | b2682779-958e-5eb7-97c9-7ea93629e537 |  | note | REQUIREMENTS / REFERENCE:
label | 6c260282-f374-5a0a-bf56-5f50bc620b97 |  | note | • WCC 1351 Cl 3.1
label | 0b747c66-d81a-5638-a74a-4f23e482d7de |  | note | • WCC 1351 Annex 4.1
label | cab415f8-1053-5b1b-8629-dadca5ebcbbb |  | note | • WCC 1121 Cl 3.1
label | c1e964ff-2170-52a0-a628-f94bd77aaa00 |  | note | ACCEPTANCE CRITERIA:
label | 35abf99e-2a70-5bd6-84b3-63563d04c990 |  | note | • WITNESS POINT: Notify principal that set-out of location design levels and design cover will be completed 3 days prior to set-out
text | cfbab94b-5e4c-5cd7-ad59-f92fc573ca7d |  | textbox | WITNESS POINT NUMBER:
text | bf79bb3e-66db-5f51-b1a6-a8a4beee3ba7 |  | textbox | DATE SUBMITTED:
text | bb1da514-0d24-54b8-8507-e2cdd68fda0d |  | textbox | SUBMITTED BY:
text | 041b9cc9-a262-5af1-a4cb-99428bd4c735 |  | textbox | SPECIFICATION AND CLAUSE:
text | b6a9f1e5-d2fd-544e-8dc6-5ebc47fed0ed |  | textbox | WITNESS POINT DESCRIPTION:
text | 40f37ce9-0e41-50d5-92f8-8e5256ce85e6 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 7 - Soil Durability Test Results
checkpoint-status |  |  | checkpoint | HOLD POINT
label | dfb8430a-80a1-5e28-a487-f9244aab0455 |  | note | REQUIREMENTS / REFERENCE: WCC 1351 Annex 4.1
label | 7fb1a4a2-0db5-58de-8519-f9ea0ec8079e |  | note | ACCEPTANCE CRITERIA:
label | d37c1a0c-95d6-5ac5-9eeb-71054ceb3f54 |  | note | • HOLD POINT: 5 days prior to commencement of site activities, submit soil durability test results to the principal
text | f4c72549-6119-5b77-ac59-c7d73d2e3be7 |  | textbox | HOLD POINT NUMBER:
text | 8d5a7e6d-6373-5314-8185-2e792c261dfa |  | textbox | DATE SUBMITTED:
text | 68675e2b-ee15-5256-af32-80f9b03433a4 |  | textbox | SUBMITTED BY:
text | 2bcc44b8-6adf-5e3b-b00f-8e6a462ba5d7 |  | textbox | SPECIFICATION AND CLAUSE:
text | 0741fb3e-bc63-5845-9f8d-ef98162c96f3 |  | textbox | HOLD POINT DESCRIPTION:
text | bb670ce0-8996-5853-a720-991c8c4d086f |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 8 - Confirmation of Conforming Soil Type
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 62c36c7b-3b00-5e09-ac3d-8293bc8a98f8 |  | note | REQUIREMENTS / REFERENCE: WCC 1351 Annex 4.1
label | d3a760a4-a3e0-5325-a4de-cdaf8ed3e8c3 |  | note | ACCEPTANCE CRITERIA:
label | 968d87f6-c005-561e-9f7d-dc42f94a74c8 |  | note | • HOLD POINT: Submit a notification confirming soil type conforms to soil type used for stormwater system design
checkpoint-group |  |  | section | 9 - ERSED Controls, Temporary Drainage
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 7088e5fa-a289-561c-a948-3d6f700be6db |  | note | ACCEPTANCE CRITERIA:
label | 807372ee-896a-5870-a091-ed86a61efe61 |  | note | • HOLD POINT: Submit to the Principal details of procedures / devices for temporary bypass drainage during construction
text | 6377a0f4-03d5-5687-8eb6-7054c6d942e5 |  | textbox | HOLD POINT NUMBER:
text | 3ec818b1-2688-5260-b5ab-e88b9db89d14 |  | textbox | DATE SUBMITTED:
text | 76c701b6-4ee1-5aae-9fde-7943cbb1dd40 |  | textbox | SUBMITTED BY:
text | 0c85dfd8-92f7-5ddf-ab8c-457c5114f387 |  | textbox | SPECIFICATION AND CLAUSE:
text | cb429af3-c43c-534b-96c0-7987fc2f8d2e |  | textbox | HOLD POINT DESCRIPTION:
text | fe7f0c52-1b58-5874-9318-67559012dae6 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 10 - Inspection of Drainage Pit
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | f882d601-edc6-5671-a346-7f148baa0b58 |  | note | REQUIREMENTS / REFERENCE: WCC 1351 Cl 3.3
label | cda88397-a472-5b9b-a49d-45af3bb26560 |  | note | ACCEPTANCE CRITERIA:
label | 649a8566-3add-5b2d-a632-4ba237b69d6b |  | note | • WITNESS POINT: Provide notification 3 days prior to excavation of drainage structures (other than pipes) for an inspection of the drainage pit such that clear width of excavation is either:
label | 2045d5ed-e385-5453-80fb-810793e89e0f |  | note | • One third of excavation face height or a minimum of 300mm
text | 5861190d-5b40-580b-8dc4-63d0ebec450e |  | textbox | WITNESS POINT NUMBER:
text | 9053050b-4fea-59a2-8b45-5ba3a3de987e |  | textbox | DATE SUBMITTED:
text | 63a3a4f0-7f6f-5dbd-9ff4-2ad311ab0722 |  | textbox | SUBMITTED BY:
text | 601d7a1e-f072-50b3-a1be-c608059f4f10 |  | textbox | SPECIFICATION AND CLAUSE:
text | c577d309-40e1-5488-9da0-8ee0d68faf63 |  | textbox | WITNESS POINT DESCRIPTION:
text | e744f803-2458-50f8-a52d-7c8582be9610 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 11 - Notice of Completed Excavation and Compaction
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 6866a579-9281-513c-a418-b30055def453 |  | note | REQUIREMENTS / REFERENCE: WCC 1351 Cl 3.3
label | 7f0ae333-36e1-52fb-a44e-6d2e89474cd8 |  | note | ACCEPTANCE CRITERIA:
label | 55a1fb1d-f5d8-5a50-974f-d4b0bec90d71 |  | note | • WITNESS POINT: Provide notice of completed excavation and compaction of foundation 1 day prior to commencement of drainage structure and foundation construction
text | c59cefab-9bad-5225-bb55-6dddbd191a60 |  | textbox | WITNESS POINT NUMBER:
text | 13ed48bc-808a-52d7-b465-38d3347744a6 |  | textbox | DATE SUBMITTED:
text | b74a00ad-23c9-5969-9f07-9d4317bf8062 |  | textbox | SUBMITTED BY:
text | 13e406a6-6ef3-5ccd-ae43-a56cb66f24dc |  | textbox | SPECIFICATION AND CLAUSE:
text | b5d8f1b7-a235-55e9-96d1-9b11ad6c9505 |  | textbox | WITNESS POINT DESCRIPTION:
text | 42732d2c-9996-5a1d-9fc9-622575d4221f |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 12 - Inadequate Foundation Material
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 856c6966-0ee8-5416-95b6-38afe83e0ed3 |  | note | REQUIREMENTS / REFERENCE:
label | 9835b021-44bf-565e-8b73-de55d48d1dd5 |  | note | • WCC 1351 Cl 3.3
label | e5b4ab3d-ec03-5074-bdb0-a12dce032ca5 |  | note | • WCC 1351 Annex 4.1
label | e84ef9aa-d814-53e6-8ef7-1273127df9de |  | note | • WCC 1112 Cl 4.3
label | 244e3d74-42df-5861-abf0-0327bdb3270e |  | note | ACCEPTANCE CRITERIA:
label | 104e5b18-5b2e-5486-aa0d-9ee830bcf512 |  | note | • WITNESS POINT: Provide notification to the Principal of the area containing unsuitable material to support the drainage system
text | c7173550-b680-50eb-a25d-d679f2f58ee5 |  | textbox | WITNESS POINT NUMBER:
text | 19ed56b6-9d06-501b-b016-4b68056df93b |  | textbox | DATE SUBMITTED:
text | 1e07919a-4ca0-562b-9a98-de444e5b7e40 |  | textbox | SUBMITTED BY:
text | c0a250ed-960e-5df3-bda8-0290691f02ef |  | textbox | SPECIFICATION AND CLAUSE:
text | f5765ccc-5936-5763-99ba-c18d6a6c2ace |  | textbox | WITNESS POINT DESCRIPTION:
text | 7c943541-b2de-5224-9889-7135164efdf7 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 13 - Foundation Inspection
checkpoint-status |  |  | checkpoint | HOLD POINT
label | e34ee506-5259-578a-a2ab-23ac9d4cc2ef |  | note | REQUIREMENTS / REFERENCE: WCC 1354 Annex 4.2
label | c0a84dae-a96f-5a52-a099-6cf4ec8be9a4 |  | note | ACCEPTANCE CRITERIA:
label | c8c36713-7521-5ce4-9d7a-ea7690b87f3e |  | note | • HOLD POINT: Provide notice of completed excavation and compaction of foundations 1 day prior to the commencement of drainage structures and foundations
text | 58f10673-e384-5833-9557-27da47d5bea5 |  | textbox | HOLD POINT NUMBER:
text | b4d26a0a-cf86-5be5-8c4a-52767f338ccd |  | textbox | DATE SUBMITTED:
text | 6435fb21-146f-51e2-901b-d2055ebcf46c |  | textbox | SUBMITTED BY:
text | 00f1fa86-f612-50f9-b329-651faf5f8842 |  | textbox | SPECIFICATION AND CLAUSE:
text | 60cfc151-7e57-51cb-aad9-5a94cefebb21 |  | textbox | HOLD POINT DESCRIPTION:
text | 42e9f501-cee9-5297-9eb4-d450285244eb |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 14 - Compaction of Subgrade - Culverts
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 6bae747e-a09d-564b-8411-85f4a25dd4f6 |  | note | REQUIREMENTS / REFERENCE: WCC 1351 Cl 1.4
label | 86439902-5498-5a9d-843d-f2d71788d56f |  | note | ACCEPTANCE CRITERIA:
label | 9a5864d5-95b0-5ca1-b99c-b0b23295ae1e |  | note | • WITNESS POINT: Provide notice to the Principal of an upcoming inspection 1 day prior to the compaction and suitability of subgrade under the culverts
text | 6e3eab0e-3e2b-5e31-88e4-3d7e184a41d9 |  | textbox | WITNESS POINT NUMBER:
text | 5aff9866-06ca-5aa3-babc-916bb7560aa5 |  | textbox | DATE SUBMITTED:
text | ff34bf8a-aba3-56c3-b5b7-871bfd6324e1 |  | textbox | SUBMITTED BY:
text | 659d6be3-146a-5eaa-a891-f65f4c991bf5 |  | textbox | SPECIFICATION AND CLAUSE:
text | 5fac6864-8d14-5e9f-ac6e-51a2b16e65b9 |  | textbox | WITNESS POINT DESCRIPTION:
text | cbf7989a-da31-5fc4-8aae-d1376d7b2f8a |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 15 - Rock Foundation Notice
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 288ad80c-5c51-5641-b85f-588f9ae066c5 |  | note | REQUIREMENTS / REFERENCE: WCC 1351 Cl 3.3
label | fa424fb3-5c6e-5136-9121-53bfe8fea75c |  | note | ACCEPTANCE CRITERIA:
label | 122ba457-2f6a-521d-91f3-5cec9b7220a4 |  | note | • WITNESS POINT: If rock is encountered at foundation level, provide notice to Principal prior to proceeding, then excavate to a depth requiring by the pipe type and backfill with compacted selected fill (if required)
text | dbb81430-b5f5-5405-95d2-b444b72eff65 |  | textbox | WITNESS POINT NUMBER:
text | 154dd4cd-a777-5ccd-901e-faa101723ff1 |  | textbox | DATE SUBMITTED:
text | 80e64595-2ac2-5e8e-800b-e39818abfb07 |  | textbox | SUBMITTED BY:
text | 0c1235ea-bedb-5193-a3bd-3c6cb00a7796 |  | textbox | SPECIFICATION AND CLAUSE:
text | a484f9c5-331d-5f61-80dd-55e81039e628 |  | textbox | WITNESS POINT DESCRIPTION:
text | 496cb7cb-c457-56f7-9460-c6685c085670 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 16 - Rock at Wingwalls or Headwalls
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | b25d4ba5-e968-5165-87cc-2d4f7644822e |  | note | REQUIREMENTS / REFERENCE: WCC 1354 Cl 3.2
label | 4ec56a96-e261-51b0-869d-dadb2712aeed |  | note | ACCEPTANCE CRITERIA:
label | 3c08b794-0a3a-5181-b79d-5ad03bef0837 |  | note | • WITNESS POINT: If rock is encountered at the bottom of excavations for wingwalls and headwalls, provide notice to Principal at completion of excavation and compaction (if required)
text | b058407f-c65d-5926-9c13-efaa53f0e8cf |  | textbox | WITNESS POINT NUMBER:
text | 2996b643-cbc2-5d1f-9d6c-6c9163955903 |  | textbox | DATE SUBMITTED:
text | 4dfd6dbf-ee0d-5539-a19e-d827a29c04c9 |  | textbox | SUBMITTED BY:
text | bd0131a4-9f20-501a-99a3-682a34c9ee5a |  | textbox | SPECIFICATION AND CLAUSE:
text | 9084d5ca-7b9a-5678-b0e9-97f24d700fa0 |  | textbox | WITNESS POINT DESCRIPTION:
text | 96b75527-0e8d-5b06-8a09-44c1fb26167e |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 17 - Rock at Gully Pits and Sumps
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 3437f311-53b3-5c53-8bd0-158789f1e1f7 |  | note | REQUIREMENTS / REFERENCE: WCC 1354 Cl 3.2
label | 1d1ba7c8-782d-5924-8206-c1796251fa70 |  | note | ACCEPTANCE CRITERIA:
label | 7d9a6114-3e21-50d0-8a1a-4cdc682a30f8 |  | note | • WITNESS POINT: For gully pits and sumps, if full depth of excavation is in sound rock, construct a neatly formed pit of the required size and omit the concrete lining except to the wall adjacent and parallel to the road. Provide notice to Principal at completion of excavation and compaction of foundation (if required)
text | 4c3e2d9a-ea6f-5e99-ab4c-8cb5491b8b01 |  | textbox | WITNESS POINT NUMBER:
text | e236ec99-683f-5b42-8ce9-d025f21f1e91 |  | textbox | DATE SUBMITTED:
text | 07dce619-8af6-58e0-b01d-7f27f4099a88 |  | textbox | SUBMITTED BY:
text | c913ae01-a63e-5123-9551-b8551027455a |  | textbox | SPECIFICATION AND CLAUSE:
text | 61ec1432-a780-530f-893d-c59c358b0344 |  | textbox | WITNESS POINT DESCRIPTION:
text | 196ac859-5780-514b-9988-80a7ece8818b |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 18 - Inspection of Pipework Installation
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 266f98bd-7208-5795-8a19-9f59cd1a5e88 |  | note | REQUIREMENTS / REFERENCE: WCC 1352 Annex 4.1
label | cbd2f5e2-4d88-5caa-8d5a-8e4bbd3e3288 |  | note | ACCEPTANCE CRITERIA:
label | 8ab6be0c-bdb1-5f74-8c09-62249cbac09c |  | note | • WITNESS POINT: Provide notice to the Client for an inspection of each section of the installed and jointed pipework prior to the commencement of trench backfilling
text | 1dc93467-eeec-570a-9d93-57b9ae170c78 |  | textbox | WITNESS POINT NUMBER:
text | d998f7c3-3f78-5d90-b18b-ad6d0308975e |  | textbox | DATE SUBMITTED:
text | 17125913-cf55-57c5-b4b0-c0195f208dae |  | textbox | SUBMITTED BY:
text | 83d86d88-a45c-5ace-8f38-ee4276ab7c72 |  | textbox | SPECIFICATION AND CLAUSE:
text | d507378b-90e7-5f3b-a5f4-40b5cb84650f |  | textbox | WITNESS POINT DESCRIPTION:
text | 5225685e-12b7-5db4-b0f5-2e192079a0af |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 19 - Installation of Precast Units
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 4a972a1a-f0d9-5f31-9977-c86562829ced |  | note | REQUIREMENTS / REFERENCE: WCC 1354 Cl 1.6
label | a7cd604f-259c-5464-a4d1-bcc84c05d512 |  | note | ACCEPTANCE CRITERIA:
label | 3e3a0d7b-430e-5368-bc5c-7a536d399a7e |  | note | • WITNESS POINT: Provide notice to the Client of the anticipated date of precast pit installation(s) 5 days prior to the anticipated date
text | eb4eddb1-52dc-593f-aefe-bbf201890f45 |  | textbox | WITNESS POINT NUMBER:
text | 1b7eb78d-840e-5eea-92de-801138bb43e0 |  | textbox | DATE SUBMITTED:
text | 424211b4-b382-5344-8329-936fc36bbb34 |  | textbox | SUBMITTED BY:
text | 8b91dd94-fc63-54a1-adf6-ad1173d3cb50 |  | textbox | SPECIFICATION AND CLAUSE:
text | f3526d6f-8ee1-5e69-869f-309056f0747b |  | textbox | WITNESS POINT DESCRIPTION:
text | c81c72d2-d4f5-5df7-b2a1-921a4f3d3ed7 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 20 - Backfill of Pipes and Precast Drainage Structures
checkpoint-status |  |  | checkpoint | VERIFICATION
label | e55585cc-401a-50d1-b050-58fc35184fdd |  | note | REQUIREMENTS / REFERENCE:
label | 62e1a5db-7699-5259-9693-515b92a38057 |  | note | • AS/NZS 2566.2
label | 18db6e3e-7e11-5363-ad5e-fde8bef3972e |  | note | • WCC 1354 Cl 3.6
label | 18ba7407-264d-59ed-a586-6547ca2a8122 |  | note | ACCEPTANCE CRITERIA:
label | e41d456c-c78d-511f-813d-8bb9aa50f0d8 |  | note | • Compact bedding and backfill as per WCC Specifications and requirements stated in the project Drawings
label | a583d80c-8933-5f3a-aa3e-9bf06cb05e72 |  | note | • Provide compaction and moisture test results (if required)
label | 505d045b-645b-5e69-9b10-b42b2248ef82 |  | note | COMMENTS / ATTACHMENTS: Compaction and moisture test results
checkpoint-group |  |  | section | 21 - Backfilling of In-Situ Drainage Structures
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | ceab9ba0-5063-5aa5-8b22-4b062af13420 |  | note | REQUIREMENTS / REFERENCE:
label | 176d3b78-8205-5da0-b5ba-a492b109192e |  | note | • WCC 1354 Cl 3.6
label | 30d27e9f-8f60-5641-b153-53a0d938d49b |  | note | • WCC 1351 Cl 3.4
label | 82b45d1f-a7de-5ab2-999b-2f3f8b505c94 |  | note | ACCEPTANCE CRITERIA:
label | a0c0a942-7ac6-50f3-8fab-005f2aae5557 |  | note | • WITNESS POINT: Do not backfill against structures less than 14 days after placing concrete or before the concrete strength is more than 15 MPa. Provide notice of in-situ concrete structure backfill 2 days prior to date of backfill (if required)
label | 7a562c3b-7a7d-56e3-82f8-b2336e33351b |  | note | COMMENTS / ATTACHMENTS: Concrete test results
text | 2cec5c82-c7b5-56b5-b0de-f31e519edc53 |  | textbox | WITNESS POINT NUMBER:
text | 5efc2ae7-90e5-5340-9c0e-3ddf4d8b1eb8 |  | textbox | DATE SUBMITTED:
text | b662fed5-d788-51a5-94d7-2717ec4c24d4 |  | textbox | SUBMITTED BY:
text | 795fefd3-7dcc-597f-bf90-c207d6fb4426 |  | textbox | SPECIFICATION AND CLAUSE:
text | 48d6970e-13df-5ed6-8247-80317b7ee4c6 |  | textbox | WITNESS POINT DESCRIPTION:
text | 196e7f89-ba41-5a33-99ae-4eb5be27443b |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 22 - Compaction Adj. to Culverts or Drainage Structures
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 9a77f4cb-fd93-583e-af51-ba00a04d1adf |  | note | REQUIREMENTS / REFERENCE: WCC 1351 Annex 4.1
label | eaef8397-bf7f-5ac0-b299-1965c1d5ed17 |  | note | ACCEPTANCE CRITERIA:
label | c28f7346-666b-52ac-8341-8e8373e8a589 |  | note | • WITNESS POINT: Prior to proceeding with the entire backfilling process, provide notice of an inspection to the Principal to observe the compaction around culverts to check compliance
text | 80b0d1c9-f55d-5e5b-ae3f-5a3fd32a5727 |  | textbox | WITNESS POINT NUMBER:
text | 70dd3f67-ba39-5f08-b327-71d0ea5126f3 |  | textbox | DATE SUBMITTED:
text | b2b453e1-12ff-599e-b745-251ab29149bb |  | textbox | SUBMITTED BY:
text | 5bfc90ea-9f63-58bf-bb9d-2edfbc044cbb |  | textbox | SPECIFICATION AND CLAUSE:
text | f0fbf0d4-dbd6-59f8-b10e-524cce9c74b5 |  | textbox | WITNESS POINT DESCRIPTION:
text | 5b49f13d-175b-574a-b80d-515c65f7f7cb |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 23 - Compaction of Pipe Drainage Bedding
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 6bb0a8af-938b-5c91-895c-d27ab800ad98 |  | note | REQUIREMENTS / REFERENCE: WCC 1351 Annex 4.1
label | 9bd3a5dc-76a4-5a66-a3ef-b7d53aa3601e |  | note | ACCEPTANCE CRITERIA:
label | 7570463f-d3b5-57d9-a96a-d6dad294d86f |  | note | • WITNESS POINT: When required to cementitiously stabilise concrete pipe bedding and haunch zones, provide notice to the Principal of the compaction of drainage bedding prior to proceeding (if required)
text | 34630ad7-8fa0-5f1c-a5f5-385e7cb12a5b |  | textbox | WITNESS POINT NUMBER:
text | a08579aa-d345-51ec-866a-bb9938170dd8 |  | textbox | DATE SUBMITTED:
text | 059c7bcc-9b65-5451-9b79-f6395b02940f |  | textbox | SUBMITTED BY:
text | e5b8eebf-b0de-5b77-8a6f-4b5c199174da |  | textbox | SPECIFICATION AND CLAUSE:
text | f3c401fe-6823-5afc-9cb3-85e520faa9db |  | textbox | WITNESS POINT DESCRIPTION:
text | d0b10c8e-b9b5-5fbd-93a1-8655b283d6a5 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 24 - Construction Traffic
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 6c8ee97a-7456-5907-9c0f-9846547e0aab |  | note | REQUIREMENTS / REFERENCE: WCC 1351 Cl 3.1
label | 58fd0577-7cd3-5a77-920e-c64ba07f9653 |  | note | ACCEPTANCE CRITERIA:
label | 144012f2-3015-5361-a904-19e05add4da4 |  | note | • HOLD POINT: If proposing to move heavy construction plant or vehicles over pipe or box culvert structures provide protective measures. Submit certificate of verification of protective measures 5 days prior to installation
text | f22e33f9-af21-5b2e-9333-e2c3701a2988 |  | textbox | HOLD POINT NUMBER:
text | d3fb7763-b12f-503b-8f85-ade4f8bcb620 |  | textbox | DATE SUBMITTED:
text | 6949a499-164e-57d1-81ed-aee59892681f |  | textbox | SUBMITTED BY:
text | 60adea97-2e63-5162-80ea-6646274b12a6 |  | textbox | SPECIFICATION AND CLAUSE:
text | 302a418d-5e58-5e61-b85d-dea9d4f385cb |  | textbox | HOLD POINT DESCRIPTION:
text | 3516d0a0-426f-53ec-ab9d-34a66e14ef62 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 25 - Completion of Works
checkpoint-status |  |  | checkpoint | VERIFICATION
label | fc175a8f-70c4-5cb6-9a2d-f0cb0b253d8c |  | note | REQUIREMENTS / REFERENCE: WCC 1351 Cl 3.9
label | a74dee69-16ab-53ce-960f-cf77f9192253 |  | note | ACCEPTANCE CRITERIA:
label | 26652416-a5a0-5b48-a14f-255640fd091f |  | note | • Inspect drainage structures first upon completion of all drainage structures and prior to commencement of pavement construction above, and again no more than 14 days prior to completion. Verify the works are within the specified tolerances, there are no visual signs of structural failure, and there is no obstruction to the flow of water
label | e686f89a-7caf-5a41-b690-a0708768201e |  | note | • On completion of the drainage system, flush all pipes clean from end to end and leave in working order
label | 76a34088-d499-5004-b0bb-49fff087d790 |  | note | COMMENTS / ATTACHMENTS:
label | 1f0f4341-3a82-55b5-ab2e-628cf95e7bc4 |  | note | • CCTV / Inspection records (Initial inspection)
label | db2a4005-73b1-5bb7-a71f-fb0c4182f23b |  | note | • CCTV / Inspection records (Final inspection)
checkpoint-group |  |  | section | 26 - Works As Executed (WAE) Drawings
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 4303f2bd-c78d-5854-8114-ba34ff90c2da |  | note | ACCEPTANCE CRITERIA:
label | abbd5756-9222-5940-8950-0965ef873de7 |  | note | • Provide Works As Executed (WAE) Drawings and Survey Reports for the completed works
label | 0c44a6cc-7f76-5624-b8a1-22ed24acec2d |  | note | COMMENTS / ATTACHMENTS: WAE Drawings, Survey Report(s)
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | e119c7bb-c0e0-5461-96ab-8d905f8787f2 |  | textbox | Lot Verified By:
text | 384d4c4c-261a-579d-9bc6-474c6224f0be |  | textbox | Lot Closed Date:
button | 0bd273c4-44ab-5159-9ba0-012871bc0b32 |  | button | Submitted to Client | Yes, No, N/A
button | 584fd6e7-6b9d-5c8b-8246-ceddd541dd3d |  | button | Reviewed by Client | Yes, No, N/A
text | e6b11544-9305-509d-80c8-4a35fdc19014 |  | textbox | Submission Comments:
checklist-sectioned |  |  | checklist | A181 - West Dapto - ITC 013 (ITP013) - Asphalt (Roadways) |  |  |  |  | Yes | A181 - West Dapto - ITC 013 (ITP013) - Asphalt (Roadways) | 81de3292-d654-48ba-9755-dc147e0dbe2b
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | b0023ede-255c-5aad-ac67-569a1f7aaa00 |  | textbox | Lot Opened On
text | ca07ec4d-6b15-577a-8325-73c5bd3e42ec |  | textbox | Date of Works
text | 3b5c95b2-25ae-5bad-b4f4-2fe3f3f4586d |  | textbox | Lot Type
text | 9b5dbc22-4582-564d-b420-86b921ba02ec |  | textbox | Start Chainage
text | b8f17e24-d6bd-5296-a1fa-6382e1ae8cc5 |  | textbox | End Chainage
text | a0bb616e-3c42-4e6c-af8e-3ae4e89d539d |  | textbox | Offset
text | 61f32538-ad3c-5297-a413-f7f201a059c0 |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Road Occupancy
checkpoint-status |  |  | checkpoint | VERIFICATION
label | e3aa36bb-3598-5010-bf03-8f4ff07f9989 |  | note | REQUIREMENTS / REFERENCE: 1144 Cl 2.1
label | 118a2aa3-277d-5b38-b313-05a6f56b414e |  | note | ACCEPTANCE CRITERIA:
label | d2090e56-1a39-55ed-b949-6c86624015c6 |  | note | • Obtain road occupancy license prior to commencing
checkpoint-group |  |  | section | 2 - Mix Design
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 78c82396-4eb8-5d1f-802a-9352e21ee72b |  | note | REQUIREMENTS / REFERENCE: 1144 Cl 1.7
label | 4fb852c2-34bf-50de-80ec-642a824a2b19 |  | note | ACCEPTANCE CRITERIA:
label | 0553ab5e-833a-542d-b5c6-264fa356f293 |  | note | • HOLD POINT: 10 days prior to mix production, submit the following:
label | 5f358b0d-3985-5497-8044-e9d88f184bec |  | note | • Documentation for material type, source, proportions, test certificates and evidence of conformance for each constituent (agg, filler, binders etc)
label | 0f51c8ac-d840-56f4-96fb-e928f47f5ecb |  | note | • Documentation and test certificates verifying the mix design meets the project requirements
label | 0bdc5ff1-d984-5399-846f-07f1c9c96169 |  | note | • Particle size distribution as a single grading and nominal size
label | f1a456b0-71cd-5c83-8860-d76fdb16912f |  | note | • Mix design to be selected from Clause 3.4 and contents to conform to Table 3.6
text | fafbb922-d04f-55ff-8845-064af3e51cd4 |  | textbox | HOLD POINT NUMBER:
text | 4cba58dd-8604-584e-a7a1-523f468c6ec3 |  | textbox | DATE SUBMITTED:
text | 48b99c1c-802f-597f-bcf3-1538a8fce221 |  | textbox | SUBMITTED BY:
text | b53c73d7-3b97-52e0-a5c1-8f5e2d294c7a |  | textbox | SPECIFICATION AND CLAUSE:
text | 5abef87b-3132-5b69-9e77-40e70beb31e0 |  | textbox | HOLD POINT DESCRIPTION:
text | 7513bf06-d31d-5e56-8777-affaf8384a8d |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 3 - Test Certificates
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 7de18a6f-a74a-5b4b-b3ad-7a3cf0f15380 |  | note | REQUIREMENTS / REFERENCE: 1144 Cl 1.7
label | ebc4b619-21cd-5819-aa7d-0868d6344619 |  | note | ACCEPTANCE CRITERIA:
label | 06520830-2ac2-55ba-952b-60a61bf4d33a |  | note | • HOLD POINT: Submit test certificates for mix production 7 days prior to ordering materials
text | a20f8bb2-1766-5e97-95a6-92df8689b27a |  | textbox | HOLD POINT NUMBER:
text | 47fda654-5a68-5f8b-8fb0-67a6ee350c0a |  | textbox | DATE SUBMITTED:
text | b10b6927-62bf-5452-89b1-4d0a20a74642 |  | textbox | SUBMITTED BY:
text | df4f0629-66d3-5ea0-99b8-9a5092e73ae6 |  | textbox | SPECIFICATION AND CLAUSE:
text | 83348d13-8ed3-5a82-acf0-06903be9bee2 |  | textbox | HOLD POINT DESCRIPTION:
text | c26c8ff2-3af7-5876-b844-620c563d5add |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 4 - Trial Mix
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 0fe67f7e-f591-5767-95de-3e8a3d427ad9 |  | note | REQUIREMENTS / REFERENCE: 1144 Cl 1.7
label | 7eb613eb-4235-5f80-aeb2-6df163aabddb |  | note | ACCEPTANCE CRITERIA:
label | c37b789d-cbf5-54af-9a2e-6e59ba91a852 |  | note | • Submit trial mix testing results for review and approval
label | 33485aaf-15d0-51b9-ab28-8f92c82e62a6 |  | note | COMMENTS / ATTACHMENTS:
label | 17c5e926-c8d9-5d55-9624-108c36005fa5 |  | note | • Trial mix testing results
checkpoint-group |  |  | section | 5 - Production Mix
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 57b0b80e-7f2e-5420-a745-a40555f7b109 |  | note | REQUIREMENTS / REFERENCE: 1144 Cl 1.7
label | 838f222a-b2bb-5762-9e6b-7e9146af238b |  | note | ACCEPTANCE CRITERIA:
label | 45bad061-b63a-5723-98fc-a044b4c72368 |  | note | • Submit evidence of conformity to the approved mix design and mix properties for each production batch
label | ffad0175-8976-57d7-b7cc-1573a83fd838 |  | note | COMMENTS / ATTACHMENTS:
label | 1c657629-2906-5094-a615-09d4decf057b |  | note | • Certificates of Conformity
checkpoint-group |  |  | section | 6 - Low Temperatures
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 6cefd6d5-4dd6-5c7a-b75b-e8e986a38e2a |  | note | REQUIREMENTS / REFERENCE: 1144
label | 60417791-cebc-5ceb-94f2-5b79d945eb65 |  | note | ACCEPTANCE CRITERIA:
label | cc05ff0c-818d-5c3e-9676-e121ea2f637a |  | note | • HOLD POINT: 1 day prior to spreading, submit proposed procedures for spreading at low temperatures, if required
text | 05795933-eed5-5a0a-b9b0-b72ab722d72e |  | textbox | HOLD POINT NUMBER:
text | efdf9590-b8c1-5635-a9ed-674db93522f6 |  | textbox | DATE SUBMITTED:
text | b992e8ae-6d3a-535c-aeef-751a1e3ea911 |  | textbox | SUBMITTED BY:
text | ba4fafab-9120-50c0-88d4-04f21eb295da |  | textbox | SPECIFICATION AND CLAUSE:
text | 7c4fd3b4-a278-53d4-b5c9-9c8a1bf6563e |  | textbox | HOLD POINT DESCRIPTION:
text | 6c7dfe54-0c9f-538a-b3de-f8769a6cbbe7 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 7 - Joints
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 398d546c-81c8-5cbb-bb7d-0f31d7fa16ca |  | note | REQUIREMENTS / REFERENCE: 1144
label | b4ed3ef9-3950-5959-83b2-7e7d435a61e4 |  | note | ACCEPTANCE CRITERIA:
label | 758217a3-553d-5ce8-9d8f-ba7942e325d8 |  | note | • HOLD POINT: 7 days prior to placing, submit a plan of joint locations
label | f013d80d-510d-523f-be54-6903652a8788 |  | note | • Provide longitudinal joints if the width requires more than one run
label | 80574453-cb66-59e7-9896-dbf726986a3b |  | note | • Transverse joints only to be used when required
label | afd85a82-3a67-5aea-ba5b-bd956ab1d370 |  | note | • Align joints with wearing course or traffic markings
label | 5f7098a0-efa7-5aed-b66d-65e899f6f39c |  | note | • Conform to requirements for hot, warm and cold joints
text | 200cb5c9-f24c-5cbd-b310-1c911c8e901e |  | textbox | HOLD POINT NUMBER:
text | 491d236e-032c-5449-a660-2938031c0d09 |  | textbox | DATE SUBMITTED:
text | daff233c-c9b3-5da2-a32a-bb4815cdc238 |  | textbox | SUBMITTED BY:
text | ba2beb9e-895d-5f91-bb51-1d4d2e8b1e9b |  | textbox | SPECIFICATION AND CLAUSE:
text | ac2c07bf-98ef-58ef-a287-1fe971bd4a86 |  | textbox | HOLD POINT DESCRIPTION:
text | 664aa11f-6b34-54db-8f7b-8b7f08d8749a |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 8 - Surface Preparation
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 3c95d294-7122-5244-b9a7-066934f86138 |  | note | REQUIREMENTS / REFERENCE: 1144
label | e10dfda5-04fb-5c00-bd54-2fa3fed5e533 |  | note | ACCEPTANCE CRITERIA:
label | 030aab97-6fcf-5ddd-8a2b-39518b36ef14 |  | note | • HOLD POINT: 7 days prior to placing, notify the Principal for inspection of the following:
label | a54bc472-0535-51d5-b73d-0024346ef921 |  | note | • Completed surface preparation including repair of defects
label | a7c74730-1044-534a-9d50-fae3932cbbf2 |  | note | • Confirm base gravel is approved for surfacing to commence
text | 0b421dea-4e73-541c-b6a9-f2acd78052b3 |  | textbox | HOLD POINT NUMBER:
text | 9e5cbdda-7a20-5f17-b1f3-4f462ccb6550 |  | textbox | DATE SUBMITTED:
text | 493cb1cd-7494-5eed-99c9-2194efc3b044 |  | textbox | SUBMITTED BY:
text | 8d8b935a-f9cb-54e7-97d3-7f011efee279 |  | textbox | SPECIFICATION AND CLAUSE:
text | d72d4236-69b3-5087-8c40-cc26e8559d14 |  | textbox | HOLD POINT DESCRIPTION:
text | 5d388f25-1d72-56c9-818d-113b21bf2c35 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 9 - Equipment Inspection
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 8f99fd6b-53c7-592b-bf7d-9759f8b239a1 |  | note | REQUIREMENTS / REFERENCE: 1144 Cl 4.3
label | cec33bbe-f0a7-5e05-8437-51835509b030 |  | note | ACCEPTANCE CRITERIA:
label | 9a272593-6a7b-5db1-87a2-5b6102371baa |  | note | • WITNESS POINT: 1 day prior to equipment use, mix production or spraying, notify the Principal to inspect the following:
label | ffe64a4b-58e2-5a04-8f1c-e55b962cf4de |  | note | • Asphalt production and delivery equipment condition
label | 5b1b065a-05d4-5bcd-aca6-65276a96df34 |  | note | • Spraying equipment condition and calibration
label | 47d645a2-ec71-579a-a071-24978edf6405 |  | note | • Mobile equipment condition
label | 1e0a95ce-f441-5540-951a-842baa7ee433 |  | note | • Do not use faulty plant or equipment
text | 0acaa6b1-6582-5547-b5a1-1f0c730c1b03 |  | textbox | WITNESS POINT NUMBER:
text | a4307735-e5b8-57e2-b16a-8a5a771b7908 |  | textbox | DATE SUBMITTED:
text | 5aa89cc2-fc82-51f8-973d-57bfb56f03a0 |  | textbox | SUBMITTED BY:
text | 2c081b37-5f22-5f23-8fcf-6eff4f81eca0 |  | textbox | SPECIFICATION AND CLAUSE:
text | 5d572bf4-cbc2-538d-bd12-0238582d60f5 |  | textbox | WITNESS POINT DESCRIPTION:
text | 02771288-c123-5394-a452-0b3966924eca |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 10 - Placement and Compaction
checkpoint-status |  |  | checkpoint | VERIFICATION
label | ce38b55f-d1fc-5c9b-8370-bbfb9ef82bac |  | note | REQUIREMENTS / REFERENCE:
label | 86083e6e-2a6b-5aeb-b203-1e5bb9294f9f |  | note | • 1144 Cl 4.4
label | e70a3c28-3c56-5a92-afed-8ef39a31b6f3 |  | note | • 1144 Cl 4.6
label | 3d2149fb-cf6f-5929-9c47-ce4706403d50 |  | note | • 1144 Cl 3.8
label | 5e6390ab-c113-5ce0-96bf-16c8a8496800 |  | note | ACCEPTANCE CRITERIA:
label | 6a363c6a-cc81-54d6-9383-f342b6b2b4a3 |  | note | • Mixing temperatures to conform to Table in Clause 4.4
label | 3ba2887b-050b-5655-83c8-93aee9d8c19a |  | note | • Clear surface of deleterious materials before tacking and placing
label | e5311e99-815c-521b-9385-1b5ab151c157 |  | note | • Protect services and fixtures adjacent to surfacing area
label | 3a3c9b67-8946-53f9-b383-7c07cca9b831 |  | note | • Apply tack coat using bitumen emulsion to AS 1160, applied at the unform rate detailed in Clause 4.6
label | 220317ac-349f-5454-a3ee-65b5e9922b11 |  | note | • Uniformly compact asphalt as soon as sufficiently cooled. Use vibrating or pneumatic tyred rollers for compaction
checkpoint-group |  |  | section | 11 - Testing
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 2dea023d-9445-500b-825f-e77419d1a83a |  | note | REQUIREMENTS / REFERENCE: 1144 Cl 1.7
label | 0501441e-b9e9-526e-8533-c89ddb106cdd |  | note | ACCEPTANCE CRITERIA:
label | 7b0d88e6-433e-5d03-b32e-c718dedc6a50 |  | note | • Provide test certificates verifying compliance with specified compaction requirements
label | 76dae59a-cb77-5d24-80f4-1196e623410e |  | note | • Frequency of testing to conform to maximum lot size and minimum number of tests
label | d7c2c39f-478d-57dc-86f5-70d20db6ea4a |  | note | • Test for all characteristics
label | ec29ffeb-8cf0-5ada-b194-bc8083091d60 |  | note | COMMENTS / ATTACHMENTS:
label | 555b674e-1352-5506-a040-8757b5932480 |  | note | • Test Certificates and Records
checkpoint-group |  |  | section | 12 - Tolerances
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 6adfe9e7-dc00-5382-bd57-ed304b015100 |  | note | REQUIREMENTS / REFERENCE: 1144 Cl 1.6 & 4.7
label | 858b4c7c-51ab-5fa4-b1a7-349e061bf40e |  | note | ACCEPTANCE CRITERIA:
label | 9ec27ce6-6f47-5b04-bffd-feaa7a2580d7 |  | note | • Levels for each course of asphalt ±10mm
label | 8fafe147-27b6-5516-8ee7-db6bbab37204 |  | note | • Average total compacted thickness of the combined asphalt courses ≥ documented thickness
label | 3dcc5825-1dac-5231-8c3d-142b3f5ff305 |  | note | • Average thickness of any individual course ≥ documented thickness by more than 10%
label | af9564c7-a7bb-58e8-9495-c56d1790cfcf |  | note | • Surface shape tolerance conforms to Table 1.6
label | 5fcf933a-0919-58cd-a17b-3a1927dc7812 |  | note | • Density assessment to conform to Clause 4.7
checkpoint-group |  |  | section | 13 - Daily Work Records
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | e2e0511b-e0db-5a82-805f-10cafad753c9 |  | note | REQUIREMENTS / REFERENCE: 1144 Cl 1.7
label | 8f0aeabe-dd48-5598-b8ce-3f43132d1156 |  | note | ACCEPTANCE CRITERIA:
label | 801b9fc0-ae11-5cf9-a3c9-5ccfd627a656 |  | note | • WITNESS POINT: Submit to the Principal on the day of delivery, the asphalt work record as per Annexure 5.1 of 1144, along with delivery dockets
text | d68d5522-b71b-53e8-982c-b487f0c8f6bb |  | textbox | WITNESS POINT NUMBER:
text | 40889abd-bc2c-56e6-b6a8-e6d8dbc3093f |  | textbox | DATE SUBMITTED:
text | dda92588-6f1c-56d9-b8e0-697ae5d5e1d4 |  | textbox | SUBMITTED BY:
text | 5ae602f2-6fda-5803-800b-a6fd8fd6b154 |  | textbox | SPECIFICATION AND CLAUSE:
text | c89ed325-cc98-5bbf-8e8d-f8228d0be73f |  | textbox | WITNESS POINT DESCRIPTION:
text | 2bc88d70-1a83-598b-bb5b-4427f63c39a5 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 14 - Spreading & Compaction
checkpoint-status |  |  | checkpoint | HOLD POINT
label | b9ada221-ebc5-587d-877a-d553ed200f5a |  | note | REQUIREMENTS / REFERENCE: 1144
label | 25a97b1f-f575-57c3-8e88-5215d1d23b14 |  | note | ACCEPTANCE CRITERIA:
label | db6856ba-48d3-5445-8bcd-9851ffe6b6ea |  | note | • HOLD POINT: Prior to commencing the next pavement lot or linemarking, notify the Principal to inspect the completed surface 2 days after compaction
text | 8a721405-b488-5f90-8423-25f090fae2ba |  | textbox | HOLD POINT NUMBER:
text | c66c37a8-ef41-5281-8382-3853d6245aaf |  | textbox | DATE SUBMITTED:
text | 02a513c5-44b7-5fdf-b97a-8c8af49e427d |  | textbox | SUBMITTED BY:
text | dd067571-7c8e-5104-af22-fe76204ecc60 |  | textbox | SPECIFICATION AND CLAUSE:
text | f86f5513-99d7-57fc-a186-c31f294de19b |  | textbox | HOLD POINT DESCRIPTION:
text | 2f26c0d7-9428-57df-83a6-16c4eaf2501f |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 15 - Asphalt Works Records
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | a6031858-92cf-5ced-8e7f-3522e576afa4 |  | note | REQUIREMENTS / REFERENCE: 1144 Cl 1.7
label | 09e9c433-9ccc-5a94-bf31-180a2a3d8825 |  | note | ACCEPTANCE CRITERIA:
label | cea1fc54-9d83-5a1b-b14c-5cbfa8b9f5cb |  | note | • WITNESS POINT: 7 days prior to finishing processes such as linemarking and placement of RPMs, submit to the Principal for inspection the following:
label | 78185418-4834-5ed1-ba4f-ca2c3bdf1bda |  | note | • QA documentation of delivery, finishing and testing
label | 0e095146-3a4f-5287-b207-56715b55f9f6 |  | note | • Survey certificate showing surface level and thickness tolerance
label | e49fda90-06c0-5a90-be4f-6de4f22fe19d |  | note | • Inspection record verifying finish, shape, alignment and width
label | ece39ca4-4364-5734-87ad-930dd4fd31cb |  | note | • Lot diagram with bounds
label | b29a5ecd-3e6f-5de4-a910-712c15670d5e |  | note | • Updated lot register
text | a99843fd-befd-538e-80c4-be1a8578600b |  | textbox | WITNESS POINT NUMBER:
text | 39e3e680-c562-525c-8fab-2c33aef1939f |  | textbox | DATE SUBMITTED:
text | 4b42078c-9bf9-56e5-b22d-4dbcbe107a18 |  | textbox | SUBMITTED BY:
text | 9634d985-a6e4-555e-99f5-393b4ad1c636 |  | textbox | SPECIFICATION AND CLAUSE:
text | d7360973-6b7a-5a66-980b-921f3a85c5a2 |  | textbox | WITNESS POINT DESCRIPTION:
text | d7548dd5-c636-5ea1-a290-34a87eba1f46 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 16 - Lot Package Closure
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 35b3aa06-ba5d-50e0-8d0b-b9863b11adaf |  | note | REQUIREMENTS / REFERENCE: 1144 Cl 1.7
label | 4f8297f2-a670-58b7-bb9c-b4fb53c4be9c |  | note | ACCEPTANCE CRITERIA:
label | 93dc78ec-0c53-5a19-b507-c309d2fdfbbc |  | note | • Provide lot package closure certificates confirming the following:
label | 166eac16-46c7-50b9-86cb-10957d0346e9 |  | note | • All inspections completed
label | 74d41de6-7537-502c-8d14-8e36cd382e5f |  | note | • All tests completed and recorded
label | f1caa0d8-b8d9-5f43-93bd-2856122bac55 |  | note | • All non-conformances notified
label | 22f77711-f185-5e28-ab3b-c4e0bbf783c9 |  | note | • Open non-conformances recorded in defects register
label | 333d3bd8-00ed-525d-a3c2-540386097213 |  | note | • Changes to design details reviewed, approved and recorded
label | 9d369787-8360-5ae8-a468-01db55684dc0 |  | note | • Construction records and as-builts available online
label | c7cd023b-9487-5c76-a62f-8a8d314db15b |  | note | • Lot package closed
label | 85aaa9c6-4dfb-57e3-a666-8d90f30b73dc |  | note | COMMENTS / ATTACHMENTS:
label | 34741ebe-98a6-5d73-be2f-db032448089b |  | note | • Lot package closure certificates
checkpoint-group |  |  | section | 17 - Non-Conforming Sections
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 4667fb31-3a94-50ab-8fbd-cc50341c03a1 |  | note | REQUIREMENTS / REFERENCE: 1144
label | a06ea839-c2e7-5e75-8a86-4f9075e5e620 |  | note | ACCEPTANCE CRITERIA:
label | 6e01e099-0d5b-5752-ae70-7b778e7c7086 |  | note | • WITNESS POINT: Provide the Principal with 1 day’s notice to inspect completed replacement and rectification of non-conforming sections prior to linemarking or opening to traffic (if applicable)
text | c4047306-33ae-54b6-b753-c27946a408b5 |  | textbox | WITNESS POINT NUMBER:
text | 5301bcbd-256c-5c7c-8c20-84d57951d028 |  | textbox | DATE SUBMITTED:
text | 103bca37-d9b2-5924-b87c-55cfe6ccbc32 |  | textbox | SUBMITTED BY:
text | efced791-ebdd-5c69-9b77-1194a53020dd |  | textbox | SPECIFICATION AND CLAUSE:
text | 115c455a-58ca-5edb-b605-8b319dc6fba3 |  | textbox | WITNESS POINT DESCRIPTION:
text | dcf7743c-d05e-5752-9cd9-a004a6d83dda |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | 595efb86-4b62-54b7-8c29-0077a6863022 |  | textbox | Lot Verified By:
text | 11709a7b-34ec-58e7-b6c8-1e70278f7e04 |  | textbox | Lot Closed Date:
button | 63843825-50e3-5c33-b45f-9b95ccd9f0dd |  | button | Submitted to Client | Yes, No, N/A
button | 1f4fbb77-d3cb-5ed1-b2a4-0a8d1c655207 |  | button | Reviewed by Client | Yes, No, N/A
text | 4df0446f-ec56-55f8-b521-f2f2100dc772 |  | textbox | Submission Comments:
checklist-sectioned |  |  | checklist | A181 - West Dapto - ITC 001 (ITP001) - Subsoil and Formation Drains |  |  |  |  | Yes | A181 - West Dapto - ITC 001 (ITP001) - Subsoil and Formation Drains | 89b126c4-34bf-423b-ae18-64ed33e9dd70
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | bdc23671-cf12-5a95-8590-ee871028b537 |  | textbox | Lot Opened On
text | 113f545f-c6a5-5d2f-884a-2f0c933d8c49 |  | textbox | Date of Works
text | 1a3156ec-f83d-55fa-b0ec-1051cb830df9 |  | textbox | Lot Type
text | 68f20b7a-5d21-5fbb-90bb-fd51444a1606 |  | textbox | Start Chainage
text | d5f5bd3b-1916-58f5-a2d8-2ddbc5d6a967 |  | textbox | End Chainage
text | 0a88b471-520d-4c3d-83d4-1b773fb522e9 |  | textbox | Offset
text | 676106be-185d-5cc3-921a-7b222d29e9ee |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Preparation Works
checkpoint-status |  |  | checkpoint | VERIFICATION
label | f84280d5-0deb-5803-9332-8fc6c3a9af36 |  | note | REQUIREMENTS / REFERENCE: Project Safety Plan, Project Environment Plan
label | 5b6f91ed-a9fe-5ca6-8182-d3a60ed72315 |  | note | ACCEPTANCE CRITERIA:
label | dfd311f1-2c99-509f-81e2-48898e27c07e |  | note | • All site personnel inducted, required SWMS completed and signed, Safety Plan approved
label | ae06b376-48a5-51f4-b41a-17ac31c3e969 |  | note | • ERSED controls installed on site, air quality visually monitored for dust etc due to construction activities, Environment Plan approved
label | f9939f44-2766-50dc-807b-39fde0558e2d |  | note | • Contact DBYD and complete excavation permit, extent of works set out with survey pegs
checkpoint-group |  |  | section | 2 - Materials
checkpoint-status |  |  | checkpoint | VERIFICATION
label | c32ad499-964c-51c6-89ba-42097fd6b44b |  | note | REQUIREMENTS / REFERENCE:
label | 5eb6f306-5217-52e3-9dbe-e8a4c53d7749 |  | note | • 1172 Cl 2
label | 14355d47-96ab-5745-81d0-7cd71d898277 |  | note | • 1172 Cl 6
label | f4ef0cec-7801-5a84-b8f6-74787698670f |  | note | • WCC 7000 C07
label | 86753c75-c0ab-5772-8567-bc909a8869d6 |  | note | ACCEPTANCE CRITERIA:
label | 198c51bf-754b-5e46-a2c3-29e82032468f |  | note | • Subsoil agg line: 100mm sleeved subsoil drainage pipe, slotted uPVC or perforated, ribbed HDPE to AS2439.1. Minimum class for uPVC pipe and fittings shall be Class 12.
label | 9e78276b-4cba-58cd-bc3f-f28576925041 |  | note | • Fabric: Non-woven geotextile, Strength Class A.
label | ad08c642-5114-5436-966e-c15187fadfbb |  | note | • Drainage aggregate: 10 or 20mm stone size drainage aggregate.
label | b2792237-1920-51a8-b4e9-210fc744fbd7 |  | note | • No Fines concrete: 20mm no fines concrete (without liner), 8:1 aggregate to cement ratio, f’c = 10 MPa, water / cement ratio = 0.41
checkpoint-group |  |  | section | 3 - Excavation – Inspection of trench and bedding
checkpoint-status |  |  | checkpoint | HOLD POINT
label | ab79948a-b193-578e-bdab-e429779dc6d6 |  | note | REQUIREMENTS / REFERENCE:
label | c97ebf1f-7ce4-5bdc-8c2e-e14614592b5c |  | note | • 1172 Cl 3.2
label | 3a97933c-4473-52be-947e-7ce83f415a0d |  | note | • 1172 Cl 3.3
label | c6d4af0b-a0a2-53f3-8cac-3b72cf936aa9 |  | note | • 1172 Cl 3.4
label | abed8fbf-1de7-5d7e-b635-f28de0918eda |  | note | • 1172 Cl 3.7
label | e781af35-e069-5a76-9c58-66f576e085ed |  | note | ACCEPTANCE CRITERIA:
label | 7ce81214-ee0f-5843-915d-6ad9cd217d87 |  | note | • Excavate trench as per drawings, backfill any over-excavation to the required level and compact to at least 95% relative compaction.
label | 73ea2ab8-4f2d-5e7e-8edc-8cdf0fb6c7ce |  | note | • Place 50mm thick compacted filter material or no fines concrete as per the drawings to create a bedding layer
label | 6a295839-c4d8-5b01-a733-6fda6378666d |  | note | • HOLD POINT: Client will inspect trench alignment and compaction of bedding prior to pipe placement
text | cfdd55dc-9f95-56ef-ab0e-b6bf28143ec4 |  | textbox | HOLD POINT NUMBER:
text | f2ae0770-7c2f-552c-84fd-120227d8695a |  | textbox | DATE SUBMITTED:
text | 788f2541-0ae7-59c2-a5fa-3cbabaa7486d |  | textbox | SUBMITTED BY:
text | 3c36c6f0-1c5a-559d-84d1-f8620610cccb |  | textbox | SPECIFICATION AND CLAUSE:
text | 52f01947-20c4-5d80-8109-3722dc990854 |  | textbox | HOLD POINT DESCRIPTION:
text | 9c6222a9-1456-5106-9642-4a3b3b678c81 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 4 - Installation – Survey of laid pipe
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 4e8a5a20-fecf-5452-aabe-acfcc0b5c0c9 |  | note | REQUIREMENTS / REFERENCE:
label | 1c7f6419-185c-53a9-b8d6-73a050947108 |  | note | • 1172 Cl 3.2
label | ce9720d6-69d7-52a9-a0b1-76483ed3d961 |  | note | • 1172 Cl 3.3
label | 5a00d607-099c-5077-b513-450f538bee8c |  | note | • 1172 Cl 3.4
label | 158ea21b-d6c0-55df-910a-12c359f48d44 |  | note | • 1172 Cl 3.7
label | 3e2d86b4-fc62-50fc-9974-bb9e76e155d7 |  | note | ACCEPTANCE CRITERIA:
label | e78092b8-4b27-5c2e-a1b7-00877dfb10fa |  | note | • Place sock-wrapped subsoils centrally within the trench on top of the filter material bedding at the correct dept, line and grades
label | a3f45c59-9581-5791-a70a-223af1b73ad6 |  | note | • HOLD POINT: Complete survey of laid pipe levels and location of centre of pipe, survey the top of the subsoil pipe every 10 metres. Provide this survey to the Client
text | 23ef7529-5292-5305-af41-656383332d43 |  | textbox | HOLD POINT NUMBER:
text | 270d50bd-7585-5ead-a439-c94e6f6ea224 |  | textbox | DATE SUBMITTED:
text | ea1a16b1-c3c1-51e3-96ec-7fbb2b81f8d4 |  | textbox | SUBMITTED BY:
text | 70a48a8e-ef21-54cc-9824-bc415e239216 |  | textbox | SPECIFICATION AND CLAUSE:
text | 03c0d652-4f33-5325-98f6-1af80c6e22a9 |  | textbox | HOLD POINT DESCRIPTION:
text | c55a1903-f4f0-57cf-aab6-6156d49de106 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 5 - Backfill
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 4aa6f975-a8d2-5b4f-8358-48a7931c894b |  | note | REQUIREMENTS / REFERENCE: 1172 Cl 3.5
label | cc2950a0-fbd9-5437-8c36-59069e3b53c0 |  | note | ACCEPTANCE CRITERIA:
label | 1fb4cefe-a74e-5e6c-a42d-076e0739476d |  | note | • Backfill with no fines concrete or filter material as per drawings.
label | c12e0e79-1689-50f2-ac3e-c853562738bd |  | note | • For no fines concrete, minimise any segregation of the concrete mix
label | 35ec962e-aaa9-5738-a9cc-b215a4706ddc |  | note | • For filter material, compact in maximum 300mm layers, taking care not to damage the subsoil lines
label | 13810fa6-7ddf-50f2-9037-2ad94ef62aba |  | note | COMMENTS / ATTACHMENTS: Concrete Pour Docket (if pouring no fines)
checkpoint-group |  |  | section | 6 - Testing
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 52f3d4eb-4d6d-58e6-a92f-15148577283a |  | note | REQUIREMENTS / REFERENCE: 1172 Cl 3.9
label | 3aefdb1e-7877-59b7-bbb6-ebe2678c56fc |  | note | ACCEPTANCE CRITERIA:
label | 32641d91-b51a-5a89-8395-96c1cad93a87 |  | note | • If over-excavation has occurred (refer Activity #3), provide test result(s) showing 95% relative compaction was achieved here
label | bec278f3-8fdb-5c48-b387-4cae52092e0a |  | note | • Completion tests: Pump clean water into the flush point at the start of each subsoil run until only clean water discharges at the outlet (Min. rate of water flow = 100 L / min at the flush point inlet)
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | 1a0a1e7f-4d68-5c14-bd4a-9b73c4e876bd |  | textbox | Lot Verified By:
text | 2eb756b9-513c-5d59-bba2-5fa4bf2318bc |  | textbox | Lot Closed Date:
button | 0e7c8c40-35b4-5672-aa7f-47a19f0f7bdf |  | button | Submitted to Client | Yes, No, N/A
button | 8a1d4405-274b-57fe-bdd3-0640dfec75c9 |  | button | Reviewed by Client | Yes, No, N/A
text | b00222dd-d8b4-5464-8698-f87704e6c286 |  | textbox | Submission Comments:
checklist-sectioned |  |  | checklist | A181 - West Dapto - ITC 004 (ITP004) - Clearing and Grubbing, Topsoil Strip |  |  |  |  | Yes | A181 - West Dapto - ITC 004 (ITP004) - Clearing and Grubbing, Topsoil Strip | a58c0f84-bc5b-4c26-aa7a-300bca531cf5
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | cf416436-bf7c-562b-8903-2d336d7d5cc6 |  | textbox | Lot Opened On
text | 884a1c01-2b1f-5247-82a1-146f4d7ff38b |  | textbox | Date of Works
text | 8a079e93-ab4d-5f79-93b1-8807f74b31ee |  | textbox | Lot Type
text | 008522f2-2c41-56aa-a90a-09694de23bb6 |  | textbox | Start Chainage
text | 4b6776be-0b3c-537c-98cc-a9f8f081c418 |  | textbox | End Chainage
text | 534a30a0-e161-4397-827b-a67748b33374 |  | textbox | Offset
text | 8d9a8dc8-9cb0-5a2a-96b8-fb1185ee37db |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Preparation Works
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 8b955aeb-cc43-5077-86c1-eb7f8386baee |  | note | REQUIREMENTS / REFERENCE: Project Safety Plan, Project Environment Plan
label | 85025479-19cb-565a-a0e2-1639d56a92c4 |  | note | ACCEPTANCE CRITERIA:
label | bbe98b40-a5ea-5847-b5ae-644398200729 |  | note | • All site personnel inducted, required SWMS completed and signed, Safety Plan approved
label | 90fbf753-d256-5402-813a-9866a0377b40 |  | note | • ERSED controls installed on site, air quality visually monitored for dust etc due to construction activities, Environment Plan approved
label | c6aee5c4-9f5e-5f3b-b2cf-1054c7aaa954 |  | note | • Contact DBYD and complete excavation permit, extent of works set out with survey pegs
checkpoint-group |  |  | section | 2 - Clearing and Grubbing Plan
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 9f7cd37b-d859-5be7-a274-98d258e13c2d |  | note | REQUIREMENTS / REFERENCE: 1111 Cl 2.1
label | 752dd574-93d8-5244-94d8-ef023cf05836 |  | note | ACCEPTANCE CRITERIA:
label | 81c293ce-127d-56c8-9705-074612a9e7cb |  | note | • Submit the following, as detailed in WCC 1111 Section 2
label | e45b2a39-1aca-5d11-afb8-58c1db5777ab |  | note | • HOLD POINT: Submission of Clearing and Grubbing Plan
text | 971b0b71-b739-5893-b25b-ca615beeb202 |  | textbox | HOLD POINT NUMBER:
text | a8477e87-99fb-5182-8438-291a50df3969 |  | textbox | DATE SUBMITTED:
text | 8becc0f9-aac7-56a8-a6a3-7f2e5ba82eb1 |  | textbox | SUBMITTED BY:
text | 78c86bfb-8cfc-580e-aa7f-e06350d074a9 |  | textbox | SPECIFICATION AND CLAUSE:
text | c6c59c3a-08ee-59aa-9fcd-0fa1f7122750 |  | textbox | HOLD POINT DESCRIPTION:
text | 6369787e-8ee2-56c9-b6f5-194ed39ad203 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 3 - Weed Management Plan
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 9baf8ac4-10cb-5d89-ab80-51048ecfdcdb |  | note | REQUIREMENTS / REFERENCE: 1111 Cl 2.1
label | 49d91b26-e273-5494-b8b0-e89570439515 |  | note | ACCEPTANCE CRITERIA:
label | 6387bc57-5fd1-5ac4-88c2-a88e08098030 |  | note | • HOLD POINT: Submission of Weed Management Plan
text | a249be4f-c9ae-5ad5-8f73-2300472e362a |  | textbox | HOLD POINT NUMBER:
text | eca66143-360f-5883-b34a-77b3baa3ef41 |  | textbox | DATE SUBMITTED:
text | f2a1191b-cbb8-50d9-b474-4e2229da023a |  | textbox | SUBMITTED BY:
text | 9123517b-7ffd-528f-b8e4-e246f36fd024 |  | textbox | SPECIFICATION AND CLAUSE:
text | c728bcef-2f83-5c5b-a1bb-fb7c6c1c0979 |  | textbox | HOLD POINT DESCRIPTION:
text | 276fa169-a07c-587b-8594-2fae55a694e2 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 4 - Clearing Report
checkpoint-status |  |  | checkpoint | HOLD POINT
label | bbb5665f-4953-5cd3-a51c-16cc9b2644be |  | note | REQUIREMENTS / REFERENCE: 1111 Cl 2.1
label | bd830059-55f8-5663-81f3-d36cf85c0f06 |  | note | ACCEPTANCE CRITERIA:
label | 02df1275-3bb7-5ef4-82bd-66834e59e42b |  | note | • HOLD POINT: Submission of Clearing Report
text | d40f9d74-8a51-5c7a-97e3-1f5a7d652b13 |  | textbox | HOLD POINT NUMBER:
text | 31f63425-0715-56b8-bf82-096f76c1d8ea |  | textbox | DATE SUBMITTED:
text | 52ccac40-18c5-5d61-8e7e-30aa7571b899 |  | textbox | SUBMITTED BY:
text | 88f3075f-a48f-56fc-aedf-92d73df2601c |  | textbox | SPECIFICATION AND CLAUSE:
text | 79330388-e2de-5600-8266-02cddf7b9fef |  | textbox | HOLD POINT DESCRIPTION:
text | 5e7840fd-2e3c-53e6-83ae-a2231a38ea19 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 5 - Survey Plan of Clearing Area
checkpoint-status |  |  | checkpoint | HOLD POINT
label | b84dae4f-a368-526e-9b69-11852debd454 |  | note | REQUIREMENTS / REFERENCE: 1111 Cl 2.3
label | ffcd3e2f-46c8-5644-ac96-a9868b0df273 |  | note | ACCEPTANCE CRITERIA:
label | 43891dc3-5f13-5c45-b740-1105a5a7b803 |  | note | • HOLD POINT: Submit a survey plan showing the proposed area for clearing to confirm the clearing perimeters
text | bf0213dc-c9e9-51e5-b1bd-a84aa0373bec |  | textbox | HOLD POINT NUMBER:
text | 769f8370-08bd-58ff-b944-abe09ce7dbf7 |  | textbox | DATE SUBMITTED:
text | a61501a5-b21c-568d-b943-0d3bc55cfd59 |  | textbox | SUBMITTED BY:
text | 43b42ffe-14d4-50a5-b21c-5b1f922bfba5 |  | textbox | SPECIFICATION AND CLAUSE:
text | 10a65026-e9ae-58a7-9376-95324478a849 |  | textbox | HOLD POINT DESCRIPTION:
text | a66ea16c-9725-5863-9b91-60a16bb5a074 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 6 - Peg Out of Clearing Area
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 4dcec293-fbea-5d80-a8ab-bf3a43b7e178 |  | note | REQUIREMENTS / REFERENCE: 1111 Cl 2.3
label | a4855d52-6b8d-5d89-8dfe-52a77dc98365 |  | note | ACCEPTANCE CRITERIA:
label | c1ec1bd2-caa7-5dbc-90a7-3aee5352b4a0 |  | note | • HOLD POINT: Peg out area for clearing
text | 1a030978-19cd-5123-a87d-16f835bd6302 |  | textbox | HOLD POINT NUMBER:
text | ce943187-6c1e-594b-9e90-267a16289301 |  | textbox | DATE SUBMITTED:
text | 10c62610-e236-52da-b14d-4a5936767d23 |  | textbox | SUBMITTED BY:
text | 41418287-dce2-5401-aebc-2f897338f9bd |  | textbox | SPECIFICATION AND CLAUSE:
text | 8ced93e1-cf84-56f3-aef3-20bcaa37ba7e |  | textbox | HOLD POINT DESCRIPTION:
text | 00d0c573-b63d-5073-9a11-c6095d8a5d0b |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 7 - Clearing Method Statement
checkpoint-status |  |  | checkpoint | HOLD POINT
label | cbf3009d-115a-5864-b64f-b6456b7b62ba |  | note | REQUIREMENTS / REFERENCE: 1111 Cl 2.3
label | 26263a28-1ec5-573b-9486-f55a3170164c |  | note | ACCEPTANCE CRITERIA:
label | b045b4f0-d3c5-556f-833c-09798f05dbc1 |  | note | • HOLD POINT: Submit a method statement for clearing including proposed methods, equipment and materials
text | 5fdadfc2-e0e2-5ade-a773-cc4be7be73b2 |  | textbox | HOLD POINT NUMBER:
text | db5bde71-ade2-518a-8595-c67231af2934 |  | textbox | DATE SUBMITTED:
text | 9d436f9e-4b54-5b28-8886-7a8b03411cb5 |  | textbox | SUBMITTED BY:
text | 791d88ec-1502-5b05-9390-c25c37715915 |  | textbox | SPECIFICATION AND CLAUSE:
text | 984cc952-7197-55a7-a457-4058cac09f8b |  | textbox | HOLD POINT DESCRIPTION:
text | 5fc53372-b22a-5752-8105-c5448865176b |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 8 - Method Statement for Work in Exclusion Zones
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 8bfc573b-6c6e-5230-9573-64c66c3cefcf |  | note | REQUIREMENTS / REFERENCE: 1111 Cl 3.1
label | d0535253-00ce-5e2c-be57-a735f2fcdaf7 |  | note | ACCEPTANCE CRITERIA:
label | f7457a72-6927-5672-8776-1b2677b6b698 |  | note | • HOLD POINT: Submit a method statement for work within exclusion zone and driplines
text | 88fa4127-115b-5883-ac29-5f7eab552dc2 |  | textbox | HOLD POINT NUMBER:
text | 61a22224-6988-55ea-815e-0d242843121c |  | textbox | DATE SUBMITTED:
text | 601adb85-34ba-5f72-b249-4dc43773b626 |  | textbox | SUBMITTED BY:
text | 4d4e15d7-3d34-5b2c-80d6-71479aee1303 |  | textbox | SPECIFICATION AND CLAUSE:
text | 565c1938-d52e-53eb-9d11-71cc5a857f6c |  | textbox | HOLD POINT DESCRIPTION:
text | ab7df643-1fa8-5a60-a72b-a05bfd8016bb |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 9 - Notice of Protected Trees
checkpoint-status |  |  | checkpoint | HOLD POINT
label | baaab4dd-e46d-5ea9-9e85-210884750233 |  | note | REQUIREMENTS / REFERENCE: 1111
label | 95273e1b-b9bf-54fa-8ee0-16ff17fc10a4 |  | note | ACCEPTANCE CRITERIA:
label | 55f04f12-b2dc-58c1-b4bd-4d21cbe9fff8 |  | note | • HOLD POINT: Notice of trees to be protected
label | a3e7250f-c55d-518f-b388-efd20016b264 |  | note | • Display a sign in a prominent position at each entrance to site, warning that trees and other plants are to be protected during the contract works
text | 3c1cb247-87f4-5102-bdb2-1c3f7d082c37 |  | textbox | HOLD POINT NUMBER:
text | 4b15314f-85eb-5b5f-8bab-03d8e8e6a4e8 |  | textbox | DATE SUBMITTED:
text | dbcb38c4-b406-5d8d-871b-2c71530009a7 |  | textbox | SUBMITTED BY:
text | e1787bee-a0ed-55b2-99fb-f1ea5a9bb4dd |  | textbox | SPECIFICATION AND CLAUSE:
text | 2d2bf0fa-081d-5dce-8f0e-313df7d5ebd2 |  | textbox | HOLD POINT DESCRIPTION:
text | 7587473c-7a11-5ea9-a169-03697611ca45 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 10 - Marking of Trees
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 9044ae81-384f-51a0-bc31-d6164f72b4a0 |  | note | REQUIREMENTS / REFERENCE: 1111
label | 4a226c59-61fa-52cb-8a46-475ddfbccb21 |  | note | ACCEPTANCE CRITERIA:
label | 349fc3c7-f326-5ae0-be90-fbb2f33b74a9 |  | note | • WITNESS POINT: Mark all trees documented for preservation or transplanting with ribbon markers
text | 0ed6e637-15c9-5570-8662-2328aaebf3ca |  | textbox | WITNESS POINT NUMBER:
text | c1d60536-e7a2-5585-bfc1-a34510ff5b53 |  | textbox | DATE SUBMITTED:
text | 6c5816ec-58cd-5bd4-a648-e16a1ad5f163 |  | textbox | SUBMITTED BY:
text | f6a6aa88-4fbb-5199-9d3f-6f178d7faf03 |  | textbox | SPECIFICATION AND CLAUSE:
text | 3c76bd1e-2095-5169-b160-3d389fbcdb6f |  | textbox | WITNESS POINT DESCRIPTION:
text | 6336ecba-0e4e-5545-a1b4-8755f9c9d909 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 11 - Marking of Unsound Trees
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 78706809-2385-51c4-a65e-5d8d527a0ec7 |  | note | REQUIREMENTS / REFERENCE: 1111
label | 06994669-506f-59d7-b41b-8a92aca3bdc4 |  | note | ACCEPTANCE CRITERIA:
label | b141c484-c032-5912-9433-5167c80801aa |  | note | • WITNESS POINT: Mark any unsound trees in the road reserve, but outside limits of clearing
text | ef88ab97-e344-522c-aa5c-6aba9e8411b7 |  | textbox | WITNESS POINT NUMBER:
text | 7d32461d-f9f2-56ea-b552-af911a32def5 |  | textbox | DATE SUBMITTED:
text | 589c6021-6941-5119-a1e1-fa30437921b8 |  | textbox | SUBMITTED BY:
text | 22747e2a-958a-56ff-8892-593db86b8128 |  | textbox | SPECIFICATION AND CLAUSE:
text | 55a120eb-0ff7-553f-9847-9c99b1987284 |  | textbox | WITNESS POINT DESCRIPTION:
text | bb6ca403-8267-5944-992e-4853b7724843 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 12 - Additional Weed Control
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 5d295a5e-7a0e-5f9d-8cfe-ccf7448cf396 |  | note | REQUIREMENTS / REFERENCE:
label | 6cdd9274-5a2f-5cee-9580-0587c9c7947e |  | note | • 1111 Cl 3.7
label | 3dfb633f-a1ef-5451-9ac9-5b43c4d3a442 |  | note | • 1111 Cl 3.8
label | 7035dbae-aef8-50a8-8d23-e9726bea92db |  | note | ACCEPTANCE CRITERIA:
label | 1c25bf40-b332-58a6-9a2b-fdb2b53f7410 |  | note | • WITNESS POINT: Identify any additional areas that require weed control
label | 743de932-bb24-5085-a306-65e7b741527f |  | note | • Treatment of cleared vegetation as necessary and as per Section 3.7
label | 3a6bbb4d-aba9-57b2-8eb0-ac912543282d |  | note | • Re-use materials wherever possible
label | c2c98b1e-160c-5fef-b652-712135994a49 |  | note | • Walk site after completion of clearing to identify any further trees or stumps that require removal
text | 3c02215d-8d14-5b03-882e-e2c3e1970182 |  | textbox | WITNESS POINT NUMBER:
text | 3da39dae-da10-5ca8-85f7-057cf9811b09 |  | textbox | DATE SUBMITTED:
text | 7b8b94a3-209a-52aa-a264-3bd7b9e5afa1 |  | textbox | SUBMITTED BY:
text | 4e785e38-c3de-5fee-ac68-3e27a1837632 |  | textbox | SPECIFICATION AND CLAUSE:
text | 0f2d979a-8fd4-57ca-b5a6-d9fd535de947 |  | textbox | WITNESS POINT DESCRIPTION:
text | a94e2554-6466-54fd-8ca6-0f7990b99385 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 13 - Topsoil Strip
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 6fa969ff-e395-51d3-9d26-2a0e02a75480 |  | note | REQUIREMENTS / REFERENCE: 0222 Cl 3.4
label | 0998c499-0360-56e1-a852-bffa00096e4c |  | note | ACCEPTANCE CRITERIA:
label | 006cf7a3-9eef-575f-bd9e-dc2258fe144d |  | note | • If the following are encountered, notify client of as-found site conditions: Bad ground, discrepancy in site conditions, rock, springs and seepages, topsoil more than 100mm deep
label | 142d2422-3f35-5208-80f4-2624a0fb0518 |  | note | • Strip topsoil to a maximum depth of 200mm and remove if unsuitable for re-use
label | 4f5046aa-8e60-58df-8354-9d4c11c29797 |  | note | • Stockpile topsoil intended for re-use as per Specification requirements
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | 2b3d731c-747c-51f3-bd21-84594726ccfa |  | textbox | Lot Verified By:
text | 26ce3c75-e8e4-5b77-8e25-448e85a93d67 |  | textbox | Lot Closed Date:
button | 2cff54aa-28d4-5ffd-981e-77440282e99a |  | button | Submitted to Client | Yes, No, N/A
button | 9a8400bd-00eb-5e6a-a271-7f2d8bf58506 |  | button | Reviewed by Client | Yes, No, N/A
text | 375aa90c-03a3-5ec5-8256-2fbeaf2b8746 |  | textbox | Submission Comments:
checklist-sectioned |  |  | checklist | A181 - West Dapto - ITC 016 (ITP016) - Utility Adjustments (Streetlights) |  |  |  |  | Yes | A181 - West Dapto - ITC 016 (ITP016) - Utility Adjustments (Streetlights) | ae523a30-2da7-464a-94bc-a692848e59ca
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | 2e826f87-8500-5a8b-8c21-68e9701ffc4e |  | textbox | Lot Opened On
text | d2a2c765-76c5-5a6b-8d09-62fc8755a7c2 |  | textbox | Date of Works
text | a76f32c3-3954-5be6-bbda-e17bb075c6aa |  | textbox | Lot Type
text | 228504d3-2617-599f-9c06-d603a60b8fad |  | textbox | Start Chainage
text | 7d5b3c13-1fac-5b74-8407-b544839921e6 |  | textbox | End Chainage
text | 4524e953-5826-4797-b272-47498f120bef |  | textbox | Offset
text | 4aa61768-832b-549c-8f49-055b32e80608 |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Preparation Works
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 7adde6ba-c11d-53af-867b-5b8da71378e6 |  | note | REQUIREMENTS / REFERENCE: Project Safety Plan
label | 7e5ef850-9a37-5d0f-b638-8622550c60c9 |  | note | ACCEPTANCE CRITERIA:
label | 8b337df2-9cc2-549e-b70a-0b21dbdec06f |  | note | • All site personnel inducted (includes environment and cultural)
label | 485ae768-452e-51c4-bbfa-d6347653f137 |  | note | • Required Safe Work Method Statements completed and signed
label | 2a1bf2c7-11d2-5040-84fb-861f94c465bb |  | note | • Subcontractor’s safety plan/procedure approved
checkpoint-group |  |  | section | 2 - Environment
checkpoint-status |  |  | checkpoint | VERIFICATION
label | c98745f0-200f-5524-8e0c-c4b07cd6a5d0 |  | note | REQUIREMENTS / REFERENCE: Project Environment Plan
label | 7401f5cb-f5e9-55f4-af65-126e1b952cdc |  | note | ACCEPTANCE CRITERIA:
label | 97139eae-5239-531b-8537-af0a54219cf5 |  | note | • Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs.
label | f23af34f-c665-5235-8c9a-aeebfdc37f83 |  | note | • Air quality to be visually monitored for dust etc. as a direct result of construction activities.
checkpoint-group |  |  | section | 3 - Preparations
checkpoint-status |  |  | checkpoint | VERIFICATION
label | ef514729-79d0-599f-ac4c-602982da3b1f |  | note | REQUIREMENTS / REFERENCE: 0223, 1341
label | 197445b8-106f-5a5c-aaac-487d7ff151ab |  | note | ACCEPTANCE CRITERIA:
label | f4029dbb-be14-535f-808c-e985b404a7b8 |  | note | • DBYD and service locating completed
checkpoint-group |  |  | section | 4 - Design Docs (D&C Contracts)
checkpoint-status |  |  | checkpoint | HOLD POINT
label | c1eea264-a3ad-53ce-9761-6340b81c4f58 |  | note | REQUIREMENTS / REFERENCE: 1197 Cl 1.5
label | aba6e42d-d060-5d95-be6f-7d2908b1250f |  | note | ACCEPTANCE CRITERIA:
label | b0e4731a-16d3-5a78-9527-c45a79cc8959 |  | note | • HOLD POINT: For Design and Construct contracts, submit design documentation to the Client for their acceptance at least 2 weeks before commencement of these works
text | 8ddd286e-4fbc-5749-b117-3fa4a9f58db0 |  | textbox | HOLD POINT NUMBER:
text | fe3c1657-32ce-5743-81b4-6e1c3efff9c3 |  | textbox | DATE SUBMITTED:
text | 999b05e4-d964-51fd-89c9-0a321e28eae7 |  | textbox | SUBMITTED BY:
text | 88bf232e-698c-5009-85ed-cb2959d3f823 |  | textbox | SPECIFICATION AND CLAUSE:
text | fd075417-9e0c-504a-851f-7d7c9332a38d |  | textbox | HOLD POINT DESCRIPTION:
text | 147e2386-f724-573c-b7ed-fe08af7ff52a |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 5 - Approval of Design
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 355ac30f-75a3-519d-9aa5-82e2f96bf854 |  | note | REQUIREMENTS / REFERENCE: 1197 Cl 1.5
label | 05ad87f8-e80e-5b4c-8540-bbdd5ec918a4 |  | note | ACCEPTANCE CRITERIA:
label | 71360dc2-7ffd-5a25-a386-1c454aa51b73 |  | note | • HOLD POINT: Provide evidence of design approval from the electricity distributor to the Client at least 5 days before commencement of these works
text | 74d7ac47-0b86-5343-b615-724a5e268081 |  | textbox | HOLD POINT NUMBER:
text | d883a2a0-d92e-5bb5-8383-948a4309488c |  | textbox | DATE SUBMITTED:
text | 97efd069-aa74-5587-b6ce-ae98c3d7c92d |  | textbox | SUBMITTED BY:
text | 9c14af33-e735-57ab-b8da-cc76e6cbc368 |  | textbox | SPECIFICATION AND CLAUSE:
text | 77114265-159e-59b6-bf1f-4a8ab469825e |  | textbox | HOLD POINT DESCRIPTION:
text | 41630d30-8683-59ce-8f79-9bdcb4a4d0b9 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 6 - Products and Materials
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 15e62a6d-4c94-59f1-a638-ee753a9276fc |  | note | REQUIREMENTS / REFERENCE: 1197 Cl 2
label | f94446bb-5358-54eb-9168-24d158b18d1b |  | note | ACCEPTANCE CRITERIA:
label | c04afa3f-9cab-5f20-8e56-84623f7cc678 |  | note | • All materials must conform to the electricity distributor’s standards
label | 76e268c2-ca8b-55f9-8be3-7f9171dc1a0d |  | note | • HOLD POINT: Provide manufacturer’s information for luminaires, fittings and accessories to the Client at least 5 days before ordering these materials
text | 73c328a4-6c4a-5352-82d5-250c080bd21d |  | textbox | HOLD POINT NUMBER:
text | 4bd78fcf-830b-5c4d-af7e-259bb5d5a388 |  | textbox | DATE SUBMITTED:
text | b833ceec-e6ed-50a4-b0d7-e44b3b740235 |  | textbox | SUBMITTED BY:
text | 7cb52ee4-deae-590d-91b9-008eb361b210 |  | textbox | SPECIFICATION AND CLAUSE:
text | b2379fe8-960a-54e7-900e-3cdfa7325f36 |  | textbox | HOLD POINT DESCRIPTION:
text | 019515a7-312b-5078-95b9-86fe50f2c73c |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 7 - Exc. and Compaction
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 293fb666-ead8-54c4-881a-4cad166c5ae6 |  | note | REQUIREMENTS / REFERENCE: 1197 Cl 3.3
label | f95b51ef-2dfc-5c06-957c-bb7264854115 |  | note | ACCEPTANCE CRITERIA:
label | e0c71ca6-e1f0-5909-85cd-7480de753fe2 |  | note | • For footings of base mounted columns, excavate footings neatly from solid material and compact to 90% maximum dry density
label | e48c1532-546d-5457-83fa-985982cccdc3 |  | note | • For other columns, install as per relevant Australian Standards, the electricity distributor’s standards, the manufacturer’s recommendations, and the project drawings and specifications
label | 45e32fab-1da4-5718-821d-909f4e9039a5 |  | note | COMMENTS / ATTACHMENTS:
label | 6bd62b12-5906-5fe6-82c1-f9c77cb2948c |  | note | • Compaction test results (if needed)
checkpoint-group |  |  | section | 8 - Base Mounted Column Footings
checkpoint-status |  |  | checkpoint | HOLD POINT
label | dc53429d-4ae1-5da9-a06c-f5af58ea2939 |  | note | REQUIREMENTS / REFERENCE: 1197 Cl 3.3
label | 165098fb-7f44-5ff1-ae5e-dfb0a46a425c |  | note | ACCEPTANCE CRITERIA:
label | 057de280-2ba6-59ce-ad93-b5f88f5ea399 |  | note | • HOLD POINT: Provide notice to the Client of the upcoming formwork installation and anchor bolt assembly location(s), at least 1 day before installation
text | e76a3e16-bd89-54b8-a9d3-454427c53599 |  | textbox | HOLD POINT NUMBER:
text | 30301a2a-3b29-56b5-932d-d178c3d45a30 |  | textbox | DATE SUBMITTED:
text | c39e54c8-a569-5e09-99a0-0efae80b9a18 |  | textbox | SUBMITTED BY:
text | 736b4aa6-a11c-51c5-9ff4-fbb9ae086781 |  | textbox | SPECIFICATION AND CLAUSE:
text | 7b109c0c-7776-5d73-92d0-a26dcb8272e5 |  | textbox | HOLD POINT DESCRIPTION:
text | f3db25c2-91c1-58c5-a9af-2cea50ad0326 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 9 - Columns Buried in Ground
checkpoint-status |  |  | checkpoint | HOLD POINT
label | d47a65f1-b198-5701-bfa5-c11463ac9322 |  | note | REQUIREMENTS / REFERENCE: 1197 Cl 3.3
label | 243431f8-6af4-5b56-8c01-15eea9e117e5 |  | note | ACCEPTANCE CRITERIA:
label | b5802d36-74f1-5ec4-a0f7-3d36ac7b82c6 |  | note | • HOLD POINT: In the event a column buried directly into the ground is unfeasible due to unsuitable soil conditions, provide details of an alternative pole mounting method to the Client, at least 3 days prior to the column installation
text | 22b031cb-7359-5823-829c-b8a890387715 |  | textbox | HOLD POINT NUMBER:
text | e6fb9bec-49a3-547d-9753-6a23141dcc58 |  | textbox | DATE SUBMITTED:
text | 3448ae0d-7e3b-59cb-9877-654350eb40b5 |  | textbox | SUBMITTED BY:
text | 78d96d6e-c706-5c12-8d74-a949b7217c75 |  | textbox | SPECIFICATION AND CLAUSE:
text | 7e454287-a8a7-5faf-9be9-23ae7de57bd1 |  | textbox | HOLD POINT DESCRIPTION:
text | e218e7ad-e9d2-5c02-b93e-bb09bf84dcad |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 10 - Installation of Assets
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 643517e2-ea30-5397-823b-27459ee8183d |  | note | REQUIREMENTS / REFERENCE:
label | e51628d3-3e6e-5e6c-8ca4-780688ffdcce |  | note | • 1197 Cl 3.3
label | 938461f5-e080-593b-9b60-01b4f54f08a0 |  | note | • 1197 Cl 3.4
label | 7e0188ec-7c7d-5435-bd71-5f6cdd8b30e8 |  | note | ACCEPTANCE CRITERIA:
label | 4b331c49-c452-5ccc-be25-c679905e10ef |  | note | • Stand streetlights as per manufacturer’s installation instructions and in accordance with crane / plant lift plan(s)
label | ec7e23f0-eb8d-522c-9336-9cb75305910a |  | note | • Install cables and power supply as per local electricity distributor’s standards, AS / NZS 3013 and as per the project drawings and specifications
checkpoint-group |  |  | section | 11 - Inspect Power Cables
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 282b9ec5-f41d-5bdd-a21f-95cb7c64bdc1 |  | note | REQUIREMENTS / REFERENCE: 1197 Cl 3.4
label | edde2e98-73b2-5e13-9c5a-a0563806ad35 |  | note | ACCEPTANCE CRITERIA:
label | 937c63f2-e0d2-569b-adb3-50bb10409fcd |  | note | • WITNESS POINT: Invite the Client to witness and inspect the completed power cable installations, at least 1 day before the inspection is due to take place
text | 9334c41e-37b7-53c0-8b9b-4569b7c70d3a |  | textbox | WITNESS POINT NUMBER:
text | 75cd90c7-6578-5723-96a4-4bdd9e64ae65 |  | textbox | DATE SUBMITTED:
text | 9bf87257-c445-53f0-b934-75e34199a8dc |  | textbox | SUBMITTED BY:
text | aff9eff3-ae6d-55cf-b2d9-6fa5bd58e774 |  | textbox | SPECIFICATION AND CLAUSE:
text | 1262a0e7-8292-5404-9bbb-0ecf200a897a |  | textbox | WITNESS POINT DESCRIPTION:
text | 106a38f3-3869-5422-a129-47cc64331479 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 12 - Testing
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 41cc4ce1-db62-5784-859c-09d0007d9ee4 |  | note | REQUIREMENTS / REFERENCE: 1197 Cl 3.5
label | efcd2e0e-c249-58d5-b7a1-63d3f472a090 |  | note | ACCEPTANCE CRITERIA:
label | 6da7e5c6-7051-5060-9749-5900597b8fbb |  | note | • WITNESS POINT: Invite the Client to witness and inspect the commissioning and verification testing of the completed streetlighting works, at least 1 day before the inspection is due to take place
label | 9880581c-ec8f-5ebd-be10-8fceaddd702a |  | note | COMMENTS / ATTACHMENTS:
label | 3fbefa78-62f7-530d-94b0-b2278bb11d0b |  | note | • Acceptance of works from utility asset owner
text | da26fded-4e5a-5ffa-90d1-3bccbbe3313a |  | textbox | WITNESS POINT NUMBER:
text | 498b4e50-e4db-52c1-b8e0-02606a4f77d0 |  | textbox | DATE SUBMITTED:
text | 13f649cf-6bdc-5308-9aad-1704ff053a01 |  | textbox | SUBMITTED BY:
text | 73e1aa58-9f20-5885-8d46-6000f1c71fd2 |  | textbox | SPECIFICATION AND CLAUSE:
text | 65a7fe99-c5a2-5b9e-96a7-4ab20e3b9319 |  | textbox | WITNESS POINT DESCRIPTION:
text | 0bc597e7-2b6a-5d1c-92cf-cc91aacd1ca3 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | 22bb7a3d-64a4-5794-b579-769a124b2403 |  | textbox | Lot Verified By:
text | 31838487-dd24-5a59-a1bd-983fcb61718f |  | textbox | Lot Closed Date:
button | af458d0c-7429-54ea-ba80-5f62499e781e |  | button | Submitted to Client | Yes, No, N/A
button | 374d505f-9253-5a3b-831b-3000c9980e29 |  | button | Reviewed by Client | Yes, No, N/A
text | ddccafb1-6905-5dc3-8678-0ecb618e0720 |  | textbox | Submission Comments:
checklist-sectioned |  |  | checklist | A181 - West Dapto - ITC 003 (ITP003) - Earthworks |  |  |  |  | Yes | A181 - West Dapto - ITC 003 (ITP003) - Earthworks | d0abb456-339c-4126-903d-71bec8f402b5
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | 74006582-9e6a-5e7b-b697-17756a8d86f0 |  | textbox | Lot Opened On
text | 4b82d43e-3e8e-560e-8fdc-2815b94ad708 |  | textbox | Date of Works
text | 8305c207-d4c3-5b9d-9704-c27500b46be7 |  | textbox | Lot Type
text | 6ae16dd8-dd73-57f4-a66f-ab7580dffc16 |  | textbox | Start Chainage
text | c0e7c22a-c52a-5b11-af1b-9be0cb7ebbe1 |  | textbox | End Chainage
text | ff10f416-21d8-4593-85ec-1841adb99b8d |  | textbox | Offset
text | 241b30af-5f3e-5d84-a77f-fd7c97929d4d |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Preparation Works
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 1be06e4b-7d2c-5afb-bb6f-5d4b27fa87ee |  | note | REQUIREMENTS / REFERENCE: Project Safety Plan, Project Environment Plan
label | d5b75720-8cbd-510b-acc0-ee40fde7a419 |  | note | ACCEPTANCE CRITERIA:
label | 37f89e38-3509-513d-896e-b57f9bf9c95c |  | note | • All site personnel inducted, required SWMS completed and signed, Safety Plan approved
label | fad0a087-6f47-5d8c-9375-005a4584f4d8 |  | note | • ERSED controls installed on site, air quality visually monitored for dust etc due to construction activities, Environment Plan approved
label | b9723893-14c0-54a0-8e96-c222482faf9d |  | note | • Contact DBYD and complete excavation permit, extent of works set out with survey pegs
checkpoint-group |  |  | section | 2 - Inspection of Foundation
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | b4e30830-424f-552e-a9ef-ecadc2c53e69 |  | note | REQUIREMENTS / REFERENCE: 1112
label | 9ebd3206-5500-535d-848d-2a4d023bc353 |  | note | ACCEPTANCE CRITERIA:
label | 11ecc424-9ea6-5499-a76b-30a57c313a88 |  | note | • Upon reaching designed floor level, an inspection between Principal & contractor of the foundation is required
label | 8a75dd6f-2de3-533b-8caa-102cba3f48e9 |  | note | • Promptly notify the Principal of areas determined to be unsuitable
label | 45bfbcb5-3297-50df-8db5-3422c48063c7 |  | note | • WITNESS POINT: Notify Client 3 days prior to inspection of foundation
label | b0ac102e-855b-5124-a63e-c12c4c997450 |  | note | COMMENTS / ATTACHMENTS:
label | 8d2fac22-87d4-56b1-8ed1-34878c6ba18a |  | note | • Existing CBR Test Results
text | cdb2f3b8-73e3-5ac4-96da-0fa6135270de |  | textbox | WITNESS POINT NUMBER:
text | 11a43681-e8ee-547a-92cb-558a74571f7d |  | textbox | DATE SUBMITTED:
text | eb8e9d4e-f021-5f8a-b8fa-83280b041486 |  | textbox | SUBMITTED BY:
text | 2e7f4018-dd07-5af6-9e71-edec6914925e |  | textbox | SPECIFICATION AND CLAUSE:
text | 53d66860-27c0-59cd-9cdf-cfcb5d7e9563 |  | textbox | WITNESS POINT DESCRIPTION:
text | 03015970-a359-5940-986e-5045e6c055d6 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 3 - Excavate Unsuitable Material
checkpoint-status |  |  | checkpoint | HOLD POINT
label | bd46fce3-ca96-5db6-aa80-cd1035edfd18 |  | note | REQUIREMENTS / REFERENCE: 1112
label | 64d74119-d97c-5697-a61a-0575b0842a83 |  | note | ACCEPTANCE CRITERIA:
label | 098ee8cb-c702-5f11-8f15-cf1d3c9760e8 |  | note | • HOLD POINT: Where unsuitable material is found, excavate to the extent directed by the Client and inspect prior to backfilling
text | 3bcef8a9-8d57-51f9-83ff-2675d6ac8ebd |  | textbox | HOLD POINT NUMBER:
text | 329e7089-8d64-5cc0-939f-6e5faa018223 |  | textbox | DATE SUBMITTED:
text | 82e4908d-0dc8-5bdb-ad27-0621a7ec5bc6 |  | textbox | SUBMITTED BY:
text | 1fa5ea79-e001-5742-bac7-5a72749e7eda |  | textbox | SPECIFICATION AND CLAUSE:
text | 95f51a57-a4b9-5553-9acf-0c581f8daae2 |  | textbox | HOLD POINT DESCRIPTION:
text | 942a3d68-e7d8-50a2-af3a-93429f7aaa72 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 4 - Inspection of Ripped Floor
checkpoint-status |  |  | checkpoint | HOLD POINT
label | ad4da597-6aba-5763-b569-ac56c450d1db |  | note | REQUIREMENTS / REFERENCE: 1112
label | 9d941628-3340-5c27-80c6-dda700b87417 |  | note | ACCEPTANCE CRITERIA:
label | e260e860-9c24-523e-b7e0-04d60f1e5836 |  | note | • HOLD POINT: In the event of recompacting, rip material in the floor to a minimum depth of 150mm. Inspection of ripped or loosened material to be carried out with Client
text | 0613049a-6eda-543f-93e8-f2fb6385072f |  | textbox | HOLD POINT NUMBER:
text | 3e47c536-c7e4-58b8-a723-502ab93c1e49 |  | textbox | DATE SUBMITTED:
text | 1c43ac45-f6f8-560d-ba48-58d119c0d162 |  | textbox | SUBMITTED BY:
text | 317ac9b5-1b5e-5d5d-85cd-496bbef8df73 |  | textbox | SPECIFICATION AND CLAUSE:
text | aaa92b37-b1bb-53cc-9910-50bca241f8b8 |  | textbox | HOLD POINT DESCRIPTION:
text | b75f054c-7b1e-5d48-976e-811e8203709f |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 5 - Inspection of Compacted Cut Floor
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 4bd4d244-6b99-52b8-8d52-ab0045e1c575 |  | note | REQUIREMENTS / REFERENCE: 1112
label | d0044a69-38b2-58b8-ae63-c882fcdacefd |  | note | ACCEPTANCE CRITERIA:
label | 82d842d5-f689-58a5-af86-6077f7b0baa6 |  | note | • HOLD POINT: Recompact cutting floor and notify Principal of completion before placing subsequent layers. Inspection of compacted floor
label | 5d401e1a-a36a-5130-afe9-588edcc50d64 |  | note | COMMENTS / ATTACHMENTS:
label | fb408b38-4a17-56a6-92b5-3d198a3d12f9 |  | note | • Compaction Test Results
text | 0cadc849-c82b-5813-8960-15218cf4c486 |  | textbox | HOLD POINT NUMBER:
text | dc3ceeae-8168-507c-8afb-f187a7d5018d |  | textbox | DATE SUBMITTED:
text | 53428342-9f02-5b79-a0d1-53aa333c4f85 |  | textbox | SUBMITTED BY:
text | abe5adf9-6eaf-5698-8a64-e3c2ba203e58 |  | textbox | SPECIFICATION AND CLAUSE:
text | edcb0fa0-dec6-5fbb-8a67-9189e8b2afaf |  | textbox | HOLD POINT DESCRIPTION:
text | f83c4aaf-72cf-527e-8102-576da6b48552 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 6 - Proof Roll Inspection
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 78c2b747-8d26-57e5-b5d4-9cdf8b53471f |  | note | REQUIREMENTS / REFERENCE: 1112
label | c52638a0-c824-56c5-b234-89ef2d9b4765 |  | note | ACCEPTANCE CRITERIA:
label | d2ad400e-3b17-59c0-ac05-719ae81016d6 |  | note | • HOLD POINT: Inspection of subgrade/pavement movement observed under roll test – after wet material and subsoil treatment applied.
text | c111358a-374e-54b7-aeb1-5edbe049e7df |  | textbox | HOLD POINT NUMBER:
text | d082c203-1fb4-5e46-ba0d-eb23fbc479dc |  | textbox | DATE SUBMITTED:
text | ae35657e-77cf-5377-95af-baa04cd917b1 |  | textbox | SUBMITTED BY:
text | 1de912e0-ac4f-52c9-ad3c-305046aa4203 |  | textbox | SPECIFICATION AND CLAUSE:
text | f0d7263d-a7cd-56d7-a4a6-784b8ec7ef95 |  | textbox | HOLD POINT DESCRIPTION:
text | 9f28bf1e-2b16-5264-8079-cc59346df1ba |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 7 - Cut / Fill Transition
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 58793c89-7387-5bbd-9564-22969b083ed2 |  | note | REQUIREMENTS / REFERENCE: 1112
label | 9e957da6-8159-5394-8ea4-540488ad6805 |  | note | ACCEPTANCE CRITERIA:
label | 263a71e6-b9cf-5dc6-a485-639b1ac08909 |  | note | • WITNESS POINT: Survey to mark intersection line. Inspection of intersection line between cutting and embankment
text | 3d773e6c-1397-5eac-b9c9-893ffe4b9c91 |  | textbox | WITNESS POINT NUMBER:
text | e4270564-2a27-5b82-88f0-7497f1a847ac |  | textbox | DATE SUBMITTED:
text | 046df221-db8f-5c3a-957e-c2caf583b51e |  | textbox | SUBMITTED BY:
text | f3a6ac18-05f6-5499-b7a3-2f797958bae6 |  | textbox | SPECIFICATION AND CLAUSE:
text | cbf7819a-3643-5915-8530-f769a363cb44 |  | textbox | WITNESS POINT DESCRIPTION:
text | 8d094092-d855-5ce9-991a-003bcc2c9cb6 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 8 - Embankments Foundation Inspection
checkpoint-status |  |  | checkpoint | HOLD POINT
label | b2808c81-b4a0-59a1-9828-39680ab95567 |  | note | REQUIREMENTS / REFERENCE: 1112
label | eb019464-3376-54a7-981c-d8061e6aaa08 |  | note | ACCEPTANCE CRITERIA:
label | 0919cf66-5ad3-5be5-b18d-9a0edfac3466 |  | note | • HOLD POINT: Inspection of embankment foundation area following removal of topsoil
text | eefc3ead-d232-5fae-8f2b-f13d56c04828 |  | textbox | HOLD POINT NUMBER:
text | bb511542-4ece-56f8-b51f-02c1c07ce1e4 |  | textbox | DATE SUBMITTED:
text | 6f4f7315-3666-543b-86a6-6883bf151482 |  | textbox | SUBMITTED BY:
text | e3c8d2b5-2052-5dcb-b434-e37de2b844b8 |  | textbox | SPECIFICATION AND CLAUSE:
text | 30b5155e-dabd-5a4f-a910-d57017815a0f |  | textbox | HOLD POINT DESCRIPTION:
text | 18462e63-0e1a-5f2a-84eb-06733d7b7b88 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 9 - Embankment Foundation Treatment Details
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 1f5ac7f1-3285-563c-973e-bcd29386476e |  | note | REQUIREMENTS / REFERENCE: 1112
label | b3950f7f-7986-5083-bdfc-1c41d4f1d942 |  | note | ACCEPTANCE CRITERIA:
label | dfdf09cd-41f2-5feb-812b-58a978979123 |  | note | • HOLD POINT: If either loosen and compact, bridging layer, working platform, geotextile/geogrid layer, drainage layer or other treatment is proposed, submit details 3 days before additional treatments
text | a677944d-1559-57c2-a897-3e20b5b92638 |  | textbox | HOLD POINT NUMBER:
text | c5344a38-72d3-59ce-baca-09e229155cb2 |  | textbox | DATE SUBMITTED:
text | 81605f0f-3c2f-51d0-a3d3-16a1cadccf7e |  | textbox | SUBMITTED BY:
text | 52aabd5a-d70d-5157-88b1-7a1480fcc080 |  | textbox | SPECIFICATION AND CLAUSE:
text | c3a09c66-8afb-514b-9f5e-720ed6e24a5a |  | textbox | HOLD POINT DESCRIPTION:
text | 08a13cc8-4f2e-5e03-9c1b-dc85bc657447 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 10 - Inspection of Trimmed and Compacted Embankment
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 74b465b0-242f-5843-a3a4-8e10cd293573 |  | note | REQUIREMENTS / REFERENCE: 1112
label | 640b23a5-98d0-5cd3-9a39-06df07f936b7 |  | note | ACCEPTANCE CRITERIA:
label | 94724a33-2116-5d47-9f30-cb609acbebdd |  | note | • HOLD POINT: Inspection of trimmed and compacted embankment prior to placement of subsequent layers
label | 05764fe2-a9e0-5fc7-be72-8348a8b47d83 |  | note | COMMENTS / ATTACHMENTS:
label | 401a8e35-652d-5483-add7-cae83dbc9f10 |  | note | • Compaction Test Results
label | 41b9496f-6629-5452-ad20-3e1f5f641699 |  | note | • Embankment Material CBR Test Results
text | e23b2056-32a7-51d4-9e45-bb2069ca6f2f |  | textbox | HOLD POINT NUMBER:
text | dbe1f938-7292-50ee-b06f-e24d00dc23f5 |  | textbox | DATE SUBMITTED:
text | 9fafe1ea-af67-5df0-8139-b8dfd8765a43 |  | textbox | SUBMITTED BY:
text | 038fef09-7803-5433-9235-38d792b8e9c9 |  | textbox | SPECIFICATION AND CLAUSE:
text | 95df673b-7004-564f-9dfb-79315ef502c5 |  | textbox | HOLD POINT DESCRIPTION:
text | 200e650e-252b-5573-b249-7af98a84f128 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 11 - Embankment Proof Roll Inspection
checkpoint-status |  |  | checkpoint | HOLD POINT
label | ecd9bbcf-7fdf-597a-8093-ca377b4a89cb |  | note | REQUIREMENTS / REFERENCE: 1112
label | 40bae9b9-4656-5f28-9477-6f1cee098b82 |  | note | ACCEPTANCE CRITERIA:
label | a301a9cc-4892-5ee1-ae0e-7b735794cae7 |  | note | • HOLD POINT: Inspection of subgrade/pavement movement observed under roll test – after wet material and subsoil treatment applied.
text | 64053c78-14ef-5ffd-a622-814bb52941ee |  | textbox | HOLD POINT NUMBER:
text | e44c8b14-3ea5-58a7-9a8e-113b92a3dc22 |  | textbox | DATE SUBMITTED:
text | 6a31a844-bb86-5324-a209-b4beb1c2f6b8 |  | textbox | SUBMITTED BY:
text | 4eb83569-7aaf-5d97-aa98-ff8c7e9abc86 |  | textbox | SPECIFICATION AND CLAUSE:
text | e7a90079-a401-58c5-bd1e-c782511e7042 |  | textbox | HOLD POINT DESCRIPTION:
text | 9bcda904-1b2c-51d3-baf9-f4ade1319b6f |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 12 - Steep Slope Inspection
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 76842e06-b00e-57b8-b1a2-fedfef768765 |  | note | REQUIREMENTS / REFERENCE: 1112
label | c923edf3-f941-5be5-8841-361681c48b38 |  | note | ACCEPTANCE CRITERIA:
label | 996c3ac3-6dd9-5449-86da-764b3a87478f |  | note | • HOLD POINT: For slopes steeper than 1:1, Client to inspect the stability of the batter before excavation below it
text | 9203fcaa-8ff7-521f-8c42-5aa9ad44b3a0 |  | textbox | HOLD POINT NUMBER:
text | 5320492a-3c20-5b67-be19-788eecaaf455 |  | textbox | DATE SUBMITTED:
text | 3e86af01-84d1-5e26-9364-12667e0fbc86 |  | textbox | SUBMITTED BY:
text | ef1b4957-be4a-5649-a437-331cd29dd401 |  | textbox | SPECIFICATION AND CLAUSE:
text | ba3d0887-39c9-5de0-9dae-273d67754f57 |  | textbox | HOLD POINT DESCRIPTION:
text | de569cfd-9012-542c-91a0-cd524914f51f |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | d4f46dbf-7aa7-54c5-bf1f-37bfe13c307c |  | textbox | Lot Verified By:
text | c3980a82-7444-51e0-9325-456149dfbe22 |  | textbox | Lot Closed Date:
button | 9b1801b1-69a7-51ee-8966-71f6e2bd1f9d |  | button | Submitted to Client | Yes, No, N/A
button | 1f3fa728-6b58-5725-946e-27a0d36669c0 |  | button | Reviewed by Client | Yes, No, N/A
text | 35a83877-2ba0-5468-9285-3448f8bf6f39 |  | textbox | Submission Comments:
checklist-sectioned |  |  | checklist | A181 - West Dapto - ITC 008 (ITP008) - Kerbs and Gutters |  |  |  |  | Yes | A181 - West Dapto - ITC 008 (ITP008) - Kerbs and Gutters | dd2d3630-cf30-4cd4-9051-cce8092976dc
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | 5f93a161-0796-551a-bdbb-4014d8c4e3f2 |  | textbox | Lot Opened On
text | f20e7011-ccd8-5f5a-a612-3865abf5119f |  | textbox | Date of Works
text | 2f9d77d2-ae42-501e-913c-ab0e35b74efc |  | textbox | Lot Type
text | 2888c04b-c94f-50b2-af92-712cb3a9718f |  | textbox | Start Chainage
text | f68168bd-133b-50a2-8394-db2b3917b8a4 |  | textbox | End Chainage
text | 86277a30-5b04-4f08-a190-9b77e68bd98e |  | textbox | Offset
text | 68073729-bad6-584c-82e8-60bbee82e571 |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Preparation Works
checkpoint-status |  |  | checkpoint | VERIFICATION
label | b490c70e-da3b-5e9d-8ba4-646f28da4967 |  | note | REQUIREMENTS / REFERENCE: Project Safety Plan, Project Environment Plan
label | 429df69b-f632-531d-b7db-b4362c93d4ea |  | note | ACCEPTANCE CRITERIA:
label | 7c28105f-b65f-51af-ae34-1ad0e413a189 |  | note | • All site personnel inducted, required SWMS completed and signed, Safety Plan approved
label | 1c87b544-7d49-5e03-9b61-e5ba708b208e |  | note | • ERSED controls installed on site, air quality visually monitored for dust etc due to construction activities, Environment Plan approved
label | e8b0541e-9136-546f-a53e-2a9d820d8adb |  | note | • Contact DBYD and complete excavation permit, extent of works set out with survey pegs
checkpoint-group |  |  | section | 2 - Materials
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 66be91d1-cc13-54d3-b43f-840d5671a70b |  | note | REQUIREMENTS / REFERENCE:
label | 15087a8e-d592-5596-bc82-ac698ba8259f |  | note | • 1122
label | ac461992-5075-519c-8853-0b5a769e4f8d |  | note | • 0319
label | f44585c8-00df-5aeb-a1fe-b08ac1c33f89 |  | note | • WCC 7000 C10
label | ab29e0a6-a1a4-5f73-8d72-5d53378fedcc |  | note | ACCEPTANCE CRITERIA:
label | c0e78322-58e9-5d82-a142-a622738b159e |  | note | • Confirm concrete mix design is acceptable for use with Client
label | d3b11ffe-4830-5b21-a7f2-d3119e780b59 |  | note | • 20 MPa concrete mix (28 day strength) as per WCC 7000 C10
checkpoint-group |  |  | section | 3 - Set-out of Demolition Works
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | cce6bd58-7baa-5432-b12d-372cdd9bb9d8 |  | note | REQUIREMENTS / REFERENCE: 1122
label | 51c1453f-0c61-5a2b-876b-56c9e2c41814 |  | note | ACCEPTANCE CRITERIA:
label | 41862d06-b995-5f3c-97c6-1c36d3b36364 |  | note | • WITNESS POINT: Client inspection of set-out of any sawcutting to existing kerbs and gutters, footpaths, driveways, road pavements
text | 62a92c39-5453-5ba9-84e5-17782d4553fe |  | textbox | WITNESS POINT NUMBER:
text | f4f3aba9-c280-5935-9cb3-4e0ec6bfd73d |  | textbox | DATE SUBMITTED:
text | 62b41a6b-704e-55d4-bfe1-ea6f5376f10b |  | textbox | SUBMITTED BY:
text | eeaff982-d7e9-5d07-8cb3-d89d246e401e |  | textbox | SPECIFICATION AND CLAUSE:
text | cbba818e-c48c-53a3-8acd-894d52bc2a59 |  | textbox | WITNESS POINT DESCRIPTION:
text | 6c9709fe-6d8e-57f9-b37d-8e649ad67221 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 4 - Temporary Drainage Arrangements
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 04ddec2e-1403-5588-ad4b-418b41af2427 |  | note | REQUIREMENTS / REFERENCE: 1122
label | b0c5b16c-2f38-537c-868f-bea5e78d973e |  | note | ACCEPTANCE CRITERIA:
label | 5e83d759-fa07-5105-9886-94ee0f601bcb |  | note | • HOLD POINT: Details of procedures and / or devices for temporary drainage arrangements while the works are taking place
text | 1d02914a-55de-581c-8db6-f7cb12f45dc6 |  | textbox | HOLD POINT NUMBER:
text | 68813fe3-4c30-5d26-ad43-4af1c6641c8c |  | textbox | DATE SUBMITTED:
text | 0cffcad8-d818-5e2f-b7f2-7300816b0d1e |  | textbox | SUBMITTED BY:
text | 252f4c2f-af22-5752-a746-574660fb0bc7 |  | textbox | SPECIFICATION AND CLAUSE:
text | 39c4cd10-9e4d-53b7-9838-3eaf811b30b6 |  | textbox | HOLD POINT DESCRIPTION:
text | 3be19b04-5610-5f63-8575-f4086fd540a1 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 5 - Ground Preparation Works
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 912fe3fe-3939-53f3-8e83-d0fe296950ca |  | note | REQUIREMENTS / REFERENCE:
label | 15b7253d-d143-5e13-bd46-c50e2658639f |  | note | • 0319
label | ebd7fe95-2d42-5aca-8146-52cc1b0670ea |  | note | • 1122
label | 0af41b02-21aa-5f75-913d-b3845300892c |  | note | ACCEPTANCE CRITERIA:
label | bb092b85-fbbf-5fe7-87e6-4fa8ca17c684 |  | note | • WITNESS POINT: Client inspection of prepared foundation / base of future kerb and gutter, shaped and compacted
text | 39fffd97-ea39-5927-98f0-52daab0c6995 |  | textbox | WITNESS POINT NUMBER:
text | 2b2e6288-5492-57a0-beb4-2b83a2a4cd99 |  | textbox | DATE SUBMITTED:
text | 50758e6c-a1bc-5646-acc0-17e203b480d7 |  | textbox | SUBMITTED BY:
text | be1bf398-0144-5b70-b2a1-0b3ffa2d92e8 |  | textbox | SPECIFICATION AND CLAUSE:
text | 4cedd0d3-21f1-56a6-b00d-b944cdf13fd1 |  | textbox | WITNESS POINT DESCRIPTION:
text | 6712fad7-80b3-542a-b13e-481b8108ffcc |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 6 - Confirm Driveway Crossovers
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 03b715cf-8fff-5055-ba44-a365cb3a16ef |  | note | REQUIREMENTS / REFERENCE: 0319
label | 8c57e9d1-a7c3-5c56-89cc-8c60cf19e7e9 |  | note | ACCEPTANCE CRITERIA:
label | 9fb0ad94-0c90-507b-ae19-ebb98e7cb09e |  | note | • WITNESS POINT: Confirm location(s) of any driveway crossovers in kerbs, gutters and channels (if required)
text | 693f84eb-95cb-5001-be35-782d575abc5d |  | textbox | WITNESS POINT NUMBER:
text | 47c01703-4d99-548b-9c4c-1127e7303b3e |  | textbox | DATE SUBMITTED:
text | bebae087-19bc-51de-9174-e642932fe08a |  | textbox | SUBMITTED BY:
text | 92670593-f84e-5355-9bfc-5d546fdecdc2 |  | textbox | SPECIFICATION AND CLAUSE:
text | d12eb081-a042-5d11-a4d4-9632bedc7815 |  | textbox | WITNESS POINT DESCRIPTION:
text | 75d278b7-a2b9-5973-a7aa-918b6dbcfcec |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 7 - Reconnect Property Stormwater
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | e9a2b41d-e1ed-5319-a40e-da0297af1cd5 |  | note | REQUIREMENTS / REFERENCE: 0319
label | 340ea7a0-5ea5-5dc5-bdbc-edb7cfde7798 |  | note | ACCEPTANCE CRITERIA:
label | 4d2b8b0a-da09-587b-8661-5f552d8560fb |  | note | • WITNESS POINT: Reconnect and extend existing property stormwater outlets through to the new kerb and / or gutter (if required)
text | 42a94c40-751b-5a50-8a84-a35e28721a12 |  | textbox | WITNESS POINT NUMBER:
text | bc98aa52-0563-5385-9f65-86eb2bce5bea |  | textbox | DATE SUBMITTED:
text | 1ffb5529-93bb-5c5a-a933-4a83a98ab768 |  | textbox | SUBMITTED BY:
text | 720e4697-1bfa-533d-a6eb-a709ad30697d |  | textbox | SPECIFICATION AND CLAUSE:
text | 5436bc0e-66b8-5e6f-b1b0-4d32d82bbcd2 |  | textbox | WITNESS POINT DESCRIPTION:
text | 8da85323-fa71-56c8-813f-da8a08467b82 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 8 - Certification of Completed Formwork
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 3b0b4613-d145-5ba3-82e9-18b4e60f5d5f |  | note | REQUIREMENTS / REFERENCE: 0319
label | 52aea14d-4ac4-589b-9e4a-868ed390d6f4 |  | note | ACCEPTANCE CRITERIA:
label | e5ba2d1a-a450-59d0-80b3-1cb4b53cf784 |  | note | • HOLD POINT: Certification of completed formwork conformance (if required)
text | 07772399-451e-5940-9858-05dd4414cfc1 |  | textbox | HOLD POINT NUMBER:
text | 8ac4f4f2-1d3b-5853-976b-b6b9994cc062 |  | textbox | DATE SUBMITTED:
text | c9d006d5-796a-561e-9a6b-24c66e7e7403 |  | textbox | SUBMITTED BY:
text | 7f6477a5-9ca7-5f47-931e-831466a83af1 |  | textbox | SPECIFICATION AND CLAUSE:
text | b94ca209-c1bb-5c1f-9d40-1171a3a12169 |  | textbox | HOLD POINT DESCRIPTION:
text | b0bdceb3-ed87-58cf-a6e0-2624d6db1d7a |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 9 - Client Inspection of Formwork
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | be56720d-d0c2-5679-b22d-2e675f22d923 |  | note | REQUIREMENTS / REFERENCE: 0319
label | 5e293f0f-333e-5a36-9083-ffcf948943d3 |  | note | ACCEPTANCE CRITERIA:
label | 6551898b-dc3b-5e49-b118-0b5ca86c59e0 |  | note | • WITNESS POINT: Client inspection of completed formwork
text | 3eaec71f-8521-520e-b3b5-9d55760c28af |  | textbox | WITNESS POINT NUMBER:
text | 1c88934b-d43f-542c-bd20-9d086d0af386 |  | textbox | DATE SUBMITTED:
text | c084d198-d5c1-5c39-85ca-708ea2b05df3 |  | textbox | SUBMITTED BY:
text | 9f5cd155-0c05-5b84-94a0-83076556c461 |  | textbox | SPECIFICATION AND CLAUSE:
text | 18766906-c548-5d41-a6b1-f9c6800d96ab |  | textbox | WITNESS POINT DESCRIPTION:
text | 7bedc36c-f143-5fe4-a3c3-66d05482f0a3 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 10 - Client Inspection of Reinforcement
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | a99fd0fc-84c2-5e59-934b-764fab418bd9 |  | note | REQUIREMENTS / REFERENCE: 0319
label | cc3c0a43-1bc9-57a2-9a59-e6412a49ee36 |  | note | ACCEPTANCE CRITERIA:
label | b1da6e16-4b80-5363-a1ac-a3c28fcfe2d1 |  | note | • WITNESS POINT: Client inspection of installed steel reinforcement including cores, fixings and embedded items fixed in place (if required)
text | ff81df74-8ace-5188-af9d-b1dc10f9d5f5 |  | textbox | WITNESS POINT NUMBER:
text | 3768e989-0e6d-5251-a859-69cee72a24a9 |  | textbox | DATE SUBMITTED:
text | 8a3cd7ad-7a94-5dcf-b545-3e6a231023b4 |  | textbox | SUBMITTED BY:
text | 22eb21b4-6cf1-565a-bc60-ac42ad932933 |  | textbox | SPECIFICATION AND CLAUSE:
text | a8fe8483-f436-54a3-849e-7f5da31bac09 |  | textbox | WITNESS POINT DESCRIPTION:
text | 0316a5b0-b94d-517a-b7c2-5322ad3b3a7b |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 11 - Trial Sections
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 224d7bf8-b77b-5e79-941f-5d7b0cc13ccc |  | note | REQUIREMENTS / REFERENCE: 1122
label | 389aa743-f261-529f-99d1-6abe909e9892 |  | note | ACCEPTANCE CRITERIA:
label | b27e8a8e-5c4f-5cb8-bfc3-a77fdce0423e |  | note | • WITNESS POINT: Construct a 3m trial section to the documented level of finish to show capability of the forming equipment and request Client inspection. Subject to approval, incorporate the trial section into the completed works
text | 3f3671ac-07af-5e79-8e0d-85ee3b24909f |  | textbox | WITNESS POINT NUMBER:
text | 82a9811b-9104-52e6-b844-51ff070c5ef2 |  | textbox | DATE SUBMITTED:
text | 663f9bf3-4aa5-5719-9944-9702c503909d |  | textbox | SUBMITTED BY:
text | 183281e7-7d7a-5e40-b37f-c5264d948c25 |  | textbox | SPECIFICATION AND CLAUSE:
text | 3330fb2a-e8ce-5767-8764-3683a0c8b358 |  | textbox | WITNESS POINT DESCRIPTION:
text | 9225672b-a266-5631-8171-0da40b130343 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 12 - Concrete Dockets and Records
checkpoint-status |  |  | checkpoint | VERIFICATION
label | d0d2d0d6-a17b-5f79-830a-9c9436404418 |  | note | REQUIREMENTS / REFERENCE:
label | 10e02c96-b421-5845-b66c-8dabe1e29087 |  | note | • 0319
label | 7d9456ea-cb0f-532a-8b31-2f4dc2a9c1ad |  | note | • 1122
label | a68ce516-7f71-508c-98ff-c83c96e735dd |  | note | ACCEPTANCE CRITERIA:
label | d864bba6-9ffe-5762-89bf-357ffa88ce27 |  | note | • Confirm weather is suitable for pouring concrete
label | cd25a3b4-c1c4-561a-b49f-1e9a93b2cde6 |  | note | • Complete concrete testing and keep pour records, if required
label | 4fe0f1ff-817f-522c-af6d-af120049c915 |  | note | • Protect finished concrete and cure as needed
label | afc0b143-f3bb-55ad-9509-42dc2b47a6a4 |  | note | COMMENTS / ATTACHMENTS:
label | 67d640b2-ab46-55a4-8e09-5ca30e9a9fe6 |  | note | • Concrete pour and test records
label | a227c929-b23d-55a0-9b30-81b7c2e4d000 |  | note | • Concrete docket(s)
checkpoint-group |  |  | section | 13 - Stripping Formwork and Backfill
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 7f13071a-43ce-5370-9027-70673664b6a6 |  | note | REQUIREMENTS / REFERENCE: 1122
label | ae31b18d-f266-50e3-9967-a45478bd0980 |  | note | ACCEPTANCE CRITERIA:
label | bc38e48a-096d-501c-a6ff-ac672f2b4e49 |  | note | • Strip kerb and gutter works once concrete has achieved suitable strength
label | 14ba88c0-f80d-5a76-9a9c-4dcf5cf723b5 |  | note | • Backfill stripped works as specified in drawings
label | 993fba8d-a704-58a1-9f57-9458939b32ed |  | note | • WITNESS POINT: Client inspection of completed backfill placed behind kerb and gutters
text | 728de726-0387-52b8-89c8-5e946411a69b |  | textbox | WITNESS POINT NUMBER:
text | 0b86acb7-b79e-59cc-9e6c-13dfbcd33857 |  | textbox | DATE SUBMITTED:
text | 8eb7c575-71ad-5838-909e-5be2fa29cbd0 |  | textbox | SUBMITTED BY:
text | a88a12c4-4bef-50fc-93f1-a87a46918e99 |  | textbox | SPECIFICATION AND CLAUSE:
text | 3d2bc356-5ebb-53a8-8e82-2422124cc78a |  | textbox | WITNESS POINT DESCRIPTION:
text | 60772279-5e7a-52d1-b7ba-890fb8960db7 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 14 - Reinstatement of Damages
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 4a1e5df5-7444-5ff3-bd20-86c45537dbd6 |  | note | REQUIREMENTS / REFERENCE: 1122
label | 5cc24be7-2c03-5d0a-aa00-6e1a7cf2318f |  | note | ACCEPTANCE CRITERIA:
label | 93af4b8f-138f-54a8-9633-7c23017c47ce |  | note | • WITNESS POINT: Reinstate any damage to footpaths, road pavement and services in the event of their damage during the works (if required)
text | c79c0b3c-6c35-5d68-9c08-d9aa569e6598 |  | textbox | WITNESS POINT NUMBER:
text | 7045f531-dc8d-599b-b13f-c1baae5333d8 |  | textbox | DATE SUBMITTED:
text | 10819cd2-4181-5ed9-b9d1-326f69725fb5 |  | textbox | SUBMITTED BY:
text | c05b4d40-3fed-5816-a957-05ae92abb62e |  | textbox | SPECIFICATION AND CLAUSE:
text | c6e5b751-1cfd-5d8c-a07c-5df32052b40e |  | textbox | WITNESS POINT DESCRIPTION:
text | fc2902d4-6690-5278-9eef-6a94a2a750b7 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | d9bc345f-f910-5238-ac82-1e6a025d30c3 |  | textbox | Lot Verified By:
text | e9c2620e-3d43-53fc-af09-1aae10f4107f |  | textbox | Lot Closed Date:
button | efbb047b-744c-59fb-bc84-659a237d1a35 |  | button | Submitted to Client | Yes, No, N/A
button | 23709ae5-23c7-5f8a-a745-62e6c8246987 |  | button | Reviewed by Client | Yes, No, N/A
text | 88b1d60a-fc93-56d0-906a-b79e08153607 |  | textbox | Submission Comments:
checklist-sectioned |  |  | checklist | A181 - West Dapto - ITP 018 Landscaping |  |  |  |  | Yes | A181 - West Dapto - ITP 018 Landscaping | dfce8d8f-4a62-41bf-a28f-96418545b2da
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | fa55485e-2f74-5c4a-901a-48da41e61370 |  | textbox | Lot Opened On
text | dc80c790-a53b-5b17-be10-ae150a11d5d3 |  | textbox | Date of Works
text | 8bc06f6a-b077-5f37-9fbe-b7ed827dc2c6 |  | textbox | Lot Type
text | 2b3b6b9e-ff54-506a-b44c-c03a2f1f5383 |  | textbox | Start Chainage
text | eec2b78c-9a7b-5b07-b2cc-62d3f1da09ee |  | textbox | End Chainage
text | ab08bb9a-5ecd-5ef9-ab46-7d0b750e42f8 |  | textbox | Offset
text | 8fd4a51f-5fc4-58d2-9b33-c9f55e91af46 |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Safety Review
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 3b9305f8-043d-5c74-9d8d-d9bb04b765fd |  | note | Requirements / Reference - Project Safety Plan
label | ba829b05-532e-515d-b9cc-2d09b7d03f6e |  | note | Acceptance Criteria - All site personnel inducted (includes environment and cultural) Required Safe Work Method Statements completed and signed. Subcontractor’s safety plan/procedure approved
checkpoint-group |  |  | section | 2 - Environment
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 19555d43-e1a8-5d58-b555-267122fd44fb |  | note | Requirements / Reference - Project Environment Plan
label | a14ec361-1707-5fd9-b637-10e7040d3b33 |  | note | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs. Air quality to be visually monitored for dust etc. as a direct result of construction activities.
checkpoint-group |  |  | section | 3 - Landscape
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 236e7a96-4a96-5042-919a-07cd9cb958a3 |  | note | Requirements / Reference - WCC 0257 Cl.1.5
label | 9fa1d978-580c-5998-a0ff-f1054b84b38c |  | note | Acceptance Criteria - Soil amelioration recommendations if required. Plant material: Submit details of proposed fertiliser Soil conditioning: If other fertiliser than gypsum is proposed. Plant provenance: All plant must be grown from locally provenanced stock. Give notice if this is not achievable. Plant source: all plant material has been grown from locally sourced stock (or local endemic species) Species: Submit written certification that all plant material is true to the required species and type. Seed Supply: Submit the proposed seed supplier(s)
label | 34f0dcf5-bf9a-5fbb-b588-65fe5b4dec19 |  | note | For Imported Topsoil, submit details for the suitability of each soil type and establishment for on-going viability of the site vegetation.
text | 0d9d44a7-b1f0-5629-a249-e96fd1fa631f |  | textbox | HOLD POINT NUMBER:
text | 9265ae11-2285-5ea0-8ebe-4dd556c2b709 |  | textbox | DATE SUBMITTED:
text | 85f6156b-3631-5fa3-bff2-934c02298bfc |  | textbox | SUBMITTED BY:
text | e2f60885-b293-5db3-a7c5-77d64459ce96 |  | textbox | SPECIFICATION AND CLAUSE:
text | 7e817683-85c7-567a-92c3-13cabeb90dce |  | textbox | HOLD POINT DESCRIPTION:
text | 17fa00d7-437e-59bc-a044-f2089ec1e616 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 4 - Slopes and Drains
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | c64cea77-e776-5c80-8812-4026369f57e0 |  | note | Requirements / Reference - WCC 0257 Cl.1.6
label | f961815f-9360-5382-a43e-3776cbbffeec |  | note | Acceptance Criteria - Witness Point: An inspection notice for prepared surface for cultivation and conditioning For slopes flatter than 3H to 1V: Before applying topsoil, tine to a depth of 200 mm to produce a loose surface and remove all large stones, rubbish and other materials that may delay germination. For cultivation depth, a 50 mm for a roughened surface with soil lumps not exceeding 50 mm For slopes steeper than 3H to 1V: Remove all loose material from fill batters and cut batters. No more than seven days before seeding. Lightly tine or roughen the surface parallel to the contours. For Open Drains: Prep Topsoil by spreading to an average thickness of 50mm, with a minimum compacted thickness at 30 mm at any location Apply Grass seeding in conformance with Seed and Turf Table
text | 469fcfd2-494c-5838-a816-331c73c5b074 |  | textbox | WITNESS POINT NUMBER:
text | e6d22bdb-fbe9-5f38-ac7f-b7ed368b2fca |  | textbox | DATE SUBMITTED:
text | f66f5273-6f5d-5e9d-bad7-727f83d5b53d |  | textbox | SUBMITTED BY:
text | 5cc1fd24-ab7b-5f11-8674-674ca3e734c5 |  | textbox | SPECIFICATION AND CLAUSE:
text | 31f53fee-7146-5361-aef9-2d902bdd905c |  | textbox | WITNESS POINT DESCRIPTION:
text | 32186c3e-d6bd-5d19-a8fb-c544d3b2e07d |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 5 - Delivery of Plants
checkpoint-status |  |  | checkpoint | HOLD POINT
label | b1833686-abbe-5d15-a904-199ca515f68b |  | note | Requirements / Reference - WCC 0257 Cl.1.6
label | e4b6f885-97de-5d3e-8079-a47a2bdffc97 |  | note | Acceptance Criteria - Hold Point: Inspect plants on arrival at site and check for physical damage or drying out, at least 3 days before planting.
text | 16afa11e-32bb-56e6-9b49-95ca9f601742 |  | textbox | HOLD POINT NUMBER:
text | e0eee004-ae99-595a-a3b3-42d453e12736 |  | textbox | DATE SUBMITTED:
text | 19b77b6d-4f30-5d04-8006-86710f5f5955 |  | textbox | SUBMITTED BY:
text | c33a422b-fcd0-5be7-ac6f-2629f4778cd7 |  | textbox | SPECIFICATION AND CLAUSE:
text | 48e7234e-5668-5675-a24b-6689840ca750 |  | textbox | HOLD POINT DESCRIPTION:
text | 5490576a-59b5-5d1a-8530-c51d36c1085f |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 6 - Turf Material
checkpoint-status |  |  | checkpoint | VERIFICATION
label | c8abf771-dead-5dd2-a02e-4bef446025d0 |  | note | Requirements / Reference - WCC 0257 Cl.2.4
label | b9951898-4ce6-5cab-b641-1104cad379c2 |  | note | Acceptance Criteria - Seed material must conform to the following: Grass and clover: Pre-packed commercially with a certificate of germination Native seed: Store seed in clean, airtight containers and keep away from direct sunlight.
label | ddb80f7f-73fc-503e-b260-d3c37d8c55ae |  | note | Turf material must conform to the following: 25 mm depth of dense, well rooted, vigorous grass growth with 25 mm depth of topsoil and free of weeds, soil pests and diseases Kikuyu grass is prohibited Supply: width of rolls > 300mm
label | 48e96dc4-82fc-5198-adf6-6bdff7a3ae84 |  | note | After turfing: Re-water to a uniform moisture condition without run-off.
checkpoint-group |  |  | section | 7 - Landscape Planting
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 145d7098-da7c-5511-99c7-0fbc427a9500 |  | note | Requirements / Reference - WCC 0257 Cl.1.6
label | 4300f8f0-b8a6-5e0a-b729-0d9b9da1dc11 |  | note | Acceptance Criteria - Hold Point: Inspection notice for set out of plants, soil conditioner and fertiliser, at least 2 days before backfilling. Do not carry out landscape planting when temperature is above 35°C or below 10°C.
label | 57076e8d-fd9b-5b04-9bb5-a153ed2f403d |  | note | Weed management of Herbicide spray: Maintain sprayed areas undisturbed for 2 weeks. Make sure there is no contact with planted material.
label | d528f885-7d50-575b-b485-3e6b78d6b527 |  | note | Weed management of synthetic weed blocking fabric - extent of area 800 mm surrounding each proposed planting. In preparation of fertilising, conform to ratio 63:18:28 and application rate: 5 kg/m2 Surface preparation for Mass Planting in mulched bed: Rip the surface at 500 mm centres to a depth of 300 mm and break up the top 200 mm of the planting bed by cultivation to a maximum of 50 mm. Surface preparation for Individual Planting: Loosen a planting area 600 mm diameter to a depth of 400 mm
text | 9258cbec-e570-571f-93b0-14fc5ad8fb48 |  | textbox | HOLD POINT NUMBER:
text | 48018049-ba75-538d-9790-453c412966b4 |  | textbox | DATE SUBMITTED:
text | 31a38c95-4efe-5606-a514-8627e6f41645 |  | textbox | SUBMITTED BY:
text | e55a6b30-f642-5136-96bb-6d86eb4e0398 |  | textbox | SPECIFICATION AND CLAUSE:
text | 10770aae-b8fb-53ae-8ee1-384e2da1c117 |  | textbox | HOLD POINT DESCRIPTION:
text | 15e89260-1b11-51d6-aa42-b35c2b1476e2 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 8 - Testing Requirements
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 12839ff0-1e7b-56e0-a7c7-45e6f3c8302b |  | note | Requirements / Reference - WCC 0257 Cl.1.6 AS 4419
label | 1afc78b4-30e7-5d8a-96b8-3791db7eaa8e |  | note | Acceptance Criteria - Imported topsoil must undergo testing that includes the material quality (pH, organic content and soluble salt) – test method AS 4419 Test material quality for Mulch – test method AS 4454
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | b3f1fd8c-6ffe-5064-836e-ff4c7d8b2ba6 |  | textbox | Lot Verified By:
text | 06693ffd-0581-516e-9a52-c22b0e4338d9 |  | textbox | Lot Closed Date:
button | 395809da-b153-54ae-b5d4-279d4e47aa67 |  | button | Submitted to Client | Yes, No, N/A
text | 68574d44-0de3-5965-9948-2286440cb760 |  | textbox | Reviewed by Client | Yes, No, N/A
text | f6e90a16-fa2e-5dbd-a4df-32cc7a2d80cc |  | textbox | Submission Comments:
checklist-sectioned |  |  | checklist | A181 - West Dapto - ITC 017 (ITP017) - Utility Adjustments (Traffic Signals) |  |  |  |  | Yes | A181 - West Dapto - ITC 017 (ITP017) - Utility Adjustments (Traffic Signals) | e5e035e2-ed04-4776-a538-07214102a3fd
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | 9aaace82-4e8c-5a91-87ef-004c197e7c07 |  | textbox | Lot Opened On
text | 4218d84a-3274-5e52-a9a5-58441e27c31e |  | textbox | Date of Works
text | 471aae22-c548-5260-8408-6bf19e6da99c |  | textbox | Lot Type
text | 4db5ca81-ab81-5084-8591-79d811a4b0a4 |  | textbox | Start Chainage
text | 4aedafa2-a99f-5a07-b2d5-d3d6304a11a1 |  | textbox | End Chainage
text | db699536-9951-47af-8566-ad084e4d1d5b |  | textbox | Offset
text | 6425f594-c5f2-5863-af46-8d36501ae205 |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Preparation Works
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 291a73af-ef24-5b02-8267-e1dac16ec948 |  | note | REQUIREMENTS / REFERENCE: Project Safety Plan
label | 2004847d-10cf-52d4-850b-ed8a9510250d |  | note | ACCEPTANCE CRITERIA:
label | d750cc31-ef10-54d4-a9f7-1100e1a75535 |  | note | • All site personnel inducted (includes environment and cultural)
label | 5dcfd796-1c8c-58b2-9e8a-fbf2cb86a091 |  | note | • Required Safe Work Method Statements completed and signed
label | 31448adb-3fe0-5f98-ac71-66e80d20f28f |  | note | • Subcontractor’s safety plan/procedure approved
checkpoint-group |  |  | section | 2 - Environment
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 389ffdf8-d23a-5a40-af4a-100128aa2316 |  | note | REQUIREMENTS / REFERENCE: Project Environment Plan
label | b22c4737-6eed-5180-a1bc-003365709588 |  | note | ACCEPTANCE CRITERIA:
label | 508f8bf9-0074-5833-a414-ef4d6ea6d88f |  | note | • Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs.
label | 1e8387dd-91de-56a7-838d-9ba44edde3aa |  | note | • Air quality to be visually monitored for dust etc. as a direct result of construction activities.
checkpoint-group |  |  | section | 3 - Design Approval
checkpoint-status |  |  | checkpoint | HOLD POINT
label | a9a9ff6a-5d06-5e16-8892-3eaa20107edf |  | note | REQUIREMENTS / REFERENCE: TS101 Cl 3.4
label | 888f5785-8092-5501-9b9e-9799435c8820 |  | note | ACCEPTANCE CRITERIA:
label | 67bfa668-40ff-5b9f-8405-2aec09556d51 |  | note | • HOLD POINT: Submission of cable installation drawings and cable connection chart
text | 21d2621e-21b5-505f-9765-838285ce2b97 |  | textbox | HOLD POINT NUMBER:
text | 241cf0db-81c2-5910-9be9-056e0657d7b5 |  | textbox | DATE SUBMITTED:
text | 8e62c965-794e-5bc6-a15e-26f10a68ad09 |  | textbox | SUBMITTED BY:
text | 4792d3bd-e67e-57e6-be39-a0281f49dcca |  | textbox | SPECIFICATION AND CLAUSE:
text | e85ad8c2-75bd-5e73-970d-b742896c40d2 |  | textbox | HOLD POINT DESCRIPTION:
text | 93d7bea4-76f7-54e0-8584-52fdee4f54fe |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 4 - Preparations
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 5d9f0e84-49c5-5770-9329-c1e153e2928a |  | note | REQUIREMENTS / REFERENCE: TS101 Cl 2.3.1
label | 364f2cfb-d069-58ab-a621-21a4759c8a4a |  | note | ACCEPTANCE CRITERIA:
label | 5c0ff8b4-2269-5dd0-a606-87c75b28b183 |  | note | • DBYD and service locating completed
checkpoint-group |  |  | section | 5 - Materials (TCS)
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 22aea092-030b-54e5-8e77-ce3d76a5bd06 |  | note | REQUIREMENTS / REFERENCE: WCC Traffic Signals TSI-SP Series
label | b4262548-1a47-5fb9-9089-9c0fb33c1257 |  | note | ACCEPTANCE CRITERIA:
label | b802bb27-3a0e-5ae0-8ad4-96b2f58659d1 |  | note | • Nominated TCS materials comply to the relevant requirements of the WCC Traffic Signals TSI-SP Series
checkpoint-group |  |  | section | 6 - Materials (ITS Devices)
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 38a75b4d-f8e2-527c-874b-c8dc25e0fa84 |  | note | REQUIREMENTS / REFERENCE: TS201 Cl 4.1
label | 2515243f-10e9-52ef-9f35-b5b315de6657 |  | note | ACCEPTANCE CRITERIA:
label | e74b20a2-379d-543d-b46b-572be675ce8b |  | note | • HOLD POINT: Prior to supply of ITS Equipment for maintenance or project works, submit confirmation that proposed ITS Devices have been approved as per devices previously accepted by TfNSW (TS200), or by project based approval (TS202) via the Director of Intelligent Transport Systems or their delegate)
text | a60436ce-1f0d-5ff4-b3e4-be1a1d4c4847 |  | textbox | HOLD POINT NUMBER:
text | c13519de-a143-5345-a6c5-721198b80ddc |  | textbox | DATE SUBMITTED:
text | 76ee0c49-7f1f-5720-88fb-ff9b43cd4dc5 |  | textbox | SUBMITTED BY:
text | 4ec2bbcb-ef2f-52c6-aaa4-d7b8aec2aa1a |  | textbox | SPECIFICATION AND CLAUSE:
text | 9333c19f-1e8c-56d3-9e0f-1b42014b7811 |  | textbox | HOLD POINT DESCRIPTION:
text | c6189266-0aae-5c2f-9cc1-0f9d21f956cf |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 7 - Materials (ITS Solution/s)
checkpoint-status |  |  | checkpoint | HOLD POINT
label | b7ec0cd2-5bd2-58bd-93ea-f5e41fbd9841 |  | note | REQUIREMENTS / REFERENCE: TS202 Cl 8.1
label | b14d1d40-0155-52ba-8850-d8a7d87fd972 |  | note | ACCEPTANCE CRITERIA:
label | e5d1979f-1574-5b3a-b3b5-2a2a5eb88fe3 |  | note | • HOLD POINT: Prior to supply of ITS Equipment for maintenance of project works, submit confirmation that the proposed ITS Solution has been approved by the Director of Intelligent Transport Systems or their delegate
text | 8fddee1c-91c3-5747-979d-60a18234f796 |  | textbox | HOLD POINT NUMBER:
text | c7bba6ef-e119-577a-bd57-0b2b2fe0d2d0 |  | textbox | DATE SUBMITTED:
text | b5aa23c3-75fe-5b7e-8218-621a0d898ac1 |  | textbox | SUBMITTED BY:
text | 451351ae-29e1-5191-8f6a-e3c667765644 |  | textbox | SPECIFICATION AND CLAUSE:
text | b60cb0ce-f88b-579e-bf25-48a6f1ecfe26 |  | textbox | HOLD POINT DESCRIPTION:
text | e5d6cb43-b579-5f10-9fb9-94aab830862b |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 8 - Excavation – Open Trenching Work
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 301c382c-7146-5c5c-ab53-623d422557c8 |  | note | REQUIREMENTS / REFERENCE: TS101 Cl 5.1.1
label | 36fff111-a1ab-525a-8fc0-f42bf1a4239c |  | note | ACCEPTANCE CRITERIA:
label | 56666667-e8e0-5b42-834a-431c6131e691 |  | note | • HOLD POINT: Submission of details of open trenching work
text | acd701ff-da62-584a-9a95-b2cc21e12ca3 |  | textbox | HOLD POINT NUMBER:
text | 1ef09bd6-a67a-560b-8568-2aaf5d085bdb |  | textbox | DATE SUBMITTED:
text | 416befad-b4c8-5f7c-8624-2be05e2ea9a1 |  | textbox | SUBMITTED BY:
text | bcb3c56e-01d5-57c1-9a93-f033aff2796c |  | textbox | SPECIFICATION AND CLAUSE:
text | 06ce126b-45c8-5c43-8abc-00443fff6b4c |  | textbox | HOLD POINT DESCRIPTION:
text | cba10dca-e55e-52ca-afe5-017a2aa34dcb |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 9 - Excavation – Modified Footing Design
checkpoint-status |  |  | checkpoint | HOLD POINT
label | c7b4b9d9-63f6-56c1-a7e6-83c80c315802 |  | note | REQUIREMENTS / REFERENCE: TS101 Cl 5.9.4
label | d65b1260-873c-5bdb-9307-562391a1e55d |  | note | ACCEPTANCE CRITERIA:
label | 8790e91f-e1a0-57ed-befe-9ec5cb7c1f7f |  | note | • HOLD POINT: Submission of details of modified footing design (if applicable)
text | b6761aa8-220e-5531-b61c-bb1cf7276cd2 |  | textbox | HOLD POINT NUMBER:
text | 12fa608b-c3fd-53f0-9154-07252a42014b |  | textbox | DATE SUBMITTED:
text | 783ac4d6-ea94-5f36-97de-b4e96531030f |  | textbox | SUBMITTED BY:
text | 8d17c23a-6414-556c-b7aa-32c03b107a0a |  | textbox | SPECIFICATION AND CLAUSE:
text | 503ca1d4-1b33-52ba-8f3f-0b9a107193fd |  | textbox | HOLD POINT DESCRIPTION:
text | 319a78a7-c999-540c-b947-baf6ebb8fe58 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 10 - Conduits and Cabling
checkpoint-status |  |  | checkpoint | VERIFICATION
label | e2060a61-fdf6-5446-a267-dc4574e96d23 |  | note | REQUIREMENTS / REFERENCE:
label | 5b2d5c61-172d-5f9e-a8d1-9e8e5c1c991d |  | note | • TS101 Cl 5.3
label | 93c84fa1-8808-5149-98bb-5e6cb88490af |  | note | • TS101 Cl 7
label | e5422a2a-d30c-5dc0-8c39-4b0e312afa21 |  | note | ACCEPTANCE CRITERIA:
label | 211f26a8-49e1-54d0-9a59-5b1bf38fd7e7 |  | note | • Install conduits and cabling as per TS101 Cl 5.3 and TS101 Cl 7, respectively
checkpoint-group |  |  | section | 11 - Approval to Stand
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 4677da9e-3322-5647-9545-12ee5aaa7e9f |  | note | REQUIREMENTS / REFERENCE: TS101 Cl 6.1.1
label | 5b5f233b-854a-545f-b749-4e80f7b8f046 |  | note | ACCEPTANCE CRITERIA:
label | 48fe7571-2625-5fe3-be57-fcfcdb69c543 |  | note | • HOLD POINT: Submission of evidence that all requirements have been satisfied prior to erection of signal post or mast arm
text | bd5b5305-dd10-539d-b469-283f47eddfea |  | textbox | HOLD POINT NUMBER:
text | c918d8f5-0bd4-5df0-b60b-184a5ec328b3 |  | textbox | DATE SUBMITTED:
text | 9369a3d2-6be3-5daf-ac32-778a7baff1c1 |  | textbox | SUBMITTED BY:
text | 50f5810f-2805-5df4-85f0-9f5c843e9141 |  | textbox | SPECIFICATION AND CLAUSE:
text | 7f55b688-f7d3-565e-9ed1-bc7c72baa137 |  | textbox | HOLD POINT DESCRIPTION:
text | 68f270f2-0155-5bd1-b3f5-2c4295623351 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 12 - Approval to Impact Awning
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | c7112dc1-460e-5847-aacd-396ef4cf30a5 |  | note | REQUIREMENTS / REFERENCE: TS101 Cl 6.1.4
label | 54946614-d831-5096-accf-067552c68087 |  | note | ACCEPTANCE CRITERIA:
label | e053bb3a-8024-502d-9cca-c747ae5470f5 |  | note | • WITNESS POINT: Submission of evidence that all necessary approvals have been obtained prior to making any opening or hole through an awning
text | f0c28cb6-cd21-517e-bb68-7238dce3a75a |  | textbox | WITNESS POINT NUMBER:
text | c11afc90-94ac-548e-8863-2ff754a15fc2 |  | textbox | DATE SUBMITTED:
text | 24ab314b-b0f2-592f-92c5-9d90f32cc0fc |  | textbox | SUBMITTED BY:
text | 83f8dddf-598e-59fa-8f12-1b9a6e617186 |  | textbox | SPECIFICATION AND CLAUSE:
text | d87915f3-3d09-5b86-beb5-d038c295288e |  | textbox | WITNESS POINT DESCRIPTION:
text | 8f5f3e98-8fbf-5519-aac9-9a6498926daf |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 13 - Proposal to Overcome Obstruction
checkpoint-status |  |  | checkpoint | HOLD POINT
label | e14a6817-2803-53f3-aa5a-9710944481c0 |  | note | REQUIREMENTS / REFERENCE: TS101 Cl 6.2.7
label | 666b7e41-7d3d-585f-b31b-7fb247fd3866 |  | note | ACCEPTANCE CRITERIA:
label | cd9787e7-b7d8-55ed-97e4-872bad78dc58 |  | note | • HOLD POINT: Submission of proposal to overcome local obstruction to mounting of lanterns or target boards
text | 054e42ae-be3b-5547-8457-01dfccf57a68 |  | textbox | HOLD POINT NUMBER:
text | 9e29501e-1747-5d73-a42c-0dee7f26b893 |  | textbox | DATE SUBMITTED:
text | e068664e-a4e3-5896-9e16-5d74991e610d |  | textbox | SUBMITTED BY:
text | 95ab9b46-fcb6-52d9-8c05-c35df6b15b9f |  | textbox | SPECIFICATION AND CLAUSE:
text | 88c9e7af-3055-5fa5-902f-75ecd8444ce9 |  | textbox | HOLD POINT DESCRIPTION:
text | 91ea533d-5883-5284-a761-c4f850aebede |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 14 - Backfilling
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 109198db-60c7-5486-b625-577d2e5f255a |  | note | REQUIREMENTS / REFERENCE: TS101 Cl 5.2
label | c6f7cdd6-3330-5c14-8d64-30c771262e58 |  | note | ACCEPTANCE CRITERIA:
label | edb7588a-972c-507e-bfa0-c1362f2979b3 |  | note | • Backfilling works comply with the relevant specifications and/or, where applicable, the conditions of the Road Opening Permit
label | 06097faf-f10b-5219-95f0-1019da616a78 |  | note | • Backfill the excavations as per Cl 5.3.6
label | 9a0dce40-b524-519e-8397-ef8367d066e6 |  | note | • Minimise the time each excavation is left open, remove excess spoil before the end of each day’s work
checkpoint-group |  |  | section | 15 - Blackouts at Existing Sites
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 4fc4b62a-dfce-5586-83f9-9cf7de166689 |  | note | REQUIREMENTS / REFERENCE: TS101 Cl 8.3
label | 21eb8f57-11af-5735-8dbc-581dd6083f8e |  | note | ACCEPTANCE CRITERIA:
label | 1928ce62-c8da-50aa-aea2-939b5e0fa22e |  | note | • HOLD POINT: Submission of required details prior to traffic signal blackout at TCS reconstruction site
text | c658f99b-a011-563a-b9b0-66fb44afe8b0 |  | textbox | HOLD POINT NUMBER:
text | 7a3d764f-d88d-52b0-b34c-279e0165a8a4 |  | textbox | DATE SUBMITTED:
text | ddd0cc5e-fc62-5493-924b-abb8e96c790c |  | textbox | SUBMITTED BY:
text | f1649399-15f0-52ae-a2d9-223e6622dcc1 |  | textbox | SPECIFICATION AND CLAUSE:
text | 52b14b2e-bb8c-5034-ba3f-fb9e507e5050 |  | textbox | HOLD POINT DESCRIPTION:
text | d18a5cb4-251c-59b5-949c-48fc3cc66269 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 16 - Testing
checkpoint-status |  |  | checkpoint | VERIFICATION
label | b69f7d23-e14a-52fb-9bdf-f2578d0149be |  | note | REQUIREMENTS / REFERENCE: TS101 Cl 8.2
label | 566b2f23-7c5c-57a8-bef9-8416dab0b305 |  | note | ACCEPTANCE CRITERIA:
label | ab4fc8de-d3ab-59fa-a76b-308669874d65 |  | note | • Complete preliminary inspections and testing and rectify any defects prior to completing commissioning tests. Provide the ITP test results to the Principal before commencement of the commissioning tests
label | d7061314-dbcc-5f57-a609-2f90bc2a9e90 |  | note | • Provide the Principal with at least 5 working days’ notice of the upcoming final inspection and commissioning tests of the TCS works
label | ada34e03-a0a2-5d6b-912c-cc38dce4a910 |  | note | • Record and submit to the Principal, the results of the final inspection and commissioning tests
label | b2883934-8d11-59df-8c9a-c09bf8581a62 |  | note | COMMENTS / ATTACHMENTS:
label | b642009a-4df8-5733-ab1f-317755b0aea5 |  | note | • ITP Test Results
label | 134fde46-783a-5ac7-a1f7-623d2aa1f02b |  | note | • Results of final inspection and commissioning tests
checkpoint-group |  |  | section | 17 - WAE and Final Completion
checkpoint-status |  |  | checkpoint | VERIFICATION
label | bfa3f089-d489-5da3-9021-e044c5ebfd0a |  | note | REQUIREMENTS / REFERENCE: TS101 Cl 10.3
label | dfa713bd-c306-598a-9d34-769bf2ca3fd1 |  | note | ACCEPTANCE CRITERIA:
label | 1b9c4160-2186-58ee-a229-57b008ed1eff |  | note | • Restore surface above trenches as per drawings and project specifications
label | 2ca4c9cf-541f-502a-be52-26728069da88 |  | note | • Where the final restoration is to be completed by others, inform the Principal and the responsible authority/agency who will undertake the final restoration, once the temporary restoration is complete. Maintain the restored areas until final restoration is carried out by the other party
label | 1c2fe031-fd01-5fb3-a3d4-b6680bf39707 |  | note | • Provide Works As Executed (WAE) drawings for the completed utility works as per TS101 Cl 10.3
label | 64320c13-9cb7-5647-8325-b5a328c966ae |  | note | COMMENTS / ATTACHMENTS:
label | b7edf894-ffa9-55af-b0fe-d1abe993cf0a |  | note | • WAE Drawings
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | 2a83f38b-ac41-5ce7-a037-ab39aa33e11e |  | textbox | Lot Verified By:
text | b6d8126a-e2a9-5807-bbfc-1276df720333 |  | textbox | Lot Closed Date:
button | 3f59bf25-1f18-5e86-aa18-6b0e297338cb |  | button | Submitted to Client | Yes, No, N/A
button | 42cb5777-3bbe-5b56-9017-c3025cd51b43 |  | button | Reviewed by Client | Yes, No, N/A
text | 24d5b23c-14e4-5c55-aaec-60f64af36699 |  | textbox | Submission Comments:
checklist-sectioned |  |  | checklist | A181 - West Dapto - ITC 012 (ITP012) - Spray Seal |  |  |  |  | Yes | A181 - West Dapto - ITC 012 (ITP012) - Spray Seal | f0a5ea6e-8c3c-4abe-980e-364a3d0934cc
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | 17bbf6e4-dd1f-593f-8ede-0fe3e2212fe3 |  | textbox | Lot Opened On
text | 0258aa14-b2b1-5e79-988f-a9e72af2ca89 |  | textbox | Date of Works
text | 4d34dedb-eebe-53c1-a957-30f5c863d2d6 |  | textbox | Lot Type
text | 2866a46a-4b66-56b1-ad79-63fe23b46317 |  | textbox | Start Chainage
text | 25ce5756-969e-5f2c-ac70-c24b543992fb |  | textbox | End Chainage
text | 23b8172c-3d83-4b1d-83b1-3b18eb3017c9 |  | textbox | Offset
text | 60ce6994-c28f-5c09-9607-9489af50d9df |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Mix Design
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 673ffdf4-9cb6-5253-b616-ac446cd7642f |  | note | REQUIREMENTS / REFERENCE: 1143 Cl 1.5
label | e3c895e8-97a5-5018-924f-e7e91878be20 |  | note | ACCEPTANCE CRITERIA:
label | 12dd09f0-f2f7-5154-bd8d-87810858227b |  | note | • HOLD POINT: Submit to the Principal documentation on material type, source, proportions, grading, application rates, test certificates and trial mix results as evidence of conformance for each constituent before commencing
text | f5bf3749-ae22-5a4a-aced-9ae34df567cb |  | textbox | HOLD POINT NUMBER:
text | 80f8b9ec-2e3a-5cc1-bde6-31c4c37f0ac5 |  | textbox | DATE SUBMITTED:
text | a5564c67-8e45-5a2b-9c62-1b91570dcd82 |  | textbox | SUBMITTED BY:
text | 4d2379ac-397c-50ac-a985-9accb70a4de1 |  | textbox | SPECIFICATION AND CLAUSE:
text | eda37573-8d70-5bcf-a46c-0a8c9396bf72 |  | textbox | HOLD POINT DESCRIPTION:
text | 694dea8c-05b7-5d3f-b7d4-f5c4961d13c4 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 2 - Execution Details
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 60efe2ec-72b5-5749-bcbc-2ac73825dbfa |  | note | REQUIREMENTS / REFERENCE: 1143 Cl 1.5
label | bcf7218b-4f34-5089-a9f7-f8de19ca2935 |  | note | ACCEPTANCE CRITERIA:
label | fe3c84d5-cfb5-5127-84a7-998ed1e25a5a |  | note | • HOLD POINT: Submit to the Principal sprayed seal design details 2 weeks prior to commencing, with evidence that the design conforms to Austroads AGPT04K Clause 4
text | 92ef251e-2105-50fa-8c8a-cbc170216da0 |  | textbox | HOLD POINT NUMBER:
text | a1c2f74a-d3bd-548b-8e0b-f31e51fe7736 |  | textbox | DATE SUBMITTED:
text | 1cf04ed6-8285-586b-af45-28233de3b2e7 |  | textbox | SUBMITTED BY:
text | f758e8b4-10f5-5b69-94ed-c816a0f7986a |  | textbox | SPECIFICATION AND CLAUSE:
text | 31c475d4-6203-50d2-8fbb-d3cfb6f3808c |  | textbox | HOLD POINT DESCRIPTION:
text | c99f93a9-2d6d-573e-be09-58b2ff5ed220 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 3 - Plant & Execution
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 5775bd63-2e9f-5be7-b661-660d93f7203e |  | note | REQUIREMENTS / REFERENCE: 1143 Cl 1.5
label | bc1f4e03-caf1-5ece-906c-60520b36b0cd |  | note | ACCEPTANCE CRITERIA:
label | d14ae62b-2074-5b20-8ab9-dc3af0ace03d |  | note | • HOLD POINT: Submit to the Principal evidence of plant and equipment registration and insurance 2 weeks prior to commencing
text | 2207ea88-3509-5b43-8d73-4cb35933ef30 |  | textbox | HOLD POINT NUMBER:
text | d099ee2f-8ea3-5572-bd69-b393d044e092 |  | textbox | DATE SUBMITTED:
text | a41251f7-fa5a-53b9-be9e-73f168989f8f |  | textbox | SUBMITTED BY:
text | f36cc806-5b8e-58f6-9719-87323d41b541 |  | textbox | SPECIFICATION AND CLAUSE:
text | bce11759-56da-5374-b350-d55e163de654 |  | textbox | HOLD POINT DESCRIPTION:
text | 8625409f-aedb-53e5-a8ee-0ad9f26d9db1 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 4 - Surface Preparation
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 65407eda-9537-528a-8a58-af0ef789f85d |  | note | REQUIREMENTS / REFERENCE: 1143 Cl 1.6 & Cl 4.2
label | 2c62fb1e-e181-5639-a6f6-de4160bbb2ee |  | note | ACCEPTANCE CRITERIA:
label | bff2b8b4-1429-5aac-b6fb-70b85ed8d133 |  | note | • HOLD POINT: Submit to the principal drawings and documents to final completed works
label | d5842ff0-dd16-5451-bbac-8de241eec4c3 |  | note | • Contractor supplied test certificates for dried back moisture % prior to spraying of primer, primer-binder or binder
label | 07ae33b8-0ece-5dc2-aad4-8c9c097ae9ac |  | note | • Perform embedment tests to Austroads AG:PT/T251 within 48 hours before spray application
label | e85569dd-95b0-5046-82b4-42cae02ed1ad |  | note | • Pavement to be swept with a rotary road or suction broom prior to priming and extend sweeping 30mm beyond edge of spray area. Remove any foreign or loose material
text | baa913af-0032-5eaf-be69-5441b7cf9d15 |  | textbox | HOLD POINT NUMBER:
text | ae5d8161-d63e-509c-a221-b4e6307a10e8 |  | textbox | DATE SUBMITTED:
text | 74f2d2d7-c7f1-5c11-9633-211db04447f8 |  | textbox | SUBMITTED BY:
text | 06cea23a-6295-59ae-a258-1866d6060320 |  | textbox | SPECIFICATION AND CLAUSE:
text | 9425da7c-5848-51b9-8de0-b0cd85c77d65 |  | textbox | HOLD POINT DESCRIPTION:
text | 5a24b94e-e6e5-54ee-9023-d081ee8e17d7 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 5 - Pavement Defects
checkpoint-status |  |  | checkpoint | VERIFICATION
label | da8c86ae-684d-53e5-80e2-9a95c521c095 |  | note | REQUIREMENTS / REFERENCE: 1143 Cl 4.2
label | 4f6aa504-b492-5ac6-8f84-b0c9054a371e |  | note | ACCEPTANCE CRITERIA:
label | 23d3959c-1a92-5b4c-9aca-ba59ab895999 |  | note | • Do not commence spraying until any defects in the pavement surface are rectified
checkpoint-group |  |  | section | 6 - Trial Section
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 220ee42f-0367-57da-8ca9-576ddd17ea64 |  | note | REQUIREMENTS / REFERENCE: 1143 Cl 1.6
label | 7f36012d-9c75-5217-b4e6-5ea316299b01 |  | note | ACCEPTANCE CRITERIA:
label | e64852e8-4afc-53dc-8b5b-dce7355eab0a |  | note | • Notify the Principal of inspection of a completed surfacing trial section
checkpoint-group |  |  | section | 7 - Spraying
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 92dbf4cd-b22c-5149-b419-726a644a44d6 |  | note | REQUIREMENTS / REFERENCE: 1143 Cl 1.5
label | d4c1be50-7595-53a1-85b5-d7f5c7a49524 |  | note | ACCEPTANCE CRITERIA:
label | 91d89233-0982-5a1c-b578-e3bd42cbd4a7 |  | note | • Submit record of temperature and weather conditions during the course of the work. Record during regular intervals with appropriate measuring procedures. Record for both sun and shaded areas
label | 8b27c093-11c5-5cce-9764-6c396574dc70 |  | note | • Submit to the Principal, spraying certificate, binder spraying temperature and work record for each spray run
label | b4b4dc5f-f07a-57e1-945f-fabb1a502cc1 |  | note | • Notify the principal of the inspection of the spraying rate
label | 37adbbbb-b3ed-5f76-9079-43847dde6949 |  | note | COMMENTS / ATTACHMENTS:
label | 851e597d-9ef9-5d0d-bdb3-060bc59c794e |  | note | • Spray records
checkpoint-group |  |  | section | 8 - Test Results
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 16357a11-0738-5411-bb3d-438321d4d6ab |  | note | REQUIREMENTS / REFERENCE: 1143 Cl 1.5 & Cl 3.7
label | b153c746-e4dc-5bc6-b6df-71d758d9e5a3 |  | note | ACCEPTANCE CRITERIA:
label | 525c64ae-2723-5d30-9c9d-67db52cf0a32 |  | note | • Test for all characteristics in conformance with maximum lot size and minimum frequencies
label | 26adaa9a-1bc7-5ae3-9986-e20ee225d46a |  | note | • Pavement surface prep is to be tested to the ball penetration Austroads test
label | 6cd7d372-a550-544f-bf92-11b9cf935db3 |  | note | • Submit test results within the maximum lot sizes and minimum test frequencies
label | 70723db6-96da-58f0-94bf-f8ae39cea536 |  | note | COMMENTS / ATTACHMENTS:
label | 53be8bf3-e8ae-5535-a455-2916bb3022b7 |  | note | • Test results
checkpoint-group |  |  | section | 9 - Primer / Binder Application
checkpoint-status |  |  | checkpoint | HOLD POINT
label | fb1feedf-af77-537f-9b07-4589476cd036 |  | note | ACCEPTANCE CRITERIA:
label | 620403bc-1153-5de0-bdae-2f286d53f85a |  | note | • HOLD POINT: Notify the Principal 2 days prior to spreading aggregate for inspection of the completed sprayed surface
label | e1a66e89-d024-57c4-b8e6-dc7cba280b58 |  | note | • Application rate is to conform to Austroads AGPT04K
label | 4597619d-1bb4-510e-8e49-456bae1b07cf |  | note | • Measure application rates and quantities applied to the mixture at 15°C
label | 63851ac1-76b8-58e8-aa59-41ceb49b4dd8 |  | note | • Primer drying period is at least 72 hours after application
label | 2ee7b979-fbc7-564e-ac76-1042c78b6906 |  | note | • Binder application to conform to Clause 4.5
label | 5cfc43a2-3237-5e47-bd41-33b8c3246c4c |  | note | • Forward speed of bitumen sprayer is to be based on items in Clause 4.5
text | bdd785d1-8b3d-5142-9f52-4e4bc7520e10 |  | textbox | HOLD POINT NUMBER:
text | 45c62609-1c85-597f-91dc-c2457fadfccf |  | textbox | DATE SUBMITTED:
text | 33f8a9d9-beb1-504b-a13f-edd5f9531084 |  | textbox | SUBMITTED BY:
text | 1904c041-d5bc-5fd4-9103-e13d83bce05b |  | textbox | SPECIFICATION AND CLAUSE:
text | 0b1aa326-8fef-5280-afe2-0ef3ffa1f273 |  | textbox | HOLD POINT DESCRIPTION:
text | 7674b2e3-c734-5bca-9e5b-f8c30323cd78 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 10 - Post Application
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 1bf5169b-b602-5f99-9cc5-9c6f2b81ca20 |  | note | REQUIREMENTS / REFERENCE: 1143 Cl 1.6 & Cl 4.10
label | 5b39886a-83d8-5bb9-84fa-f4d520410931 |  | note | ACCEPTANCE CRITERIA:
label | bc9ca0e0-7622-5d0d-bcfc-2a809aa5adde |  | note | • HOLD POINT: Notify the Principal of inspection for completed rolled surface with linemarking, services fixtures and warning signs cleaned and in place prior to opening for traffic (if applicable), otherwise complete inspection of the swept surface
label | cb1600c0-91c6-5aac-84b6-b395743febc6 |  | note | • Surface is to conform to Austroads AGPT04K and is generally of good quality
label | 6ec0b984-329a-5992-91d2-ad939550b9df |  | note | • Appearance is to be uniform, clean and with straight edges
label | 5ea95b05-b8ec-5ea0-b483-0e4760accc70 |  | note | • Loose aggregate is to be removed after sweeping and conform to Clause 4.10
label | f69a1e5b-f816-51b9-a823-84ba14b9374f |  | note | • Provide warning signs for newly completed surfacing
text | 8ac845b7-4df8-5df3-ab36-6c2192b81116 |  | textbox | HOLD POINT NUMBER:
text | 80f4ce69-03b8-5578-bb92-cbace8322720 |  | textbox | DATE SUBMITTED:
text | 05bc2b29-e806-5d56-9849-cae25ac598fd |  | textbox | SUBMITTED BY:
text | 2c01fd35-496d-53da-83da-62257c9377f0 |  | textbox | SPECIFICATION AND CLAUSE:
text | eb90f469-3873-5387-95a4-2ff61133afcf |  | textbox | HOLD POINT DESCRIPTION:
text | d3ea1d9d-7bd5-5566-8693-9cb3fa501b97 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 11 - Non-Conformance
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 2ac15c01-aeee-58e1-b342-bba597ee9d8f |  | note | ACCEPTANCE CRITERIA:
label | 8841c68f-33a0-57f2-b187-e713a1640105 |  | note | • WITNESS POINT: Notify the Principal of inspection for completed remedial treatment of non-conforming sections
label | dfdfe267-bf80-5b48-b92a-3b42cb3b98b5 |  | note | • Area not within 5% of the application rate are non-conforming
text | b1ba80ec-1d0c-51bd-a8f9-0ff363ab6d13 |  | textbox | WITNESS POINT NUMBER:
text | dcbed8dd-53a0-5928-9c9d-7898594ebbe0 |  | textbox | DATE SUBMITTED:
text | cf034eb0-86dd-5ae1-a941-3d9c02566f68 |  | textbox | SUBMITTED BY:
text | f3f90246-8d2f-5804-ba15-f19621e0f067 |  | textbox | SPECIFICATION AND CLAUSE:
text | c765799d-8991-5178-bc09-a9c2b58933b6 |  | textbox | WITNESS POINT DESCRIPTION:
text | e9636f88-e3ad-5b3d-9ac1-dd7ad36695c7 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 12 - Works As Executed (WAE)
checkpoint-status |  |  | checkpoint | VERIFICATION
label | d165e74e-844c-5ea9-94f3-8aa4d7d6cac1 |  | note | ACCEPTANCE CRITERIA:
label | f3dcc51b-5c94-5665-8102-cce6199eb6ef |  | note | • Submit drawings and documents of final completed works. Contractor to provide Schedule 6.2 – Schedule of Job, Details of Works As Executed (WAE)
label | ac785003-18ab-5776-ab1c-a7cd3699200c |  | note | COMMENTS / ATTACHMENTS:
label | 54f67bc6-18b1-5308-8ee5-e2a3783865e9 |  | note | • WAE Drawings
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | 4860a078-8b4d-5afa-80b0-5f8c1dbc132d |  | textbox | Lot Verified By:
text | 4ec2e5ea-9cba-5fc8-9b5f-8a8bd0114815 |  | textbox | Lot Closed Date:
button | b29c46e5-d2b4-5b6b-9cfd-2d3933d05991 |  | button | Submitted to Client | Yes, No, N/A
button | ad095f31-a0b0-5c4e-b04c-6b9bc4090bd3 |  | button | Reviewed by Client | Yes, No, N/A
text | 2a3f71ef-14af-5df5-82c1-99230c24c197 |  | textbox | Submission Comments:
checklist-sectioned |  |  | checklist | A181 - West Dapto - ITC 007 (ITP007) - Utilities (Excl. Water, Streetlights and Traffic Signals) |  |  |  |  | Yes | A181 - West Dapto - ITC 007 (ITP007) - Utilities (Excl. Water, Streetlights and Traffic Signals) | f5c5af08-9b04-4ecd-84ac-4bafc02bccb9
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | e631329d-ba2e-51b9-b5ac-9dd5596009cd |  | textbox | Lot Opened On
text | bad000ce-e3c7-5f86-a158-4d57352180ab |  | textbox | Date of Works
text | 2a509db0-06ba-5083-ac34-c9fbc29d5250 |  | textbox | Lot Type
text | 47f91aa3-0181-57c0-a102-829c86eba887 |  | textbox | Start Chainage
text | 20889a90-1e6f-5ef7-b5c0-0b4b0ee909e5 |  | textbox | End Chainage
text | 8fb59da9-b492-491c-9282-819b7a34f8e1 |  | textbox | Offset
text | b20b7024-3f1d-5a08-bbfc-6837ca502340 |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Preparation Works
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 0f4111e5-1942-5d39-8291-3a30ea67d398 |  | note | REQUIREMENTS / REFERENCE: Project Safety Plan, Project Environment Plan
label | 33d746eb-c410-550b-ada2-8ad24808d4a7 |  | note | ACCEPTANCE CRITERIA:
label | 3a6253ab-a5b6-5f9a-97a0-702555d9e3c5 |  | note | • All site personnel inducted, required SWMS completed and signed, Safety Plan approved
label | 45a27856-2b82-53ad-936c-ff84d1a5e1ee |  | note | • ERSED controls installed on site, air quality visually monitored for dust etc due to construction activities, Environment Plan approved
label | 2f845f7f-ab61-5865-bb40-4c938fd9e4a9 |  | note | • Contact DBYD and complete excavation permit, extent of works set out with survey pegs
checkpoint-group |  |  | section | 2 - Design Documentation
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 07099a5e-36a4-5a27-bbb8-ef82fcf9ca92 |  | note | REQUIREMENTS / REFERENCE: WCC 1391 Cl 2
label | 8d0b20bc-ce42-50aa-84a5-16f383ac0284 |  | note | ACCEPTANCE CRITERIA:
label | 93cfdecf-b8f0-5051-b692-452664313e2c |  | note | • HOLD POINT:
label | 884e6098-1003-5661-a50c-7ce6ebb48793 |  | note | • Prepare documentation based on the concept drawings, including conduit alignment and chainages, obstructions, number and types of conduits, any pits and lid details
label | dec4875a-3440-5e4a-84fa-2bc252f2616f |  | note | • Prepare a design report including choice of cable route, reasoning behind pit locations, site specific environmental requirements, reasoning for any variations to the concept design
text | 155bed7c-09a8-50bb-9e48-b8de19fa3e49 |  | textbox | HOLD POINT NUMBER:
text | f855da77-0862-533f-b66c-379d2fee12f3 |  | textbox | DATE SUBMITTED:
text | e84e023f-df30-53a1-900b-c31773629b80 |  | textbox | SUBMITTED BY:
text | b352af67-1ac6-524f-9b9b-e3c1ce2f7875 |  | textbox | SPECIFICATION AND CLAUSE:
text | 4ada9f39-5728-5d73-85df-52106a00e3b1 |  | textbox | HOLD POINT DESCRIPTION:
text | d5d85cd5-a8b7-5abf-8f48-d96a7e1e0315 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 3 - Authority Approval of Design
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 23afe467-6f28-510e-b7b9-196c5191125d |  | note | REQUIREMENTS / REFERENCE: WCC 1391 Cl 2.2
label | ff2a5e7a-5c31-50b4-9e3c-7144c6021586 |  | note | ACCEPTANCE CRITERIA:
label | 79ddfabb-5801-503f-8e65-1474edb61ed7 |  | note | • HOLD POINT:
label | e451d05c-2674-51a4-9d26-35243278ef75 |  | note | • Provide evidence of the service distributor’s design approval
text | 6435d040-eda2-5f43-bf0f-b575937ae21d |  | textbox | HOLD POINT NUMBER:
text | 640504b5-b701-5471-8632-ae054463d80d |  | textbox | DATE SUBMITTED:
text | 6b6b1956-4f0e-58a3-a185-d427363e3735 |  | textbox | SUBMITTED BY:
text | 6a8778c6-abe8-5956-bde9-0d75877a2e30 |  | textbox | SPECIFICATION AND CLAUSE:
text | 3ab1aaa8-4590-5a04-a067-9e6fca6757da |  | textbox | HOLD POINT DESCRIPTION:
text | 908e17a3-a07e-5aa2-8cd9-dfe1a924dd8b |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 4 - Utility Construction Materials
checkpoint-status |  |  | checkpoint | HOLD POINT
label | dfdef1ef-32d4-5009-906c-d126860b7bfd |  | note | REQUIREMENTS / REFERENCE: WCC 1391 Cl 3
label | 27967738-5b1e-5752-8b72-0d211a89f676 |  | note | ACCEPTANCE CRITERIA:
label | bd7dcc3a-f333-5b66-a26e-3501fdc7867b |  | note | • HOLD POINT:
label | 897f783b-5966-586c-849a-708efe25410c |  | note | • All materials are as per WCC requirements and project drawings, and have been approved for use in the works
text | ef7c7f4a-ac30-5b22-800d-5f4ceb411f67 |  | textbox | HOLD POINT NUMBER:
text | a03e98cd-44ac-5771-8e55-2387714a45c6 |  | textbox | DATE SUBMITTED:
text | 13ba1055-bf29-5a35-bc8d-7ff5ef52e482 |  | textbox | SUBMITTED BY:
text | 9bd5c956-7d2a-538a-9be5-bd4ade625b16 |  | textbox | SPECIFICATION AND CLAUSE:
text | 0a4e6531-2c90-5a2d-b23c-a0a5c3e17817 |  | textbox | HOLD POINT DESCRIPTION:
text | bfb14ae0-8422-5c81-91d5-056109baf502 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 5 - Set Out of Works
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 8cfb097e-4b1b-59fd-bb2f-253f01f346d0 |  | note | REQUIREMENTS / REFERENCE: WCC 1391 Cl 4.1
label | 43b173cb-d603-5801-b9cf-41ef452a2cd2 |  | note | ACCEPTANCE CRITERIA:
label | 47120768-9d5d-54b1-bedc-4a25187505ba |  | note | • HOLD POINT:
label | ca871668-1e0c-5b6c-8ff1-b140c0db58a4 |  | note | • Set out the location, lengths and levels of the cable network and pits, as documented at least 1 day prior to commencing excavation
text | 320cd173-d464-55fa-a899-7fd3b6c87417 |  | textbox | HOLD POINT NUMBER:
text | 48027599-14a9-5f50-96d0-d94c0ef120f5 |  | textbox | DATE SUBMITTED:
text | 948e8b9e-bc29-5541-9a3f-8ba19771c4e0 |  | textbox | SUBMITTED BY:
text | bf4aca93-71cc-5eeb-9ff7-943bbfc20f37 |  | textbox | SPECIFICATION AND CLAUSE:
text | b0381cfc-4585-58bb-88f6-d0706e5e9c8e |  | textbox | HOLD POINT DESCRIPTION:
text | 0e18036a-2a4c-5007-be41-863d2faab46e |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 6 - Installation of Utility Assets
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 96bdffac-33cd-5d6d-a8dc-70ede8258c47 |  | note | REQUIREMENTS / REFERENCE: WCC Cl 4.2, 4.3
label | d2a5f277-46ad-5d92-a9ac-60029ba78bb9 |  | note | ACCEPTANCE CRITERIA:
label | 070f693a-03c2-57dd-8662-3256c0abf47c |  | note | • Lay conduits in straight lines parallel or normal to the carriageway, avoid unnecessary bends. Install and provide required cover as per drawings
label | b8720637-a319-5a13-85b3-bd95a6042d01 |  | note | • Set pits flush with finished level of the surrounding area, shape surrounding area
label | 6f505d3c-4707-5681-b962-f1a1a7ba6347 |  | note | • Provide bedding and connect conduits into pit as per drawings
label | dca67e14-600d-5c7e-8a19-c6878644ffef |  | note | • Locate pits as per design documentation and WCC 1391 Cl 4.3
checkpoint-group |  |  | section | 7 - Backfill Materials and Backfill
checkpoint-status |  |  | checkpoint | VERIFICATION
label | e1b60571-a1ec-5684-bd9d-ebd938d4a66a |  | note | REQUIREMENTS / REFERENCE:
label | 2cf63883-cbf5-524a-9bd5-48e41e0732b4 |  | note | • WCC 0223
label | 35551483-9406-5f13-b3d1-85be56d759fd |  | note | • WCC 1391 Cl 4.4
label | a0a58b97-f148-5eed-88aa-cee15061aff0 |  | note | ACCEPTANCE CRITERIA:
label | bf023670-8009-5a4c-bd46-7aa9ff98a44a |  | note | • Use fill materials suitable for project earthworks
label | 5c8ad795-05bc-50c7-af02-fb566e093313 |  | note | • Do not commence backfill until conduit system as been inspected, record survey data prior to backfill
label | 61c737aa-dd5c-52e0-a448-189c2fada5b1 |  | note | • Compact backfill material as per drawings and conduct density and moisture testing
label | 1cc5a805-9627-554a-949e-2036098dc684 |  | note | • Re-use existing surface materials where possible
label | a1534f59-9534-5241-afe6-1da63238a71b |  | note | COMMENTS / ATTACHMENTS: Compaction Test Report
checkpoint-group |  |  | section | 8 - Testing of Installed Conduits
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 5013864a-6e64-5af7-a70a-0e0172edf3e9 |  | note | REQUIREMENTS / REFERENCE: WCC 1391 Cl 4.5
label | e2632ac5-be11-5790-a3e4-a9fa814a270c |  | note | ACCEPTANCE CRITERIA:
label | 1a4dd3ef-711c-5b0d-969f-0488ef1e3c0c |  | note | • WITNESS POINT:
label | 7e891045-7d9f-5dcd-8375-c2d778807a44 |  | note | • Use a test mandrel through each conduit, test completed conduits for ovality at least 14 days after compaction of completed backfill. Provide results to the Client. Immediate replace any damaged sections of conduit
text | 62554b7f-1a84-54c9-9643-2c308b5722b5 |  | textbox | WITNESS POINT NUMBER:
text | f635313d-6c99-5f78-bc7e-f9dffaceea94 |  | textbox | DATE SUBMITTED:
text | ecadd597-cde3-5810-9ee1-5cef7a5007d1 |  | textbox | SUBMITTED BY:
text | e6894f08-46e8-569f-8e25-82d009542460 |  | textbox | SPECIFICATION AND CLAUSE:
text | ce8a25e7-c9e1-5094-ab29-1369e7f9865f |  | textbox | WITNESS POINT DESCRIPTION:
text | a7544104-7eec-5ac4-9a63-23066af709f7 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 9 - Marking of Kerbs
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | bd8bfeb5-867d-5d20-b714-5fd380e2fb1e |  | note | REQUIREMENTS / REFERENCE: WCC 1391
label | 162f210e-e668-5182-8339-884956dbc6ae |  | note | ACCEPTANCE CRITERIA:
label | b04731ab-5f1d-5dcb-b498-646b6db5062f |  | note | • WITNESS POINT:
label | 989f95bc-6350-59d9-9b82-3e694f16aa8d |  | note | • Mark the face of kerbs, showing the route of conduits (if required)
text | a004371e-8eb4-52a2-b1ca-5d6da3654661 |  | textbox | WITNESS POINT NUMBER:
text | eade7814-7f6b-5384-9082-d1b821c20aaa |  | textbox | DATE SUBMITTED:
text | 7a57f66d-4496-5a8e-95ed-53412d73c7a8 |  | textbox | SUBMITTED BY:
text | 38422bab-71b6-5f92-bd49-3601e11c7bc9 |  | textbox | SPECIFICATION AND CLAUSE:
text | fe84ea30-3c6e-5c4d-99cb-cba64471b3ec |  | textbox | WITNESS POINT DESCRIPTION:
text | 130f6b15-039a-58f6-93c5-e9b82a4a29e2 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 10 - Final Inspection (Completion)
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 4b2fbb26-6484-535e-b87b-8277b9439aa3 |  | note | REQUIREMENTS / REFERENCE: WCC 1391
label | 25cf8b0c-b771-5ca4-8816-56b8651e510a |  | note | ACCEPTANCE CRITERIA:
label | b4b9635d-8c91-54bf-bfad-0a42c069c10b |  | note | • HOLD POINT:
label | 03296fcd-a2fd-5a5e-80e9-8eee9bc543d6 |  | note | • Complete a final inspection with the Client, confirming:
label | b5ab55ba-6c2c-58d4-bbf9-aecf93ce7ec8 |  | note | • Correct number of conduits installed
label | 9b0643f0-e6b8-51e2-89dc-94f51a6ebd1b |  | note | • Draw wire in each conduit
label | d232d413-2246-5d2b-8fed-951ced636347 |  | note | • Pits are free of debris and ingress of water
label | dd695e55-7f00-5ee2-b4ca-e5dc459432da |  | note | • Pit lids fit securely
label | 6d073535-0c58-5cf9-971a-dadbbe5a5afb |  | note | • Labels on pit lids
text | 29aa95b0-d65f-52ee-ac0b-686d5ba9ab41 |  | textbox | HOLD POINT NUMBER:
text | c531b93c-5f56-500b-b234-60f9de594fdb |  | textbox | DATE SUBMITTED:
text | e0921690-d1b3-5f34-8030-23ecb4062998 |  | textbox | SUBMITTED BY:
text | 2b725a7c-48c3-5b06-bc81-e24fec2a5482 |  | textbox | SPECIFICATION AND CLAUSE:
text | 72e8fbda-56b4-55c4-8740-bd472c6fb60f |  | textbox | HOLD POINT DESCRIPTION:
text | b496bb1c-615f-5a0a-8f3d-cd23f4b60d14 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 11 - WAE Drawings
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 60804639-3b74-5809-af2b-f29c1510236c |  | note | REQUIREMENTS / REFERENCE: WCC 1391
label | b769bc0a-f21c-5869-9b62-b0fae53343e4 |  | note | ACCEPTANCE CRITERIA:
label | 3bfbd6ff-0176-5b18-8e11-1dcbf2a7b97d |  | note | • Provide Works As Executed (WAE) Drawings, showing locations of all conduits and pits for each installed utility service
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | d9418ebd-dae3-591e-8b5c-34e050833e21 |  | textbox | Lot Verified By:
text | 53c42a44-8b9f-5d63-a0ca-241207b71f72 |  | textbox | Lot Closed Date:
button | cb0ed557-c2b4-5e20-8802-1ff89c8f0cd5 |  | button | Submitted to Client | Yes, No, N/A
button | 4792c71f-0d80-5d8e-8d31-65162955f744 |  | button | Reviewed by Client | Yes, No, N/A
text | 4f92cfc8-45d8-5773-893f-c63e1c9c3bc1 |  | textbox | Submission Comments: