## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | A181 - West Dapto - ITC 019 (ITP019) - Linemarking | [5 empty] | A181 - West Dapto - ITC 019 (ITP019) - Linemarking
section | Lot Information
checkpoint | Lot Information complete
textbox | Lot Opened On
textbox | Date of Works
textbox | Lot Type
textbox | Start Chainage
textbox | End Chainage
textbox | Offset
textbox | Control Line
section | 1 - Safety Review
checkpoint | VERIFICATION
note | Requirements / Reference - Project Safety Plan
note | Acceptance Criteria - All site personnel inducted (includes environment and cultural). Required Safe Work Method Statements completed and signed. Subcontractor’s safety plan/procedure approved.
section | 2 - Environment
checkpoint | VERIFICATION
note | Requirements / Reference - Project Environment Plan
note | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs. Air quality to be visually monitored for dust etc. as a direct result of construction activities.
section | 3 - Removal of Redundant Markings
checkpoint | HOLD POINT
note | Requirements / Reference - WCC 1192 Cl.1.4
note | Acceptance Criteria - Remove or mask immediately before or after placement of new markings. Make sure the surface is clean, undamaged with surface texture, reflectivity characteristics and colour comparable to the adjacent pavement surface.
note | • For temporary masking use black non-reflective masking tapes with skid resistance properties. Methods of application: Submit method of application of materials and methods to protect the work from premature trafficking.
note | • Removal of redundant markings: Submit details of method for removing redundant pavement markings, at least 24 hours before the removal of markings. (HP)
textbox | HOLD POINT NUMBER:
textbox | DATE SUBMITTED:
textbox | SUBMITTED BY:
textbox | SPECIFICATION AND CLAUSE:
textbox | HOLD POINT DESCRIPTION:
textbox | BRIEF NOTES:
signoff | HOLD POINT SIGN OFF
section | 4 - Permanent Pavement Marking Tape Samples
checkpoint | HOLD POINT
note | Requirements / Reference - WCC 1191 Cl.1.6
note | Acceptance Criteria - If marking tape is required, submit samples and product details at least 5 days prior to material ordering and delivery. (HP)
textbox | HOLD POINT NUMBER:
textbox | DATE SUBMITTED:
textbox | SUBMITTED BY:
textbox | SPECIFICATION AND CLAUSE:
textbox | HOLD POINT DESCRIPTION:
textbox | BRIEF NOTES:
signoff | HOLD POINT SIGN OFF
section | 5 - Type Tests and Material Properties
checkpoint | HOLD POINT
note | Requirements / Reference - WCC 1191 Cl.1.6
note | Acceptance Criteria - Road pavement marking: For longitudinal lines, conform to the following:
note | o White and/or yellow road marking paint
note | o White and/or yellow thermoplastic or cold applied plastic material
note | o For waterborne paint: To AS 4049.3
note | o Solvent-borne paint: Do not use without prior approval, conform to AS 4049.1.
note | • Anti-skid pavement markings: Angular, polishing resistant particles which provide skid resistance. Apply anti-skid media, if the skid resistance on the existing is less than 45 BPN or equivalent.
note | o Colour: compatible with marking colour
note | o Transverse lines and other markings: 0.4 to 0.7 mm
note | o For longitudinal linemarking: 0 to 2.0mm
note | o Anti-skid material application rate: Minimum 0.20 k/m2.
note | • Thermoplastic material: To AS 4049.2
note | • For Non-profile thermoplastic pavement marking material:
note | o Longitudinal line markings: Sprayed or extruded thermoplastics applied uniformly.
note | o Transverse lines and other markings: If required, screed thermoplastic material using a mobile applicator and templates to control the pattern – Thickness: 3mm ± 1mm.
note | • Two-part cold applied plastic pavement marking material: Measured at 23°C and to AS 1580.401.8
note | o For trowel or screed applied material (containing intermix glass beads): Maximum 20 minutes for 2.0 ± 0.25 mm applied film thickness.
note | o For spray material (not containing glass beads): Maximum 5 minutes for 0.200 ± 0.025 mm applied film thickness.
note | o Longitudinal line marking: Sprayed material
note | o Application rates for two-part cold applied pavement materials and glass beads table:
note | – – – – – – – – – – – – – – – – – – – – – – – – – – –
note | Material ¦¦ Longitudinal linemarking: Sprayed application ¦¦ Transverse lines and other markings: Trowelled, screeded or extruded ¦¦ Transverse lines and other markings: Sprayed
note | – – – – – – – – – – – – – – – – – – – – – – – – – – –
note | Cold applied material thickness (excluding surface applied beads) ¦¦ 0.5 ± 0.05 mm (wet) ¦¦ 2.0 ± 0.2 mm (dry) ¦¦ 1.00 ± 0.1 mm (wet)
note | Completed marking thickness ¦¦ – ¦¦ – ¦¦ 2.0 ± 0.2 mm
note | Surface applied glass beads*:
note | – Type (AS/NZS 2009) ¦¦ Type D-HR (adhesive coated) ¦¦ Type B ¦¦ Type B
note | – Rate retained in the painted surface ¦¦ ≥ 400 g/m2 ¦¦ ≥ 300 g/m2 ¦¦ ≥ 300 g/m2
note | Anti-skid material ¦¦ ≥ 200 g/m2 ¦¦ ≥ 200 g/m2 ¦¦ ≥ 200 g/m2
note | – – – – – – – – – – – – – – – – – – – – – – – – – – –
note | * Glass beads coated with a compatible coupling agent for an improved adhesive bond with thermoplastic or two-part cold applied road marking material.
note | – – – – – – – – – – – – – – – – – – – – – – – – – – –
note | • Reflective glass beads: To AS/NZS 2009
note | o Bead type: B-HR, C-HR or D-HR
note | o Incorporate glass beads in thermoplastic material in the proportion of a minimum 20% of total mass
note | o Type B glass beads rate: Minimum 0.30 kg/m2
note | o Type D-HR glass beads: Minimum 0.50kg/m2
note | Raised Pavement Markers: Reflective and non-reflective markers to AS/NZS 1906.3
note | o Hot melt bitumen adhesive to wearing surface
note | o Sampling: To AS/NZS 1960.3
note | o Application: To the manufacturer’s recommendations.
note | o Removal: If required, remove to the manufacturer’s recommendations.
note | • Material properties: Submit test reports from a registered laboratory verifying material property conformance, including for paint, glass beads, raised pavement markers and thermoplastic material. (HP)
note | • Test currency: Not older than 3 years.
note | • Quality verification: If material/product quality verification can be obtained from the supplier, documented tests need not be repeated.
textbox | HOLD POINT NUMBER:
textbox | DATE SUBMITTED:
textbox | SUBMITTED BY:
textbox | SPECIFICATION AND CLAUSE:
textbox | HOLD POINT DESCRIPTION:
textbox | BRIEF NOTES:
signoff | HOLD POINT SIGN OFF
section | 6 - Setting Out
checkpoint | HOLD POINT
note | Requirements / Reference - WCC 1192 3.2
note | Acceptance Criteria - Setting out: Completion of pavement marking set-out, at least 5 days prior to marking application. (HP)
textbox | HOLD POINT NUMBER:
textbox | DATE SUBMITTED:
textbox | SUBMITTED BY:
textbox | SPECIFICATION AND CLAUSE:
textbox | HOLD POINT DESCRIPTION:
textbox | BRIEF NOTES:
signoff | HOLD POINT SIGN OFF
section | 7 - Surface Preparation
checkpoint | HOLD POINT
note | Requirements / Reference - WCC 1192 3.2
note | Acceptance Criteria - Surface preparation: Completes surface preparation, before applying pavement markings, at least 1 day prior to marking application. (HP)
textbox | HOLD POINT NUMBER:
textbox | DATE SUBMITTED:
textbox | SUBMITTED BY:
textbox | SPECIFICATION AND CLAUSE:
textbox | HOLD POINT DESCRIPTION:
textbox | BRIEF NOTES:
signoff | HOLD POINT SIGN OFF
section | 8 - Completion Inspection
checkpoint | HOLD POINT
note | Requirements / Reference - WCC 1192 3.2
note | Acceptance Criteria - Completion: Completed pavement marking, at least 1 day before inspection. (HP)
textbox | HOLD POINT NUMBER:
textbox | DATE SUBMITTED:
textbox | SUBMITTED BY:
textbox | SPECIFICATION AND CLAUSE:
textbox | HOLD POINT DESCRIPTION:
textbox | BRIEF NOTES:
signoff | HOLD POINT SIGN OFF
section | Identified Records
checkpoint | Please upload any Identified Records here
section | Lot Verification
checkpoint | Lot Verification complete
textbox | Lot Verified By:
textbox | Lot Closed Date:
button | Submitted to Client | Yes, No, N/A
textbox | Reviewed by Client | Yes, No, N/A
textbox | Submission Comments: