## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | a20e68e3-7eb9-4a4b-9030-61b18ae528c5 |  | checklist | Cesspit |  |  |  |  | Yes | Cesspit Checklist | 310a61b8-17ce-43da-869c-b085cd7649cd
checkpoint-status | 494bdc57-4e33-46e9-a62c-0e87c23ca4e0 |  | checkpoint | Is the sump set on correct LL
checkpoint-status | 526d8dde-c8a8-46d2-90f6-d412dd03cab6 |  | checkpoint | Installation Process
checkpoint-status | a7212117-10b5-4a9b-a978-6d427e879dfc |  | checkpoint | Council Inspection and As-Built
checklist-flat |  |  | checklist | Label # |  |  |  |  | Yes | Fire Penetration | ce1f7e62-a3d5-4b40-a5a5-fef7a2e2bea2
checkpoint-no-status |  |  | checkpoint | Has smoke seal been used?
radio | 78e9fd5a-7e08-4dac-a15b-915b3a117651 |  | radio |  | No,Yes
checkpoint-no-status |  |  | checkpoint | What system has been used?
boolean | 3c7ff7de-4a92-4858-9e83-e004aa1b5423 |  | tickbox | Collar
boolean | 1e6aa794-5429-4266-9bac-7bcf08cd789d |  | tickbox | Wrap
boolean | 1db1676d-8099-4c10-8211-b286724084dc |  | tickbox | Other
text | 040c0e22-f74a-41de-8770-cbf20b423db6 |  | textbox | Please Specify:
checklist-flat |  |  | checklist | First Fix |  |  |  |  | Yes | Add FF | 316290d5-750a-4ddd-9ef8-49ad46e4c823
checkpoint-status |  |  | checkpoint | Is the fixture in the right position?
checkpoint-status |  |  | checkpoint | Are pipes coming out the straight?
checkpoint-status |  |  | checkpoint | Are fixings nogs correct?
checkpoint-status |  |  | checkpoint | Has the pipework been tested?
checklist-flat |  |  | checklist | Miscellaneous Test Sheet |  |  |  |  | Yes | Miscellaneous Test Sheet | 4e503bc5-80db-4b48-8543-c02c7a23f144
checkpoint-status |  |  | checkpoint | Miscellaneous test sheet
checklist-flat |  |  | checklist | FWG Second Fix |  |  |  |  | Yes | FWG Second Fix Checklist | bb12b91f-97fb-4ede-9266-24e1af7e14fa
checkpoint-status |  |  | checkpoint | Has the fixture been fitted correctly
checkpoint-status |  |  | checkpoint | Has the fixture been tested (add photos)
checkpoint-status |  |  | checkpoint | Is the silicone neat and tidy
checkpoint-status |  |  | checkpoint | Is the fixture free from damage
checkpoint-status |  |  | checkpoint | Have the lines been flushed
checkpoint-status |  |  | checkpoint | Is the fixture free from leaks
checklist-flat |  |  | checklist | Label # |  |  |  |  | Yes | 25) Add Fire Penetration | b030226f-9d2e-4ffe-bdab-04733558e8f9
checkpoint-no-status |  |  | checkpoint | Has smoke seal been used?
radio | 78e9fd5a-7e08-4dac-a15b-915b3a117651 |  | radio |  | No,Yes
checkpoint-no-status |  |  | checkpoint | What system has been used?
boolean | 3c7ff7de-4a92-4858-9e83-e004aa1b5423 |  | tickbox | Collar
boolean | 1e6aa794-5429-4266-9bac-7bcf08cd789d |  | tickbox | Wrap
boolean | 1db1676d-8099-4c10-8211-b286724084dc |  | tickbox | Other
text | 040c0e22-f74a-41de-8770-cbf20b423db6 |  | textbox | Please Specify:
checklist-flat |  |  | checklist | Flood Test Sheet |  |  |  |  | Yes | Flood Test Sheet | d9b1cd75-42c1-4555-a3ff-8a2809f19afe
checkpoint-status |  |  | checkpoint | Flood Test Date
checkpoint-status |  |  | checkpoint | Flood Test Duration
checkpoint-status |  |  | checkpoint | No sign of water on any joints
checkpoint-status |  |  | checkpoint | No water drop during test
checklist-flat |  |  | checklist | Fit Off |  |  |  |  | Yes | Add Fit Off | a3555a91-9ca1-4dd2-a8c1-8f3a9f2f2751
checkpoint-status |  |  | checkpoint | Are all cover flanges installed?
checkpoint-status |  |  | checkpoint | Is fixture stable and installed correctly?
checkpoint-status |  |  | checkpoint | Is the fixture free from damage?
checkpoint-status |  |  | checkpoint | Has the fixture been tested?
checklist-flat |  |  | checklist | Aquatherm Pressure Test Sheet |  |  |  |  | Yes | Aquatherm Pressure Test Sheet | 517470d5-a8ed-4240-8b60-f41bf08a2c50
checkpoint-status |  |  | checkpoint | Installation Details
button | 93fc2cce-4a6e-4a48-a85b-8e9dac04a136 |  | button | Type of Installation | Commercial,Domestic
select | 0891b48d-28be-4564-8cd2-765c1aac9253 |  | dropdown | Type of Pipe: | Aquatherm blue pipe,Aquatherm green pipe,Aquatherm grey pipe,Aquatherm lilac pipe,Aquatherm orange system,Aquatherm red pipe
text | 44d0058f-38ed-4e3c-905f-383f77f9f640 |  | textbox | Time Testing Started:
text | 25abef4f-adca-4bf1-9248-cc84663ac6f8 |  | textbox | Time Testing Finished:
text | dc5a2b5a-de0a-4f63-bc72-a889bd0a74df |  | textbox | Test Period (minutes):
text | e6ef9777-906e-424b-8329-626a7151f33d |  | textbox | Installers #:
checkpoint-status |  |  | checkpoint | Declaration: I declare that I have installed the above product in accordance with aquatherm specifications with no branding mix
text | e0cd90ab-c1df-4201-8246-569943f8645a |  | textbox | Name:
checklist-flat | ff457fef-aa5c-4574-85fa-4632397ce4c4 |  | checklist | ORG Checklist |  |  |  |  | Yes | ORG Checklist | b35ca15f-98eb-4f01-934f-789d96a92676
checkpoint-status | cdd72e15-bedb-4394-a879-c562d61085f8 |  | checkpoint | Installed in correct location
checkpoint-status | 148fe040-a82f-4e8d-a3cb-11e36c9a88d8 |  | checkpoint | Riser level
checkpoint-status | 9dd90fbe-1286-4532-9184-00ca982b6e03 |  | checkpoint | Is the ORG fixture connection done
checkpoint-status | 1fda1adc-4e43-4e6e-a6e4-bf0906f0ccad |  | checkpoint | Concrete placed under the gully base
checkpoint-status | c669cd36-bab5-4709-bfff-e2e146bd306e |  | checkpoint | Gully dish installed
checklist-flat |  | checklist-flat is not dependant but can't have own status | checklist | Pipework Test sheet |  |  |  |  | Yes | 10) Add Pipework Testsheet | 3d4a1589-7f25-45bf-ad5c-210bd51b0eb1
checkpoint-no-status |  |  | checkpoint | Flush – All pipework installs to be flushed for minimum of 2 minutes on full with maximum pressure available.
text | 0d3459c4-33fc-42a1-b3aa-77e602df24c9 | Hidden property width:100 | textbox | Duration
text | a533b7cb-15d7-4f7e-bed9-fb71fe8f2e28 | Hidden property width:100 | textbox | Free Flowing
checkpoint-no-status |  |  | checkpoint | Drop Test – Pipework to be subjected to a drop test. No less than 3 drops. Test is used to confirm pipework will withstand environmental extremes.
text | 7962a8d8-ce7f-49f1-b244-44262c4aeb6f |  | textbox | 1 st test pressure:
text | 3c6ad13d-e627-4d87-b26c-1f17d5446e9f |  | textbox | Duration:
text | 29aea5fd-4a2c-4e66-8cae-6f8471f66f5a |  | textbox | Rest time:
text | 823ecc56-7bec-4073-ad01-0a0cd9fe3cdf |  | textbox | 2 nd test pressure:
text | 59e6bf31-b8ba-4c06-ba29-f8a179d468d6 |  | textbox | Duration:
text | d958669a-35ab-46e5-a4c5-89599aaabf39 |  | textbox | Rest time:
text | 9245f833-4587-42f3-b43d-996e3928d4bb |  | textbox | 3 rd test pressure:
text | 5df57267-c866-436a-a2f5-36be1aca2914 |  | textbox | Rest time:
text | d51066fe-8ef7-4c22-a2b6-fd9155d2e425 |  | textbox | Duration:
checkpoint-no-status |  |  | checkpoint | Hydro static test – Pipework to be subjected to a hydrostatic test for no less than 30mins. Record pressure drop if any. Acceptable drops are allowed if within manufacturers allowances.
text | 9829c9e0-a1ca-40d4-8aec-e68cfa3b6dde |  | textbox | Test pressure:
text | 82429beb-bc98-419c-bf72-1ce769acdd0f |  | textbox | Duration:
text | d6762c94-3820-4f02-8efe-50e8a3b3a320 |  | textbox | Drop:
checklist-sectioned |  |  | checklist | QA Checklist |  |  |  |  | Yes | QA Checklist | fd5618f3-fe45-4e44-83d9-b1c2433dde34
checkpoint-group |  |  | section | Roof outlet questions
checkpoint-status |  |  | checkpoint | Is overflow on correct pipe
checkpoint-status |  |  | checkpoint | Are clamp rings secure
checkpoint-status |  |  | checkpoint | Is gutter free of debris
checkpoint-status |  |  | checkpoint | Has pipework been tested ( Insert photo - mandatory for all testing)
checkpoint-status |  |  | checkpoint | Is pipework secure to outlet
checkpoint-status |  |  | checkpoint | Has acoustic lagging been completed
checkpoint-status |  |  | checkpoint | Are the pipes labelled correctly
checkpoint-group |  |  | section | Vent Questions
checkpoint-status |  |  | checkpoint | container
checkpoint-group |  |  | section | General QA
checkpoint-status |  |  | checkpoint | Pressure Test Sheets
checkpoint-status |  |  | checkpoint | Downpipes
checkpoint-status |  |  | checkpoint | Service duds
checkpoint-group |  |  | section | Drainage
checkpoint-status |  |  | checkpoint | Are all pipe falling
checkpoint-status |  |  | checkpoint | All joints secure and tested
checkpoint-status |  |  | checkpoint | Are all upstands labelled
checkpoint-status |  |  | checkpoint | Is backfill complete
checkpoint-status |  |  | checkpoint | Are all pioe protections in place
checkpoint-status |  |  | checkpoint | All upstand locations secure
checkpoint-status |  |  | checkpoint | Has works been signed off by council
checklist-flat | 83ca7832-c4e9-4194-a21f-eea924fca6e2 |  | checklist | Photos |  |  |  |  | Yes | Photos | 6499bdc7-c556-4d09-aa3f-6c7fa4810834
checkpoint-status | 11881716-d32d-4e98-b218-5de09fe5cbab |  | checkpoint | Attach Photos
checklist-flat |  |  | checklist | Express Plumbing Quality Assurance checks and Commissioning |  |  |  |  | Yes | Express Plumbing Quality Assurance checks and Commissioning | 23e1da25-ee3e-480b-94cd-3a143799e533
checkpoint-no-status |  |  | checkpoint | Express Plumbing Quality Assurance checks and Commissioning
label | 8cd63223-b1f3-4f34-9910-335b9309577d |  | note | Express Plumbing uses a online live document system of recording different stages of the construction process through out the build program. With the aid of mobile devices and computers we record with photographic evidence the construction build process, what things look like behind walls and below ground. We follow up these photos with the end product finish and have checkpoints for each fixture to have passed off at each stage so you can be assured of the quality Express Plumbing has archived during your project.
label | 82789061-d20c-448c-bc72-280d357bafaa |  | note | The system provides a accurate recording of what has happened on site and also provides a means of recording and resolving any defects. During checkpoint sign offs for each fixture a series of questions are asked in relation to the fixture, ie “are the pipes coming out of the wall straight?” or “Has the council inspection been passed?”. If the Express Plumbing site supervisor finds a defect he is able to send a job request immediately to any of his site staff and the repairing staff member is able to take a photo of his repair for the supervisor to approve.
label | 8ecd6366-fa14-4fd0-bd07-51f74df937c9 |  | note | All dates and time of data entered or altered are recorded next to each question. Our commissioning processes also forms part of this live document with specific fixture questions and photos during the commissioning being recorded i.e. temperature gauge photo of a running hot tap on a basin etc. We are also able to provide our Fire Register through the same system and record locations with the labels and assign a photo of each penetration to that location. We also break down the locations into areas and floors.
label | de6f5e10-f8f4-436f-a7e4-27ed61710029 |  | note | As built are also recorded during the project and are loaded into the system before the hole or ceiling is covered in. These can be on request turned into any format you may wish to have these sent to you (there may be additional costs).
label | f17d3ffd-0b01-489a-92fb-6de7fea2e7ec |  | note | Express Plumbing supervisor’s are authorised and given access to the specific job they may be running. Access is only given through Web page authorisation from the Express Project Management team. On site teams under the supervisor do not have full access to the system and can only log repairs to defects with in the system. All on site data entry, passing off of fixture, logging of finished works, fire register recording and As built entry may only be preformed by the authorised Express Plumbing Site Supervisor.
checkpoint-no-status |  |  | checkpoint | QA Hierarchy Flow Chart
text | f3083c51-d697-4f21-a7e7-216ef499e346 |  | textbox | Project Manager:
text | a10cba99-d8df-472c-9941-6d0e90e16089 |  | textbox | Site Supervisor:
text | f61c7730-cb04-4122-91d4-98b506629bfa |  | textbox | Site Defect Repairer:
checklist-flat |  |  | checklist | FWG First Fix |  |  |  |  | Yes | FWG First Fix Checklist | b71932ec-4412-4ee5-9430-72d1879a2dbc
checkpoint-status |  |  | checkpoint | Correct Position
checkpoint-status |  |  | checkpoint | Flange Level
checkpoint-status |  |  | checkpoint | Construction Cap On
checkpoint-status |  |  | checkpoint | Tested
checklist-flat |  |  | checklist | Pipework Test sheet |  |  |  |  | Yes | Add Potable Water Pressure Test Sheet | fca156b4-0629-4cc9-8b00-4e397901f452
checkpoint-status |  |  | checkpoint | Photos attached - Pressure gauge and/or flood test
checkpoint-no-status |  |  | checkpoint | Flush – All pipework installs to be flushed for minimum of 2 minutes on full with maximum pressure available.
text | 0d3459c4-33fc-42a1-b3aa-77e602df24c9 | Hidden property width:100 | textbox | Duration
text | a533b7cb-15d7-4f7e-bed9-fb71fe8f2e28 | Hidden property width:100 | textbox | Free Flowing
text | 7962a8d8-ce7f-49f1-b244-44262c4aeb6f |  | textbox | 1 st test pressure:
text | 3c6ad13d-e627-4d87-b26c-1f17d5446e9f |  | textbox | Duration:
text | 29aea5fd-4a2c-4e66-8cae-6f8471f66f5a |  | textbox | Rest time:
text | 823ecc56-7bec-4073-ad01-0a0cd9fe3cdf |  | textbox | 2 nd test pressure:
text | 59e6bf31-b8ba-4c06-ba29-f8a179d468d6 |  | textbox | Duration:
text | d958669a-35ab-46e5-a4c5-89599aaabf39 |  | textbox | Rest time:
text | 9245f833-4587-42f3-b43d-996e3928d4bb |  | textbox | 3 rd test pressure:
text | 5df57267-c866-436a-a2f5-36be1aca2914 |  | textbox | Rest time:
text | d51066fe-8ef7-4c22-a2b6-fd9155d2e425 |  | textbox | Duration:
checkpoint-no-status |  |  | checkpoint | Drop Test – Pipework to be subjected to a drop test. No less than 3 drops. Test is used to confirm pipework will withstand environmental extremes.
text | 7962a8d8-ce7f-49f1-b244-44262c4aeb6f |  | textbox | 1 st test pressure:
text | 3c6ad13d-e627-4d87-b26c-1f17d5446e9f |  | textbox | Duration:
text | 29aea5fd-4a2c-4e66-8cae-6f8471f66f5a |  | textbox | Rest time:
text | 823ecc56-7bec-4073-ad01-0a0cd9fe3cdf |  | textbox | 2 nd test pressure:
text | 59e6bf31-b8ba-4c06-ba29-f8a179d468d6 |  | textbox | Duration:
text | d958669a-35ab-46e5-a4c5-89599aaabf39 |  | textbox | Rest time:
text | 9245f833-4587-42f3-b43d-996e3928d4bb |  | textbox | 3 rd test pressure:
text | 5df57267-c866-436a-a2f5-36be1aca2914 |  | textbox | Rest time:
text | d51066fe-8ef7-4c22-a2b6-fd9155d2e425 |  | textbox | Duration:
text | 9829c9e0-a1ca-40d4-8aec-e68cfa3b6dde |  | textbox | Test pressure:
text | 82429beb-bc98-419c-bf72-1ce769acdd0f |  | textbox | Duration:
text | d6762c94-3820-4f02-8efe-50e8a3b3a320 |  | textbox | Drop:
checkpoint-no-status |  |  | checkpoint | Hydro static test – Pipework to be subjected to a hydrostatic test for no less than 30mins. Record pressure drop if any. Acceptable drops are allowed if within manufacturers allowances.
text | 9829c9e0-a1ca-40d4-8aec-e68cfa3b6dde |  | textbox | Test pressure:
text | 82429beb-bc98-419c-bf72-1ce769acdd0f |  | textbox | Duration:
text | d6762c94-3820-4f02-8efe-50e8a3b3a320 |  | textbox | Drop:
checklist-sectioned |  |  | checklist | Hose Taps Checklist |  |  |  |  | Yes | Hose taps | 58787704-2cfd-41c6-aca7-f277e74cbe21
checkpoint-group |  |  | section | Checks
checkpoint-status |  |  | checkpoint | Position Correct
checkpoint-status |  |  | checkpoint | Pipes coming out of wall straight
checkpoint-status |  |  | checkpoint | Fixings nogs in place
checkpoint-status |  |  | checkpoint | Prevention against waterhammer
checkpoint-status |  |  | checkpoint | All joints watertight and tested
checkpoint-status |  |  | checkpoint | Has fire rating been completed?
checklist-flat |  |  | checklist | Meter Commissioning Report |  |  |  |  | Yes | Meter Commissioning Report | 4820f8d3-a314-4e59-af88-69ba99f03103
checkpoint-status |  |  | checkpoint | Is water meter installed according to IFC and is water live?
text | cac4f757-710a-4f17-9f4f-e12fe4ff9121 |  | textbox | Water meter reading at handover:
text | d803dc8a-ecb6-42ce-8759-9378589b3cd1 |  | textbox | Water meter size:
text | b8c03996-55b7-41c8-84d5-60a560ab574e |  | textbox | Water meter asset number:
text | 1c20080e-fca3-41b2-84a0-341f39794071 |  | textbox | Water meter serial number:
checkpoint-status |  |  | checkpoint | Is gas meter installed according to IFC and is water live?
text | c2fa59eb-8248-4731-b179-7bda6945f375 |  | textbox | Gas meter reading at handover:
text | 62725d7b-5058-4062-bab3-2e83930b6601 |  | textbox | Gas meter size:
text | 553dc1e7-50bc-4834-86f7-69aecf8e12dd |  | textbox | Gas meter asset number:
text | ecb1be83-ab77-4686-9441-a0b928525daf |  | textbox | Gas meter serial number: