## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP 001 Speed Panel |  |  |  |  | Yes | ITP 001 Speed Panel | 12a4aa56-48bd-44cc-a8e9-ee4ae78a9e65
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | 505a259a-6347-5f1f-b5ee-07302c5e5334 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 652690e7-047f-569e-bdc5-6cb8c6ddef80 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4
label | bf5fcfc0-a343-504f-8b3d-d247ea907360 |  | note | Buildup Inspection Code: W
label | 6b9cfe0d-6d6d-5b7a-a1a0-b9dce3ec653c |  | note | Lendlease Inspection Code:
label | c545497c-1ea4-5109-8dc3-e49c745ee125 |  | note | Lendlease Sign/Date:
label | e04a21b3-6ef7-51bc-8f40-c8426ab6fd90 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Wall dimension checked against drawings & setout; Wall types confirmed against partition plans
label | 6915ecaf-9821-50f7-8817-b81d5db3e12a |  | note | Acceptance Criteria: Latest drawing revision checked
label | 28b7ece8-d006-5304-b4aa-417b550cacc0 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Series BR3ADB2 -; Wall Setout Plans BR3ADF3 - Fire Stairs
label | 98095145-bc7d-582a-b6da-0b7379638ee2 |  | note | Buildup Inspection Code: W
label | e3329207-67b2-5639-ab0f-0b43b9126d31 |  | note | Lendlease Inspection Code:
label | 69563dbc-6d80-54f4-a5aa-65a4e06ca1f2 |  | note | Lendlease Sign/Date:
label | 6c073063-43e6-5898-a4aa-776ae4e78b13 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | C-Track installed as manufacturer's specification to top, bottom and both sides
label | c9918bb9-c83d-5b5b-999a-8d3ebbee9932 |  | note | Acceptance Criteria: Hilti 606 Sealant applied between C-track and concrete and along internal corner. Anchor @500 Centre & max 100 from end
label | 6b4e0a6a-a192-5069-986e-b0c693a98371 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 58d24deb-3ca1-5436-9497-d7aa3cd716d4 |  | note | Buildup Inspection Code: W
label | af4ef637-35ae-5bb4-8c25-1e733e543c05 |  | note | Lendlease Inspection Code:
label | 0ed6a0f3-0648-572f-aec9-78200633ff9f |  | note | Lendlease Sign/Date:
label | 6641c5b0-3778-5cef-bc8c-42fe6912d37d |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Panels installed as manufacturer's specifications
label | 79341bd0-6231-5bf9-9cc3-34f838d21a06 |  | note | Acceptance Criteria: Each panel interlocked, fixing @ max vertically 1000mm centre on joints and 250 mm horizontally, fixing @ max 500mm on C-track, 2 fixings at 45" for every corner. Sealant full placed around C-track
label | 54dacd97-0a98-5737-a513-f7f1c416b38a |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | e6662f25-f897-5cbc-8237-496fc347e15b |  | note | Buildup Inspection Code: W
label | b1f0b3b0-b860-50c9-8dbd-b836acdf0cc2 |  | note | Lendlease Inspection Code:
label | efc4e73a-afd0-5fb6-9db5-300f90212834 |  | note | Lendlease Sign/Date:
label | 73567203-4a30-5616-9b96-80d32d2a4b4e |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Comprehensive first of type inspection
label | 368b55b9-5e5d-5346-b7b7-c2bd63d9edd2 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4; Supplier / Manufacturer inspection report
label | 910717be-1ce0-5b22-8f47-2071f993c472 |  | note | Buildup Inspection Code: W
label | fd79ed1d-cf37-5729-8909-eb1b3c93482b |  | note | Lendlease Inspection Code:
label | c8e06bb9-e25e-5489-820f-06b5956acb06 |  | note | Lendlease Sign/Date:
label | 832ebd10-67cb-546c-a259-c96fb6019d75 |  | note | Lendlease Comment/Result:
checklist-flat |  |  | checklist | ITP 007 Skirting Installation |  |  |  |  | Yes | ITP 007 Skirting Installation | 3837e4f0-57b7-4633-9f63-a5a771ded175
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | b67ac715-fba2-56e0-8815-f90b517b096b |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | fcfc448e-4707-58af-b74f-f9f434fdb2b2 |  | note | Buildup Inspection Code: W
label | f5c6601d-0362-58c5-98ed-bbe7664176ea |  | note | Lendlease Inspection Code:
label | c9156eb0-3ce1-5d7f-9126-afc85ec5ccce |  | note | Lendlease Sign/Date:
label | dfb12641-6683-55b3-8ec5-f4ec8396d99a |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Set out Timber skirting size & type as per wall finish set out plan
label | f171b065-aa5a-5a84-b365-3b47b7b017cc |  | note | Acceptance Criteria: Latest Drawing Revision Checked
label | e0ef24b0-2eee-5b7a-a478-d00944cb05bc |  | note | References: Series: BR3ADL2-Internal Architectural Details; BR3ADB2-Wall Setout Plans
label | c7f8cc83-0e56-5be2-b14e-7dcd219526c4 |  | note | Buildup Inspection Code: W
label | a73ff754-d9e8-5ad1-8172-3e5bc138c7cc |  | note | Lendlease Inspection Code:
label | 29a0c4d8-308f-5f53-9db3-ffb5291d81ed |  | note | Lendlease Sign/Date:
label | 3bfba11a-188b-5e1c-9a67-270e54cdf0c9 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Timber skirting installed as manufacturer's specification to Top, bottom side
label | 7d98cfb5-5925-5081-83a7-8c4fed8ff5ea |  | note | Acceptance Criteria: Straight and plumb and square, no sharp edge, gap less than 3mm, sealed with silicone Ref
label | 940b23db-1e6c-5701-a611-bbdbd7b3142d |  | note | Buildup Inspection Code: W
label | 395ee49c-63f3-5c6b-9e17-2890bd829693 |  | note | Lendlease Inspection Code:
label | 0d1e9790-eeed-55c8-b743-7a5476302274 |  | note | Lendlease Sign/Date:
label | 80d63cbe-47c9-55b9-bb04-c3b198841ef0 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | No unreasonable gap or holes on the wall
label | c9eceaa5-e804-594c-8016-8a95242b1d10 |  | note | Acceptance Criteria: Eye Inspection
label | a3bf9dbd-6045-56b8-805d-15817b9f9b42 |  | note | Buildup Inspection Code: W
label | 527ed8ca-5d90-5916-aa56-89bc214e62fd |  | note | Lendlease Inspection Code:
label | f48fc8fc-14dc-5088-b737-458d066ae7dd |  | note | Lendlease Sign/Date:
label | 19359160-01cc-50ed-8608-861777540916 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Timber skirting fixing and inspect for damage prior to hand over
label | b922cce4-5819-5f31-a3d6-1360804bf565 |  | note | Acceptance Criteria: Inspected and approved
label | 572a21e1-74ff-564b-96a1-784392b9cd42 |  | note | Buildup Inspection Code: W
label | ecff069b-7218-55de-839e-8ec08f35babf |  | note | Lendlease Inspection Code:
label | 6620a4ef-1a10-5d01-864e-233e1f6bf166 |  | note | Lendlease Sign/Date:
label | 0d687e5b-8002-556c-83bd-3539fa269f23 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | 1af3e526-11f7-5f5f-afc1-432be79ae0cf |  | note | Buildup Inspection Code: W
label | 492c8b1a-14a5-56e1-b5d0-28f41af56ed5 |  | note | Lendlease Inspection Code:
label | 2614aa7e-6c05-574f-80bc-00e515313039 |  | note | Lendlease Sign/Date:
label | e4ae052f-e590-5463-b3f2-86a072f344ea |  | note | Lendlease Comment/Result:
checklist-sectioned |  |  | checklist | ITP 006 FF&E Installation |  |  |  |  | Yes | ITP 006 FF&E Installation | 591cf335-dadb-4b1f-bfe3-d66e9bcf6501
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | 3c759d05-24f5-5986-935d-9adcd8acafcf |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 613e23ed-8f56-520d-bd4d-45cd3a3e05ad |  | note | Buildup Inspection Code: W
label | 01897124-a714-530c-befd-92e75f108d72 |  | note | Lendlease Inspection Code:
label | 0612948d-d52b-50e5-8741-3c17dc2eaa0c |  | note | Lendlease Sign/Date:
label | 07b5eb37-d623-55d0-ab78-ba04e9fea6cf |  | note | Lendlease Comment/Result:
checkpoint-group |  |  | section | FFE Installation
checkpoint-status |  |  | checkpoint | All of FFE Products must approved by Lendlease
label | 420bf66d-b5d6-54da-8d1a-0670b4b9ede7 |  | note | Acceptance Criteria: Sample Form Approval Finish Schedule
label | ae8586ea-ae77-56e3-9854-6c59592c0c89 |  | note | References: Series: BR3ADL2-Internal Architectural Details
label | fbc24199-3b5d-50e9-b1ca-32e85b322422 |  | note | Buildup Inspection Code: W
label | c7b0fd51-d6d2-5100-9145-fb2e26c0a6b4 |  | note | Lendlease Inspection Code:
label | 12405273-acd7-5677-b9eb-6bdf906002ec |  | note | Lendlease Sign/Date:
label | 3b84e28f-c0f0-5060-a3b4-ea33b5c89574 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | All of FFE products have to supported by Noggins
label | 25a6d4e8-a117-5bb3-a99e-afd83e9c0189 |  | note | Acceptance Criteria: Noggin Markup Plan
label | dba9871a-04ec-5749-9a50-df30689d16b0 |  | note | Buildup Inspection Code: W
label | fe0d3c34-94bf-5b3e-9e10-b0fc6681d678 |  | note | Lendlease Inspection Code:
label | 24b42e37-9187-5942-8694-6a5d0c233367 |  | note | Lendlease Sign/Date:
label | a1dabc82-6217-590a-809e-e9ea1a4f159f |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | No unreasonable gap or holes on the wall
label | e66eeef9-4dd3-5d1b-afab-e4cfcc6f7c39 |  | note | Acceptance Criteria: Eye Inspection
label | 3be8e1fa-dcf0-5c8f-81f4-c4c0abddca04 |  | note | Buildup Inspection Code: W
label | e6f0c3e4-7815-597e-ba57-e857f9e0eb62 |  | note | Lendlease Inspection Code:
label | 8dc4a03a-c689-5d84-b7cd-cfaa819ebaef |  | note | Lendlease Sign/Date:
label | 8c12ee0d-e6ea-5c41-bc20-eb4eb64d5fdc |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Height and location must follow the requirement
label | 75a1d653-bcfd-542d-92f5-e273be94474e |  | note | Acceptance Criteria: Noggin Markup Plan
label | fb1f0512-0465-5ee5-8e09-8d67d650d0e4 |  | note | References: Series: BR3ADL2-Internal Architectural Details
label | b961e0bb-eada-554d-a749-36e8b60a2eaf |  | note | Buildup Inspection Code: W
label | 980d491a-3b8d-5d8e-b44a-64a45e2eeacc |  | note | Lendlease Inspection Code:
label | 4dbf250d-f216-5859-80da-276b12f9eb9e |  | note | Lendlease Sign/Date:
label | b7f6cadc-0297-5289-8118-63a8480d37de |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | FFE installation should not affect the wall finish. The wall with good patching as well
label | dde833df-a694-5dcb-8748-62dd9c36968d |  | note | Acceptance Criteria: Eye Inspection
label | 5e7d7201-879f-5cb7-ba6c-7ffa7c622f2d |  | note | Buildup Inspection Code: W
label | 99e0a3e0-46f7-5d7f-ac66-80c293352256 |  | note | Lendlease Inspection Code:
label | 0440d531-85d5-51e3-a9be-886c3a4164c1 |  | note | Lendlease Sign/Date:
label | 1cc781ba-b599-52e8-bf42-c449e56dfe87 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | 816aabce-c548-542f-80cc-511e30dd7f7c |  | note | Buildup Inspection Code: W
label | f2113f64-f195-5e93-ac3e-6507c40a88a2 |  | note | Lendlease Inspection Code:
label | 94f3eaa7-59f8-5a72-a15b-2a2c4afd2327 |  | note | Lendlease Sign/Date:
label | 2072ea7c-af03-5d64-b950-ac4543f90879 |  | note | Lendlease Comment/Result:
checklist-sectioned |  |  | checklist | ITP 005 Installation of Ceiling System |  |  |  |  | Yes | ITP 005 Installation of Ceiling System | 86fc27f8-f70d-44f8-8a0f-086f460f7446
checkpoint-group |  |  | section | Ceiling Framing
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | 6fd34eb6-0258-5b03-8858-d598d84f9310 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | e0ccec2a-3117-595c-829f-1252110e5bc5 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | a2f62ef7-e309-57ac-bb30-6394dc972bdc |  | note | Buildup Inspection Code: W
label | df030848-1cd6-55d0-85cb-27923da04206 |  | note | Lendlease Inspection Code:
label | 6c0b5754-f5f3-5d70-8116-45948afb9491 |  | note | Lendlease Sign/Date:
label | a5ad9392-fd1b-5ebb-a7b6-b3d6c691d32c |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Ceiling framing dimension and FCL checked against drawings and Setout, Ceiling types confirmed against RCPs
label | 6470f2e5-3db6-507d-973a-452ba330643e |  | note | Acceptance Criteria: Latest Drawing Revision Checked
label | 2aab80cf-c5c4-527e-b9d9-97f11e292519 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008; Series: BR3ADG1-Reflected Ceiling Plans
label | fd5bca2f-d054-529c-a8d3-53186664fe8a |  | note | Buildup Inspection Code: W
label | 813d9320-cde3-5f6a-b564-791f5c839186 |  | note | Lendlease Inspection Code:
label | 85d3c740-8898-54a2-8afd-d32ba7c3c874 |  | note | Lendlease Sign/Date:
label | 65a43ff3-39b7-5c37-b80f-37c8612a56ef |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | All above-ceiling services are installed and ready for ceiling framing
label | 2ab79fd1-c933-5587-91ac-3904b0c02a05 |  | note | Acceptance Criteria: Confirm with Lendlease that all wall service rough ins have been completed and approved prior to sheeting
label | c7684e4e-1f74-5dec-95e0-ae3fac7bdae8 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | 501db827-e566-5aca-a672-e7b8493804c7 |  | note | Buildup Inspection Code: W
label | ea2c39b5-c038-5227-b68c-ec0e9e898295 |  | note | Lendlease Inspection Code:
label | a2d960f4-e81d-5f81-911c-4adc19fe96a0 |  | note | Lendlease Sign/Date:
label | 444177fb-41ae-588b-8667-25c620d27fff |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Ceiling framing completed as Rondo designs
label | 13a21532-652b-5110-9216-1f0362a31275 |  | note | Acceptance Criteria: Suspending point max 1200mm*1200mm Grid, TCR @max 600 space and max200 from wall, FC @max 600 space and max 100 from wall. Correctly braced. Two sides fixed and two sides free
label | 81bb33b8-51fb-57c1-887b-778e5b45cae4 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;KEY-LOCK Suspended Seismic Ceiling Specification
label | e87b98aa-69f5-521e-a146-9895bae806a2 |  | note | Buildup Inspection Code: W
label | a0e7f630-12d5-5e3b-8757-1a401ddeef38 |  | note | Lendlease Inspection Code:
label | a08b74c2-6802-5afb-8130-cb2baed788c1 |  | note | Lendlease Sign/Date:
label | a5e9e526-3b49-5d04-8e1f-4e9ec309b76c |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Bulkhead and Bracing completed as Kanuf designs
label | 3ac8a27d-db57-54e5-a76c-99210a66bd47 |  | note | Acceptance Criteria: Anchor used with Load sharing washer
label | 9121aa87-4df1-505d-9493-76795342de51 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;KEY-LOCK Suspended Seismic Ceiling Specification
label | 7def0908-75cb-592f-8b83-90dc326096df |  | note | Buildup Inspection Code: W
label | 64a47dab-2163-5c8f-93f8-8e449103a638 |  | note | Lendlease Inspection Code:
label | 7a06bf4e-be83-5514-968a-462a840056d3 |  | note | Lendlease Sign/Date:
label | d4ba3138-8782-5872-a287-2c8c21c27ca7 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Allowance for access panels and service penetration (Lights and Grill)
label | 6b25f842-7e00-5fc0-b179-e0212f960ee5 |  | note | Acceptance Criteria: Framing not in the way of services or AP
label | 0e91185b-3d18-5612-9631-f2e476e7b521 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Coordinated RCP drawing series
label | c135b42a-755b-53e7-9820-437b73cf38c8 |  | note | Buildup Inspection Code: W
label | c53a1e78-e62f-56a6-8355-e9d6cf81f268 |  | note | Lendlease Inspection Code:
label | 24ba2288-d76e-510e-8ed5-975aa477031f |  | note | Lendlease Sign/Date:
label | 1d05d6be-87e2-5ca5-84c7-93ffa8b53e28 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Timber Noggins and Ceiling support installed as required
label | ccd2e6ed-d526-5602-a062-085659c5abf9 |  | note | Acceptance Criteria: Reference that set out of noggins to be checked against Room Layout sheet Elevations
label | 1f54f6b0-753c-5f92-ba61-be7e1faa813e |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | c82aa8ab-b385-50d5-94f5-f99b7fe4e79f |  | note | Buildup Inspection Code: W
label | 308ea5b1-7917-5616-bcec-469c704e82f0 |  | note | Lendlease Inspection Code:
label | 6ff6bd9b-483e-5d97-917c-7d96c79266d5 |  | note | Lendlease Sign/Date:
label | 96b23f6a-6fe8-5793-8a1d-447c34f24401 |  | note | Lendlease Comment/Result:
checkpoint-group |  |  | section | Close Ceiling
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | ddee755b-a256-57fc-9435-e4650fe1c966 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | bd41d246-7d65-52fb-8341-977a6a91c14d |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | 59bb2a99-2151-5fab-9475-932c45d3f0f4 |  | note | Buildup Inspection Code: W
label | 1ea6bc05-bb35-5876-8467-8082349abd5e |  | note | Lendlease Inspection Code:
label | a6d1a083-1456-5ac7-acdd-f9a5e2d8eb7d |  | note | Lendlease Sign/Date:
label | 2ee4e057-7af1-5181-9056-063fa0edfb5a |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Check all services roughed in and not using ceiling frame as a support, all seismic supports have been installed for service by others, ceiling closeout checklist received by Lendlease
label | 71f32160-69e5-585d-85c1-7b4376cd71ad |  | note | Acceptance Criteria: Minimum 3mm gap kept from ceiling frame
label | 2ef02bf4-4844-55ec-bba0-87893b86fbdc |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;KEY-LOCK Suspended Seismic Ceiling Specification
label | f5bdb03d-4844-5a48-ab95-0914d09deea1 |  | note | Buildup Inspection Code: W
label | c15ad7ed-8163-585e-97df-a05348f76653 |  | note | Lendlease Inspection Code:
label | 004404c4-6dea-586c-b618-b6aac11aba23 |  | note | Lendlease Sign/Date:
label | a6dedf7d-ba63-523b-b257-4a6d36c43aa0 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Installation of acoustic insulation to the ceiling
label | 6e0bd6e7-597f-56cb-b6b1-3caef3ada4a2 |  | note | Acceptance Criteria: acoustic insulation must extend 900mm from acoustic wall
label | 96f5c9be-b9d4-5aab-be98-c86f5a4e1da0 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008; Series: BR3ADS2-Insulation Ceiling Plans
label | 9cc126ed-c740-5fa8-9c81-10455ed3570f |  | note | Buildup Inspection Code: W
label | 78faf2da-9ad1-58e3-98e8-6e9a7ff5850f |  | note | Lendlease Inspection Code:
label | 438e98f7-7c0c-5051-b044-40a67e7f5a9a |  | note | Lendlease Sign/Date:
label | 48f43cb1-5628-574d-bd7e-8bd90681a6eb |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Sheeting carried as per manufacturer’s specification, specified sheeting as per schedule. Ensuring correct layering and components and completed fixing as pec
label | 76d647e4-27cc-58b5-aef8-110255554ddc |  | note | Acceptance Criteria: Staged Fixing @200mm max centre at edges, fixing @300mm max centre in field, Staged butt joint by 600mm min. Back blocking battens used on butt joints
label | d791787d-6e65-5fad-a3c7-2861b120b6a4 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;BCA Report 210721: 1740 R1.0
label | e11693c4-6bb5-5c65-b9f2-2f0bc6366794 |  | note | Buildup Inspection Code: W
label | 64104c56-2b7e-53c8-a11d-c3b7285cfd83 |  | note | Lendlease Inspection Code:
label | af6b034e-b652-5fc3-83d6-e4b39df591c8 |  | note | Lendlease Sign/Date:
label | 09e8044f-ee2d-5ce7-bfb0-0bcdae96fdc7 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Access panel installed as required
label | 40b16dab-c8c5-5ae5-9f0e-2dceac66672b |  | note | Acceptance Criteria: Correct location, square with wall or bulkhead
label | 1f1f7752-5095-5da4-8a92-7b4385cd9341 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;BCA Report 210721: 1740 R1.0
label | 7bf2b3ca-ddcc-53f1-9f27-0f927f1b3161 |  | note | Buildup Inspection Code: W
label | 35cd0bc5-e217-562c-8ed2-6abdb8d9154f |  | note | Lendlease Inspection Code:
label | d19ac457-dfb6-5399-a3a7-625146a0ca7f |  | note | Lendlease Sign/Date:
label | 376d3d03-485d-5fa2-b1cf-182bca8f3a5e |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Caulking to acoustic / fire / smoke/ details.
label | 74f38c33-3477-5535-ad11-a1b46e67a7dc |  | note | Acceptance Criteria: Max 20mm with slab/ column, flush
label | 9885cf67-6ae8-5527-a3ad-6581c1791b0a |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;BCA Report 210721: 1740 R1.0
label | 4932fbb7-c6e3-52c3-a701-587f56835f93 |  | note | Buildup Inspection Code: W
label | 87bbb433-dcd2-51a1-b2d7-2e3ac7697e29 |  | note | Lendlease Inspection Code:
label | 050b7a3c-dff0-5000-bfe3-1e1061aeace4 |  | note | Lendlease Sign/Date:
label | 35766a41-a4d9-55ba-8149-b71f489a2ad8 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Set and sand ready for painting
label | b74ddbb8-ce4f-553d-8ca0-8d9357755446 |  | note | Acceptance Criteria: No bubbles, no lump, square, not over sanded
label | 2f8145e8-04a4-5c7f-9863-75dc1f19dd21 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;BCA Report 210721: 1740 R1.0
label | 2bf6986a-bcd2-5011-9048-3ab78c26f9cd |  | note | Buildup Inspection Code: W
label | d3580a80-f19f-5cd8-8d45-68ed07fa1ff2 |  | note | Lendlease Inspection Code:
label | 3aeebea5-5c49-53a3-a0ca-17dd35502b1f |  | note | Lendlease Sign/Date:
label | afbbd66c-d83a-593e-bad5-fe18b5b5132d |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | d13ad879-b74c-56bd-8c55-dc5aa962dcec |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Siniat&Rondo Inspection
label | 9c88e507-cc36-550e-bff7-7cd6576eab88 |  | note | Buildup Inspection Code: W
label | 04e48913-d9c4-5932-bb58-2c1cdc1a1d18 |  | note | Lendlease Inspection Code:
label | baf25f56-d9ad-5cb0-b10f-5f195deae726 |  | note | Lendlease Sign/Date:
label | 5c2ad7f1-3cef-5e01-a8c3-b9b84a6346ad |  | note | Lendlease Comment/Result:
checklist-flat |  |  | checklist | ITP 004 Door and Door Hardware Installation |  |  |  |  | Yes | ITP 004 Door and Door Hardware Installation | b423c161-fe1d-4b9a-92e0-cc6d354e9886
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | c0236195-a27a-5d11-89e8-327cc1fa6da8 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 39216d9e-5366-540c-9958-c36efcb10076 |  | note | Buildup Inspection Code: W
label | 14dc693b-3ee3-5793-affa-423c7fe3d94f |  | note | Lendlease Inspection Code:
label | bbd31796-a4b6-50c5-8ea7-14599ac4284f |  | note | Lendlease Sign/Date:
label | 2cacf42e-06d6-5220-850d-504088a2a4bd |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Opening dimension checked against drawings and Setout, Door types and leaf size confirmed against partition plan
label | ed85abf2-61b5-5765-a19d-37e2ac2115a7 |  | note | Acceptance Criteria: Latest Drawing Revision Checked
label | 125a007f-3c86-5299-bae6-a02f03039c51 |  | note | References: Series:BR3ADB2-Wall Setout Plans; Door Schedule - BR3AT1332[C2]
label | d5089eeb-ef48-53b0-933b-5b42751ff69b |  | note | Buildup Inspection Code: W
label | b874eb43-02c4-5583-a676-2b5df2e9defc |  | note | Lendlease Inspection Code:
label | c6df68cb-cec8-5d01-aa5b-54f5b31ea21c |  | note | Lendlease Sign/Date:
label | 3475221a-fe38-561f-90fb-b928d561048f |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Door frame installed as manufacturer's specification to Top, bottom and both sides
label | f30b1a5f-7889-514f-b53b-ed32f9eb34b5 |  | note | Acceptance Criteria:Straight and plumb and square, no sharp edge, gap less than 20mm, sealed with silicone
label | 824bf92c-9eb7-5edf-956c-c68a03f91b4c |  | note | Buildup Inspection Code: W
label | 71b457c4-3372-5b2d-8b01-b8fca2b08af0 |  | note | Lendlease Inspection Code:
label | 6a69788a-508e-5d05-b1a7-dc1a5e24620b |  | note | Lendlease Sign/Date:
label | 2ab35dd3-825a-58a6-a08a-95b925b95654 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Door Hardware Installation and Check
label | c5b655c0-2155-5bc1-b62f-90f68c920df8 |  | note | Acceptance Criteria: Correct Hardware type followed as shop drawings. All of door hardware followed the finish Schedule
label | cf1b13e8-c7a7-538b-95fe-e082bc943afb |  | note | Buildup Inspection Code: W
label | abcafa98-fe30-56ca-800f-38d51a113781 |  | note | Lendlease Inspection Code:
label | 6053bb30-7a7f-5d6a-9b52-44672ffdce82 |  | note | Lendlease Sign/Date:
label | 4100e5fd-ae39-554c-ae6d-71b1b3e3b1dc |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Door Smoke sealed cabinet
label | 162a5f35-1a29-5ec5-82bb-3fe81728d2e2 |  | note | Acceptance Criteria: Latest Drawing Revision Checked
label | 8ebe20d4-64bf-5bf5-a939-7b297787bed6 |  | note | Buildup Inspection Code: W
label | 7ca944ce-e749-5943-a814-61e9ec3c63a9 |  | note | Lendlease Inspection Code:
label | 63bce28b-adbe-52d9-a061-dda3fb5d9f2b |  | note | Lendlease Sign/Date:
label | e78b9116-911f-5704-9b5c-bf13a133f0b3 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | bcb0d1b1-e8e3-5295-9f3e-1db6c7a243bb |  | note | Buildup Inspection Code: W
label | c9364ff4-dd17-5bde-86d1-626e67c93c20 |  | note | Lendlease Inspection Code:
label | 02779734-9ad7-573a-be2c-21aabd4053ba |  | note | Lendlease Sign/Date:
label | 4970dd4c-4fd5-514c-a77e-db753ebf7e9e |  | note | Lendlease Comment/Result:
checklist-sectioned |  |  | checklist | ITP 003 Installation of Internal Partitions |  |  |  |  | Yes | ITP 003 Installation of Internal Partitions | e1b3b42f-136b-469a-8b5f-6cbc317b1846
checkpoint-group |  |  | section | Wall Framing
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | aefdbe02-dc48-587f-bfd4-76e88303c110 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 865435c4-6dee-5e2a-bad3-e2d4adb42445 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | b7199c52-5b58-5cc2-bc54-8c39a4514a2d |  | note | Buildup Inspection Code: W
label | 4e1b9d34-1fdd-5533-8492-a9bf0a612df7 |  | note | Lendlease Inspection Code:
label | 466deb9d-065d-568a-8fa7-26ba1478c1b4 |  | note | Lendlease Sign/Date:
label | fc49dddb-0bd8-599a-8736-f517b96f0c81 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Wall framing completed to Rondo designs, checked for square, plumb and twisting
label | a237567a-ce8d-5b65-8311-48ba1b44fc2c |  | note | Acceptance Criteria: slotted Deflection Track used; additional noggin installed for onside sheeting frame
label | 1736ca7c-a6d0-575f-a4c1-c0f07ebbd7bd |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | 41fc5557-40d1-5adc-9e02-c6efee3cbf36 |  | note | Buildup Inspection Code: W
label | 37d274ed-3d09-51e2-95d8-fd976493633b |  | note | Lendlease Inspection Code:
label | 0a8802da-f91a-5c87-b531-ad4a67279304 |  | note | Lendlease Sign/Date:
label | a52fe1fe-21eb-5a22-aa73-c7f655247b72 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Allowance for access panels and service penetration
label | 5207fd21-03f1-5a3a-aa7f-9ad37c321ca7 |  | note | Acceptance Criteria: Bridging Track supported by offcut studs
label | 51e73e22-4658-5ac9-8850-c493b8bc12b7 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | 54b85c42-87e7-5dab-a3fe-b77dfaddc0cd |  | note | Buildup Inspection Code: W
label | c18c3078-04b1-5b42-894e-843d2ac1f4d8 |  | note | Lendlease Inspection Code:
label | 2b7902d7-128d-5264-b38f-2fe7791b5488 |  | note | Lendlease Sign/Date:
label | 8a52cf9d-f658-5e0d-a92c-5ec8a621700b |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Openings (Including doors, windows, removable parts) installed to correct position and height, with right opening towards, plumb and square, as per Rondo designs
label | 551ae40c-555f-5b75-92f5-6a47f40d7bf2 |  | note | Acceptance Criteria: Jamb header or sill used correct components
label | cf4c0fbf-0059-5531-9f94-0387b1e42287 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | 2049b920-4740-50fa-b334-fb820b7a6e26 |  | note | Buildup Inspection Code: W
label | 4f43ded0-97ea-50c7-85f9-c680bba24135 |  | note | Lendlease Inspection Code:
label | 07c29e1a-4d27-5105-9771-0ebdfec47429 |  | note | Lendlease Sign/Date:
label | a57d5561-95bf-5fe1-8c0d-93853be62afc |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Plywood Noggins and structural stud installed for all fixtures
label | 09859712-4b07-5e50-a915-37a1c7fdcbf6 |  | note | Acceptance Criteria: Reference that set out of noggins to be checked against Room Layout sheet Elevations
label | 30726a87-10f0-567d-b67d-77dbcca70a16 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | 58bff7a7-79be-58c1-abb1-75aea9d10df7 |  | note | Buildup Inspection Code: W
label | fef943f6-6310-593c-833d-321ac4ebd372 |  | note | Lendlease Inspection Code:
label | 7d2ae7f6-8767-531c-bf23-6e63941619a1 |  | note | Lendlease Sign/Date:
label | d121c303-6d2b-54fa-85f1-e2d710c94831 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Door and window Frame installed as per manufacturer's specification stud installed for all fixtures
label | 520b09d4-f0b9-5e87-8bb6-042284435728 |  | note | Acceptance Criteria: Plumb, square and same height, core-filled
label | 57e446b8-f031-5a0b-a00d-6f787e3b4a0d |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | fba790f7-5f99-5d99-b55c-0dc5257ec80b |  | note | Buildup Inspection Code: W
label | b2469f00-1767-5919-90ac-b4c53a43332b |  | note | Lendlease Inspection Code:
label | 08f5aaaa-0cea-50be-b879-eaf860e25c2e |  | note | Lendlease Sign/Date:
label | efe43ebc-812a-5292-993d-b572035a7f74 |  | note | Lendlease Comment/Result:
checkpoint-group |  |  | section | Wall Sheeting
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | c5ac061b-3d91-5d9d-8014-7caa32daa050 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 5b96b98f-ae87-5061-a1af-c2904a83ae2e |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | c4e41180-dc21-51f9-912e-b899e2f31a14 |  | note | Buildup Inspection Code: W
label | ff41a087-935a-5afc-b15e-45483fa8e277 |  | note | Lendlease Inspection Code:
label | aa259c3c-6438-5fd5-91f3-5873b0fbfe28 |  | note | Lendlease Sign/Date:
label | 1dc090e6-e197-5634-b9b7-2c789644714a |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Sheeting carried as per manufacturer’s specification, specified sheeting as per schedule. Ensuring correct layering and components and completed fixing as specification
label | 68a86854-ba05-5f45-b543-5c080e496c25 |  | note | Acceptance Criteria: Staged Fixing at edges, fixing@50mm max centre in field, Staged joints min 300 mm between different layers
label | 4fdde0ac-eaed-5d60-89b2-b6a4828dec72 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | 453babbc-b03c-5fe8-9ae9-41063bcadf11 |  | note | Buildup Inspection Code: W
label | 6fd00493-125e-5889-980a-017b0644f98d |  | note | Lendlease Inspection Code:
label | 324c6afb-d0cf-5b82-a9c4-2e1c5ca2d058 |  | note | Lendlease Sign/Date:
label | 2e2a7689-dc66-5631-af30-87a8266026f4 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Caulking to acoustic / fire / smoke/ details.
label | 644dfe11-7f96-509b-8ac1-629091c8ffbc |  | note | Acceptance Criteria: Max 20mm with slab/ column, flush
label | 184e4ff6-fba8-5ab3-a7e7-8373227d79a4 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | 6d3b0b2f-85a7-5d98-bdec-147bdf29a101 |  | note | Buildup Inspection Code: W
label | d9c822e0-c625-5d40-85d6-7322c4503af2 |  | note | Lendlease Inspection Code:
label | 54064a20-24f0-54f5-98d0-3a896143c300 |  | note | Lendlease Sign/Date:
label | 7c6c1fd6-2fd2-5c67-bc50-c74b2181a342 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Penetration sheeted and sealed as per builder' drawings
label | aff980f4-5ff6-5e64-b35d-f88de202b3f4 |  | note | Acceptance Criteria: Opening square and flush, fully sealed
label | ec5343a4-a746-5ad8-ad22-86335bce533f |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | 1a0f1e8c-1bd3-58ed-a170-83b3b0b84fa0 |  | note | Buildup Inspection Code: W
label | 6ec43cdb-5339-507e-9845-4a971c6db802 |  | note | Lendlease Inspection Code:
label | 25542917-8534-5bc6-82d3-02aab9a26695 |  | note | Lendlease Sign/Date:
label | 5141b4bc-0f94-505a-a865-6900e5f265c8 |  | note | Lendlease Comment/Result:
checkpoint-group |  |  | section | Sheeting (Close Wall)
checkpoint-status |  |  | checkpoint | All in wall Services signed off by other trades, wall closeout checklist received by Lendlease
label | 1d7c51a3-b227-5afb-bcb9-bc317b2480f8 |  | note | Acceptance Criteria: Confirm with Lendlease that all wall service rough in have been completed and approved prior to sheeting
label | 4fa5fffe-90a5-5e9b-9046-eb4020051a5c |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | e8539681-254c-59e5-8588-fb24caaf2e6e |  | note | Buildup Inspection Code: W
label | c6e0272f-f0ff-57f2-8a45-69abb93fb0fe |  | note | Lendlease Inspection Code:
label | be348099-030d-5681-afaf-913433210514 |  | note | Lendlease Sign/Date:
label | ded7b9b3-e325-522b-9932-8c7556f9a12f |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Insulation completed as per acoustic report, partition plans and spec
label | fc4dd1e1-b279-5268-b74d-a368cfae747f |  | note | Acceptance Criteria: As required Insulation, no gap can be seen
label | d9b26b2c-a86a-578f-a834-bab2a5e63ab0 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADL1-Wall Type
label | d5b310c7-7fa1-55c3-8721-980317fddefb |  | note | Buildup Inspection Code: W
label | 3b09c0c6-328b-58f8-87b4-211210e231ac |  | note | Lendlease Inspection Code:
label | deed7c98-ba60-5f2d-b2f3-051f589099d5 |  | note | Lendlease Sign/Date:
label | 157b4daa-dbdc-5605-ab7c-09d7a0323219 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Plywood Noggins and structural stud installed for all FFE
label | dd21f585-601b-5057-8205-4273c8ea23b2 |  | note | Acceptance Criteria: Checked against current RLS
label | 82c529c2-6c36-57f8-8175-49b4c1b8f084 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADL2Internal Architectural Details
label | 39691b6e-4ed3-5740-8bed-e5a49ff5d2b8 |  | note | Buildup Inspection Code: W
label | f8dc2867-7f09-52f7-acf8-6dd6a2322198 |  | note | Lendlease Inspection Code:
label | 15213977-827b-5c08-a5fe-9ed53cc58893 |  | note | Lendlease Sign/Date:
label | a8e889f4-717f-5d07-a847-381517ed7985 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Close wall
label | d9a1bd57-23f8-5a1b-9a42-8619b45751b4 |  | note | Acceptance Criteria: Staged Fixing at edges, fixing@50mm max centre in field, Staged joints min 300 mm between different layers
label | 92001908-199c-5135-8a06-6610bd0db9b8 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | fbb8367d-060a-55f9-8e52-4ae09bae12ae |  | note | Buildup Inspection Code: W
label | b6ec1868-2238-5ea5-a386-005da835ad09 |  | note | Lendlease Inspection Code:
label | d3b576c4-4ff9-5797-ae28-df7085255b09 |  | note | Lendlease Sign/Date:
label | 8ffac380-f422-5e64-90ca-5b9a345726b5 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Caulking to acoustic / fire / smoke/ details
label | 578df23c-9ea4-5410-b353-162c13f94ce9 |  | note | Acceptance Criteria: Max 20mm with slab/ column, flush
label | c0b060d8-79c7-5706-98cd-154fb4caa9d9 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | 23ca6093-a45b-50bc-912d-ebf379268ae7 |  | note | Buildup Inspection Code: W
label | 248e669d-4fd0-588c-b926-6c580a7f141a |  | note | Lendlease Inspection Code:
label | 09d35c8f-a237-5283-8aa5-318213bbe145 |  | note | Lendlease Sign/Date:
label | 9a358868-86e2-52c8-a0b6-6e3974169ca2 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Set and sand ready for painting
label | dce3d5e0-3282-5907-9a94-d9bdd3200e8f |  | note | Acceptance Criteria: Meet Level 4 of finish requirement
label | 6ec6719d-f91b-56e1-a468-c5d2be62fe19 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | c7538373-b78d-53cd-8ea9-875d11a7d97f |  | note | Buildup Inspection Code: W
label | a3b44d0e-13ed-527d-8fed-eb67fdc0e919 |  | note | Lendlease Inspection Code:
label | 9be2a9ba-a182-528c-a414-19259ca27074 |  | note | Lendlease Sign/Date:
label | 7c39751c-7faf-5fd7-afef-33b0ee35a729 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | f5809686-e3a6-5470-9a57-eda2f3a12eb0 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008; Siniat & Rondo Inspection
label | b47e7d76-26c0-582e-877f-93d9313b5ff1 |  | note | Buildup Inspection Code: W
label | 0fa26da5-c994-5096-a312-fac79f615934 |  | note | Lendlease Inspection Code:
label | cad9409f-3a76-53a1-a7f1-26d5c4aea353 |  | note | Lendlease Sign/Date:
label | 89f1f7d6-b6fa-51c7-a88e-2d4e1211906d |  | note | Lendlease Comment/Result:
checklist-flat |  |  | checklist | ITP 001b Speed Panel |  |  |  |  | Yes | ITP 001b Speed Panel | f04e8cf9-ebac-4899-9297-355a2a25c59a
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | b3a3dd06-5361-51e6-b002-384577e53640 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | d1b8b086-a740-55cf-8151-d43d3aa7b412 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4
label | 0c132582-34cd-5b84-95a6-7c962644aa18 |  | note | Buildup Inspection Code: W
label | 2a77bcf8-b71d-560d-b351-f45c594adf69 |  | note | Lendlease Inspection Code:
label | d2f5492a-3cfe-5b17-b81d-b1f023fa942b |  | note | Lendlease Sign/Date:
label | 8c6acaad-b142-55b6-b132-58010f302620 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Wall dimension checked against drawings & setout; Wall types confirmed against partition plans
label | cac1aaeb-32ec-5512-9e8e-2e2da27e96ea |  | note | Acceptance Criteria: Latest drawing revision checked
label | d05ba9ee-ea29-5aef-a62a-6b38c4d6c750 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Series BR3ADB2 -; Wall Setout Plans BR3ADF3 - Fire Stairs
label | 253d1022-dd12-5067-9356-2415d79afcd1 |  | note | Buildup Inspection Code: W
label | 7bcabc6a-5696-5ec1-9ad5-c66c91c078f5 |  | note | Lendlease Inspection Code:
label | ac58cd64-32f4-55a9-a4d6-c72f51a1d2f0 |  | note | Lendlease Sign/Date:
label | 07226d62-9853-560d-bbd0-205680c0ab4d |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | C-Track installed as manufacturer's specification to top, bottom and both sides
label | b9dc819e-a61c-54fa-8fc3-db19a0304294 |  | note | Acceptance Criteria: Hilti 606 Sealant applied between C-track and concrete and along internal corner. Anchor @500 Centre & max 100 from end
label | 5bc3ee0d-9b50-57c9-9d2f-194c7abe0323 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 3be1732f-f196-59df-8059-10fa6a73fe0a |  | note | Buildup Inspection Code: W
label | 47e60c65-a07e-51d9-aa41-7ddb48cd566c |  | note | Lendlease Inspection Code:
label | a80e2ac6-8497-56ed-8dc2-47c879451413 |  | note | Lendlease Sign/Date:
label | df79b9d2-ae47-59c3-89ec-1a8e808ec0ea |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Panels installed as manufacturer's specifications
label | 90c963ea-3b8e-5aa2-92e4-643ac9862d3a |  | note | Acceptance Criteria: Each panel interlocked, fixing @ max vertically 1000mm centre on joints and 250 mm horizontally, fixing @ max 500mm on C-track, 2 fixings at 45" for every corner. Sealant full placed around C-track
label | 064a81bf-0724-59e7-b41b-859a3bb53d0a |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 18c326be-c2e3-540e-989e-7f8e7d99b040 |  | note | Buildup Inspection Code: W
label | fdd5760a-02d3-524b-8803-a6e531bdcbf4 |  | note | Lendlease Inspection Code:
label | 66344869-a676-572f-8ed9-06c3c7060e06 |  | note | Lendlease Sign/Date:
label | bd86772d-a54b-5865-b532-d78c04f8e670 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Penetration cut, trimmed and sealed as per builder' drawings
label | 36ad7809-30ce-52cf-b430-9b3582ece9a8 |  | note | Acceptance Criteria: Max 500mm centre fixing on C-track, 2*fixings on corner, fully sealed with Hilti 606
label | 1e859362-945a-5eb3-8103-f943acb880a6 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | af617791-fd6f-5daf-9111-5ba8968023bf |  | note | Buildup Inspection Code: W
label | a239d35f-4388-547b-a3b9-b1291b3ecb86 |  | note | Lendlease Inspection Code:
label | ad614810-7b18-5773-b056-dfbeb910802d |  | note | Lendlease Sign/Date:
label | 0c4bdaa1-efcf-5b6a-8b6b-a11e529fc6be |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Door Frame installed as per manufacture's specification
label | 9eb9c39a-e297-53f4-bdfd-c63d4bf847c9 |  | note | Acceptance Criteria: Plumb, square and same height, core-filled
label | 989a42de-8690-5a3e-a8d1-db24aa07ba2e |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 31eeb225-936b-55d6-a46c-ae7320c0da34 |  | note | Buildup Inspection Code: W
label | c9fd8aea-65df-56bd-96d4-801bb5a173f8 |  | note | Lendlease Inspection Code:
label | d3c86b4a-09a8-5528-b841-698783eda14f |  | note | Lendlease Sign/Date:
label | f429bc55-fbed-5ddb-99a0-6b45f13c24d3 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Flashing head-protection
label | e448947d-6d74-5bbd-995a-9bacd1afd05c |  | note | Acceptance Criteria:Min 120mm deep, stagged fixing @max 250mm
label | 00c22ca5-4102-5b0a-b27f-bebd678e7c2b |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 78df7e06-af9c-50b0-b206-d395c097b832 |  | note | Buildup Inspection Code: W
label | e2840b46-b222-5945-b87b-b4f35d1cac92 |  | note | Lendlease Inspection Code:
label | 8526c404-1d8e-574d-918d-c33f53f5932d |  | note | Lendlease Sign/Date:
label | 81a0641b-bc52-5152-970c-3e989c5d7d20 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Fully sealed joints one side in pressurized shaft
label | 4df65fe6-8899-5cc5-b436-d90ae42680c4 |  | note | Acceptance Criteria: Continues beads
label | d57a585f-1494-5b5f-98a1-08fa2592e7a4 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | d46f7ab4-975a-57d3-9b87-60c16ae14b36 |  | note | Buildup Inspection Code: H
label | d45361b9-cae3-57dc-94d3-b92e162c2400 |  | note | Lendlease Inspection Code: H
label | cb29b959-2ab3-5b98-84b2-a6c4ea0ba2a5 |  | note | Lendlease Sign/Date:
label | ac8c3f51-c51c-5c1a-8352-4201835f2410 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Comprehensive first of type inspection
label | 4d2cb795-b7f6-5614-8a6e-44fc73cf90b7 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4; Supplier / Manufacturer inspection report
label | 537d2580-6209-5472-bdf5-49b6d4178acd |  | note | Buildup Inspection Code: W
label | fa0677ad-b0c7-54c3-9e22-073b3fd83751 |  | note | Lendlease Inspection Code:
label | cfe04327-fb44-52bb-a677-48308fb12002 |  | note | Lendlease Sign/Date:
label | 01ceb185-ae3f-517e-b1a4-d2b88545e300 |  | note | Lendlease Comment/Result:
checklist-flat |  |  | checklist | ITP 001a Speed Panel |  |  |  |  | Yes | ITP 001a Speed Panel | f7d5705c-95c1-4b0c-8ccd-5bd86f7d3aa2
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | 344f7f80-c71a-574b-bd2f-bd72ac7319cd |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 8303427a-537e-5f16-b411-1241a6cde7cc |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4
label | 36ac0ff7-88cb-53c8-b80d-89bd94d2f446 |  | note | Buildup Inspection Code: W
label | 73b5d6e6-544a-532b-88af-b02685f7def9 |  | note | Lendlease Inspection Code:
label | 8e29c554-f918-5794-91ba-e9666382c40c |  | note | Lendlease Sign/Date:
label | 6247e75b-fc58-5c2f-a14f-b49d15b535b4 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Wall dimension checked against drawings & setout; Wall types confirmed against partition plans
label | 97293294-b2be-507d-b88d-b65aed044d39 |  | note | Acceptance Criteria: Latest drawing revision checked
label | b6fe35c9-4be2-5173-be9b-c71ae2913dc1 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Series BR3ADB2 -; Wall Setout Plans
label | 948aad9e-747c-551a-84ab-9fe14879585e |  | note | Buildup Inspection Code: W
label | a4487488-3192-59b8-99be-9b12192169d9 |  | note | Lendlease Inspection Code:
label | feecbc9a-ce86-5a33-972e-05572085986b |  | note | Lendlease Sign/Date:
label | 5cc470e3-33ed-5bba-aea3-a95b7b9658e1 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | C-Track installed as manufacturer's specification to top, bottom and both sides
label | 36cc3943-5638-5591-b195-a32fd46b9c5b |  | note | Acceptance Criteria: Hilti 606 Sealant applied between C-track and concrete and along internal corner. Anchor @500 Centre & max 100 from end
label | 9eb6a253-c6e3-5f9e-a65d-e45c7e0cdc4c |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 0ab2af92-3f99-5b43-97c7-5ff3d5bf388d |  | note | Buildup Inspection Code: W
label | 8b4f45c0-12de-5221-9959-0bf65917a75c |  | note | Lendlease Inspection Code:
label | daf05b9c-4946-523c-8b6b-a77397b8acc9 |  | note | Lendlease Sign/Date:
label | 5ab5c200-44ec-5a19-bde5-ceb6a5f4c9fe |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Panels installed as manufacturer's specifications
label | a3b82229-6898-591e-a3b6-22e702825739 |  | note | Acceptance Criteria: Each panel interlocked, fixing @ max vertically 1000mm centre on joints and 250 mm horizontally, fixing @ max 500mm on C-track, 2 fixings at 45" for every corner. Sealant full placed around C-track
label | 161f49e2-8241-5475-a43f-65eea2fcf76c |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 8d798af6-a732-557e-97c2-c129dc7ec58f |  | note | Buildup Inspection Code: W
label | 56e11b1c-8736-58ef-839b-ace066573387 |  | note | Lendlease Inspection Code:
label | 83453905-61ec-537f-85af-7f512ced451b |  | note | Lendlease Sign/Date:
label | 2880a66b-3cb2-5d30-b892-267475265018 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Penetration cut, trimmed and sealed as per builder' drawings
label | 23efbdd9-3ff2-5705-a18a-773dc44a34b8 |  | note | Acceptance Criteria: Max 500mm centre fixing on C-track, 2*fixings on corner, fully sealed with Hilti 606
label | b34ccda7-fc7f-55c2-9ee5-a43b0e4807e2 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 5edf86c4-1661-59d2-96fb-d8ee6a5fb680 |  | note | Buildup Inspection Code: W
label | c9ee27bb-e713-50c7-809c-a38b381f9556 |  | note | Lendlease Inspection Code:
label | f4d4fb03-0646-568a-9ce7-94757ccf8c0f |  | note | Lendlease Sign/Date:
label | 1b1b594c-8cab-568d-b2b9-04ba8f737150 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Door Frame installed as per manufacture's specification
label | d5952db0-00fe-5105-b3be-754240bb99a4 |  | note | Acceptance Criteria: Plumb, square and same height, core-filled
label | 3d68e605-71f6-526c-aefe-3b93790d6b7b |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 9e042b20-71a6-58af-866f-bc13d0628204 |  | note | Buildup Inspection Code: W
label | cc2a0a14-7ef8-5e92-ada7-4408062e0151 |  | note | Lendlease Inspection Code:
label | ff868538-6165-52c1-b3a0-3b7f44216db5 |  | note | Lendlease Sign/Date:
label | a6e214e4-d491-5ca6-8668-afa78f551860 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Flashing head-protection
label | 1b869cb1-5eae-5ffc-b715-7d2224f6addd |  | note | Acceptance Criteria:Min 120mm deep, stagged fixing @max 250mm
label | 5c455ee4-298f-5043-b337-1320bfb8cfa3 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 1135575c-e95c-560c-b081-cc0c5d5ad142 |  | note | Buildup Inspection Code: W
label | e01fd2a1-600a-5325-a308-4054eca7edb8 |  | note | Lendlease Inspection Code:
label | e226fb20-7ccc-522b-8e90-5b19c4aa7a41 |  | note | Lendlease Sign/Date:
label | f84162b3-6c7f-509d-b8e5-48863fef31eb |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Comprehensive first of type inspection
label | d1892028-2bb1-5a57-aee7-dd3e70bd80ff |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4; Supplier / Manufacturer inspection report
label | 09026e69-38dd-57ac-8568-93d732fffc46 |  | note | Buildup Inspection Code: W
label | cd897766-b773-5ef7-88f7-42a329f1050f |  | note | Lendlease Inspection Code:
label | c4a2be3a-3ddc-5f6f-855f-297c2d714b39 |  | note | Lendlease Sign/Date:
label | fe0b0b40-3b34-56d1-ab39-bf985fcf9fcf |  | note | Lendlease Comment/Result:
checklist-sectioned |  |  | checklist | ITP 002 Installation of Soffit Insulation |  |  |  |  | Yes | ITP 002 Installation of Soffit Insulation | fba9fe1b-d9bc-4742-be5c-fb2333faf73a
checkpoint-group |  |  | section | Materials delivery
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | d649bac0-6378-5ec5-ae92-89a08b84dcf3 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 65fefa6a-a175-5e97-82f6-d6156d8dab38 |  | note | References: Australian Standards AS/NZS 4859.1 and AS 5637.1.
label | 0842680e-bcdb-5fbd-83fd-5e42498fe839 |  | note | Buildup Inspection Code: W
label | f68d9dcb-bf38-530f-9a76-d9f3e215ffb5 |  | note | Lendlease Inspection Code:
label | 53931893-84d1-5caf-ada8-c04cdb5c1527 |  | note | Lendlease Sign/Date:
label | 74c961fe-7e82-5d16-ab7e-2aefeac723a5 |  | note | Lendlease Comment/Result:
checkpoint-group |  |  | section | Under Slab Insulation
checkpoint-status |  |  | checkpoint | Insulation dimension checked against drawings and Setout; Insulation types confirmed against Insulation set out plans
label | dc36f303-431f-58f3-a3e6-39d2a1b3e476 |  | note | Acceptance Criteria: Latest drawing revision checked
label | 9b7a58cf-3350-51b6-b27f-e7c2e849657f |  | note | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Series: BR3ADS2-Insulation Ceiling Plans
label | ddeedb4b-1dd4-5afe-bfa4-500a0ff50e48 |  | note | Buildup Inspection Code: W
label | cc0fcc98-5a9a-5db3-a624-3539b3640024 |  | note | Lendlease Inspection Code:
label | c895d137-5d3d-51af-b925-e0ca41424f5a |  | note | Lendlease Sign/Date:
label | 6473e87c-c65c-5060-a75c-010e84631330 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | The foil surface of the insulation board should face down
label | 8d8138e8-3737-5796-b58e-04ea0e319958 |  | note | Acceptance Criteria: Inspected and confirmed
label | 47037bae-4812-5420-8097-864732b030fc |  | note | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | b4899a6f-ba2f-5997-ba9f-13525567b255 |  | note | Buildup Inspection Code: W
label | f58996c2-f4a1-5405-9ce9-9337bc6763fe |  | note | Lendlease Inspection Code:
label | 151abaa0-d7a2-5f2f-a588-0af49d1eb486 |  | note | Lendlease Sign/Date:
label | c50ce5ce-7e97-5038-bdd9-b3050eeecd56 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Fix insulation panel to concrete soffits with minimum 5 No. Appropriate insulation fasteners with a minimum head diameter of 35 mm
label | 89ec89ef-9f81-5e9a-b957-762101a0d2ac |  | note | Acceptance Criteria: Inspected and confirmed
label | ddbda5d5-26db-59aa-8699-77de157cf562 |  | note | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | f7791db0-da76-5388-80c2-3faff7f27f5b |  | note | Buildup Inspection Code: W
label | d4446e5f-c576-5540-b315-5e3448fefe32 |  | note | Lendlease Inspection Code:
label | e413493c-48fd-5319-8e8c-29df32b67dfd |  | note | Lendlease Sign/Date:
label | 586da979-11bc-5fa0-8bfc-124cad4d22ca |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Tape board joints with a minimum 96mm wide appropriate aluminium foil tape, detail as per attached Installation Instructions
label | 43ff3000-c560-5ac9-b2cc-c14b10008441 |  | note | Acceptance Criteria: Inspected and confirmed
label | 6e08d942-34bf-50f1-9843-36a182cb9d68 |  | note | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | 5ae5a74b-77d4-505d-b76b-0f490f617c2f |  | note | Buildup Inspection Code: W
label | a0689a34-c9ea-5bf8-970f-2ca8fb19e687 |  | note | Lendlease Inspection Code:
label | 9e57ee84-291c-572c-82b9-d2d727d95a22 |  | note | Lendlease Sign/Date:
label | f833f742-e23e-59b4-acb4-6ee06728e3ae |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Exposed board edge covered with foil tape lapped 48mm on to underside
label | 7c837e33-56d8-5f96-945c-7ad790b31b52 |  | note | Acceptance Criteria: Inspected and confirmed
label | a3f42f6e-4880-54ff-9fd5-f0567e87909a |  | note | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | dc649257-cff3-5c20-810c-7b8643d01fc3 |  | note | Buildup Inspection Code: W
label | 92b55d6b-1f4d-5f03-8419-b3d69f9ac4e2 |  | note | Lendlease Inspection Code:
label | 77dadd6d-281d-5189-afaf-2cdb631987e1 |  | note | Lendlease Sign/Date:
label | e4ed9415-ea93-5de0-9afe-78ca68397a54 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Check against cast-in penetrations. All penetrations/collars/dampers to be fully exposed
label | 6df8425a-be28-5163-90c3-ef96f84662d0 |  | note | Acceptance Criteria: Inspected and confirmed
label | 46586813-f301-5fc5-8cdd-f484d08295a9 |  | note | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | 2b9c624f-800b-580a-b2e5-282ff1c3bf47 |  | note | Buildup Inspection Code: W
label | c94a8cf1-dbc4-5682-b1a6-c386855fb617 |  | note | Lendlease Inspection Code:
label | 273318c2-663d-5d3a-966c-019a4630d449 |  | note | Lendlease Sign/Date:
label | 694590eb-25f2-56bf-958f-9a241be2d110 |  | note | Lendlease Comment/Result: