## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP 006 FF&E Installation |  |  |  |  | Yes | ITP 006 FF&E Installation | 08ca46ea-87be-47c2-89fb-f482a3774242
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | c2abbd2b-d4f6-571c-9984-9e6948ac37d6 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | cdea156b-6e64-5fb1-b681-b91dfd2f15f0 |  | note | Buildup Inspection Code: W
label | 980d5aa4-82ed-5e52-b203-7a7288cead5c |  | note | Lendlease Inspection Code:
label | 3c41905e-c207-5f67-a938-658bf2485f2f |  | note | Lendlease Sign/Date:
label | f338ce94-7878-5fa1-8cb4-7a5c7a3980a3 |  | note | Lendlease Comment/Result:
checkpoint-group |  |  | section | FFE Installation
checkpoint-status |  |  | checkpoint | All of FFE Products must approved by Lendlease
label | 7b941512-a948-52e6-a239-fa44f2b86e94 |  | note | Acceptance Criteria: Sample Form Approval Finish Schedule
label | 2476dde4-901d-5315-b446-b991352e4e4e |  | note | Series: BR3ADL2-Internal Architectural Details
label | 2eba437b-70ef-5522-b383-cb4a56854bc0 |  | note | Buildup Inspection Code: W
label | 4437e369-66eb-5e64-9c91-7c519ba42d13 |  | note | Lendlease Inspection Code:
label | 89d32fcf-2742-5990-8709-36d25d0bebde |  | note | Lendlease Sign/Date:
label | afe6db77-25da-5108-821f-ef0bf37a3c2f |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | All of FFE products have to supported by Noggins
label | d8788752-c124-5d1a-a9a0-b69427392a7c |  | note | Acceptance Criteria: Noggin Markup Plan
label | 5210f45f-d20a-5472-91b6-59971d2b555c |  | note | Buildup Inspection Code: W
label | 830b6ebc-a10b-560e-9287-3462a5b3086c |  | note | Lendlease Inspection Code:
label | 1a4909eb-61a0-5f4b-a518-49d53182655e |  | note | Lendlease Sign/Date:
label | 3b02f4a1-2066-510b-a5e7-be5f34766ae6 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | No unreasonable gap or holes on the wall
label | 986e03fa-ca5e-517a-811d-8bb6ae807fce |  | note | Acceptance Criteria: Eye Inspection
label | 67e58164-ecf1-5d39-b7a6-d3d3f2990d98 |  | note | Buildup Inspection Code: W
label | 259b4e7c-afe8-5374-8ac6-29e590bb7359 |  | note | Lendlease Inspection Code:
label | 838e04e2-1556-5354-971e-9ff8dce427ce |  | note | Lendlease Sign/Date:
label | 4a882c14-1ada-542d-9cbb-7f9cff49f8b2 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Height and location must follow the requirement
label | ac65213f-9b9d-5da2-b2da-b648bc4cb4e3 |  | note | Acceptance Criteria: Noggin Markup Plan
label | 8475da4a-1e91-58e2-a596-210dd552bbd1 |  | note | Series: Series: BR3ADL2-Internal Architectural Details
label | 98331a6a-60d7-5c3c-a8a6-00b605eab0ab |  | note | Buildup Inspection Code: W
label | c0b67e02-fa98-50ec-bc59-1eec84112fdb |  | note | Lendlease Inspection Code:
label | 9f80e201-7971-51b7-8b45-4887c997ad17 |  | note | Lendlease Sign/Date:
label | eab2375b-8f0b-57c9-a6e6-bae18874f1f8 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | FFE installation should not affect the wall finish. The wall with good patching as well
label | f0fb56bb-bf84-5047-93b3-cd1728b5a6e4 |  | note | Acceptance Criteria: Eye Inspection
label | 8cc2db58-904f-5a05-8bfd-ae379749800f |  | note | Buildup Inspection Code: W
label | 05caedf7-ac78-5780-9890-b875af2c3399 |  | note | Lendlease Inspection Code:
label | ac3a2cb2-75fa-5252-bbf4-726bfd519759 |  | note | Lendlease Sign/Date:
label | 90d23d2b-4e7e-5d14-83ea-51d1e0389e88 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | e89047ff-97c4-59ea-a5c1-f5da1d49dc85 |  | note | Buildup Inspection Code: W
label | 0a70d048-2224-5748-afbb-1b895bf8310d |  | note | Lendlease Inspection Code:
label | 1b6b92f5-4c1b-52a5-adc2-3f7110e541b2 |  | note | Lendlease Sign/Date:
label | ce46cd0e-1de2-5a83-993d-3b20b9076e2f |  | note | Lendlease Comment/Result:
checklist-flat |  |  | checklist | ITP 004 Door and Door Hardware Installation |  |  |  |  | Yes | ITP 004 Door and Door Hardware Installation | 0c672970-0fa6-4c38-811b-70dcc78847b4
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | 079f1112-3dab-5166-9032-b34d1851e645 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 1d417e47-3d76-588e-b45d-6bbd63550dde |  | note | Buildup Inspection Code: W
label | 4bacbea9-05ce-5d43-817f-8fea16687f3a |  | note | Lendlease Inspection Code:
label | fbfa84e4-1964-5782-a2dc-f736a6da97f2 |  | note | Lendlease Sign/Date:
label | cee7f272-3617-5cef-b4b8-28bc0dcb3e51 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Opening dimension checked against drawings and Setout, Door types and leaf size confirmed against partition plan
label | d4d3e4aa-09b6-5528-8086-30875d826a75 |  | note | Acceptance Criteria: Latest Drawing Revision Checked
label | dd9402a0-7ac4-5a58-ac3a-c72276aa4fed |  | note | Series:BR3ADB2-Wall Setout Plans Door Schedule - BR3AT1332[C2]
label | 7744bfcf-bdc9-5773-890d-9495b59be50f |  | note | Buildup Inspection Code: W
label | bfa4b46a-5e52-547a-a95f-17542b1467c2 |  | note | Lendlease Inspection Code:
label | 291c6628-f1f2-5683-a367-72e2ed7d8357 |  | note | Lendlease Sign/Date:
label | 5313176f-2f62-593a-b75b-f2a3b3a161f2 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Door frame installed as manufacturer's specification to Top, bottom and both sides
label | 84dbf7cc-2ccb-51c0-805b-b8e2ac939dde |  | note | Straight and plumb and square, no sharp edge, gap less than 20mm, sealed with silicone
label | d1a25443-b62a-5318-a913-cad0a4996da8 |  | note | Buildup Inspection Code: W
label | 3de69013-951f-5b70-94aa-d87bfa861435 |  | note | Lendlease Inspection Code:
label | beb7b193-c072-53d1-861e-f1c26448cb10 |  | note | Lendlease Sign/Date:
label | db50b057-b4e7-55fd-bd0b-3637c92cd5bb |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Door Hardware Installation and Check
label | df10ef95-1f84-5134-b943-2c6fd71b8cdd |  | note | Correct Hardware type followed as shop drawings. All of door hardware followed the finish Schedule
label | 590f4940-cebd-5a2f-97c2-9c8444a8803b |  | note | Buildup Inspection Code: W
label | dae28c75-73c7-5dce-8fb8-a70373d64b74 |  | note | Lendlease Inspection Code:
label | e013579c-73ab-5a05-8cba-cc8cdff23cf9 |  | note | Lendlease Sign/Date:
label | fb0a7ae2-ed69-5986-8eeb-fcf83310d943 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Door Smoke sealed cabinet
label | 4d1d4426-8737-5d0b-a2c3-769368c14f83 |  | note | Acceptance Criteria: Latest Drawing Revision Checked
label | 77012489-62ea-5d7f-a7c7-3c5c204e346c |  | note | Buildup Inspection Code: W
label | b2f4f504-fc55-59ce-a20b-b9b8d80848e6 |  | note | Lendlease Inspection Code:
label | d9cda0ae-4c34-5ecb-9e46-2fe5002675a8 |  | note | Lendlease Sign/Date:
label | b0ebfa4a-36bd-5805-846d-5aa7fa1622e8 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | b9015113-9735-5e31-8feb-555878035277 |  | note | Buildup Inspection Code: W
label | 63748b82-7903-58d6-a7d2-eaec6cf483f0 |  | note | Lendlease Inspection Code:
label | e55964b9-de8b-5764-bb5d-e1ea31395b53 |  | note | Lendlease Sign/Date:
label | e46b8b7f-b943-5047-9c77-a2d6638d7176 |  | note | Lendlease Comment/Result:
checklist-sectioned |  |  | checklist | ITP 005 Installation of Ceiling System |  |  |  |  | Yes | ITP 005 Installation of Ceiling System | 84b627c3-f0ff-4451-a68d-c6a9df2d5929
checkpoint-group |  |  | section | Ceiling Framing
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | 8ccb6fb9-e176-51a1-9930-647eb93019c7 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | d10cdab7-0ac7-543d-98cc-da1170e92335 |  | note | Buildup Inspection Code: W
label | 1d5f4c46-27a8-534c-9c65-d86867d052cd |  | note | Lendlease Inspection Code:
label | 461b89ad-4ac1-559b-a7a6-a18698c58f37 |  | note | Lendlease Sign/Date:
label | 47a9b1be-9676-522f-a097-b2b72f1d307f |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Ceiling framing dimension and FCL checked against drawings and Setout, Ceiling types confirmed against RCPs
label | 3f9936b0-c863-5714-b294-0003009def40 |  | note | Acceptance Criteria: Latest Drawing Revision Checked
label | d30cb238-495a-5392-af9b-98eed58a6c52 |  | note | Series: BR3ADG1-Reflected Ceiling Plans
label | 552e894c-c89e-580c-a409-fd5ab70c6048 |  | note | Buildup Inspection Code: W
label | c839f2b5-4fdc-57c5-907e-2e06a5a93fc9 |  | note | Lendlease Inspection Code:
label | 4dfb9345-9064-5c84-bd66-b31503cb7ebf |  | note | Lendlease Sign/Date:
label | d1627f13-8bfc-594e-8656-c89a8b350be3 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | All above-ceiling services are installed and ready for ceiling framing
label | f65348f6-8492-5c19-bd98-f062983230bf |  | note | Acceptance Criteria: Confirm with Lendlease that all wall service rough ins have been completed and approved prior to sheeting
label | a41909cf-86dc-5969-b343-a39a5403dd5d |  | note | Buildup Inspection Code: W
label | ffe06e91-133f-5407-852f-7a9a8a0fe592 |  | note | Lendlease Inspection Code:
label | ca2052ef-38e9-5488-a701-b76cf982199f |  | note | Lendlease Sign/Date:
label | 0f8b2a47-2e21-56e8-8b86-202a8cb3db88 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Ceiling framing completed as Rondo designs
label | 16003e51-59c9-522c-abfc-0732c2c68e2d |  | note | Acceptance Criteria: Suspending point max 1200mm*1200mm Grid, TCR @max 600 space and max200 from wall, FC @max 600 space and max 100 from wall. Correctly braced. Two sides fixed and two sides free
label | 39e47704-171c-5f50-892e-9f9e80fdc464 |  | note | KEY-LOCK Suspended Seismic Ceiling Specification
label | 1ac816da-c950-509a-a231-edd7dc0c97cc |  | note | Buildup Inspection Code: W
label | 30a4d41c-7f58-5350-a182-19d3597dfbb6 |  | note | Lendlease Inspection Code:
label | eb1c763b-fc3f-5ffe-93f5-e79615c2e41f |  | note | Lendlease Sign/Date:
label | 5e9209a7-6247-5160-b4d1-611346153875 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Bulkhead and Bracing completed as Kanuf designs
label | e6954f65-ae15-5698-82b7-bbe8710e1b87 |  | note | Acceptance Criteria: Anchor used with Load sharing washer
label | bc36b04b-aed0-5fc9-89c6-f4e2a6611845 |  | note | KEY-LOCK Suspended Seismic Ceiling Specification
label | 9cf89332-dd15-5ea8-b1fe-76953db87453 |  | note | Buildup Inspection Code: W
label | 602a3962-eea4-5a1b-825c-55ab62090b43 |  | note | Lendlease Inspection Code:
label | b6130cab-9e10-5c91-8ae8-23c2e4b4af5b |  | note | Lendlease Sign/Date:
label | f6f0bcfc-be8f-52c4-a902-da27f69c5be6 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Allowance for access panels and service penetration (Lights and Grill)
label | c957dfe0-aeac-5f97-8ac9-5ecf8f960c27 |  | note | Acceptance Criteria: Framing not in the way of services or AP
label | 1588148f-c996-5b54-ba00-551dd167d4fe |  | note | Coordinated RCP drawing series
label | cc0a5fa1-96c1-5a77-82a0-b5d6ba63e3a3 |  | note | Buildup Inspection Code: W
label | 0c6acd99-8911-50b0-ae91-ee9967210613 |  | note | Lendlease Inspection Code:
label | 421fd30f-2043-5753-94fe-a1a8b481d05c |  | note | Lendlease Sign/Date:
label | 2b03106d-a31c-5dad-8525-3987e4b78f47 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Timber Noggins and Ceiling support installed as required
label | 3d0e936a-9a34-5137-8bfb-4c4484d824d9 |  | note | Acceptance Criteria: Reference that set out of noggins to be checked against Room Layout sheet Elevations
label | 97bfef7d-09a8-5842-9cc0-bbfa51d6a2b3 |  | note | Buildup Inspection Code: W
label | 5d1a398d-8229-5e9a-b202-b48c0af4a5b3 |  | note | Lendlease Inspection Code:
label | d6e390ca-39ca-555a-91bb-aadc0fd67c99 |  | note | Lendlease Sign/Date:
label | a1a0483d-36ae-5e74-b321-f8b0d202e0ad |  | note | Lendlease Comment/Result:
checkpoint-group |  |  | section | Close Ceiling
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | 0f8736d5-982c-5ae2-b395-cd414b5f54d1 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 08a95d04-cc0c-5114-8a7f-44fc4e146b76 |  | note | Buildup Inspection Code: W
label | 43fdadd0-06f6-59eb-b2e6-0f4ce31ee91c |  | note | Lendlease Inspection Code:
label | 58d07f9b-9e07-509c-ae86-5cc153847f73 |  | note | Lendlease Sign/Date:
label | e58637b2-6bbf-5890-ab2d-05287c2da1e3 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Check all services roughed in and not using ceiling frame as a support, all seismic supports have been installed for service by others, ceiling closeout checklist received by Lendlease
label | 81aff81c-6fc1-5adf-a5f0-cef7f92d7530 |  | note | Acceptance Criteria: Minimum 3mm gap kept from ceiling frame
label | 442564ea-bd6f-5a30-822a-d69f4c17c4ca |  | note | KEY-LOCK Suspended Seismic Ceiling Specification
label | 2def8a40-fadc-5f90-9b0d-787a04037d3a |  | note | Buildup Inspection Code: W
label | 22b1b47e-4499-5b67-8be6-df8345fcf66a |  | note | Lendlease Inspection Code:
label | 80a9d84e-a346-5ffd-ad9c-68f21a65b231 |  | note | Lendlease Sign/Date:
label | 6915005f-897e-5331-be29-ea4e2eb9f0d3 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Installation of acoustic insulation to the ceiling
label | eb138e17-445d-598d-801b-35b3a3bfbfde |  | note | Acceptance Criteria: acoustic insulation must extend 900mm from acoustic wall
label | fd008660-083c-5a31-adee-89f9e54b6192 |  | note | Series: BR3ADS2-Insulation Ceiling Plans
label | 1c10d24c-8c2a-5c6d-ab8f-bd7235f4bf7b |  | note | Buildup Inspection Code: W
label | dbbb369c-a57c-5065-9bc8-2137c6a43775 |  | note | Lendlease Inspection Code:
label | 981b4a73-1046-5cdf-b198-9e6aafc1a3a2 |  | note | Lendlease Sign/Date:
label | b9de9516-6c46-53f9-8d2c-a0f964f79488 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Sheeting carried as per manufacturer’s specification, specified sheeting as per schedule. Ensuring correct layering and components and completed fixing as pec
label | 381e9365-30c1-5f31-9911-9af5317712c0 |  | note | Acceptance Criteria: Staged Fixing @200mm max centre at edges, fixing @300mm max centre in field, Staged butt joint by 600mm min. Back blocking battens used on butt joints
label | a52ac08e-47a7-5e5b-9491-53ad23dfcdf4 |  | note | BCA Report 210721: 1740 R1.0
label | 4ab56bb0-e094-5b4d-90a5-f34d1f4b94e0 |  | note | Buildup Inspection Code: W
label | 90645b15-fd70-5f41-a9e7-43453d18fd4b |  | note | Lendlease Inspection Code:
label | b1c1b48a-abe2-53d6-9faa-3415b6e2704f |  | note | Lendlease Sign/Date:
label | 7f9d52d4-ee42-5fb7-80a2-8d6ad73e6876 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Access panel installed as required
label | 422434b7-258a-55e8-8a65-83edce8e9343 |  | note | Acceptance Criteria: Correct location, square with wall or bulkhead
label | cad379e2-ec02-5510-8506-3fb8f41a8811 |  | note | BCA Report 210721: 1740 R1.0
label | 5e033fe6-82cb-505e-a202-fb24eab332ac |  | note | Buildup Inspection Code: W
label | 47fd9242-746a-51b7-978a-357dd4001931 |  | note | Lendlease Inspection Code:
label | 4c104619-e873-54ef-a6e3-a10af52d5f52 |  | note | Lendlease Sign/Date:
label | abb19fd6-5daf-5a9c-a718-6b1c89abbe49 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Caulking to acoustic / fire / smoke/ details.
label | 54c3e6f3-5bd2-56a8-9824-90a7dcf64ea3 |  | note | Acceptance Criteria: Max 20mm with slab/ column, flush
label | 96b4257a-8222-5fbd-986a-685815fd527e |  | note | BCA Report 210721: 1740 R1.0
label | d75d5fdb-a49c-58df-8d32-549a466e761d |  | note | Buildup Inspection Code: W
label | d5b45041-8403-5462-a72e-e834b197ee06 |  | note | Lendlease Inspection Code:
label | 6896b5b4-c197-5e9d-a373-c0d8db40c9ec |  | note | Lendlease Sign/Date:
label | 67b0a7d6-104a-50e9-b86e-9143a8a305c0 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Set and sand ready for painting
label | 37609a90-dfa1-5a54-93b6-f370008aba13 |  | note | Acceptance Criteria: No bubbles, no lump, square, not over sanded
label | 9bedb68a-1df9-5d81-afb8-a95263c18cd8 |  | note | BCA Report 210721: 1740 R1.0
label | e5a06a6c-1e7b-55b9-ace6-a248fb78f248 |  | note | Buildup Inspection Code: W
label | 0db4dc05-7bfa-513f-8e29-af87a573cdcc |  | note | Lendlease Inspection Code:
label | c8f63e6e-29bd-5169-953f-8f0cd8191c36 |  | note | Lendlease Sign/Date:
label | 13fb5243-f60b-54dd-b429-b9b72bc00da8 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | 1165729c-003b-53b7-9ef7-81a0fd526bef |  | note | Siniat&Rondo Inspection
label | 85ffeb7d-a733-5f59-9836-a9039ce34f6e |  | note | Buildup Inspection Code: W
label | e5334b2c-b5a1-5dde-aa1d-123f3e55de08 |  | note | Lendlease Inspection Code:
label | ff7d3e1d-ecf4-51f8-afd8-f801dcd145dc |  | note | Lendlease Sign/Date:
label | 8a624119-33c9-5f6e-a645-c1c517512a49 |  | note | Lendlease Comment/Result:
checklist-sectioned |  |  | checklist | ITP 002 Installation of Soffit Insulation |  |  |  |  | Yes | ITP 002 Installation of Soffit Insulation | 998c62c8-5cbf-4998-8a1b-341ddc1c30dc
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | c01c324e-ca5a-5d5a-82e4-7309b4f37079 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 84764a4a-1380-5a3d-bccc-cfde4673bb78 |  | note | References: Australian Standards AS/NZS 4859.1 and AS 5637.1.
label | 431a92d4-4ec9-5b7e-a5d9-03cc38e9d7e4 |  | note | Buildup Inspection Code: W
label | 5952a1c3-5743-5cbf-bcab-70c7f386869c |  | note | Lendlease Inspection Code:
label | 19df4c2a-ac1d-5444-bf28-8f8d960c4321 |  | note | Lendlease Sign/Date:
label | 43b69f2d-b2dc-52ac-a8a5-b0f71f774fbb |  | note | Lendlease Comment/Result:
checkpoint-group |  |  | section | Under Slab Insulation
checkpoint-status |  |  | checkpoint | Insulation dimension checked against drawings and Setout; Insulation types confirmed against Insulation set out plans
label | 67664a62-2bf9-5ef1-ad7a-20f84dbbbf23 |  | note | Acceptance Criteria: Latest drawing revision checked
label | 344e5c82-1a2a-5c22-a35c-cf94fc78c7fa |  | note | Series: BR3ADS2-Insulation Ceiling Plans
label | 7865c40c-2757-57ba-9c94-3aa4b0b85421 |  | note | Buildup Inspection Code: W
label | d5bd0423-9804-59b3-a1b7-18a29a202974 |  | note | Lendlease Inspection Code:
label | b168d9c4-743b-506b-8959-ef959822fb0b |  | note | Lendlease Sign/Date:
label | 1d046bce-3af5-5dca-84c1-5ed422c0f01b |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | The foil surface of the insulation board should face down
label | 68e12c8e-65a7-5693-bf6c-c9486cd14a67 |  | note | Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | d54ca48e-ecc9-529b-8899-88d2ebb93f07 |  | note | Buildup Inspection Code: W
label | ef3f997d-51e1-55ce-b958-164f03baa952 |  | note | Lendlease Inspection Code:
label | cf9fddac-d8f8-57a7-a7e0-b51b1ceea54f |  | note | Lendlease Sign/Date:
label | e4e71d62-3a6f-512d-9a08-8232254e57bc |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Fix insulation panel to concrete soffits with minimum 5 No. Appropriate insulation fasteners with a minimum head diameter of 35 mm
label | d63db5e2-9eb8-5d64-8382-65e1fd573105 |  | note | Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | 719903b8-dc99-58bb-ba3f-77474d8f26e5 |  | note | Buildup Inspection Code: W
label | baa30174-d804-56d5-9e54-bf73c2e2e479 |  | note | Lendlease Inspection Code:
label | a62ab3a9-6a07-5b87-862b-b52e3a78280d |  | note | Lendlease Sign/Date:
label | 892120b6-d132-5c11-a5ef-7bf742d7462a |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Tape board joints with a minimum 96mm wide appropriate aluminium foil tape, detail as per attached Installation Instructions
label | d374de79-4435-535d-9002-ac73933ca79b |  | note | Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | 17c064b3-c91b-5609-b2f8-5c837bbf3352 |  | note | Buildup Inspection Code: W
label | d93bab89-4635-5434-9435-e2a6257f8714 |  | note | Lendlease Inspection Code:
label | 8a88a2e3-38f5-5437-a247-dfcfc9c666d6 |  | note | Lendlease Sign/Date:
label | 557e26d3-6cff-53ae-a469-277bb20cfffe |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Exposed board edge covered with foil tape lapped 48mm on to underside
label | 60bccecf-89e2-5099-a540-0371807a933c |  | note | Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | 7fa786ae-8d4b-56e7-a06c-59ff49568be3 |  | note | Buildup Inspection Code: W
label | 32199de6-1dba-5cc4-a1a6-3a06b5a4b377 |  | note | Lendlease Inspection Code:
label | d0225112-0552-5b63-b5b3-5adc32efec40 |  | note | Lendlease Sign/Date:
label | 808139a0-0149-5769-90a6-13b7cb3fa68e |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Check against cast-in penetrations. All penetrations/collars/dampers to be fully exposed
label | 842fc341-348b-5a04-acbc-9b194866d5b6 |  | note | Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | 4cf13bae-3427-5b99-ac2a-8d9a5a6965bf |  | note | Buildup Inspection Code: W
label | 38637e23-ed5f-517d-8a1d-9c481bf2c216 |  | note | Lendlease Inspection Code:
label | ddf155b7-5950-54cc-81e3-f4ad8698637e |  | note | Lendlease Sign/Date:
label | 91890264-d785-5181-b077-7ce6489eed6f |  | note | Lendlease Comment/Result:
checklist-flat |  |  | checklist | ITP 007 Skirting Installation |  |  |  |  | Yes | ITP 007 Skirting Installation | c47f575a-98b5-488b-8d16-136a1b146f70
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | 2058b252-d911-565f-a69f-16423a69bf28 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 73ee2e30-1d0f-5b3e-8b4a-82b050c0dfdc |  | note | Buildup Inspection Code: W
label | 65cbccbb-5a2e-5d2b-95d1-b1cff001e83d |  | note | Lendlease Inspection Code:
label | 59eba635-5cbe-577e-be29-d07716bfa2ba |  | note | Lendlease Sign/Date:
label | 0332f8f4-f30d-5b62-b5d7-bfd1a5678d5b |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Set out Timber skirting size & type as per wall finish set out plan
label | 43b1d786-6fce-5b30-bc23-6b19c75d65ff |  | note | Acceptance Criteria: Latest Drawing Revision Checked
label | a1cc546e-8ba5-551f-a31a-a3ef6f6fbbd1 |  | note | Series: BR3ADL2-Internal Architectural Details BR3ADB2-Wall Setout Plans
label | 3adac091-ec2e-5e45-acbe-f817785ac2c6 |  | note | Buildup Inspection Code: W
label | b9aabbc4-7e20-566a-94be-5b62cb66d254 |  | note | Lendlease Inspection Code:
label | 4cbffd8b-dc32-59fb-a850-aa66e3ab3913 |  | note | Lendlease Sign/Date:
label | 7eca43b0-d8ad-5c50-bd36-ca8c6de13cd8 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Timber skirting installed as manufacturer's specification to Top, bottom side
label | 4936f854-7ded-5ac5-a9da-9323fdd1ed00 |  | note | Acceptance Criteria: Straight and plumb and square, no sharp edge, gap less than 3mm, sealed with silicone Ref
label | 34c3463f-26d1-58b8-9b06-eea58dfdeadb |  | note | Buildup Inspection Code: W
label | ec631d1e-e65f-55bc-b668-a9987d4f5cba |  | note | Lendlease Inspection Code:
label | 87119f2a-2b6d-5e74-a040-642392d876e8 |  | note | Lendlease Sign/Date:
label | 1dd8ec1e-8f28-5c16-97f7-54f739459639 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | No unreasonable gap or holes on the wall
label | 83b0b825-56e8-5a4c-92ba-c6656d8a29fc |  | note | Acceptance Criteria: Eye Inspection
label | 1143549d-ecad-59d5-868e-e78a0c9d1413 |  | note | Buildup Inspection Code: W
label | 80ab6abf-280a-521a-a1d2-cef1fcf76738 |  | note | Lendlease Inspection Code:
label | c6fdaa16-75e0-5898-acad-5ec8a19dc929 |  | note | Lendlease Sign/Date:
label | b583eb85-c10a-58c4-8ea5-b04b69ee6a1c |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Timber skirting fixing and inspect for damage prior to hand over
label | eee90216-f251-5476-9797-c735ba4540f3 |  | note | Acceptance Criteria: Inspected and approved
label | 80c63d5a-1cf6-518c-aff6-ceeb89fc8756 |  | note | Buildup Inspection Code: W
label | 138e049a-3b60-5c71-ac05-a45128cf169c |  | note | Lendlease Inspection Code:
label | 6813e8fc-c750-53b3-af04-1988e0e0b68b |  | note | Lendlease Sign/Date:
label | 0a06ffeb-9004-53ac-872b-293a24e314ef |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | 6ea47192-1939-5466-a098-8ee6eaea055d |  | note | Buildup Inspection Code: W
label | 779b72da-71eb-5ecc-8a95-f5a2c9689388 |  | note | Lendlease Inspection Code:
label | 38583753-7d9f-5b92-885a-0dae65accc7a |  | note | Lendlease Sign/Date:
label | c053e79e-ec61-5d28-8c50-d80c7f261444 |  | note | Lendlease Comment/Result:
checklist-flat |  |  | checklist | ITP 001 Speed Panel |  |  |  |  | Yes | ITP 001 Speed Panel | c5180ef2-7f9f-4896-ae8f-1aa92423c386
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | 8e24d5cd-ef03-5334-8145-6b0a2e38a581 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 94f3436a-1f7f-5430-aae7-0e1282c7714d |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4
label | 0b1ceb7a-e8a4-5bdd-ad5a-f20f36bce9a1 |  | note | Buildup Inspection Code: W
label | 6fa01492-440f-5711-a227-e8369ca383df |  | note | Lendlease Inspection Code:
label | 812c5813-bf1b-5bd3-bca2-6f20181e4f7c |  | note | Lendlease Sign/Date:
label | 28b48b71-6fb7-509e-8d88-b40d965335e2 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Wall dimension checked against drawings & setout; Wall types confirmed against partition plans
label | 062d1ddf-2f98-54aa-a91b-11e843ce2e71 |  | note | Acceptance Criteria: Latest drawing revision checked
label | 7e8d1535-1841-54e4-b945-ec49a1f26bb4 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Series BR3ADB2 -; Wall Setout Plans BR3ADF3 - Fire Stairs
label | 301cfe28-301f-5364-b6ba-8e716f739ded |  | note | Buildup Inspection Code: W
label | 87a44666-9082-572f-84e2-ecd8aae56dc4 |  | note | Lendlease Inspection Code:
label | 2ee0bc45-84c2-5a38-b3d3-2152ec7ad1ff |  | note | Lendlease Sign/Date:
label | 144b97c8-a67d-5dbd-b571-2c8490f8533a |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | C-Track installed as manufacturer's specification to top, bottom and both sides
label | a0751e1b-18d6-5332-94f4-c330a1fe2fd3 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | d2e3aeba-95d6-5eae-958d-8edb7ad3f94a |  | note | Acceptance Criteria: Hilti 606 Sealant applied between C-track and concrete and along internal corner. Anchor @500 Centre & max 100 from end
label | 97450deb-3dac-5af6-8f50-20ffba3bcae8 |  | note | Buildup Inspection Code: W
label | a4bbd3eb-bee1-5624-9c83-ce234029a28d |  | note | Lendlease Inspection Code:
label | 6146f5f4-2ab7-55a4-9a7b-0dcc950492a3 |  | note | Lendlease Sign/Date:
label | 6a3b3020-2d5a-5ff1-97f4-fa8f0bcf2eb8 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Panels installed as manufacturer's specifications
label | 0f5ae4bb-721a-54fe-a1a5-2cbd490884bf |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 633cd53b-9530-54d5-8026-8041b5ad2089 |  | note | Acceptance Criteria: Each panel interlocked, fixing @ max vertically 1000mm centre on joints and 250 mm horizontally, fixing @ max 500mm on C-track, 2 fixings at 45" for every corner. Sealant full placed around C-track
label | e47d1349-2acc-5ec3-abad-46151ad9c097 |  | note | Buildup Inspection Code: W
label | 1d27e422-86d5-52f3-8587-0be079f5e040 |  | note | Lendlease Inspection Code:
label | f8f0f50b-7718-548c-bf73-340c41fc03ff |  | note | Lendlease Sign/Date:
label | e617cc63-96c3-5a8c-b6d8-9b4066e57a6c |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Comprehensive first of type inspection
label | 5f18ecfd-40c6-527f-8db9-82e928697d80 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4; Supplier / Manufacturer inspection report
label | d407e042-d2bb-5cc6-af7c-6b73a2a90fa1 |  | note | Buildup Inspection Code: W
label | 23955e3c-9b8a-5eb3-bcb4-55ae656dfb55 |  | note | Lendlease Inspection Code:
label | 40fb006c-a3a9-5592-b9ba-f484b4915280 |  | note | Lendlease Sign/Date:
label | 0006cae8-e483-521c-bb98-28fcdb9866c2 |  | note | Lendlease Comment/Result:
checklist-sectioned |  |  | checklist | ITP 003 Installation of Internal Partitions |  |  |  |  | Yes | ITP 003 Installation of Internal Partitions | ef6f2698-0b89-4dbc-8f39-391ff3fc32b6
checkpoint-group |  |  | section | Wall Framing
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | e2aef0d4-0b60-5db8-af66-1f8d981a3696 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | af7cabba-94fe-5233-9279-04d7cd377b6a |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | d0df392b-e109-55bb-87aa-a4d434f44b3d |  | note | Buildup Inspection Code: W
label | 493388d7-c8b0-5e4e-aa1f-699619b387ff |  | note | Lendlease Inspection Code:
label | 9d239220-e801-5615-af30-f8e916306d84 |  | note | Lendlease Sign/Date:
label | b687bb69-c8b9-5d7d-bb08-ef8c8c3d85a2 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Wall framing dimension checked
label | facdcd4c-c097-5051-8bc1-fd33e6278b10 |  | note | Slotted Deflection Track used; additional noggin installed for onside sheeting frame
label | 7629c058-e3b8-5c40-a998-3aac8107133e |  | note | Series: BR3ADB2-Wall Setout Plans
label | 014b9299-9cdf-5abe-b74d-e73aaf9d7b76 |  | note | Buildup Inspection Code: W
label | 8d306349-8237-5e87-9ca7-1b701ad18c69 |  | note | Lendlease Inspection Code:
label | d098fec5-8c16-5d39-a59d-b0098d67f76f |  | note | Lendlease Sign/Date:
label | 7c17454b-c71e-5e8d-ad4c-4041a6d242b2 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Allowance for access panels and service penetration
label | 220116aa-0d69-56bd-87db-ce60ed4ad21b |  | note | Acceptance Criteria: Bridging Track supported by offcut studs
label | cdb1e887-3870-5e18-9105-202b8d2db63d |  | note | Internal partition designs: 10246-22-001 -SK00 - 10246-22-001 -SK15
label | 81cdbcab-bbfa-57c1-9dbf-61fbc0d2949d |  | note | Series: BR3ADB2-Wall Setout Plans And BR3ADL1-Wall Type
label | e4900ef6-e3e8-581e-9b93-57b6c459f80e |  | note | Buildup Inspection Code: W
label | 535a36b6-671f-50e6-a7f1-38d63f51a520 |  | note | Lendlease Inspection Code:
label | 56fc0283-1d6d-5e8e-955b-1d5c8dc02489 |  | note | Lendlease Sign/Date:
label | 1bfcc0c3-36e1-5731-896d-1e16239eaa4d |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Openings (Including doors, windows, removable parts) installed to correct position and height, with right opening towards, plumb and square, as per Rondo designs
label | e7080cbc-3632-53e8-89ba-344f3e4d4fb7 |  | note | Acceptance Criteria: Jamb header or sill used correct components
label | 8d41f137-05e6-5b46-8064-e0db49d69029 |  | note | Internal partition designs: 10246-22-001 -SK00 - 10246-22-001 -SK15
label | 50cb2912-9bdf-5dba-807b-f2339c4c8a20 |  | note | Series: BR3ADB2-Wall Setout Plans And BR3ADL1-Wall Type
label | 39d8f68a-bf3a-5f5a-a642-553a6bc6c6a8 |  | note | Buildup Inspection Code: W
label | 1b6e1930-0a58-5103-94e5-d20dfaa2f338 |  | note | Lendlease Inspection Code:
label | b70921a4-5185-51e9-ba54-b16d68d8be28 |  | note | Lendlease Sign/Date:
label | 712e82cf-46c3-535c-8f7e-15edbb5b0964 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Plywood Noggins and structural stud installed for all fixtures
label | 9dbfae9a-a961-5099-a354-11839b430be0 |  | note | Acceptance Criteria: Reference that set out of noggins to be checked against Room Layout sheet Elevations
label | 99b566fc-ac74-5e97-80b4-b0dd9e2de540 |  | note | Internal partition designs: 10246-22-001 -SK00 - 10246-22-001 -SK15
label | 4e0cd057-eb0d-506d-ab87-bf1c63f14a74 |  | note | Series: BR3ADB2-Wall Setout Plans And BR3ADL1-Wall Type
label | 2050e76c-a7d1-5552-9272-da98ce3e3de4 |  | note | Buildup Inspection Code: W
label | 11772af1-82d5-5f2b-a2f6-a10ca2fd1722 |  | note | Lendlease Inspection Code:
label | 23d65783-1b76-5ad0-8761-8e1b29046ff8 |  | note | Lendlease Sign/Date:
label | d40c2665-f578-53aa-98e5-ac9f5a55f84b |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Door and window Frame installed as per manufacturer's specification stud installed for all fixtures
label | cfa71d56-c1c1-5f4c-b56c-fee471478e24 |  | note | Acceptance Criteria: Plumb, square and same height, core-filled
label | db56ea00-04eb-5734-9455-d64866cad669 |  | note | Internal partition designs: 10246-22-001 -SK00 - 10246-22-001 -SK15
label | 7fbebbdf-3ac1-5bec-85af-d507afa3b021 |  | note | Series: BR3ADB2-Wall Setout Plans And BR3ADL1-Wall Type
label | 23e05484-4d0f-51fb-a8f6-59b900d5f813 |  | note | Buildup Inspection Code: W
label | b6985a2a-eadb-5da5-a6db-50a8b962b4e8 |  | note | Lendlease Inspection Code:
label | 1e6f4851-be82-545a-b705-4eb6b7be66c1 |  | note | Lendlease Sign/Date:
label | 086fe43f-01b3-5cc3-b728-2316176810d0 |  | note | Lendlease Comment/Result:
checkpoint-group |  |  | section | Sheeting (One Side)
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | 9943d771-e801-5a1a-972a-eff94af52e19 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | ebaf8bc6-a965-57a9-8a3a-c957f8bcd22f |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | 3bca9619-45d6-57c3-ba89-8110fd3f38ed |  | note | Buildup Inspection Code: W
label | 866dbe68-c41b-5f88-b65e-31cb0f5827ad |  | note | Lendlease Inspection Code:
label | 0ede35d8-3042-539f-bc0c-45dd4189c60c |  | note | Lendlease Sign/Date:
label | 02874717-1b18-5604-9fc3-9c70cec1839f |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Sheeting carried as per manufacturer’s specification, specified sheeting as per schedule. Ensuring correct layering and components and completed fixing as specification
label | 3ef4865a-9df9-56da-9582-1b216aaf6ca1 |  | note | Acceptance Criteria: Staged Fixing at edges, fixing@50mm max centre in field, Staged joints min 300 mm between different layers
label | 8bbcd3a0-8767-5bb6-a324-5d6572ef2419 |  | note | Series: BR3ADB2-Wall Setout Plans And BR3ADL1-Wall Type
label | 8b379e89-f9b9-5afb-a8bd-d22cf82692f8 |  | note | Buildup Inspection Code: W
label | 8567e648-c220-54ab-92d6-f4113934b5aa |  | note | Lendlease Inspection Code:
label | 14e039f2-6705-564c-bfb0-5cc2dbd47c42 |  | note | Lendlease Sign/Date:
label | 2fbfe656-c759-593a-b5a3-486fbf5c9623 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Caulking to acoustic / fire / smoke/ details.
label | 5e9c85c0-7023-5110-806f-0c78dc656d46 |  | note | Acceptance Criteria: Max 20mm with slab/ column, flush
label | 2d0ab5b4-1b10-5cb8-82a0-c08c72959b4d |  | note | Series: BR3ADB2-Wall Setout Plans And BR3ADL1-Wall Type
label | c51e7ec8-e389-560b-952d-6454a9dde7a9 |  | note | Buildup Inspection Code: W
label | 80428c71-85d9-5c4a-9a9f-fb07f6d1ece3 |  | note | Lendlease Inspection Code:
label | 8fde32dc-bb85-51d4-b134-7bc642ba73d1 |  | note | Lendlease Sign/Date:
label | d597d094-66b2-53fc-99f1-40796beaa4a8 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Penetration sheeted and sealed as per builder's drawings
label | f5c5d73d-510d-5a8e-ac74-b7ab9a978a06 |  | note | Acceptance Criteria: Opening square and flush, fully sealed
label | 45c12722-6ca6-52d2-b2fb-73d2eb042b25 |  | note | Series: BR3ADB2-Wall Setout Plans And BR3ADL1-Wall Type
label | b9b822f8-bcae-5e79-8476-402600f22af4 |  | note | Buildup Inspection Code: W
label | 9b6c8c08-42be-5014-96aa-866ad5dadaff |  | note | Lendlease Inspection Code:
label | 514f70e1-ef7b-5379-b42f-2156b385dcee |  | note | Lendlease Sign/Date:
label | 209295b4-8de8-56e3-9bb4-a98c22477c91 |  | note | Lendlease Comment/Result:
checkpoint-group |  |  | section | Sheeting (Close Wall)
checkpoint-status |  |  | checkpoint | All in wall Services signed off by other trades, wall closeout checklist received by Lendlease
label | dc3c429c-b981-5776-8b1f-8bec016aca1b |  | note | Acceptance Criteria: Confirm with Lendlease that all wall service rough in have been completed and approved prior to sheeting
label | 0c3107ca-eaad-5b38-be1e-ecdb1d723184 |  | note | Buildup Inspection Code: W
label | 51ceebac-27fd-516b-aa82-0aa9020750ab |  | note | Lendlease Inspection Code:
label | 76b8352b-8228-55fe-809b-537f59bd9629 |  | note | Lendlease Sign/Date:
label | 3685800b-c7c9-5c83-a13e-d379bc810c55 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Insulation completed as per acoustic report, partition plans and spec
label | a9408b2b-c354-54c1-9074-b588d00dedf1 |  | note | Acceptance Criteria: As required Insulation, no gap can be seen
label | 4bea2370-f9b3-511a-9f44-9705d4da30c4 |  | note | Series: BR3ADL1-Wall Type
label | c41427b5-297c-57f5-bbdd-6bb0b3b7e211 |  | note | Buildup Inspection Code: W
label | 4e599fd2-e633-5845-af92-de72cf20d5fa |  | note | Lendlease Inspection Code:
label | 4d7c8434-7ac8-5df5-8b68-395c956685e4 |  | note | Lendlease Sign/Date:
label | b63f59f1-a282-57fc-b2c0-d01665850b12 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Plywood Noggins and structural stud installed for all FFE
label | 50747465-0c76-5314-8655-3d22908c401f |  | note | Acceptance Criteria: Checked against current RLS
label | bbbf86c1-87de-5b67-845a-539fcd054c31 |  | note | Series: BR3ADL2-Internal Architectural Details
label | 1e59e90c-1e72-569c-bbb7-871bcad14eda |  | note | Buildup Inspection Code: W
label | 65f182e6-8b78-5f09-ad8c-8213540b341d |  | note | Lendlease Inspection Code:
label | 1cf7f24a-f68b-50f6-81c8-38074659e548 |  | note | Lendlease Sign/Date:
label | ae8dc7d6-dfbc-5030-a162-042eb8093b48 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Close wall
label | 2f71f231-7938-53c4-990a-835a81c5a7fa |  | note | Acceptance Criteria: Staged Fixing at edges, fixing@50mm max centre in field, Staged joints min 300 mm between different layers
label | a00ae179-afd6-5b86-a5e8-70ae4f61542a |  | note | Series: BR3ADB2-Wall Setout Plans And BR3ADL1-Wall Type
label | 493f2516-0540-5809-a6d3-ca0c996e3663 |  | note | Buildup Inspection Code: W
label | 0c7a9335-db2f-5a11-9d51-5a759b85e54a |  | note | Lendlease Inspection Code:
label | 327bbdb4-1c3d-51fc-84d7-fdab4c4c4588 |  | note | Lendlease Sign/Date:
label | 3d2d3e7d-a6fe-5041-a73a-a262e97b5cc0 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Caulking to acoustic / fire / smoke/ details
label | 00a349c0-17a5-5f35-9977-f14f5fa41db7 |  | note | Acceptance Criteria: Max 20mm with slab/ column, flush
label | b63dfd26-2124-577d-b3bf-3de1f47b66c3 |  | note | Buildup Inspection Code: W
label | bea71560-f74f-59cb-b69c-f68778c2d15f |  | note | Lendlease Inspection Code:
label | 81d31c1e-d709-51a3-b2b5-59c4d398931e |  | note | Lendlease Sign/Date:
label | be0469f5-7da8-5af8-a1ca-7a44c46851ef |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Set and sand ready for painting
label | 1ca7f117-78ec-5545-84e6-6ba32ff9e494 |  | note | Acceptance Criteria: Meet Level 4 of finish requirement
label | 5713d3c3-1205-5b5e-b422-a78512a9fa39 |  | note | Buildup Inspection Code: W
label | bb33d115-4371-5c16-bf82-4801c25764f7 |  | note | Lendlease Inspection Code:
label | fd456b4d-1fb8-5a51-a80c-4823fae57c6c |  | note | Lendlease Sign/Date:
label | fb6c41fc-7646-5489-92a7-77e6f48d9ff1 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | d610bc12-4edf-55c5-b624-9ec57f5419ff |  | note | Acceptance Criteria: Siniat & Rondo Inspection
label | 64aad2ca-ff64-59c8-8d51-c7821c010a6d |  | note | Buildup Inspection Code: W
label | 4a69b3f7-78ac-5d7f-a752-344c49c7ddba |  | note | Lendlease Inspection Code:
label | 89e13239-9ef6-548f-b169-c5e8465a6b0d |  | note | Lendlease Sign/Date:
label | e38834a2-3109-53cd-a68d-5dd5d66b5ea8 |  | note | Lendlease Comment/Result: