## Sheet3
Inspection and Test Plan Te Ara o Te Ata Concrete Culvert - ITP - 012
This ITP has been prepared by |  |  | Reviewed by [as applicable] |  |  | Reviewed by DSR | [7 empty] | Approved by [as applicable]
Rev Number | Name | Signature | Date | Name | Signature | Date | Name |  | Signature |  | Date |  |  | Name |  | Signature |  | Date
Rev 01 | Libby Whyte | L.W | 2023-02-08 | William McCracken | W.M | 2023-02-20 | Matthew Wenborn |  | MJW
Rev 02 | Matthew Wenborn | M.J.W |  |  |  | 2023-05-02 | Danny Beasant (Geotechnical Engineer) |  | DB
Rev 03
Rev 04
ITP NO: 012 |  | Project: Te Ara o Te Ata | [5 empty] | Method Statement Ref: |  |  | Rev.B
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. | [7 empty] | Responsibilities PE = MTM Alliance Construction TWD = Temporary Design Team
Activity/Specification: Concrete Culvert | [7 empty] | Area Location / Work Breakdown: Length of Mt Messenger Bypass
Item | Construction Step or Material |  | Specifications and Standards |  | Acceptance criteria and testing |  |  |  | Method (H,I,W,R) |  |  |  | Verifying Records Checklists, Test and Supplier Certificates |  | Site Engineer approved | DSR Engineer verification | Certified Complete (Date, relevant checklist title/lab report number etc)
Responsible [tick]
[5 empty] | Method/Description | Test frequency |  | Conformance Criteria | Contractor | Designer | Client | Lab
1.0 Pre-Construction
1.1.0 Pre-construction approvals
1.1.1 | Construction Environmental Management Plan |  | MMA-ENV-RMP-RPT-15631 |  | Document Review | Prior to work starting |  | Ensure all crew members are briefed on the CEMP | H |  |  |  | Signed CEMP
1.1.2 | Construction Work Plan |  | CWP |  | Document Review | Prior to work starting |  | Ensure all crew members are briefed on the CWP | H |  |  |  | Signed off CWP
1.1.3 | IANZ accredited testing organisation |  | Details of proposed testing organisation |  | Document Review | Once prior to works commencing |  | Designer review and approval required on all test equipment calibration certificates and frequency on testing | H | H |  |  | Test and supplier certificates
1.1.4 | IFC's specification |  | MMA-DES-DNG-E1-10686 |  | Document Review | Once prior to works commencing |  | Obtain copy of the Concrete Culvert Specification | H | H |  |  | IFCspecifications or Written approval from PAB
1.1.5 | IFC drawings |  | Obtain IFC drawings |  | Document Review | Once prior to works commencing |  | Ensure all drawings are approved and of the latest revision, or written approval from PAB | H | H |  |  | IFC drawings or Written approval from PAB
1.1.6 | Approved Drainage Strings |  | MMA-DES-GEM-E1-REF-30611 |  | Document Review | Every new Drainage Line and prior to work commencing |  | Designer to confirm and approve strings to be loaded on the equipment | H | H |  |  | IFC Cover Form
1.1.7 | Approval of stockpile location |  | MMA-DES-GEO-E1-SPC-3859 |  | Document Review & Approval | Prior to works commencing |  | Approved stockpile location | H | R |  |  | Written approval from DSR
1.2.0 Material compliance
1.2.1 | Materials - pipes and fittings |  | TNZ F/3 |  | Confirm pipe diameter, class and jointing type as shown on the drawings and that pipes are in correct and good condition. | Each delivery to site |  | Accepted by DSR | H | W |  |  | Onsite Check Sheet
1.2.2 | Materials – pipes and pre-cast units (wingwalls) |  | TNZ F/3, AS/NZS 4058, AS 1646, NZS 3109 and NZS 3101 |  | Specification compliance – manufacturer’s certificate to TNZ F/3 for pipe and pre-cast units | Each delivery to site |  | Provided to DSR | H | W |  |  | Compliance Cettifcates
1.2.3 | Materials – Grading for Bedding, Haunch and Sides Zones AP20 |  | MMA-DES-DNG-E1-10686 and CPAA guidance "Selecting Materials for Bedding Steel Reinforced Concrete Pipe" |  | NZS 4407 Test 3.8.1 (or similar approved) Determination of the particle size distribution Standard method by wet sieving | 2 per 400m3, 3 per 400-1500m3, 4 per 1500-4000m3 and for over 4000m3, 1 additional test per 1000 m3 |  | Material conforms to grading envelope . | H | W |  | I | Test Report
1.2.4 | Materials – Testing for Bedding, Haunch and Sides Zones AP20 |  | MMA-DES-DNG-E1-10686 and AS/NZS 3725:2007 Table 6 |  | Determination of the linear shrinkage NZS 4402.2.6 Determination of the Weathering Index NZS 4407.3.11 Determination of the Crushing Resistance NZS 4407.3.10 | 2 per source then 1 per 1000 m3 |  | Material conforms to: Maximum linear shrinkage (Maximum of 10%) Weathering Index (AA or BA ) Crushing Resistance (> 100 kN ) | H | W |  | I | Test Report
1.2.5 | Materials – Compaction Curves Bedding, Haunch and Sides Zones AP20 |  | AS/NZS 3725:2007 |  | Establish a relationship between MDD and DI (density index) to determine the target MDD (NZS 4402.4.2.1 for the minimum dry density and NZS4402.4.2.2 for the maximum dry density). | 3 no. tests per source with minimum 5 points |  | Accepted by DSR | H | W |  | I | Test Report
1.2.6 | Materials - Grading GAP 65 |  | MMA-DES-DNG-E1-10686 |  | NZS 4407 Test 3.8.1 (or similar approved) Determination of the particle size distribution Standard method by wet sieving | 2 per 400m3, 3 per 400-1500m3, 4 per 1500-4000m3 and for over 4000m3, 1 additional test per 1000 m3 |  | Material conforms to grading envelope . | H | W |  | I | Test Reports
1.2.7 | Materials - Testing GAP 65 |  | MMA-DES-DNG-E1-10686 and AS/NZS 3725:2007 |  | Determination of the Weathering Index NZS 4407.3.11 Determination of the Crushing Resistance NZS 4407.3.10 | 2 per source then 1 per 1000 m3 |  | Material conforms to: Weathering Index (AA or BA ) Crushing Resistance (> 100 kN ) | H | W |  | I | Test Reports
1.2.8 | Materials – Compaction Curves GAP 65 |  | AS/NZS 3725:2007 |  | Establish the optimum moisture content and minimum and maximum dry density. NZS4402 Supplement No 1:1988 - Test 4.1.1 or similar approved | 3 no. tests per source with minimum 5 points |  | Accepted by DSR | H | W |  | I | Test Report
1.2.9 | Materials - Structural Fill and for Overlay Zones |  | MMA-DES-GEO-E1-SPC-3859 |  | Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2 Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4 Triaxial (Single stage min. 3 samples) - BS 1377 Part 8: 1990. Methods of tests for Soils for civil engineering purposes – Test 7 or Test 8 | 1 test per 20,000m3 |  | Report Only | H | W |  | I | Test Report
1.2.10 | Material - Rip Rap - Grading |  | MMA-DES-DNG-E1-10686 |  | NZS 4407 Test 3.8.1 (or similar approved) Determination of the particle size distribution Standard method by wet sieving | 1 per source then 1 per 500 m3 |  | Material conforms to grading envelope | H | W |  | I | Test Report
1.2.11 | Material - Rip Rap |  | MMA-DES-DNG-E1-10686 |  | Determination of: Weathering Index Coarse Aggregate dry density NZS4407.3.11 Crushing Resistance of Coarse Aggregate NZS4407.3.10 Solid Density of Aggregate NZS4407.3.7.1 & 2 Point Load Strength ASTM D5731 UCS Rock AS4133.4.2.2 | 1 per source then 1 per 1000 m3 |  | Material conforms to: Weathering Index of a Coarse Aggregate (AA to CA) Crushing Resistance of Coarse Aggregate (> 100 kN) Solid Density of Aggregate (≥ 2.6 tonnes per m3) Point Load Strength (>1.5 MPa) UCS Rock (>30 MPa) | H | W |  | I | Test Report
1.3.0 Geosynthetics
1.3.3 | Visual inspection - geotextiles |  |  |  | To inspect geotextile and is the proper type and no tears, rips or other signs of deterioration. | Check each lot (1 roll) |  | Accepted by DSR | H | W |  |  | Onsite Checklist
1.3.4 | Geotextiles |  | TNZ F/7 2003 |  | Specification compliance – manufacturer’s certificate to TNZ F/7 2003 | Check each lot (1 roll) |  | Accepted by DSR | H | W |  |  | Manufactures Certifcate
2.0 Construction
2.1.0 Trench Excavation
2.1.1 | Trench Subgrade |  | MMA-DES-DNG-E1-10686 |  | Testing trench foundation material to assess is undercut is required. Scala penetrometer test as per NZS4402.6.5.2 for non-cohesive materials. The CBR value of the subgrade soils shall also be measured using the in-situ CBR test in accordance with NZS4402 Test 6.1.3. | 2 nos. scala penetrometer tests / 5m of trench 1 per ancillary structure |  | Pipe cover to permanent road subgrade greater 1.0 m - CBR >=5%, Pipe cover to permanent road subgrade 0.3m and 1.0 m - CBR >=8%, Pipe cover to permanent road subgrade less than 0.3m - CBR >=10%, Beneath temporary construction haul roads - CBR >=10% | W | W |  |  | Test Report
2.1.2 | Trench Benching |  | MMA-CON-CMA-ITP-31067 (around CU17 using the same design slope (0.5H:1V in papa rock) as the finished geo slope) |  | 1.5m benches to be constructed strating from rock (pap) top | Daily |  | Ensure all crew members are briefed on maximum slope requirments | H |  |  |  | Onsite Check List
2.2.0 Pipe Bedding and Construction
2.2.1 | Construction of embedment, bed, haunch and side zones using AP20 |  | MMA-DES-DNG-E1-10686 and AS/NZS 3725:2007 |  | Nuclear Densometer Direct Mode NZS 4407 4.2.1 or Nuclear Densometer Backscatter Mode NZS 4407 4.3.1 | 2no NDM test "sets" per 10 m max centres tests on combined lifts upto 300mm lift and minimum of test at the bottom layer, middle of pipe and top of pipe |  | HS2 - Min 90% MDD HS3 - Min 95% MDD | W | W |  | I | Test Report
2.2.2 | Construction of Overlay Zone |  | MMA-DES-GEO-E1-SPC-3859 |  | Nuclear Densometer Direct Mode NZS 4407 4.2.1 or Nuclear Densometer Backscatter Mode NZS 4407 4.3.1 . Undrained shear Strength | 1no NDM and 1no Shear Vane Test per 20m max canters at 300mm lifts |  | Min 92% Avg 95% MDD Average >150 kPa, All tests >120 kPa | W | W |  | I | Test Report
2.2.3 | Construction of pipe |  | MMA-DES-DNG-E1-DRG-4070 |  | Visual test prior to backfill above the side zones – line and level, correct installation, and joints are all sealed. | Review every 10m and witness every 25m |  | Departure from the design level on the pipeline must not exceed 20 mm Departure from the design grade of the pipeline must not exceed 0.1% | W | W |  | I | Test report
2.2.4 | Construction of Wingwalls |  | MMA-DES-DNG-E1-DRG-4070 |  | Foundation and bedding testing as per pipes, using AP65 as opposed to AP20. Visual inspection of joints between pipe and wingwall | Each Wingwall |  | Min 90% MDD | W | W |  | I | Test report Onsite Checksheet
2.2.5 | Construction of Antiseep Collars |  | MMA-DES-DNG-E1-DRG-4052 |  | Antiseep collars to be embeded 200mm horizontaly into side of trench and 400mm below base of trench. To be located every second pipe joint. Concrete strength >=25MPa | Each Anti Seep Collar |  | Accepted by DSR | W | H |  |  | DSR Inspection (Pre-Pour) Pre-Pour Checksheet
2.2.6 | Construction of Cut Off Toes |  | MMA-DES-DNG-E1-DRG-4070 |  | Cut off Toe to be embeded 1m (or note 4) from top of wingwall base, to be consructed as per IFC Drawings | Each Cut Off Toe |  | Accepted by DSR | W | H |  |  | Pre-Pour Checksheet Detail Sheets
2.2.7 | Construction of Inlet/Outlet Channels |  | MMA-DES-DNG-E1-DRG-4080, 4084 & 4093 |  | DSR to inpect geotextiles before rip - rap is laid. Max drop heights to be adhered to when placing rip-rap | Each Channels |  | Accepted by DSR | W | W |  |  | Geotextile Installation Check Sheet
2.2.8 | Fish Passage |  | MMA-DES-DNG-E1-10686, MMA-DES-DNG-E1-DRG-4060, 4061, 4080 & 4084 |  | 25% embedment depth with meandering low flow path from voild filled riprap. Spat ropes for CU-17 | Review every 10m and witness every 25m |  | Accepted by DSR | W | W |  |  | Onsite Checksheet
2.2.9 | Construction of Safety Rail |  | MMA-DES-E1-DRG-4092 |  | Constructed as per IFC Drawings | Each Fence |  | Accepted by DSR | W | W |  |  | Onsite Checksheet
3.0 Post Construction
3.1 | Survey/as-builts |  | MMA-DES-DNG-E1-10686 |  | As built survey of coordinates and invert levels, structures, and pipe ends | Every 25m |  | Departure from the design level on the pipeline must not exceed 20 mm Departure from the design grade of the pipeline must not exceed 0.1% | H | R |  |  | As-Built
3.2 | Post Construction CCTV inspection |  | Water NZ Gravity Pipe Inspection Manual |  | Check conformance with the specification and assess the asset condition post construction | To be completed following pipe construction but prior to spat rope installation |  | Accepted by DSR | H | R |  |  | CCTV log Report as per the standard