## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | OSD Tank |  |  |  |  | Yes | OSD Tank | 1b12089c-fe50-4c44-8831-5e4cdc8264bc
checkpoint-status |  |  | checkpoint | Area accessible and ready (If failed please take a photo)
checkpoint-status |  |  | checkpoint | Surface has been checked and confirmed acceptable
label | f17fcffd-1999-5c9f-86b2-266efa26419c |  | note | Mapailastic Smart
holdpoint |  |  | signoff | Signed by RCC & Tight Seal
checkpoint-status |  |  | checkpoint | Ensure walls have been scuffed
checkpoint-status |  |  | checkpoint | ECO Prime grip to walls & floor walls junctions
checkpoint-status |  |  | checkpoint | Ensure joints are treated in accordance with post completion movement tolerances
checkpoint-status |  |  | checkpoint | Caulking Preparation
checkpoint-status |  |  | checkpoint | 1st Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (1st Coat)
checkpoint-status |  |  | checkpoint | 2nd Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (2nd Coat)
checkpoint-status |  |  | checkpoint | Application to correct DFT (Ensure photo is taken) DFT required for walls (1.0mm) and floor (1.5mm)
checkpoint-status |  |  | checkpoint | Ensure all penetrations by others are sealed to ensure works are not compromised.
holdpoint |  |  | signoff | Signed by RCC & Tight Seal
checklist-flat |  |  | checklist | External Area ITP |  |  |  |  | Yes | External Area ITP | 3c811b29-bb37-4500-b252-cf71c7c38fdc
checkpoint-status |  |  | checkpoint | Area accessible and ready (If failed please take a photo)
checkpoint-status |  |  | checkpoint | Surface has been checked and confirmed acceptable
label | 3ee47697-ab93-54cb-a25e-d5bc17663376 |  | note | GCP Silcor 560
holdpoint |  |  | signoff | Signed Tight Seal
checkpoint-status |  |  | checkpoint | Primer (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 1hr (Primer)
checkpoint-status |  |  | checkpoint | Ensure joints are treated in accordance with post completion movement tolerances
checkpoint-status |  |  | checkpoint | Caulking Preparation
checkpoint-status |  |  | checkpoint | 1st Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (1st Coat)
checkpoint-status |  |  | checkpoint | 2nd Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (2nd Coat)
checkpoint-status |  |  | checkpoint | Application to correct DFT (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Ensure all penetrations by others are sealed to ensure works are not compromised.
holdpoint |  |  | signoff | Signed Tight Seal
checklist-flat |  |  | checklist | Roof Tops & Exposed Areas |  |  |  |  | Yes | Roof Tops & Exposed Areas | 6642698a-ffd6-4ffc-a915-31e337a8baab
checkpoint-status |  |  | checkpoint | Area accessible & ready (If failed please take a photo)
checkpoint-status |  |  | checkpoint | Surface has been checked and confirmed acceptable
label | a5ae34e4-3e52-5adf-8cf2-a785f9b1be76 |  | note | GCP Silcor 575 LB Floors 1.5mm DFT
holdpoint |  |  | signoff | Signed by RCC, Tight Seal
checkpoint-status |  |  | checkpoint | Primer (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 1hr (Primer)
checkpoint-status |  |  | checkpoint | Ensure joints are treated in accordance with post completion movement tolerances
checkpoint-status |  |  | checkpoint | Caulking Preparation
checkpoint-status |  |  | checkpoint | 1st Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (1st Coat)
checkpoint-status |  |  | checkpoint | 2nd Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (2nd Coat)
checkpoint-status |  |  | checkpoint | Application to correct DFT (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (Silcor Top Coat 75)
holdpoint |  |  | signoff | Signed by RCC & Tight Seal
checklist-flat |  |  | checklist | Internal Liquid Waterproofing ITP |  |  |  |  | Yes | Internal Liquid Waterproofing ITP | fca88f1d-8721-4b7c-9bca-6b509ca85772
checkpoint-status |  |  | checkpoint | Area accessible and ready (If failed please take a photo)
checkpoint-status |  |  | checkpoint | Surface has been checked and confirmed acceptable
checkpoint-status |  |  | checkpoint | Floors are scraped, vaccum and puddle flanges exposed
holdpoint |  |  | signoff | Signed Tight Seal
checkpoint-status |  |  | checkpoint | Ensure moisture content of slab is under 4.5%(Ensure photo is taken)
label | edeaeacb-8857-5543-a868-fe976a21ca86 |  | note | GCP Silcor 560 Floors 1.5mm
checkpoint-status |  |  | checkpoint | Primer (Ensure photo is taken) - SILCOR Primer BS
checkpoint-status |  |  | checkpoint | Correct curing time allowed 1hr (Primer)
checkpoint-status |  |  | checkpoint | Ensure angles are installed as per metre mark
checkpoint-status |  |  | checkpoint | Caulking Preparation
checkpoint-status |  |  | checkpoint | 1st Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (1st Coat)
checkpoint-status |  |  | checkpoint | 2nd Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (2nd Coat)
checkpoint-status |  |  | checkpoint | Application to correct DFT (Ensure photo is taken) - DFT required for walls (1 mm) and floor (1.5mm)
checkpoint-status |  |  | checkpoint | Flood Test 24 hours (Ensure photo is taken)
holdpoint |  |  | signoff | Signed Tight Seal