## Project Breakdown
Frankston Hospital AT |  |  | Checklists
QA / ITP's
L14 - South Roof
|  | Box Gutter | Box Gutter Installation checklist
|  | Insulation | Insulation checklist
|  | Roof | Roof Installation checklist
|  | Flashing | Flashing/Capping Installation Checklist
|  | Roof Penetration | Roof Penetrations checklist
L14 - South Roof Parapet
|  | Parapet Cladding | Parapet Wall Cladding checklist
L14 - North Roof
|  | Box Gutter | Box Gutter Installation checklist
|  | Insulation | Insulation checklist
|  | Roof | Roof Installation checklist
|  | Flashings | Flashing/Capping Installation Checklist
|  | Roof Penetration | Roof Penetrations checklist
L14 - North Roof Raised
|  | Roof | Roof Installation checklist
L14 - North Roof Parapet Cladding
|  | Parapet Cladding | Parapet Wall Cladding checklist
West Canopies Roof
|  | Box Gutter | Box Gutter Installation checklist
|  | Roof | Roof Installation checklist
|  | Flashings | Flashing/Capping Installation Checklist
Main Entrrance Canopy Roof
|  | Box Gutter | Box Gutter Installation checklist
|  | Insulation | Insulation checklist
|  | Roof | Roof Installation checklist
|  | Flasings | Flashing/Capping Installation Checklist
|  | Roof Penetration | Roof Penetrations checklist
CEP Exhaust Roof
|  | Insulation | Insulation checklist
|  | Roof | Roof Installation checklist
|  | Fascia Gutter | Eaves Gutter Installation Checklist
|  | Flashings | Flashing/Capping Installation Checklist
CEP Exhaust Cladding
|  | Wall Cladding | Wall Cladding checklist
Link Bridge North Roof
|  | Askin Panel Roof | Askin Panel Installation checklist
|  | Flashings | Flashing/Capping Installation Checklist
|  | Box Gutter | Box Gutter Installation checklist
Link Bridge Centre Roof
|  | Askin Panel Roof | Askin Panel Installation checklist
|  | Flashings | Flashing/Capping Installation Checklist
|  | Box Gutter | Box Gutter Installation checklist
Link Bridge South Roof
|  | Askin Panel Roof | Askin Panel Installation checklist
|  | Flashings | Flashing/Capping Installation Checklist
|  | Box Gutter | Box Gutter Installation checklist
Airlock Roof
|  | Askin Panel Roof | Askin Panel Installation checklist
|  | Flashigns | Flashing/Capping Installation Checklist
Courtyard Cladding
|  | Askin Panel Wall Cladding | Askin Panel Wall Cladding checklist
|  | Flashings | Flashing/Capping Installation Checklist
L13 North Wall Cladding
|  | Wall Caldding | Wall Cladding checklist
L13 East Wall Cladding
|  | Wall Cladding | Wall Cladding checklist
L13 South Wall Cladding
|  | Wall Cladding | Wall Cladding checklist
L13 West Wall Cladding
|  | Wall Cladding | Wall Cladding checklist
L7 Plant Wall Cladding
|  | Wall Cladding | Wall Cladding checklist
|  | Flashings | Flashing/Capping Installation Checklist
Box Gutter - Existing
|  | Box Gutter | Box Gutter Installation checklist
Overflow - Project Wide
|  | Overflow | Project Wide Overflow Installation checklist
Variations
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
OH&S
Daily Prestart Toolbox Forms
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Weekly Toolbox Forms
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
SWMS
Onsite Material Install Form1
Foremans Diary Reports
COVID Tracking Reports
Delivery Dockets | Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Checklist Library | Add Delivery Docket
Add Non Conformance Corrective Action Report
Add Offhire Information
Add Onsite Material Install Form
Add Pre-Start Tool Box
Add Tool Box Training
Add Variation
Inspection Reports | Wire Mesh Install
Handrail Install

## Example Project Area
INSERT PROJECT AREA NAME HERE
type | name | values
checklist | Insulation checklist
section | Material Inspection
checkpoint | Insulation: Roof sarking on medium weight paper
100mm glasswool on medium sarking
checkpoint | Thermal spacer: 80mm thermal spacer
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Monoclad
checkpoint | Coating Type: Standard Colorbond
checkpoint | Insulation Type: Roof sarking on medium weight paper
checkpoint | 100mm glasswool on medium sarking
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: Monoclad screws
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations checklist
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Roof Ventilator: Ventlite 410mm Roof with Colorbond base
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Soffit Cladding checklist
section | Material Inspection
checkpoint | Soffit Cladding type: 0.42mm Colorbond Matt Mini Corry
checkpoint | Top hat support: 0.75mm tophat
checkpoint | Flashing Material: 0.61mm Colorbond
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding type: 0.48mm Kliplok Colorbond Matt
checkpoint | Top hat support: 0.75mm x 25mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Matt
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Insulation under gutter: Sisalation
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 0.61mm Colorbond
checkpoint | Gutter Flashing: Colorbond to match
checkpoint | Sumps / Outlets: 0.61mm Colorbond
checkpoint | Overflows:
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Eaves Gutter Installation Checklist
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Eaves Gutter: Eaves gutter 115
checkpoint | Half round 200mm
checkpoint | Eaves Gutter Brackets: Eaves gutter 115
checkpoint | Half round 200mm
checkpoint | Gutter Flashing:
checkpoint | Stop ends: 115mm Quad stop ends
checkpoint | Downpipes:
checkpoint | Pops: 0.61mm Colorbond
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Ortech Installation Checklist
section | Material Inspection
checkpoint | Ortech Material: S50 Plain Durra Board
checkpoint | S50 Cement Sheet Faced Durra Boards
checkpoint | Durra Panel - S50 Soundsorb Fabric Finish
checkpoint | Powdercoating Durra Beams and T-Units
checkpoint | Ortech Beams: Durra Beam (Lowder)
checkpoint | Ortech T-Units: T- Unit (lower)
checkpoint | Ortech Accessories: Aluminium Angles (Bottom & Top of Panels)
checkpoint | Caulking to Precast
checkpoint | Caulking to Stub Colums
checkpoint | Durra Panel Wedges - Lower
checkpoint | Aluminium Sealing Tape - Lower
checkpoint | Ortech Screw/Fixings: Durra Beam Bolts
T-Unit Fixings
section | Installation
checkpoint | Select correct beam type and length
checkpoint | Layout beams in correct alignment
checkpoint | Select correct Tee units
checkpoint | Ensure Tee units screw fitted securely in grid
checkpoint | Durra panels installed fitted firmly into beams/tees
checkpoint | Wedge cleats installed locking Durra panel securely in place
checkpoint | Inspection durra panel for perforation
checkpoint | Repair and perforations with aluminium sealing tape.
checkpoint | Review tightness of all bolts and prior to lifting
checkpoint | Attach Ortech lifting jig
checkpoint | Elevate and visually inspect underneath for defects or misalignment
checkpoint | Confirm finsihed ceiling is free from defects
checkpoint | Place module in position and complete connections to cleats
checkpoint | Review connections prior to dis-engaging lifting frame
checkpoint | Ortech and Durra panel not exposed to weather for long periods prior to installation.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding checklist
section | Material Inspection
checkpoint | Parapet Wall Cladding type: 0.48mm Kliplok Colorbond Matt
checkpoint | Top hat support: 0.75mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Matt
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Ampelite Polycarbonate Installation checklist
section | Material Inspection
checkpoint | Material Item: Ampelite Cool lite GC 2400gsm Kliplok Profile
checkpoint | Purlin Strips for Fibreglass
checkpoint | Screws and Washers for Fibreglass
checkpoint | Other: Dual Fibreglass Roof System?
section | Installation
checkpoint | Are the oversize holes up to 15mm diameter and drilled at all fixing points
checkpoint | Are the side lap perimeters sealed with thick sealing foam strips
checkpoint | Material installed as per Ampelites recommendations.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Kingspan Installation checklist
section | Material Inspection
checkpoint | Panel:
checkpoint | Internal liner colour:
checkpoint | External liner colour
checkpoint | Buildex fixings 14 x 95mm SDS - bonded washer
checkpoint | buildex type 17 12 x 20mm stitching screws
checkpoint | 6mm Kingspan Butyl tape
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Kingspan Spec
checkpoint | Panels located correctly
checkpoint | Fixings as per Kingspan Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Ampelite EEFAS Installation checklist
section | Material Inspection
checkpoint
checkpoint
checkpoint
checkpoint
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Ampelite EEFAS system spec
checkpoint | Panels located correctly
checkpoint | Fixings as per EEFAS system Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Eurobond Installation checklist
section | Material Inspection
checkpoint | Wall Cladding - 150mm Insulated Panel - Eurobond Rainspan
checkpoint | Insulated Panel Wall Cladding - Butyl Tape to Side Laps
checkpoint | RS1 - Base Support to bottom of panels (Rainscreen 150mm)
checkpoint | Insulated Panel Wall Cladding - Airseal tape to Panel Top & Bottom
checkpoint | Insulated Panel Wall Cladding - 150mm Panel Screws
checkpoint | Wall Cladding Top Hat - 1.6mm - Ledger Angle to base of panels
checkpoint | Wall Flashing - 0.61mm Colorbond - Wall Trim - 200mm - Internal
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Top Trim - 200mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Internal Trim - 200mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Wall Trim - 400mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Foot Flashing 400mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Louvre Trim - 400mm
checkpoint | Wall Penetration - 1000mm x 1000mm
checkpoint | Wall Penetration - Downpipe penetrations
checkpoint | Wall Penetration - Outrigger screen penetrations
checkpoint | Wall Penetration - Overflows through facade
checkpoint | Butyl tape to wall flashings
section | Installation
checkpoint | Eurobond Firemaster panel to span between floor levels
checkpoint | Fireban caulking inserted to all panel joins
checkpoint | Gal support angles installed with masonry fixings
checkpoint | 300mm centres and caulked to concrete
checkpoint | 3mm top movement angle with slotted holes to allow minus 10mm + 25mm movement as per project engineer
checkpoint | All flashings installed with fireban caulking and compliant fixings
checkpoint | Panel fixed at base with stainless steel 197mm screws x 4 in each panel
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Dridesign - Zone 3 - Section C - Wall
checklist | Dridesign Installation checklist
checkpoint | Dri Design Panels - Aluminium panels - non perforated
checkpoint | Dri Design Panels - Aluminium panels - 80m2 only perforated to bleacher area
checkpoint | Insulation - Wall - Acoustic Black Perforated - 50mm
checkpoint | Metal Wall Cladding - Custom On Site Panel
checkpoint | PVC Tape to the rear of the Cassette Top Flanges
section | Installation
checkpoint | Aluminium - Small face extrusion
checkpoint | Aluminium - Wall Trim - 400mm
checkpoint | Aluminium - Window Trim - 400mm
checkpoint | Aluminium - Foot Flashing - stepped to stairs
checkpoint | Wall Penetration - Overflow slots through facade
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Rosanna Strips
section | Material Inspection
checkpoint | Insulated Panel Wall Cladding - Rosanna External Top Hats
section | Installation
checkpoint | Rosanna Strips: Straight and in correct plane.
checkpoint | Plumbness
checkpoint | Adequate Fixings according to Manufacturer's Specification
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Skyguard hail guard graing
section | Material Inspection
checkpoint | Skyguard hail guard grating
section | Installation
checkpoint | Hail guard: Sized correctly
checkpoint | Not hindering stormwater flow on box gutter
checkpoint | Adequate Fixings according to Manufacturer's Specification
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Plyboard
section | Material Inspection
checkpoint | 22mm Particleboard
section | Installation
checkpoint | Minimal gaps between particle board
checkpoint | Screwed onto purlin
checkpoint | 10 screws per board for 400mm x 800mm
checkpoint | 15 screws for board for 2000mm x 800mm
checkpoint | 20 screws per board for 3600mm x 800
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Soaker Gutter Installation checklist
section | Material Inspection
checkpoint | Insulation under gutter: 60mm Blanket
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Soaker Gutter: 0.61mm Colorbond
checkpoint | Gutter Flashing: Colorbond to match
section | Installation
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Soaker gutter installed to sizes as shown in specification and drawings.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Askin Performance Panel Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding type: 100mm / 120mm Mineral Wool Panel
checkpoint | Curved Wall Cladding type: 100mm / 120mm Mineral Wool Panel
checkpoint | Top hat support: 1mm x 25mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Matt
checkpoint | Type of Fixings: Stainless Screws
section | Installation
checkpoint | Butyl Tap to Panel Top & Bottom
checkpoint | Ledger Angle
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | METECNO SPAN PANEL INSTALLATION
section | Material Inspection
checkpoint | Panel: Metecnospan 80mm roof panel
checkpoint | Internal liner colour: Surf Mist
checkpoint | External liner colour : Surf Mist
checkpoint | Buildex fixings 14 x 175mm - bonded washer
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Metecno Spec to SHS steel member
checkpoint | Panels located correctly
checkpoint | Fixings as per Metecno Spec
checkpoint | Gun grade Butyl sealant to underside lap of panel 6mm
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## L14 South Roof
L14 - South Roof
type | name | values
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets: #3
checkpoint | Insulation under gutter: 60mm
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel
checkpoint | Gutter Flashing: Colorbond
checkpoint | Material separation tape for Gutter Flashing
checkpoint | Sumps / Outlets: High Capacity Overflow
checkpoint | Overflows: Siphonic Sumps & Overflow
checkpoint | Box Gutter Expansion Join
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation checklist
section | Material Inspection
checkpoint | Insulation: 80mm glasswool on medium sarking
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Colorbond Kliplok
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: Screws to suit kliplok without Neo
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Material Separation Tape
checkpoint | Plywood under cappings
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations checklist
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Dektite #7
checkpoint | Penetration 0.61mm Colorbond - 400mm Dia
checkpoint | Penetration for I-Beam
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## L14 South Roof Parapet
L14 - South Roof Parapet
type | name | values
checklist | Parapet Wall Cladding checklist
section | Material Inspection
checkpoint | Parapet Wall Cladding type: 0.42mm Spandek
checkpoint | Top hat support: 0.75mm x 50mm Top Hat
checkpoint | Top hat support: 0.75mm x 100mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Matt
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## L14 - North Roof
L14 - North Roof
type | name | values
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets: #3
checkpoint | Box Gutter Brackets: #1
checkpoint | Insulation under gutter: 60mm
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel
checkpoint | Gutter Flashing: Colorbond
checkpoint | Material separation tape for Gutter Flashing
checkpoint | Sumps / Outlets: High Capacity Overflow
checkpoint | Overflows: Siphonic Sumps (fix only)
checkpoint | Box Gutter Expansion Join
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation checklist
section | Material Inspection
checkpoint | Insulation: 80mm glasswool on medium sarking
checkpoint | Mediumweight Paper under Helipad
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Colorbond Kliplok
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: Screws to suit kliplok without Neo
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Material Separation Tape
checkpoint | Plywood under cappings
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations checklist
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Dektite #7
checkpoint | Penetration for I-Beam
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## L14 - North Roof Raised
L14 - North Roof Raised
type | name | values
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Ridge Capping
checkpoint | Apron / Capping Flashing
checkpoint | Thermal Spacer: Ashgrid 120mm
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## L14 North Roof Parapet
L14 - North Roof Parapet Cladding
type | name | values
checklist | Parapet Wall Cladding checklist
section | Material Inspection
checkpoint | Parapet Wall Cladding type: 0.42mm Spandek
checkpoint | Top hat support: 0.75mm x 50mm Top Hat
checkpoint | Top hat support: 0.75mm x 100mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Matt
checkpoint | Wall Panetration
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## West Canopies Roof
West Canopies Roof
type | name | values
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets: #1
checkpoint | Insulation under gutter: Sisalation
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel
checkpoint | Gutter Flashing: Colorbond
checkpoint | Material separation tape for Gutter Flashing
checkpoint | Sumps / Outlets: High Capacity Overflow
checkpoint | Overflows: Siphonic Sumps (fix only)
checkpoint | Box Gutter Expansion Join
checkpoint | Leafguard Sump Covers
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Roof Insulation: Proctor Wrap HTR
checkpoint | Roof Sheets: 0.48mm Colorbond Kliplok
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: Screws to suit kliplok without Neo
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Material Separation Tape
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Main Entrance Canopy
Main Entrrance Canopy Roof
type | name | values
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets: #3
checkpoint | Insulation under gutter: Sisalation
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel
checkpoint | Gutter Flashing: Colorbond
checkpoint | Material separation tape for Gutter Flashing
checkpoint | Sumps / Outlets: S/S Inline Sump with High Capacity Overflow
checkpoint | Box Gutter Expansion Join
checkpoint | Leafguard Sump covers
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation checklist
section | Material Inspection
checkpoint | Insulation: 100mm Glasswool on Medium Sarking
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Colorbond Kliplok
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: Screws to suit kliplok without Neo
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Material Separation Tape
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations checklist
checkpoint | Flashing Material: 0.61mm Colorbond
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## CEP Exhaust Roof
CEP Exhaust Roof
type | name | values
checklist | Insulation checklist
section | Material Inspection
checkpoint | Insulation: 60mm Glasswool on Medium Sarking
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Colorbond Kliplok
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: Screws to suit kliplok without Neo
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Eaves Gutter Installation Checklist
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Eaves Gutter: Eaves gutter 115
checkpoint | Eaves Gutter Brackets: Eaves gutter 115
checkpoint | Gutter Flashing:
checkpoint | Stop ends: 115mm Quad stop ends
checkpoint | Downpipes: Colorbond 100mm Dia
checkpoint | Pops: 0.61mm Colorbond
checkpoint | Spreader - 100mm Colorbond 1 bend
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Material Separation Tape
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## CEP Exhaust Cladding
CEP Exhaust Cladding
type | name | values
checklist | Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding type: 0.42mm Spandek
checkpoint | Wall Insulation: 60mm Glaswool on Medium Sarking
checkpoint | Top hat support: 0.75mm x 25mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Matt
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Link Bridge North Roof
Link Bridge North Roof
type | name | values
checklist | Askin Panel Installation checklist
section | Material Inspection
checkpoint | Panel: Askin Volcore Metric 150mm
checkpoint | Internal Colour:
checkpoint | External liner colour: Paperbark
checkpoint | 14–14 x 205mm with bonded washer
checkpoint | buildex type 17 12 x 20mm stitching screws
checkpoint | 6mm Butyl tape
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Side lap of the sheets
checkpoint | Panels located correctly
checkpoint | Fixings as per Manufacturer's Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Material Separation Tape
checkpoint | Plyboard under cappings
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets: #2
checkpoint | Insulation under gutter: Sisalation
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel
checkpoint | Box Gutter liner - 50mm Askin Panel
checkpoint | Gutter Flashing: Colorbond
checkpoint | Material separation tape for Gutter Flashing
checkpoint | Sumps / Outlets: High Capacity Overflow
checkpoint | Box Gutter Expansion Join
checkpoint | Leafguard Sump Covers
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Link Bridge Centre Roof
Link Bridge Centre Roof
type | name | values
checklist | Askin Panel Installation checklist
section | Material Inspection
checkpoint | Panel: Askin Volcore Metric 150mm
checkpoint | Internal Colour:
checkpoint | External liner colour: Paperbark
checkpoint | 14–14 x 205mm with bonded washer
checkpoint | buildex type 17 12 x 20mm stitching screws
checkpoint | 6mm Butyl tape
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Side lap of the sheets
checkpoint | Panels located correctly
checkpoint | Fixings as per Manufacturer's Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Material Separation Tape
checkpoint | Plyboard under cappings
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets: #2
checkpoint | Insulation under gutter: Sisalation
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel
checkpoint | Box Gutter liner - 50mm Askin Panel
checkpoint | Gutter Flashing: Colorbond
checkpoint | Material separation tape for Gutter Flashing
checkpoint | Sumps / Outlets: High Capacity Overflow
checkpoint | Box Gutter Expansion Join
checkpoint | Leafguard Sump Covers
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Link Bridge South Roof
Link Bridge South Roof
type | name | values
checklist | Askin Panel Installation checklist
section | Material Inspection
checkpoint | Panel: Askin Volcore Metric 150mm
checkpoint | Internal Colour:
checkpoint | External liner colour: Paperbark
checkpoint | 14–14 x 205mm with bonded washer
checkpoint | buildex type 17 12 x 20mm stitching screws
checkpoint | 6mm Butyl tape
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Side lap of the sheets
checkpoint | Panels located correctly
checkpoint | Fixings as per Manufacturer's Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Material Separation Tape
checkpoint | Plyboard under cappings
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets: #2
checkpoint | Insulation under gutter: Sisalation
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel
checkpoint | Box Gutter liner - 50mm Askin Panel
checkpoint | Gutter Flashing: Colorbond
checkpoint | Material separation tape for Gutter Flashing
checkpoint | Sumps / Outlets: High Capacity Overflow
checkpoint | Box Gutter Expansion Join
checkpoint | Leafguard Sump Covers
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Airlock Roof
Airlock Roof
type | name | values
checklist | Askin Panel Installation checklist
section | Material Inspection
checkpoint | Panel: Askin Volcore Metric 120mm
checkpoint | Internal Colour:
checkpoint | External liner colour: Jasper
checkpoint | 14–14 x 170mm with bonded washer
checkpoint | buildex type 17 12 x 20mm stitching screws
checkpoint | 6mm Butyl tape
section | Installation
checkpoint | Caulking to side laps
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Side lap of the sheets
checkpoint | Panels located correctly
checkpoint | Fixings as per Manufacturer's Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Material Separation Tape
checkpoint | Plyboard under cappings
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Courtyard Cladding
Courtyard Cladding
type | name | values
checklist | Askin Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding type: 150mm Mineral Wool Askin Volcore Vivid
checkpoint | Ledger Angle: 75 x 150mm x 1.6mm
checkpoint | Flashing Material: 0.61mm Colorbond Matt
checkpoint | S/S Screws to suit 150mm Panel
checkpoint | 1.2mm x 40mm Top Hat
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Join caulking on the side lap
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | 6mm Butyl tape
checkpoint | Fish Plates for 1.6mm Aluminium foot flashing
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Butyl Tape to Internal Flashings
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## L13 North Wall Cladding
L13 North Wall Cladding
type | name | values
checklist | Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding type: Custom Louvre Style Flashing
checkpoint | Thermal Spacer 800mm - 80mm
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Wall Fixing Angle 1.6mm GAL- 300mm x 700mm
checkpoint | Wall Infill Angle 1.6mm GAL - 300mm x 500mm
section | Installation
checkpoint | Wall Penetration - Overflow Caulking
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## L13 East Wall Cladding
L13 East Wall Cladding
type | name | values
checklist | Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding type: Custom Louvre Style Flashing
checkpoint | Thermal Spacer 800mm - 80mm
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Wall / Soffit - Purlin Bridging Plates
checkpoint | Plyboard under Cappings
section | Installation
checkpoint | Wall Penetration - Overflow Caulking
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## L13 South Walls Cladding
L13 South Wall Cladding
type | name | values
checklist | Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding type: Custom Louvre Style Flashing
checkpoint | Thermal Spacer 800mm - 80mm
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Wall / Soffit - Purlin Bridging Plates
checkpoint | Plyboard under Cappings
section | Installation
checkpoint | Wall Penetration - Overflow Caulking
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## L13 West Wall Cladding
L13 West Wall Cladding
type | name | values
checklist | Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding type: Custom Louvre Style Flashing
checkpoint | Thermal Spacer 800mm - 80mm
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Wall / Soffit - Purlin Bridging Plates
checkpoint | Plyboard under Cappings
section | Installation
checkpoint | Wall Penetration - Overflow Caulking
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## L7 Plant Wall Cladding
L7 Plant Wall Cladding
type | name | values
checklist | Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding type: Custom Louvre Style Flashing
checkpoint | Thermal Spacer 800mm - 80mm
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Plyboard under Cappings
section | Installation
checkpoint | Wall Penetration - Overflow Caulking
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Box Gutter - Existing
Box Gutter - Existing
type | name | values
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets: #2
checkpoint | Insulation under gutter: 60mm
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 0.61mm Colorbond
checkpoint | Gutter Flashing: Colorbond to match
checkpoint | Sumps / Outlets: Inline Sump / High Capacity Overflow 0.61mm Colorbond
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Overflow - Project Wide
Overflow - Project Wide
type | name | values
checklist | Project Wide Overflow Installation checklist
section | Material Inspection
checkpoint | Overflow: 1.2mm 316 Stainless Steel
section | Installation
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Caulking done to façade penetration
checkpoint | Size of Overflow is Adequate according to the Standards
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative: