## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Add Delivery Docket | [5 empty] | Delivery Docket | 46cd9896-0022-421d-89fa-24a2cf8072d2
section | Details
checkpoint | Please take photo or attach docket
checklist | Add Non Conformance Corrective Action Report | [5 empty] | Non Conformance Corrective Action Report - | 89c288e3-c10f-4ad2-85aa-1913eeb00fbc
section | Details
checkpoint-no-value | Report
textbox | Report Reference:
textbox | Customer Name:
textbox | Job Number:
textbox | Purchase Order Number:
textbox | Delivery Docket No:
note | Part
textbox | Part Description:
textbox | Part Identification:
note | Non-Compliance
textbox | Non-compliance description:
note | Cause
note | Root cause description of the non-compliance:
tickbox | Technical Detail
tickbox | Production
tickbox | OH&S
tickbox | Delivery
tickbox | Client Side (Handling/Application)
note | Corrective Action
note | Action taken to correct the immediate non-compliance:
note | Quality Assurance
tickbox | Rework
tickbox | Accepted Under Concession
tickbox | Replace
tickbox | No Action Required
note | OH&S
tickbox | Re-Induction
tickbox | Warning
tickbox | Rectification
tickbox | SWMS Review
note | Preventative Action
textbox | Action neccessary to eliminate the root cause of the non-compliance:
note | Verification
textbox | Verify the corrective and preventative action taken is adequate and effective:
textbox | Manager's Name:
note | Customer Validation
textbox | Validate the corrective and preventative action is adequate and effective:
textbox | Representative Name:
checklist | Add Offhire Information | [5 empty] | Offhire Information - | 3c0ec7bb-f018-4c3e-86a9-d84bc4a319b2
section | Details
checkpoint | All Offhire Information Completed
textbox | Site:
textbox | P.O Number:
textbox | Offhire No.:
textbox | Offhire Date:
textbox | Hire Company:
textbox | Plant/Materials:
textbox | Full/Part Offhire:
textbox | Missing Parts:
textbox | Damage:
checklist | Add Onsite Material Install Form | [5 empty] | Onsite Material Install Form | 47033a2c-7bc1-4725-b05a-c9badaa9ca09
section | Details
checkpoint | Onsite Material Install Details Completed
textbox | Job:
textbox | Area:
textbox | Details of Works Completed:
textbox | Actual Onsite Hours:
textbox | Allowed or Budgeted Hours:
textbox | Comments:
checklist | Add Pre-Start Toolbox | [5 empty] | Pre-Start Toolbox | a7e47604-c95a-44ca-82c6-c24643ad87aa
section | Pre-Start Toolbox
checkpoint | Pre-Start Toolbox
textbox | Project:
textbox | Location:
textbox | Job No:
textbox | Supervisor:
textbox | Foreman:
textbox | Builder:
textbox | CONDUCTED BY:
textbox | TOOLBOX DATE:
signoff | Attendees - Add Signature here
section | BEFORE STARTING WORK
checkpoint | Have SWMS been read, signed and methodology understood and agreed to.
checkpoint | Has every worker been inducted into site.
checkpoint | Has consultation been conducted about the task to be undertaken
checkpoint | Does everyone have the necessary training and qualification to perform the task
checkpoint | Does everyone have the correct PPE for the task
checkpoint | Have handrail & wire mesh inspections been completed prior to accessing roof.
checkpoint | Is safe access and egress to all areas acceptable to your work group.
checkpoint | Has the apprentice been allocated an experienced tradesman to work with
checkpoint | Will work area impact overhead powerlines or live electrical wiring and are correct permits and SWMS available.
checkpoint | Have manual handling issues been identified and assessed
checkpoint | Are perimeter exclusion zones required and have they been installed
checkpoint | (Working at height tasks) Have live edges/voids/fall hazards been identified and have they been barricaded / excluded
checkpoint | Have plant pre-start inspection checks been completed, have checks been made to ensure ground conditions are safe for plant operation.
checkpoint | Are safety measures in place for working near a suspended loads
checkpoint | Notes
textbox | Notes
checklist | Add Tool Box Training | [5 empty] | Tool Box Training | 0c4d82bb-9ace-492c-bdd4-94efddecce03
section | Details
checkpoint | All Tool Box Training Details Complete
textbox | Foreman:
textbox | Any OH&S Issues
textbox | Action to be taken
textbox | Suggestions:
textbox | Please list all present at your toolbox training session:
textbox
textbox
textbox
textbox
textbox
textbox
textbox
textbox
textbox
textbox
textbox
textbox
textbox
textbox
textbox
note | Add additional attendees in comments below as required
checklist | COVID Contact Tracing Register - add additional register | [5 empty] | Record COVID Contact Tracing Details | e0d48544-4adf-4137-bee6-b947c879c636
section | Details
checkpoint | All COVID Contact Tracing Register details inputted below
textbox | Building:
textbox | Work Area:
textbox | Employee Names:
textbox | Time Frames:
checklist | Foremans Diary Checklist | [5 empty] | Foremans Diary: | 4fdd496a-845c-47de-9753-1b9b9f2354a0
section | Details
checkpoint | Foremans diary - all details inputted and complete
textbox | Date:
textbox | Tasks completed productivity feedback: (inc hours worked ordinary time & overtime):
textbox | OHS - include comments on accidents and incidents:
textbox | Quality achievement / issues:
textbox | Supplier issues:
textbox | No. employees on site:
textbox | No. employee sick / leave:
textbox | NCR’s:
textbox | Hours worked:
textbox | Lost time:
textbox | Machinery on hire:
textbox | List employees on site:
textbox | Other:
checklist | Guardrail Installation Handover | [5 empty] | Guardrail Installation Handover | 2afc46cc-3f5e-4dca-8293-fec2f9e82ac2
section | Details
checkpoint | Roof Edge Protection - Completion of Installation
textbox | Issue Date:
textbox | Inspection Date:
textbox | No:
textbox | Time:
note | Person or organization requiring the roof edge protection
textbox | Name:
textbox | Address:
textbox | Site Address:
textbox | Location on Site:
textbox | Installer organization name:
textbox | Phone No:
textbox | Address:
dropdown | Type of Roof Edge: | Prefabricated proprietary system, Scaffolding
textbox | Name of system:
textbox | Type of scaffolding:
textbox | Name of person in charge of installation:
note | Installer's Statement: All Relevant inspections and checks have been carried out prior to the issue of this Certificate.
textbox | Certified issued on behalf of:
textbox | By: (Print Name)
textbox | Certified Received on behalf of:
textbox | By: (Print Name)
checklist | Handover | [5 empty] | Handover | a9a5a42c-3227-4781-b9a3-a49d3bff0534
section | Details
checkpoint | Roof edge protection - Completion of installation
textbox | Issue date
textbox | No:
textbox | Inspection date
textbox | Time am / pm
textbox | Person or organization requiring the roof edge of protection
textbox | Name
textbox | Address
textbox | Site address
textbox | Location on site
textbox | Installer organisation name
textbox | Phone no:
textbox | Address
dropdown | Type of roof edge protection | Prefabricated proprietary system, Scaffolding
textbox | Name of system
textbox | Type of scaffolding
textbox | Name of person in charge of installation
note | Installer organisation name: All relevant inspections & checks have been carried out prior to the issue of this Certificate
checkpoint | Certified issued on behalf of:
checkpoint | Certified received on behalf of
checklist | Handrail Inspection Report | [5 empty] | Handrail Inspection Report | 590bb197-e2e5-4c8f-ae47-d7b575aa50ff
section | Details
checkpoint | Handrail Inspection Report Complete
textbox | Supervisor:
textbox | Foreman:
textbox | Builder:
textbox | Inspection by:
textbox | Inspection date:
note | Report to be completed and compliance achieved for all areas of roof with temporary handrail works.
note | Report to be conducted by a person Authorised, experienced and deemed competent by the Company HSE.
checkpoint | Bolt plate fixings
checkpoint | Rail joiners tight
checkpoint | Rail spacings not over 450mm
checkpoint | Top rail height 900mm -1100mm
checkpoint | Toe board infills if required
checkpoint | Deck clamp installations
checkpoint | Third rail not to exceed 250mm from building
checkpoint | Corner Joins / chain corners tight
checkpoint | V clamps correctly engaged with purlin toe
checkpoint | G clamps correctly engaged with purlin toe
checkpoint | Post distance from corners not exceeding 1mtr
checkpoint | Post spacings not to exceed 3mtr
checkpoint | Panel clamp installations
checkpoint | Support bar installations
checkpoint | Top posts / T posts wing bolts tight
checkpoint | Tele Extensions tight where required
checkpoint | Rail lapping 100mm min lap
checkpoint | Installation Compliance
checklist | Hazard Inspection Report | [5 empty] | Hazard Inspection Report | f5c54ff7-abb0-496a-8621-d369cc714ec3
section | Details
checkpoint | Hazard Inspection Report
textbox | Inspection date
textbox | Project
textbox | Work Area
textbox | Identified Hazard
textbox | Corrective Action Required
textbox | Action By
textbox | Due Date
checkpoint | Signed off be Foreman
checklist | Variation Contract | [5 empty] | Variation Contract - | 52b14531-d459-429c-971f-ef95a1636a19
section | Details
checkpoint-no-value | Job Details
textbox | Details of Work (Inc. Location)
textbox | Client:
textbox | Project:
textbox | Reason for Variation:
textbox | Job No:
textbox | Hours:
textbox | Materials Equipment:
textbox | Site Instruction No:
textbox | Agreed Value:
checkpoint | Foreman Sign Off
textbox | Name:
checkpoint | Project Manager Sign Off
textbox | Name:
checkpoint | Signature of Authorising Officer
textbox | Name:
checklist | Wire Mesh Inspection Report | [5 empty] | Wire Mesh Inspection Report | e9c0d486-f3aa-4f39-84c2-65288dcf14ea
section | Details
checkpoint | Wire Mesh Inspection Report Complete
textbox | Supervisor:
textbox | Foreman:
textbox | Builder:
textbox | Inspection by:
textbox | Inspection date:
note | Report to be completed and compliance achieved for all areas of roof with wire mesh installation.
note | Report to be conducted by a person Authorised, experienced and deemed competent by the Company HSE.
checkpoint | Lapping adjoining wire
checkpoint | Tension
checkpoint | Maximum span purlin check 1.2m
checkpoint | Ring clamps corrected spacing ( If required)
checkpoint | Mesh material compliance AS/NZS4389
checkpoint | Parallel longitudinal alignment
checkpoint | Transverse wires 90deg to purlins
checkpoint | Transverse wires above logitudinal
checkpoint | Wiring around penetrations reinstated/ repaired?
checkpoint | Tags ends correctly tied
checkpoint | Tie configuration for timber fix correct
checkpoint | Timber fix
checkpoint | Lap twitching - correct spacing spacing if required
checkpoint | Longitudinal joins
checkpoint | Purlin wrapping where required
checkpoint | Twitching required over large penetrations ?
checkpoint | Start Gap
checkpoint | End Gap
checkpoint | Pre-drilled wire strip installed correctly
checkpoint | Job compliance