## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Box Gutter Installation | [5 empty] | Box Gutter Installation Checklist (L14 - South Roof)
section | Material Inspection
checkpoint | Box Gutter Brackets: #3
checkpoint | Insulation under gutter: 60mm
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel
checkpoint | Gutter Flashing: Colorbond
checkpoint | Material separation tape for Gutter Flashing
checkpoint | Sumps / Outlets: High Capacity Overflow
checkpoint | Overflows: Siphonic Sumps & Overflow
checkpoint | Box Gutter Expansion Join
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Insulation Checklist (L14 - South Roof)
section | Material Inspection
checkpoint | Insulation: 80mm glasswool on medium sarking
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (L14 - South Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Kliplok
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: Screws to suit kliplok without Neo
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (L14 - South Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Material Separation Tape
checkpoint | Plywood under cappings
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations | [5 empty] | Roof Penetrations Checklist (L14 - South Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Dektite #7
checkpoint | Penetration 0.61mm Colorbond - 400mm Dia
checkpoint | Penetration for I-Beam
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding | [5 empty] | Parapet Wall Cladding Checklist (L14 - South Roof Parapet)
section | Material Inspection
checkpoint | Parapet Wall Cladding type: 0.42mm Spandek
checkpoint | Top hat support: 0.75mm x 50mm Top Hat
checkpoint | Top hat support: 0.75mm x 100mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Matt
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Box Gutter Installation Checklist (L14 - North Roof)
section | Material Inspection
checkpoint | Box Gutter Brackets: #3
checkpoint | Box Gutter Brackets: #1
checkpoint | Insulation under gutter: 60mm
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel
checkpoint | Gutter Flashing: Colorbond
checkpoint | Material separation tape for Gutter Flashing
checkpoint | Sumps / Outlets: High Capacity Overflow
checkpoint | Overflows: Siphonic Sumps (fix only)
checkpoint | Box Gutter Expansion Join
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Insulation Checklist (L14 - North Roof)
section | Material Inspection
checkpoint | Insulation: 80mm glasswool on medium sarking
checkpoint | Mediumweight Paper under Helipad
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (L14 - North Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Kliplok
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: Screws to suit kliplok without Neo
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (L14 - North Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Material Separation Tape
checkpoint | Plywood under cappings
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations | [5 empty] | Roof Penetrations Checklist (L14 - North Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Dektite #7
checkpoint | Penetration for I-Beam
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (L14 - North Roof Raised)
section | Material Inspection
checkpoint | Ridge Capping
checkpoint | Apron / Capping Flashing
checkpoint | Thermal Spacer: Ashgrid 120mm
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding | [5 empty] | Parapet Wall Cladding Checklist (L14 - North Roof Parapet Cladding)
section | Material Inspection
checkpoint | Parapet Wall Cladding type: 0.42mm Spandek
checkpoint | Top hat support: 0.75mm x 50mm Top Hat
checkpoint | Top hat support: 0.75mm x 100mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Matt
checkpoint | Wall Panetration
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Box Gutter Installation Checklist (West Canopies Roof)
section | Material Inspection
checkpoint | Box Gutter Brackets: #1
checkpoint | Insulation under gutter: Sisalation
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel
checkpoint | Gutter Flashing: Colorbond
checkpoint | Material separation tape for Gutter Flashing
checkpoint | Sumps / Outlets: High Capacity Overflow
checkpoint | Overflows: Siphonic Sumps (fix only)
checkpoint | Box Gutter Expansion Join
checkpoint | Leafguard Sump Covers
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (West Canopies Roof)
section | Material Inspection
checkpoint | Roof Insulation: Proctor Wrap HTR
checkpoint | Roof Sheets: 0.48mm Colorbond Kliplok
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: Screws to suit kliplok without Neo
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (West Canopies Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Material Separation Tape
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Box Gutter Installation Checklist (Main Entrrance Canopy Roof)
section | Material Inspection
checkpoint | Box Gutter Brackets: #3
checkpoint | Insulation under gutter: Sisalation
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel
checkpoint | Gutter Flashing: Colorbond
checkpoint | Material separation tape for Gutter Flashing
checkpoint | Sumps / Outlets: S/S Inline Sump with High Capacity Overflow
checkpoint | Box Gutter Expansion Join
checkpoint | Leafguard Sump covers
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Insulation Checklist (Main Entrrance Canopy Roof)
section | Material Inspection
checkpoint | Insulation: 100mm Glasswool on Medium Sarking
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Main Entrrance Canopy Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Kliplok
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: Screws to suit kliplok without Neo
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Main Entrrance Canopy Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Material Separation Tape
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations | [5 empty] | Roof Penetrations Checklist (Main Entrrance Canopy Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Insulation Checklist (CEP Exhaust Roof)
section | Material Inspection
checkpoint | Insulation: 60mm Glasswool on Medium Sarking
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (CEP Exhaust Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Kliplok
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: Screws to suit kliplok without Neo
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Eaves Gutter Installation | [5 empty] | Eaves Gutter Installation Checklist (CEP Exhaust Roof)
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Eaves Gutter: Eaves gutter 115
checkpoint | Eaves Gutter Brackets: Eaves gutter 115
checkpoint | Gutter Flashing:
checkpoint | Stop ends: 115mm Quad stop ends
checkpoint | Downpipes: Colorbond 100mm Dia
checkpoint | Pops: 0.61mm Colorbond
checkpoint | Spreader - 100mm Colorbond 1 bend
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | Size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (CEP Exhaust Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Material Separation Tape
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Wall Cladding | [5 empty] | Wall Cladding Checklist (CEP Exhaust Cladding)
section | Material Inspection
checkpoint | Wall Cladding type: 0.42mm Spandek
checkpoint | Wall Insulation: 60mm Glaswool on Medium Sarking
checkpoint | Top hat support: 0.75mm x 25mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Matt
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Askin Panel Installation | [5 empty] | Askin Panel Installation Checklist (Link Bridge North Roof)
section | Material Inspection
checkpoint | Panel: Askin Volcore Metric 150mm
checkpoint | Internal Colour:
checkpoint | External liner colour: Paperbark
checkpoint | 14–14 x 205mm with bonded washer
checkpoint | Buildex type 17 12 x 20mm stitching screws
checkpoint | 6mm Butyl tape
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Side lap of the sheets
checkpoint | Panels located correctly
checkpoint | Fixings as per Manufacturer's Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Link Bridge North Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Material Separation Tape
checkpoint | Plyboard under cappings
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Box Gutter Installation Checklist (Link Bridge North Roof)
section | Material Inspection
checkpoint | Box Gutter Brackets: #2
checkpoint | Insulation under gutter: Sisalation
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel
checkpoint | Box Gutter liner - 50mm Askin Panel
checkpoint | Gutter Flashing: Colorbond
checkpoint | Material separation tape for Gutter Flashing
checkpoint | Sumps / Outlets: High Capacity Overflow
checkpoint | Box Gutter Expansion Join
checkpoint | Leafguard Sump Covers
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Askin Panel Installation | [5 empty] | Askin Panel Installation Checklist (Link Bridge Centre Roof)
section | Material Inspection
checkpoint | Panel: Askin Volcore Metric 150mm
checkpoint | Internal Colour:
checkpoint | External liner colour: Paperbark
checkpoint | 14–14 x 205mm with bonded washer
checkpoint | Buildex type 17 12 x 20mm stitching screws
checkpoint | 6mm Butyl tape
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Side lap of the sheets
checkpoint | Panels located correctly
checkpoint | Fixings as per Manufacturer's Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Link Bridge Centre Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Material Separation Tape
checkpoint | Plyboard under cappings
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Box Gutter Installation Checklist (Link Bridge Centre Roof)
section | Material Inspection
checkpoint | Box Gutter Brackets: #2
checkpoint | Insulation under gutter: Sisalation
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel
checkpoint | Box Gutter liner - 50mm Askin Panel
checkpoint | Gutter Flashing: Colorbond
checkpoint | Material separation tape for Gutter Flashing
checkpoint | Sumps / Outlets: High Capacity Overflow
checkpoint | Box Gutter Expansion Join
checkpoint | Leafguard Sump Covers
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Askin Panel Installation | [5 empty] | Askin Panel Installation Checklist (Link Bridge South Roof)
section | Material Inspection
checkpoint | Panel: Askin Volcore Metric 150mm
checkpoint | Internal Colour:
checkpoint | External liner colour: Paperbark
checkpoint | 14–14 x 205mm with bonded washer
checkpoint | Buildex type 17 12 x 20mm stitching screws
checkpoint | 6mm Butyl tape
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Side lap of the sheets
checkpoint | Panels located correctly
checkpoint | Fixings as per Manufacturer's Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Link Bridge South Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Material Separation Tape
checkpoint | Plyboard under cappings
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Box Gutter Installation Checklist (Link Bridge South Roof)
section | Material Inspection
checkpoint | Box Gutter Brackets: #2
checkpoint | Insulation under gutter: Sisalation
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel
checkpoint | Box Gutter liner - 50mm Askin Panel
checkpoint | Gutter Flashing: Colorbond
checkpoint | Material separation tape for Gutter Flashing
checkpoint | Sumps / Outlets: High Capacity Overflow
checkpoint | Box Gutter Expansion Join
checkpoint | Leafguard Sump Covers
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Askin Panel Installation | [5 empty] | Askin Panel Installation Checklist (Airlock Roof)
section | Material Inspection
checkpoint | Panel: Askin Volcore Metric 120mm
checkpoint | Internal Colour:
checkpoint | External liner colour: Jasper
checkpoint | 14–14 x 170mm with bonded washer
checkpoint | Buildex type 17 12 x 20mm stitching screws
checkpoint | 6mm Butyl tape
section | Installation
checkpoint | Caulking to side laps
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Side lap of the sheets
checkpoint | Panels located correctly
checkpoint | Fixings as per Manufacturer's Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Airlock Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Material Separation Tape
checkpoint | Plyboard under cappings
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Askin Wall Cladding | [5 empty] | Askin Wall Cladding Checklist (Courtyard Cladding)
section | Material Inspection
checkpoint | Wall Cladding type: 150mm Mineral Wool Askin Volcore Vivid
checkpoint | Ledger Angle: 75 x 150mm x 1.6mm
checkpoint | Flashing Material: 0.61mm Colorbond Matt
checkpoint | S/S Screws to suit 150mm Panel
checkpoint | 1.2mm x 40mm Top Hat
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Join caulking on the side lap
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Courtyard Cladding)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | 6mm Butyl tape
checkpoint | Fish Plates for 1.6mm Aluminium foot flashing
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Butyl Tape to Internal Flashings
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Wall Cladding | [5 empty] | Wall Cladding Checklist (L13 North Wall Cladding)
section | Material Inspection
checkpoint | Wall Cladding type: Custom Louvre Style Flashing
checkpoint | Thermal Spacer 800mm - 80mm
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Wall Fixing Angle 1.6mm GAL- 300mm x 700mm
checkpoint | Wall Infill Angle 1.6mm GAL - 300mm x 500mm
section | Installation
checkpoint | Wall Penetration - Overflow Caulking
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Wall Cladding | [5 empty] | Wall Cladding Checklist (L13 East Wall Cladding)
section | Material Inspection
checkpoint | Wall Cladding type: Custom Louvre Style Flashing
checkpoint | Thermal Spacer 800mm - 80mm
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Wall / Soffit - Purlin Bridging Plates
checkpoint | Plyboard under Cappings
section | Installation
checkpoint | Wall Penetration - Overflow Caulking
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (L13 East Wall Cladding)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Wall Cladding | [5 empty] | Wall Cladding Checklist (L13 South Wall Cladding)
section | Material Inspection
checkpoint | Wall Cladding type: Custom Louvre Style Flashing
checkpoint | Thermal Spacer 800mm - 80mm
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Wall / Soffit - Purlin Bridging Plates
checkpoint | Plyboard under Cappings
section | Installation
checkpoint | Wall Penetration - Overflow Caulking
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (L13 South Wall Cladding)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Wall Cladding | [5 empty] | Wall Cladding Checklist (L13 West Wall Cladding)
section | Material Inspection
checkpoint | Wall Cladding type: Custom Louvre Style Flashing
checkpoint | Thermal Spacer 800mm - 80mm
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Wall / Soffit - Purlin Bridging Plates
checkpoint | Plyboard under Cappings
section | Installation
checkpoint | Wall Penetration - Overflow Caulking
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (L13 West Wall Cladding)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Wall Cladding | [5 empty] | Wall Cladding Checklist (L7 Plant Wall Cladding)
section | Material Inspection
checkpoint | Wall Cladding type: Custom Louvre Style Flashing
checkpoint | Thermal Spacer 800mm - 80mm
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Plyboard under Cappings
section | Installation
checkpoint | Wall Penetration - Overflow Caulking
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (L7 Plant Wall Cladding)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Box Gutter Installation Checklist (Box Gutter - Existing)
section | Material Inspection
checkpoint | Box Gutter Brackets: #2
checkpoint | Insulation under gutter: 60mm
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 0.61mm Colorbond
checkpoint | Gutter Flashing: Colorbond to match
checkpoint | Sumps / Outlets: Inline Sump / High Capacity Overflow 0.61mm Colorbond
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Project Wide Overflow Installation | [5 empty] | Project Wide Overflow Installation Checklist (Overflow - Project Wide)
section | Material Inspection
checkpoint | Overflow: 1.2mm 316 Stainless Steel
section | Installation
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Caulking done to façade penetration
checkpoint | Size of Overflow is Adequate according to the Standards
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative: