## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
cd19570a-5856-471c-8be2-69cbdd696097 | checklist | ITP - Dig-out in Tie-in Rev 0 | itp | ITP - Dig-out in Tie-in
a5bd40f0-67e2-4a91-9f98-897d130c3f37 | section | 1.0 Dig-out in Tie In Locations
a460c8ae-e960-459c-b3be-2949768971e0 | checkpoint | 1.01 - Excavation
764e77e3-2a2f-5c95-9a42-b0fecd9581a8 | note | Detail of Activity / Test - Excavate from finish road level (FRL)/existing road level at a depth specified in the design drawing
d9a58506-3311-5892-ab0c-2dc828edfec3 | note | Action (Hold, Monitor, Witness) - M
afc319dd-15e4-5a99-b05c-e9da26508d21 | note | Minimum Test Frequency - In pavement tie In locations
dcf14c33-7634-5a1f-9efe-b0c25bc4a2ba | note | Inspection / Test method - Measure / Photo
8ff02490-714e-54ff-8850-f6f57ebd03f1 | note | Acceptance Criteria - Site Engineers Approval
19caac46-f106-56de-a29e-ac7da9f00838 | note | Record documents (QCP - Quality Control Portal) - Checksheet
67179c22-2317-5249-9436-98ba086a488f | note | Responsibility - Contractor
a7d5d238-ef61-5623-a47a-a0733a8c56fd | note | Site Engineer - A
dfaf2c0f-899d-5c55-91b6-7e0e8dd293d4 | note | Eng. Rep / NZTA - I
95004611-9c28-5f82-a2f7-9ee1d5c43299 | note | Contractor - R
4d585319-e04e-4dec-8fa5-9f736e16fa91 | checkpoint | 1.02 - Geogrid
ccedcd99-e0fe-53b4-b69d-79e8f768e84a | note | Detail of Activity / Test - Install geogrid (prosolve 30x30mm or similar approved)
ca0442cb-3e04-538e-aa47-730c45fcb406 | note | Action (Hold, Monitor, Witness) - M
a92a544b-af15-5e29-8176-c6499d1aa9bb | note | Minimum Test Frequency - For each pavement tie In locations
a989e1ea-f7c5-5430-9ee4-05be55bf6427 | note | Inspection / Test method - Photo
260bb3c5-7f2b-560d-b505-5bbde7dd1c4e | note | Acceptance Criteria - Site Engineers Approval
b731ab90-23e1-5767-856c-f7dd4d6e4e37 | note | Record documents (QCP - Quality Control Portal) - Checksheet
6fbe90b9-e203-5ac1-a7d8-608ced0279e2 | note | Responsibility - Contractor
b65694a0-ab3b-56aa-a534-789cdfb52832 | note | Site Engineer - A
1ad19a9b-d75f-5eee-ab19-0dffba66bce2 | note | Eng. Rep / NZTA - I
2d00f20a-1a22-5243-aa4d-a8a00e901b5d | note | Contractor - R
47fc737d-8872-4085-9b1a-66ec6493b17e | checkpoint | 1.03 - Sub-base Backfilling Compaction
5dd6fe45-1a63-5b77-b087-6a3ff693e7ac | note | Detail of Activity / Test - 1st layer backfill at a depth specified in the design drawing, use AP65/Stockedpiled material approved by the Engineer
43a93bd9-a768-5ad6-9027-9fa34e639be7 | note | Action (Hold, Monitor, Witness) - M
7e1d7405-c49a-543e-a0d7-90975782009a | note | Inspection / Test method - Measure / Photo
ec753371-ea93-5df6-9231-69d52ee1e228 | note | Acceptance Criteria - Site Engineers Approval
3b94f186-4164-5ee4-9f66-eac08fc9d879 | note | Record documents (QCP - Quality Control Portal) - Checksheet
1eba9dee-d61f-53c0-9302-0f5e46f9d1e8 | note | Responsibility - Contractor
a5f47443-31ae-5156-b5f9-4a060912f645 | note | Site Engineer - A
97289082-b35d-56ad-a7a3-ee41d38b29dd | note | Eng. Rep / NZTA - I
c607c2ca-3c71-5a7f-9a82-6419f84c498c | note | Contractor - R
e56c1abf-e290-49e5-8437-f950f4e89c5b | checkpoint | 1.04 - Sub-base Backfilling Compaction
440fa11a-399a-5b77-bedc-20d711da92ec | note | Detail of Activity / Test - AP65/AP40 2nd layer backfill at a depth specified in the design drawing
76d33847-88e2-58a2-b4ac-dedf958be343 | note | Action (Hold, Monitor, Witness) - M
d6aec0f5-ca5b-5b78-ad59-48f589546ba0 | note | Minimum Test Frequency - 5 per 1,000m2
7bad4293-d276-53cb-818e-6248b11ad26b | note | Inspection / Test method - NZS 4407.4.2.1/Clegg
be85cbda-3e27-5e1e-aff5-8ef83505bd10 | note | Acceptance Criteria - Average DoC ≥ 95%
bb2c728a-4043-5b64-9f76-b4a1df9b1c00 | note | ○ Minimum DoC ≥ 92% or CIV 30
8daa130a-3ab8-59ad-8c27-68a1af73eab4 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
35a9932e-b764-55bc-8702-1a9228280e66 | note | Responsibility - Contractor
1d03f2d6-fe7f-56a4-ae5e-d0803e44842c | note | Site Engineer - A
76688aa3-450a-5b63-8eee-967dbadf0425 | note | Eng. Rep / NZTA - I
15f9e5de-dca2-5af6-8bea-863ed4a32f89 | note | Contractor - R
d1a2af34-d883-4af3-99b1-eb6765235f4c | checkpoint | 1.05 - Sub-base Backfilling Compaction
8eb79871-5633-527e-9ebe-4f9e4ba8c24d | note | Detail of Activity / Test - AP40 3rd layer backfill at a depth specified in the design drawing
3ceb6005-0760-56d9-a576-48389ac2cf15 | note | Action (Hold, Monitor, Witness) - M
1007fead-8ef0-53ef-97f2-7b407c5e1e7d | note | Minimum Test Frequency - 5 per 1,000m2
b7769466-3fd1-516f-a16d-59df56a2ea52 | note | Inspection / Test method - NZS 4407.4.2.1
e34e350f-aa82-5cf0-983c-1aac08718d16 | note | Acceptance Criteria - Average DoC ≥ 95%
f6860a8b-df6e-5fc4-a566-c9511febcd4b | note | ○ Minimum DoC ≥ 92%
c684e17a-5f6c-5958-81a1-a2bc4639b58c | note | Record documents (QCP - Quality Control Portal) - IANZ Report
f3499f46-d8b8-51df-b606-4262f4e03168 | note | Responsibility - Contractor
663e7f96-136e-5de6-8817-176996e71e02 | note | Project Specific Notes / Instructions - Final backfill layer and testing will be done in FBS ITP
bf9a41dd-61e0-55b8-9d6d-71dee9ab3c90 | note | Site Engineer - A
a412a283-4bc4-5acf-886b-832765c6b0fc | note | Eng. Rep / NZTA - I
b137f1ae-a565-5070-acd8-9e7db1557e4e | note | Contractor - R
0383ac13-69b9-4c42-a55e-36b2e218e325 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cf95c3c8-7e5d-55cc-946b-5036bfdc2ec3 | textbox | Contractor's Rep Name:
b807502b-5978-5603-bfd9-a2cec6ff048f | textbox | Engineer's Rep. Name:
d2011aee-9886-51e7-9b11-583dfb8e90ca | date | Date:
6786b6bf-17dc-4274-87cc-8bb1d50f3789 | signoff | Add Signature