## QA - RoofLogic UltraTherm MSR C
type | name | values
checklist | Rooflogic UltraTherm Xtreme Roofing System with Fibretite Membrane
section | Prestart
checkpoint | Area accessible
holdpoint | Raise remedial / request review
checkpoint | Edge protection and safety installed
holdpoint | Raise remedial / request review
checkpoint | Substrate acceptable (clean, dry and stable)
holdpoint | Raise remedial / request review
section | Surface Preparation
checkpoint | All purlins are in place
holdpoint | Raise remedial / request review
checkpoint | Under flashings installed
holdpoint | Raise remedial / request review
checkpoint | Sheets in good condition for roof installation
holdpoint | Raise remedial / request review
section | RL Base Deck
checkpoint | Installed in accordance with specification
checkpoint | Installed in accordance with project specific and Rooflogic standard details
checkpoint | Correct fasteners used and installed with correct frequency (i.e. 1 fastener per trough along every purlin line
section | Vapour Control Layer
checkpoint | Vapour Control Layer installed to top face of acoustic board
checkpoint | Correct side laps (80mm) and end laps (100mm)
checkpoint | Vapour Control Layer to be installed in accordance with project details. Ensure Vapour Control Layer is correctly terminated to ensure vapour control continuity at roof openings, transitions and at horizontal to vertical roof/cladding junctions, under flashings installed as per detail
checkpoint | Any damage to vapour control layer repaired to ensure vapour control layer 100% continuous.
section | Install RL PIR Board and RL Roof Board HD
checkpoint | RL PIR Board insulation to be installed continuously over vapour control layer to roof and gutter in accordance with architectural drawings
checkpoint | Any damaged insulation board to be cut out and replaced with new, tightly butted piece of PIR Board (minimum 300mm x 300mm piece.)
checkpoint | PIR insulation to be dry prior to application of RL Roof Board and Fibertite membrane.
checkpoint | Roof Board HD to be installed over PIR Board and mechanically attached to the substrate. Fasteners to be installed in accordance with the prescribed fixing pattern.
section | Fibertite Membrane
Install Fibertite membrane in strict accordance with Project Specification.
section | Adhering Fibertite Membrane
checkpoint | Ensure substrate (e.g Roof Board) is dry and free from dirt, debris or contamination.
cherkpoint | Select adhesive as specified 440 220
checkpoint | Adhesive applied as per specification -Ref specification cl .3.13 in project specification
checkpoint | Penetrations dressed correctly and boots seals clamped
section | Welding Fibertite Membrane
checkpoint | Seams wiped clean (both surfaces to be welded) with Acetone and clean, white cotton rag
checkpoint | Test welds of works to be carried out on completion of works with hand- held or robotic welders
checkpoint | Seams to be welded clear of dirt, debris, moisture and adhesive residues.
checkpoint | Any welding deficiencies rectified on the same day they are seam probed
checkpoint | Night joints are installed daily, as required, to ensure that no moisture is allowed to migrate under the installed membrane.
checkpoint | Area left clean & free of other materials/debris to avoid damage
section | Final Inspection
checkpoint | System installation is complete
checkpoint | All membrane terminated with either thermoplastic weld or mechanical clamp/termination (drain clamps with no missing bolts)
checkpoint | No exposed membrane terminations that could allow water behind
checkpoint | All terminations details in accordance with project specific and standard RL construction plans and detail drawings.
checkpoint | Any damage to system and/or membrane have been recorded/ rectified
checkpoint | All construction equipment and materials removed from roof/site.
checkpoint | Maintenance Documents submitted to Main Contractor/Building Owner