## Sheet1
section | Prestart | section | Prestart | TRUE | TRUE
checkpoint | Area accessible | checkpoint | Area accessible | TRUE | TRUE
signoff | Raise remedial / request review | signoff | Raise remedial / request review | TRUE | TRUE
checkpoint | Edge protection and safety installed | checkpoint | Edge protection and safety installed | TRUE | TRUE
signoff | Raise remedial / request review | signoff | Raise remedial / request review | TRUE | TRUE
checkpoint | Substrate acceptable (clean, dry and stable) | checkpoint | Substrate acceptable (clean, dry and stable) | TRUE | TRUE
signoff | Raise remedial / request review | signoff | Raise remedial / request review | TRUE | TRUE
section | Surface Preparation | section | Surface Preparation | TRUE | TRUE
checkpoint | All purlins are in place | checkpoint | All purlins are in place | TRUE | TRUE
signoff | Raise remedial / request review | signoff | Raise remedial / request review | TRUE | TRUE
checkpoint | Under flashings installed | checkpoint | Under flashings installed | TRUE | TRUE
signoff | Raise remedial / request review | signoff | Raise remedial / request review | TRUE | TRUE
checkpoint | Sheets in good condition for roof installation | checkpoint | Sheets in good condition for roof installation | TRUE | TRUE
signoff | Raise remedial / request review | signoff | Raise remedial / request review | TRUE | TRUE
section | RL Base Deck | section | RL Base Deck | TRUE | TRUE
checkpoint | Installed in accordance with specification | checkpoint | Installed in accordance with specification | TRUE | TRUE
checkpoint | Installed in accordance with project specific and Rooflogic standard details | checkpoint | Installed in accordance with project specific and Rooflogic standard details | TRUE | TRUE
checkpoint | Correct fasteners used and installed with correct frequency (i.e. 1 fastener per trough along every purlin line | checkpoint | Correct fasteners used and installed with correct frequency (i.e. 1 fastener per trough along every purlin line | TRUE | TRUE
section | Vapour Control Layer | section | Vapour Control Layer | TRUE | TRUE
checkpoint | Vapour Control Layer installed to top face of acoustic board | checkpoint | Vapour Control Layer installed to top face of acoustic board | TRUE | TRUE
checkpoint | Correct side laps (80mm) and end laps (100mm) | checkpoint | Correct side laps (80mm) and end laps (100mm) | TRUE | TRUE
checkpoint | Vapour Control Layer to be installed in accordance with project details. Ensure Vapour Control Layer is correctly terminated to ensure vapour control continuity at roof openings, transitions and at horizontal to vertical roof/cladding junctions | checkpoint | Vapour Control Layer to be installed in accordance with project details. Ensure Vapour Control Layer is correctly terminated to ensure vapour control continuity at roof openings, transitions and at horizontal to vertical roof/cladding junctions, under flashings installed as per detail | TRUE | FALSE
checkpoint | Any damage to vapour control layer repaired to ensure vapour control layer 100% continuous. | checkpoint | Any damage to vapour control layer repaired to ensure vapour control layer 100% continuous. | TRUE | TRUE
section | Install RL PIR Board and RL Roof Board HD | section | Install RL PIR Board and RL Roof Board HD | TRUE | TRUE
checkpoint | RL PIR Board insulation to be installed continuously over vapour control layer to roof and gutter in accordance with architectural drawings | checkpoint | RL PIR Board insulation to be installed continuously over vapour control layer to roof and gutter in accordance with architectural drawings | TRUE | TRUE
checkpoint | Any damaged insulation board to be cut out and replaced with new, tightly butted piece of PIR Board (minimum 300mm x 300mm piece.) | checkpoint | Any damaged insulation board to be cut out and replaced with new, tightly butted piece of PIR Board (minimum 300mm x 300mm piece.) | TRUE | TRUE
checkpoint | PIR insulation to be dry prior to application of RL Roof Board and Fibertite membrane. | checkpoint | PIR insulation to be dry prior to application of RL Roof Board and Fibertite membrane. | TRUE | TRUE
checkpoint | Roof Board HD to be installed over PIR Board and mechanically attached to the substrate. Fasteners to be installed in accordance with the prescribed fixing pattern. | checkpoint | Roof Board HD to be installed over PIR Board and mechanically attached to the substrate. Fasteners to be installed in accordance with the prescribed fixing pattern. | TRUE | TRUE
|  | section | Fibertite Membrane
Install Fibertite membrane in strict accordance with Project Specification.
section | Adhering Fibertite Membrane | section | Adhering Fibertite Membrane | TRUE | TRUE
checkpoint | Install Fibertite membrane in strict accordance with Project Specification. |  |  | FALSE | FALSE
checkpoint | Ensure substrate (e.g. Roof Board) is dry and free from dirt, debris or contamination. | checkpoint | Ensure substrate (e.g Roof Board) is dry and free from dirt, debris or contamination. | TRUE | FALSE
checkpoint | Select adhesive as specified | cherkpoint | Select adhesive as specified 440 220 | FALSE | FALSE
button |  |  |  | FALSE | TRUE
checkpoint | Adhesive applied as per specification -Ref specification cl .3.13 in project specification | checkpoint | Adhesive applied as per specification -Ref specification cl .3.13 in project specification | TRUE | TRUE
checkpoint | Take into account ambient air temperatures and humidity levels | checkpoint | Penetrations dressed correctly and boots seals clamped | TRUE | FALSE
section | Welding Fibertite Membrane | section | Welding Fibertite Membrane | TRUE | TRUE
checkpoint | Test welds carried out daily with hand-held welders |  |  | FALSE | FALSE
checkpoint | Test welds carried out when commencing and re-commencing welding with robotic welder (e.g. start of day, after break.) |  |  | FALSE | FALSE
checkpoint | Seams to be welded clear of dirt, debris, moisture and adhesive residues. | checkpoint | Seams wiped clean (both surfaces to be welded) with Acetone and clean, white cotton rag | TRUE | FALSE
checkpoint | Seams wiped clean (both surfaces to be welded) with Acetone and clean, white cotton rag | checkpoint | Test welds of works to be carried out on completion of works with hand- held or robotic welders | TRUE | FALSE
checkpoint | Hand and Robotic welding to be carried out by trained personnel familiar with equipment and membrane | checkpoint | Seams to be welded clear of dirt, debris, moisture and adhesive residues. | TRUE | FALSE
checkpoint | Daily inspections of all completed work by way of seam probing to ensure all welds are secure, fully closed and watertight | checkpoint | Any welding deficiencies rectified on the same day they are seam probed | TRUE | FALSE
checkpoint | Any welding deficiencies rectified on the same day they are seam probed | checkpoint | Night joints are installed daily, as required, to ensure that no moisture is allowed to migrate under the installed membrane. | TRUE | FALSE
checkpoint | Night joints are installed daily, as required, to ensure that no moisture is allowed to migrate under the installed membrane. | checkpoint | Area left clean & free of other materials/debris to avoid damage | TRUE | FALSE
section | Final Inspection | section | Final Inspection | TRUE | TRUE
checkpoint | System installation is complete | checkpoint | System installation is complete | TRUE | TRUE
checkpoint | All membrane terminated with either thermoplastic weld or mechanical clamp/termination (drain clamps with no missing bolts) | checkpoint | All membrane terminated with either thermoplastic weld or mechanical clamp/termination (drain clamps with no missing bolts) | TRUE | TRUE
checkpoint | No exposed membrane terminations that could allow water behind | checkpoint | No exposed membrane terminations that could allow water behind | TRUE | TRUE
checkpoint | All terminations (details in accordance with project specific and standard RL construction plans and detail drawings. | checkpoint | All terminations details in accordance with project specific and standard RL construction plans and detail drawings. | TRUE | FALSE
checkpoint | Any damage to system and/or membrane have been recorded/ rectified | checkpoint | Any damage to system and/or membrane have been recorded/ rectified | TRUE | TRUE
checkpoint | All construction equipment and materials removed from roof/site. | checkpoint | All construction equipment and materials removed from roof/site. | TRUE | TRUE
checkpoint | Maintenance Documents submitted to Main Contractor/Building Owner | checkpoint | Maintenance Documents submitted to Main Contractor/Building Owner | TRUE | TRUE