## Master List Templates
Warnings | Id | Type | Name | Values | Prompting Name | Resource Id
| a4715e4f-bfd7-53fe-b4ac-2c95038275db | checklist | Add Delay / Damage |  | Notice of Delay/Damage | cc9b07d0-57b6-4cf2-b1b4-2af67cfdc18d
| d67d1f9a-530c-5ac4-ada0-4630b559dd43 | checkpoint-no-value | Notice of Delay/Damage
| 04d652de-4dce-46c0-a1ef-3432b444bcae | textbox | Reference Point
| e72120d4-51ec-451b-856c-a513bf3b3c98 | textbox | Description
| c925a483-418b-5420-b389-591ef23eb6a5 | signoff | Request Review / Send for Acknowledgement
| 6e201a15-bcad-52b8-9179-94426a1c5170 | checkpoint-no-value | Delay/Damage Acknowledged
| 967ee202-a218-46c4-98c8-b6d773c666b2 | button |  | No,Yes
| a362baa3-7967-5d9d-9f4c-b39d7a17e70e | checklist | Add Roof Report |  | Roof Report | 4c7a83b4-3dbc-44ff-b93e-668983c73433
| 8111ace1-1386-5c1f-8290-3df28e3c8d3f | checkpoint-no-value | Details
| f6e85027-50b7-557d-88d2-d90a5a78b987 | textbox | Reviewed By
| b03cf79b-10d7-5a03-8527-0fe9f99985a8 | textbox | Address
| 98c6ba7b-d3ec-5f61-a822-108a425c2579 | checkpoint | Building Age/Specs/documents
| 210e1e71-73e3-50f6-9f1f-81cbbabfe029 | textbox | Type of roof
| c5a2655d-0387-5f11-91a9-2b9a6b4c4ead | textbox | m2
| 3bc1c557-6a66-52b3-9698-ced9ed2c7edd | textbox | Purlin/Material/Spacing
| 6f20935b-689e-59bc-9ebe-2b529999b141 | checkpoint | Flashings and Gutters
| 36e335d3-7f1d-5c1e-83c6-e72b204afe3e | checkpoint | Services
| 5f65c3bb-0606-5c35-896a-a84079858286 | checkpoint | Observations
| b457b5d0-a6e5-53b5-bd5c-98e06a34d984 | textbox | Expectancy
| 9b05a942-901d-5acd-b280-f0c867ac9466 | textbox | Recommendations
| 97e6de16-03a7-5a5d-a33f-1f261c0fe779 | textbox | Estimate
| 31f884dc-4dfa-5171-9626-9f8a1060529d | checklist | Add Variation |  | Variation Details - | 740b2e42-f0eb-4d80-bf0b-728c7110867e
| af43077e-903d-5d88-8da8-e50a24463098 | checkpoint | Variation Details Approved
| 28d26279-c304-4689-8317-1deb797dc8fe | textbox | Reference/Drawing/Instruction Number
| 2247155b-6de8-434c-a1e1-058d724a6a62 | textbox | Variation Area
| ae7fc046-dca9-4fab-98f8-374caeb044ec | textbox | Materials & labour breakdown
Invalid dependant | 822653e1-1a8d-5c1e-9229-bee00e9e7e9a | signoff | Request Variation Acknowledgement
| 8d20db40-ceeb-512f-b832-5bd4676ee2c5 | checkpoint | Variation Completed
Invalid dependant | d302c95c-762e-5e5c-a32b-f0e8b483eb06 | signoff | Request Variation Signoff
| 513602b4-a55b-4ce2-8073-0a73c8e3ae53 | checklist | Charge Up Sheet |  | Charge Up Sheet | 7fbb5c4b-73e1-46e6-bcbc-646fd93c33d1
| 45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| 7f13a2c9-c9aa-4c0e-ab2d-ac8e45d6ef20 | checkpoint | Details
| d79a2570-6909-5bb7-adae-24c2064efd7e | textbox | Project
| 331fda8f-f0e4-586a-bbc2-c89aed258607 | date | Date:
| 3c8a8191-d510-5ced-894c-bdc3fa57ee00 | textbox | Variation Description:
| efb29f45-08dd-59ab-8dc3-3b925506029e | textbox | Staff Names:
| 69a1df50-3782-5837-b593-e457661ac779 | note | Hours worked
| cb3a6fcf-63d7-5036-925a-5d3be3e64ecb | textbox | FROM:
| 8b571dd3-2412-5d0e-a805-c94c972ee65e | textbox | TO:
| 9c022897-d754-5b74-aae2-eb538285f300 | textbox | Travel (KM'S)
| c68cf2ce-5f9e-555c-9ff3-2d5e2f5d2f79 | button | Materials Ordered: | Yes,No
| f7f6793c-344d-524f-b46c-abc78ffe4192 | textbox | Please note where orders were placed OR attach the order
| a4b1fac8-ddf7-4232-90a8-cd44b35eb74b | checkpoint | Callout/Measure
| 104300e9-e956-4b86-95fc-5456f3e65a07 | checkpoint | Iron
| a5801c4e-c22d-41e5-939b-576875330a0b | checkpoint | Ridging/Flashing
| e6ed17c5-5017-44ea-be79-b46d1c56ee21 | checkpoint | Downpipes
| 2031baf7-58ef-4332-8eb7-e9d2b6ca4bc5 | checkpoint | Droppers/Bends/Brackets etc
| 78550fe2-198d-426f-b36a-482ddfd14f73 | checkpoint | Spouting/Fascia
| e533a81f-ddcc-4b05-a80b-869d565fb1db | checkpoint | Stopend/Bracket/Corners
| 64815423-39c2-4a85-9e06-b4be28f13016 | checkpoint | Screws
| a538dfbf-d000-4f36-bd8c-19cef0ca0a4d | checkpoint | Paper/Netting
| 4e1ed599-1371-46ec-a545-97d4809bffe1 | checkpoint | Sealants/Rivets/Other
| 8bbd0f58-1703-4dec-a9ca-05896c883ab6 | checkpoint | Clearlites/EPDM/Profile Washers
| 76ee89cb-fc6a-4d4e-b1c2-5b754099e556 | checkpoint | Access/Scissor
| fe611019-e07b-4ea2-90dc-53e6655eb668 | checkpoint | Edge Protection
| d6fcfd04-e5cc-4e9d-b528-b3cbeba856a5 | checkpoint | Site Manager Signoff
| eef0e216-77fc-5a5e-837c-c3b2ae520740 | textbox | Site Manager Name:
| 16d1c55f-7d32-4fe4-8073-0ace8685d22c | signoff | Site Manager Signature:
| def5d389-518d-46b7-8cba-318115fc0e0c | checklist | Daily Pre-Start Safety Briefing |  | Daily Pre-Start Safety Briefing | 9ab87051-7630-4d29-83b0-b0917260e32e
| 76dbaa65-eefa-4d14-9d72-03b723e1044e | checkpoint | Daily Pre-Start Safety Briefing
| 50d7f882-d375-5474-be64-f391b8aa61b6 | date | Date
| 88ad505b-1a3f-48ca-aca8-16ecc8f67cb5 | checkpoint | What work is notifiable and has it been notified?
| 282c1f5c-f581-5753-8d8d-04cacadee935 | button | Any notifiable work? | yes, no
| ac65481d-18d2-59ec-9604-c3434ddd0dbe | textbox | Details if Yes
| 5484da70-2e5e-4e2a-a329-1b75700c7ef2 | checkpoint | Weather conditions
| 7397fd2e-613a-596d-86d7-06edd468a61c | dropdown | Conditions | Sunny, Overcast, Cloudy, Rainy
| 00b3af91-76d2-5b58-996c-7842defa5888 | textbox | Additional comments:
| bd2fe09f-77c3-4be7-9bc3-0729bea43943 | checkpoint | Hazards
| d7242154-f7a8-545d-b2cf-1416afdac1cd | tickbox | Electrical leads - Inspected and tagged
| ce053bb4-e010-5802-ba22-69baccc58868 | tickbox | EWP - Operators licenced
| 5d9dfc74-daa6-53b1-9168-da622d5a6cd3 | tickbox | Falling objects - Isolate the drop zone and wear head protection
| b923fb89-b84a-50ed-8d20-16b26f29af14 | tickbox | Flying objects - Wear head protection
| b7eaafbc-77b8-5528-893e-695873a0cc3c | tickbox | Ladders - Safe and secure. 3 points of contact
| 8376abff-3937-5b30-8802-15e13eb8097e | tickbox | Live power - Disconnect as necessary
| 2c9b5ccc-000b-56e8-9075-7bfb3c4f2b8f | tickbox | Noise - Hearing protection
| 7223d0aa-f823-5752-bd60-e114b5b6820d | tickbox | Other contractors - Daily Pre-Start Briefing attendance required
| 5362018f-8943-5159-9917-623c34ee981a | tickbox | Power tools - Ensure guards are fitted and use RCD
| fa936e7c-f928-5b83-9d01-068763cae6a5 | tickbox | Public and visitors - Is the construction area fenced off and safe
| dff3b7af-519f-5047-a7e0-040bc951931f | tickbox | Rotating machinery - Ensure guards are fitted at all times
| fe03d4e5-8d84-5875-85d5-ac6763983751 | tickbox | Scaffolding - Scaffold secure and certified
| 3cd1abba-3a5f-57e3-ae5c-af6e3efae2de | tickbox | Sun & Heat - Hat, sunblock & drinking water
| e4057eea-24af-5b13-ba5e-ccd417349d6c | tickbox | Traffic controls - Spotter/Hi Viz/cones/signage as required
| eafdff2a-7ad7-5299-9ca9-dfc1086463c1 | tickbox | Fall from height - Safety checks completed on all work at height gear
| 2ece561e-3197-4cac-9e64-9f2471c01beb | checkpoint | PPE Required
| 789b0648-fb52-5233-86f3-429c164b83b0 | tickbox | Hi Viz Vest
| 1daf8bf1-b8b3-52d2-b8e9-bd5fac8505eb | tickbox | Hard Hats
| 462e48cc-995a-54d8-a39e-dddfb60a559a | tickbox | Safety boots
| c76932b9-c689-5bf6-bd37-a1cd0c6a686f | tickbox | Safety glasses
| deae40da-762a-53fb-af42-43a3d5973485 | tickbox | Hearing protection
| f1bc0201-5c16-5ac3-80f5-bee8ce7fccfe | tickbox | Gloves
| 7c8d2cde-013f-50f9-8a5d-8fa7040682a4 | tickbox | Dust Masks
| 68ae5256-2f3e-5faf-be99-5fb362aa3587 | tickbox | Overalls
| 49ff0bea-f442-4a54-b589-647595bf68b8 | checkpoint | Other
| 9305205f-b3bf-518e-8cbc-a042317a84eb | textbox | Deliveries due today:
| 43eb8af0-090f-53c1-bfe3-ec7ce6768f74 | textbox | Contractors onsite
| a587695b-b981-5118-9e65-9b8b479dc1cd | button | Signage checked | yes, no
| e0298205-eae2-498d-a181-07d922e00fa1 | checkpoint-no-value | Attendees
| e4147b47-195e-540b-a9cd-b609c4200df7 | textbox | Details
| 84eaf979-8f2c-585d-a99f-e75767bed40d | checklist | Final Defects/QA |  | Final Defects/QA | 22be846f-fb9b-4f3e-9cfc-44035b4c8f99
| ed79fde6-44a2-5703-a914-614090f8e51f | section | Roof plan
| d6971343-ddd4-46be-a524-3febeab545bd | checkpoint | Roof plan
| 9121f4c1-6850-5e63-84b6-992fd44fda2f | section | Final Defects/QA
| 202ff361-321c-5047-92c6-17c46b38c9df | checkpoint-no-value | Defect 1
| 99c14c54-54dd-5b34-88ca-9622af9d1ff8 | textbox | Defect 1
| 8bdec126-5007-5798-b551-fa8d29799664 | textbox | Description
| 5a952478-f365-5370-82c6-d549fcc1cab9 | textbox | Remedy
| b11144fe-251e-5b14-870a-677ba102af97 | checkpoint-no-value | Defect 2
| 28e7f0c5-d465-512a-801d-b6b83fedd401 | textbox | Defect 2
| 3ca58f6a-cd7f-59f6-9a32-c2ab79524c44 | textbox | Description
| da264929-8e10-5005-a334-fcd9e8389e6f | textbox | Remedy
| fb05294c-e75b-5975-9d45-0d8d3933d1cd | checkpoint-no-value | Defect 3
| 95db6c31-85ec-59bd-8167-ea96dd4eb816 | textbox | Defect 3
| d1525c8d-6905-5b54-984a-4fb3cad2f7ef | textbox | Description
| 2aaffdc7-32ec-509b-95fe-e6256ceeb7dd | textbox | Remedy
| 1ea5e028-b464-5c64-a3a4-bc326994962b | checkpoint-no-value | Defect 4
| 9cff4209-3da1-53f3-a2b0-6e83efe699ad | textbox | Defect 4
| 877f7182-958c-56bf-abd1-b5df6765506b | textbox | Description
| b4e99f6f-683d-58f2-a0e9-1a83eac48a1c | textbox | Remedy
| 37502fe0-6392-523f-8de6-e74fd63772e2 | checkpoint-no-value | Defect 5
| c76edce2-b11d-50db-949b-f623142804be | textbox | Defect 5
| 9618b7bb-78e1-5a3c-86d3-28c5b604ffe3 | textbox | Description
| 71ead0ba-29ec-59c1-845e-589f614f35c1 | textbox | Remedy
| c4af5504-4e71-52bf-b872-e3423d3ba1ce | checkpoint-no-value | Defect 6
| d9891ea2-6526-5f45-ad6c-ac3719c58221 | textbox | Defect 6
| 3b466fe3-3c3a-5b3a-ab57-cb1569a5d4f8 | textbox | Description
| 514e59c5-21f8-5372-827d-1bdea98e0988 | textbox | Remedy
| b2f60c94-2455-5bd3-b378-18f65987a6eb | checkpoint-no-value | Defect 7
| 2a6a5cb8-3cd0-5b2c-9cbd-4f50c431ba0d | textbox | Defect 7
| b9bb367b-b9c0-5155-9eef-5860242bfe25 | textbox | Description
| daf1a02b-046c-5042-805f-ae27d1f679f9 | textbox | Remedy
| 8c511431-24a0-5e71-a230-b0d9ad4a4a79 | checkpoint-no-value | Defect 8
| 8d77825a-a82a-5739-8551-56a0792cbf28 | textbox | Defect 8
| 7be39ba8-1a73-5b56-8c8e-75d8f550770d | textbox | Description
| df5fef14-4fef-598b-a0d0-d2e0a57e4547 | textbox | Remedy
| e0d05127-f36a-5cca-8615-c27eceb3c111 | checkpoint-no-value | Defect 9
| 4c38fb85-34ef-5791-bdb3-8d62b49e7b5d | textbox | Defect 9
| 9c24bad0-2318-5142-ad21-313b36309845 | textbox | Description
| 26d7437d-43b1-512f-91e5-c0780cc7889c | textbox | Remedy
| d7b979a5-5c58-5381-be1d-e4482d2ff23b | checkpoint-no-value | Defect 10
| 268886f7-3a6c-5036-8579-ce2a46897b07 | textbox | Defect 10
| fefd87f2-1b86-5cac-b024-eec5d59d9570 | textbox | Description
| a1d93520-8cd7-504a-94af-01a55e1b0154 | textbox | Remedy
| 18936497-d2e8-5bf8-b34b-5576c9d7942b | checkpoint-no-value | Defect 11
| b4fff958-76ec-5690-9f6c-1355fd1ed000 | textbox | Defect 11
| e2e5851d-2ba6-53f9-8455-55a0d34edbba | textbox | Description
| f2b14505-9240-5df5-8728-549ad59fbbfa | textbox | Remedy
| e228141e-e35c-57e3-b1cf-2cc186cefa81 | checkpoint-no-value | Defect 12
| a82dd386-2fa4-5807-9e4e-8c863a5eb3a4 | textbox | Defect 12
| 1b9eb1d6-ae5c-5806-8df1-0b93d06478c4 | textbox | Description
| 704b218f-a392-596e-8485-b8a2ae797ff9 | textbox | Remedy
| d98b6dd5-11d5-542d-bcc2-b751c94aa45a | checkpoint-no-value | Defect 13
| a92782db-6f2e-52e8-a1be-04e3bd130326 | textbox | Defect 13
| 0a6ad192-a23a-524c-929c-0968714829e0 | textbox | Description
| 6efe2053-8dce-51d8-8c3a-609898d3b4db | textbox | Remedy
| 8ab3a225-48c1-51e0-80e1-699fcd20e974 | checkpoint-no-value | Defect 14
| 7d43a771-5f03-5fd7-b778-5e5c1c59ef7b | textbox | Defect 14
| 67b9216a-2d62-516f-9831-88806969fb23 | textbox | Description
| f2e4c40a-5dea-5c55-a3dc-f45710df9dc2 | textbox | Remedy
| 80331898-2ec7-5437-869e-a22eb9d2ecd3 | checkpoint-no-value | Defect 15
| 2d5f791f-2c2e-5ff9-a21c-ab0c1d020f19 | textbox | Defect 15
| f9841055-18b7-536c-bdfb-b3b5b011f6c3 | textbox | Description
| ced8b610-a8df-578a-a5f1-05eb144b3018 | textbox | Remedy
| 9cd7e282-55d5-57f4-9905-ef669c8c14c1 | checkpoint-no-value | Defect 16
| 5906f4dd-9107-500a-ab16-36b44750a513 | textbox | Defect 16
| 9365d138-0d27-58a4-8902-8d95db844da9 | textbox | Description
| 0ecbeb25-8578-5b7c-b31c-db15be216da9 | textbox | Remedy
| 6f69d76b-3f41-57ea-abf5-7d40c85de442 | checkpoint-no-value | Defect 17
| cfda99e0-a5e5-5597-9cc1-8011abf0869e | textbox | Defect 17
| 5d9f0c15-3619-5662-b81f-90fe155b7db7 | textbox | Description
| 4b06b835-2cbc-5b4f-9f3c-82e2efd89e46 | textbox | Remedy
| 3641bf74-b866-5235-a231-ea9827299340 | checkpoint-no-value | Defect 18
| b7ba5387-f09c-580a-9abc-57bc5206573e | textbox | Defect 18
| 4b65bbb5-4ac5-5adb-a248-43a08545b742 | textbox | Description
| 0a38c54e-2edc-5e5b-92f0-839dfa3af857 | textbox | Remedy
| 330be3b3-f917-56ba-9cc1-29be1e2e6476 | checkpoint-no-value | Defect 19
| dd76146a-0b76-5743-a13b-61f58c484a4e | textbox | Defect 19
| ce885260-66d0-5ef2-892d-8cfb24ea0b62 | textbox | Description
| 18a4d634-8d24-5047-b8dc-be2eed8cebe5 | textbox | Remedy
| 0f25ee3e-1373-588d-a716-692c4f064029 | checkpoint-no-value | Defect 20
| ced8e003-0959-5378-8c71-5cc0398f56f3 | textbox | Defect 20
| 72dc75e7-7406-52e9-938b-52e595fc719b | textbox | Description
| b87891e4-5e17-53cb-b4ec-d4b73867773e | textbox | Remedy
| 40e180f3-7f66-5069-ac1f-cee3d89d8a1b | checkpoint | Closed off
| d8ffafc2-b6f5-543f-88ad-d3cdb75f7ed6 | checklist | Flood Test Record |  | Flood Testing Record | a9d4fd0c-2528-4c68-bd38-ed36b9a8be2d
| 8111ace1-1386-5c1f-8290-3df28e3c8d3f | checkpoint-no-value | Details
| 79f8bac1-a316-4160-a763-d0e8bf330cc3 | textbox | Roof zone area
| 49d519a0-43a1-4af5-aaab-5ef44cf1acf6 | dropdown | Time under testing | 48 hours, 72 hours,24 hours
| a117e752-917a-5135-a7e4-2d47dea0921c | checkpoint | Outcome of flood test
| 0067f6d7-000e-5793-a71c-270f7e384e5a | checkpoint-no-value | Roofing contractor's signature (use paperclip to sign on screen)
| 2aecc4ae-bf85-4eb8-8529-0126292206d6 | textbox | Company
| 45d1e654-8171-457e-9503-ae273f0e361c | textbox | Company rep
| 043ce5f1-4a51-5115-acdf-399eb2cf8b37 | checkpoint-no-value | Main contractor's signature (use paperclip to sign on screen)
| 093875ef-77da-4f5c-925e-823a0b66c2d0 | textbox | Company
| c5660b8c-252e-41d0-9a3d-07fd8ef4b78a | textbox | Company rep
| 092a5d35-a23e-5f51-b85f-b30b695272d2 | checklist | H&S - Accident / Incident for Register |  | H&S - Incident / Accident for Register | 6a915984-006c-4684-9c22-307f7a988524
| 8111ace1-1386-5c1f-8290-3df28e3c8d3f | checkpoint | Details
| 8cda870c-753f-5137-9817-f83dbbc3ba7b | textbox | Date & time
| 43b983e5-5bf8-5976-aeca-9949de9e5682 | textbox | Name of Person
| 3ab28167-bd09-57f3-b93a-b83ce22e17f1 | textbox | Description of accident/near miss
| 0304d0fa-7d8b-5288-b869-cb4d429324e0 | textbox | Cause of harm (if any)
| 030c3127-762a-5b1e-bd08-02634d52cfd6 | textbox | Type of injury or disease
| da68050c-5bc8-5d1a-a2d0-7a12e3a4f55e | checkpoint | Immediate Action Taken
| c98e01d5-790e-5866-8e95-772c4d9b01c8 | tickbox | First Aid
| ad061492-f0ab-50bd-88c9-48c918f1ed04 | tickbox | Corrective Action
| ca667166-e882-5333-a703-8dc3824cb01f | tickbox | Review Risk Register
| 335dfac9-0b66-58be-a8f9-975d37b4c2f6 | checkpoint | Does the incident require Work Safe notification
| 53a6732a-82d9-5575-9e1c-fa232b948ab6 | button |  | Yes,No
| 76b99723-72cc-542b-82e6-3836b82ed050 | checkpoint | Is the incident the subject of a Toolbox Talk
| 880c93d9-2333-5a7e-aa2b-d78653e3ead3 | tickbox | Yes
| 683a7547-43ae-5590-bcbc-a142953938db | checkpoint | Signed Off
| 3692b921-7927-5be0-8665-655dd4671e0d | checklist | H&S - Accident / Incident Full Report |  | H&S - Accident and Incident Full Report | 649d2f73-a6b3-4b65-9687-55e6f78ecce1
| 1e73e335-4fa9-567b-a94b-c2f5490516df | section | Employee to Complete
| b44195bd-c0a4-5680-aed8-885e7c3ad764 | checkpoint-no-value | Information about the employee who had the incident
| 791e5f8b-957a-4e5c-ae2a-dbea0994ad62 | textbox | Name
| 41a7f6d6-9313-487b-8dcc-9b277dd4f16f | dropdown | Role | Client, Contractor, Visitor,Employee
| 1e2fe6ca-d24d-465b-9e4e-c50a681f2481 | textbox | Job title (if employee
| 1a039a8f-3f21-494a-b3ac-567764d019bb | textbox | Contact telephone
| 4442ebb8-f60e-50ea-8154-56309093aaa1 | checkpoint-no-value | Information about the incident
| a5d6bb9c-5e9f-49da-aa40-247c16a5cb77 | dropdown | Type of incident | Accident, Property Damage, Property Loss,Near Miss
| 4be9c3ef-228e-4be2-b5ff-fcbadcab3c31 | textbox | When did the incident happen?
| 768ccefc-717f-4f1b-911d-904dc970bc9f | textbox | Where did the incident happen?
| c4587cb6-e9b5-49cd-b5f1-20cb1d1029e7 | textbox | What happened? (Include details of any object, machine or substance involved, or property lost or damaged.)
| 4852316b-6944-45ef-b08a-4add1a45c98e | button | Was a known significant hazard involved? | No,Yes
| 6bcea14e-258b-4b74-a51a-ec00162bc35f | textbox | If YES - what was the significant hazard?
| 89279f72-6406-568d-861f-2bd1f93eef3c | checkpoint-no-value | Name(s) of any witnesses
| 0fc0fb37-5796-43f2-9c05-dd3677ab0063 | textbox | Name and contact info
| 28590cb0-b269-4805-b18e-9d3b80ad1d32 | textbox | Name and contact info
| ea53a9a7-0719-4d58-9c11-a58ca89d006f | textbox | Name and contact info
| 4301b38d-8a77-470f-8246-d945eaaa03ca | textbox | Name and contact info
| 5066017b-a70d-42e5-961b-bf70d88eb09f | textbox | Name and contact info
| a3b3f9c6-9349-5490-a06a-8766c052739d | checkpoint-no-value | What injury or injuries were sustained?
| 9326d889-dc5e-4cd2-a9f4-35d1f8ea6c64 | textbox | Body part injured (plase indicate which side of the body e.g. right or left)
| d9c2ca4b-4232-4322-be1e-415ed0b69e42 | textbox | Type of injury (e.g. break or sprain)
| f3be42c8-2f9b-44f5-809e-43344b38b4aa | button | Is this a notifiable injury? | No,Yes
| 22597bbe-e03e-4890-a68d-02ab6fddbb63 | textbox | If YES - Work Safe NZ
| c0b74e12-5bce-506c-9ff5-1e8710716bcc | checkpoint-no-value | What trearment was given?
| 501e09a6-a1ab-426d-96a1-743d129bacb3 | tickbox | First Aid
| 823f018c-9c45-45e6-9208-8a2bfd1e1f12 | tickbox | Physiotherapy
| d8135d84-9e2b-412d-84a6-e8e8998b05f4 | tickbox | Massage therapy
| c6b1f7dd-bf20-43b1-96ff-642735cb341f | tickbox | Doctor (GP)
| 29bb6b52-1a1c-42b7-9398-f288ce24fc18 | tickbox | Hospital
| 06dc9c0d-5d57-4c45-b8c0-35d2a8f0a5b4 | tickbox | Emergency services
| 3b5602b9-da77-48cf-baa5-b84994c2cc2f | tickbox | Other
| da5e368b-5e84-52f0-82d8-82be7c89aa5d | checkpoint | The above report provides a true, accurate and complete account of the accident / incident / near miss
| 6fd64a8c-5a03-4fd9-813e-d2a1ea1e1fad | note | Employee to Sign
| 6bb7806e-b892-5156-b233-c03be09eb308 | section | Manager to Complete with Employee
| 8111ace1-1386-5c1f-8290-3df28e3c8d3f | checkpoint-no-value | Details
| 42b74fe1-2e33-43bb-869c-80ff911b6249 | textbox | What (in your opinion) were the causal factors of this incident?
| 40fe19d3-b5af-532e-b4ae-6a6200913eb8 | checkpoint-no-value | Hazard identification
| 1e0b1dc2-a946-4360-84cf-228007cf2d0c | button | New Hazard Identified | No,Yes
| e34e2ae5-fde4-4cd0-83c6-95609442b7a4 | button | Significant | No,Yes
| 65447533-330f-45f1-ac14-9b11376e15aa | note | If YES identify the hazard management process to be done e.g. update hazard register and put in recommended actions below
| 3a453423-a1fd-540f-b29a-f619da71aed9 | checkpoint-no-value | Recommended Actions - Has the Hazard Management Process been undertaken
| 81cebe0c-bc93-4278-bdbe-8c13afbcf0b8 | button |  | No,Yes
| e2410cb2-0178-4ccb-a8de-52c46b875fa7 | textbox | What has been done?
| ec792840-9bfe-49f6-8271-b1ed28400b2c | textbox | Person responsible for this?
| bfbc08e2-8f7b-488e-b308-0d20f45563b4 | textbox | By when?
| 97e279d1-af6d-5137-8e10-c322e3fff906 | checkpoint-no-value | Recommended Actions - Is a review of Safety Management System required?
| 99ab7927-c71f-4898-a1d0-67df21f24d19 | button |  | No,Yes
| e792e9e7-bf45-4a64-b192-8729d6fdb682 | textbox | Which part?
| 9688f557-0559-4387-b49d-9a1c60f306a8 | textbox | Person responsible for this?
| 7437ff28-6a0b-494c-aef0-270caf445ec7 | textbox | By when?
| 5e4bdda8-248f-5658-bffc-6fa674701629 | checkpoint-no-value | Other recommended actions
| c904865d-72e1-4704-b510-dcfb8d6a04e8 | textbox | Specific actions to prevent recurrence
| b091d029-5f3c-486c-bea4-be8b9d8aa3c0 | textbox | Person responsible for this?
| 0bec84c9-7e23-4da5-be40-46a881e42227 | textbox | By when?
| 0e731c78-4c41-4127-9aff-2316ba5c5a81 | textbox | Specific actions to prevent recurrence
| 170a60de-1873-4940-a769-ec3f02eec828 | textbox | Person responsible for this?
| 5c05522e-5642-4c8b-a02f-1ebfeb6900b9 | textbox | By when?
| cc083986-69ff-52ed-9057-42a9c3a80409 | checkpoint | All relevant staff members have received information regarding the incident, changes of operation / procedures.
| 212333ca-0bcf-4192-ba6d-fa63f41df598 | textbox | Person responsible for this?
| 31833c13-0eb9-4c4a-8b36-3ef052dd0967 | textbox | By when?
| 097796a8-48f6-5ec3-bc5a-76b162b189d4 | checkpoint | If a notifiable incident has ocurred, have WSNZ (as relevant) reporting procedures been followed.
| 6236c182-4787-5f04-915b-d18709ebae57 | checkpoint | Have internal reporting systems been followed?
| 07adee93-1283-4cda-a38f-c936c1fe52ad | note | E.g. Toolbox, Close out
| 176b822c-20b3-5f7d-9210-fa00cad35d94 | checkpoint | Has the incident been recorded on the Accident Database
| 3354a6f3-5050-591c-af7d-6bb47ebc3f0a | checkpoint-no-value | Overall comments
| 91d68b65-398e-47c4-87ce-38dd20981ac3 | note | E.g. Health and Safety review actions.
| 030f26cf-68a4-5ecf-9ff3-cab9ecb17240 | checkpoint | Manager Sign Off
| c13838b3-7aaf-4883-bd80-6bad71839a26 | note | Manager to sign
| c1142197-1e98-5249-bc11-f36d998e6089 | checklist | H&S - Task Analysis |  | Task Analysis | 8dea143f-ce6e-4616-9ee9-cd635f61c346
| 45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| 8111ace1-1386-5c1f-8290-3df28e3c8d3f | checkpoint | Details
| 40427842-5edf-5c38-852f-748774fb461c | textbox | Job description:
| f8a26940-83c9-5173-9119-de3884d9db9a | textbox | Project/site:
| d4bdfc02-f6ac-5b28-b548-e16ce6dd3232 | textbox | Date:
| 4276a48e-0d28-545b-bde9-7032ff473375 | textbox | PPE required:
| 9ac26ff1-b960-5524-aed0-79ecc069db9c | textbox | Plant required:
| c20227fa-24fe-5aab-9467-071e08047cb0 | textbox | Signage required:
| 9768303f-39fb-549c-baf2-c56b3553def3 | signoff | Person completing this task analysis to sign here
| a83eac8f-b9d5-5eb0-8dc8-dc1694c6f016 | checkpoint | Task 1
| 5f39c8e8-b1f1-5b32-95d7-fb79de09df7a | textbox | Describe steps required:
| c8f656e9-1059-5d4c-8c92-86781bb0089a | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| 62cc8668-f7ef-5d2a-9824-1d7a1d72e854 | textbox | Identify hazards:
| 97086881-cfaf-5d44-bde2-0d77d059acf0 | button | Select action required | Eliminate, Minimise
| 89d9a6d6-2d7f-5883-a0a9-bd1c18eb9307 | textbox | Control methods:
| abb7ef83-c3ce-5169-a630-ae0da8642837 | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| 42c21dbd-9bff-5051-bd1f-f936237b2320 | checkpoint | Signoff
| cc191907-6808-5a08-b7e6-5d947e1865eb | signoff | All persons involved in this task analysis to sign here
| 15528ba3-d1f6-5918-a3aa-3ef338fe1ead | checkpoint | Task 2
| 13c69e11-f4af-5a03-a111-7c7fcb52451d | textbox | Describe steps required:
| daa69e9e-573c-5763-8546-9f46164345a1 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| e5e0dbec-c9b7-5c80-afa1-341b3aa72364 | textbox | Identify hazards:
| 09dfe371-002f-57fb-8253-044fe1251023 | button | Select action required | Eliminate, Minimise
| 74b4a096-f4a1-50da-b2e7-899cd2a3cc28 | textbox | Control methods:
| 24c20771-f400-56a2-91fa-e2db1d2821c5 | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| 1be8acc6-d979-4750-bf0a-a41e6b41ec6b | checkpoint | Signoff
| 3b2241a7-4391-5e74-b296-abd8081d6688 | signoff | All persons involved in this task analysis to sign here
| 80436cc7-4dbf-5cce-a6c8-7f08ccd202f9 | checkpoint | Task 3
| b94aa874-2c71-5b40-9774-2c3f0945c50e | textbox | Describe steps required:
| 53db78eb-bec9-587f-a417-9c5afa559594 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| d981a12f-564f-5477-ba27-ce3c90a640ea | textbox | Identify hazards:
| 91c09d5c-e3cc-50f8-9ade-bcd941d821cc | button | Select action required | Eliminate, Minimise
| 29f4ca79-80e6-55e2-8830-182a6bde991b | textbox | Control methods:
| 397f99cf-4219-558b-9c2f-93355accc2c9 | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| 428ce69b-de38-47c8-ba97-ad15ab45f7d4 | checkpoint | Signoff
| 20a46ba7-4201-553b-9717-c37d7fbf4bb4 | signoff | All persons involved in this task analysis to sign here
| 79d35d09-3c5b-59ae-9c63-46dff1027007 | checkpoint | Task 4
| eac8044d-2706-58e1-86fc-07655dd04e6d | textbox | Describe steps required:
| e8badd54-559e-5faf-957c-ca0b22c99d40 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| 6ab3f7a8-f670-52f3-beb4-98aad500f6f0 | textbox | Identify hazards:
| f13c9ab0-9b6b-53a6-8922-567c1a3d003e | button | Select action required | Eliminate, Minimise
| 25e5e6c9-4f3e-5883-a609-570eeb9a7786 | textbox | Control methods:
| 95b199ac-b0f1-558b-a19e-89875042615a | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| 2bdf171b-4a14-4425-80aa-e36d96e54c5d | checkpoint | Signoff
| 31c5e2e2-2eac-5cdb-8625-84bfc48087cd | signoff | All persons involved in this task analysis to sign here
| 6146adf6-9f16-515c-aa5b-6e6839d23cdf | checkpoint | Task 5
| 5cd5f2d2-eb32-5e73-8d31-9c8d8a23edd6 | textbox | Describe steps required:
| 01cc5107-54cc-5b51-8c2c-c0b5bb6377b7 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| 95ac8ec0-1b72-56a4-85e4-2e0ea871c37b | textbox | Identify hazards:
| ba52b3e3-3fc8-55cc-94ca-f83743bb3665 | button | Select action required | Eliminate, Minimise
| 6f7544c1-a398-50f6-bc30-f10c2afa2f20 | textbox | Control methods:
| 99f6629d-6ba0-5b04-acee-218fbcbfce47 | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| b0d7b6f5-8f5d-46f6-a3be-aedb2599334f | checkpoint | Signoff
| 6c175da0-a605-5cee-aba2-b37a97cbb207 | signoff | All persons involved in this task analysis to sign here
| 5f31f459-8312-4596-bfcf-2998ba9f0e26 | checkpoint | Signoff
| 1c8eb113-fc3e-59c3-bc00-a9c88ffa1697 | signoff | All persons involved in this task analysis to sign here
| c28028db-cc55-5320-ac76-ddfc80b73a42 | checkpoint | Task 6
| f2148293-360e-5d70-81af-15b3152cb9ed | textbox | Describe steps required:
| da03e97a-e4ca-5a47-b561-ad38255e238f | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| 03b89aad-a483-546c-9547-308fdc0f4672 | textbox | Identify hazards:
| af0601c9-d2f5-5d3c-a3eb-290cb45e12e4 | button | Select action required | Eliminate, Minimise
| 19eea0f4-22b3-531e-bee9-f3e6c557a047 | textbox | Control methods:
| 2d215a5a-f4b0-58af-abf5-3df8e8d5aaed | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| 21007e7b-02fd-48ed-bb5d-8e8d83934eaa | checkpoint | Signoff
| 2252213d-3085-5f96-ba54-27b3fa9fca11 | signoff | All persons involved in this task analysis to sign here
| 85e0067e-4b6d-42f5-9e39-14085cc5371f | checkpoint | Signoff
| 1e14e842-27cb-5315-b439-d64368d12a7c | signoff | All persons involved in this task analysis to sign here
| 188d0909-6098-5af6-bcd6-e2425dbd9f88 | checkpoint | Task 7
| 3ef654c4-8999-5782-b1f3-318fa06bdf2f | textbox | Describe steps required:
| 98306632-b8e4-5957-8fe7-3e8d8c877f41 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| daf4336f-e186-5e8c-ba99-6683b1a33565 | textbox | Identify hazards:
| 92939a0f-a21d-54ff-b4e5-98de9c8f0459 | button | Select action required | Eliminate, Minimise
| 47e81353-478a-59ac-a426-47e7096853f7 | textbox | Control methods:
| 23f6b1a7-a7b2-579b-91be-f6b90460847d | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| 6ba05570-90a0-45b3-94e7-2b6f10621b0c | checkpoint | Signoff
| ecb5534e-72f3-5f92-b352-c9621c5ddb51 | signoff | All persons involved in this task analysis to sign here
| 1b718dba-8340-4b65-bd3d-303f2d38abaa | checkpoint | Signoff
| 18bd7645-d99b-51ba-907a-a3de5a658315 | signoff | All persons involved in this task analysis to sign here
| 5a12e103-3d03-586b-89a1-b42fe5dfa007 | checkpoint | Task 8
| ea02dec5-28a3-5b6e-b9ac-1be280723da2 | textbox | Describe steps required:
| 4ccd39e3-1698-59f5-a7f5-422f08ca822f | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| 82b5b459-9be5-5117-9631-b8441773e83d | textbox | Identify hazards:
| e6495d0b-e788-5f74-b60a-d1a7eff325d2 | button | Select action required | Eliminate, Minimise
| 193ef846-0971-5191-b661-87a847f3a813 | textbox | Control methods:
| dea97879-10dd-5a09-ae3d-0b7ed66fa95c | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| ee27594a-3c26-4955-8e52-432d3fc47c9b | checkpoint | Signoff
| bca2b149-852b-547b-b1eb-c26858c01c90 | signoff | All persons involved in this task analysis to sign here
| ea891b3b-a1ba-4f3b-80cf-a06c41c6c809 | checkpoint | Signoff
| eb96c9a3-c398-5337-a0de-248ae563741f | signoff | All persons involved in this task analysis to sign here
| c79776d5-975a-50d9-861a-664305bc3a6a | checkpoint | Task 9
| 3856dbbe-e610-552f-befe-8a4601a7e7a0 | textbox | Describe steps required:
| 83014112-1370-5a99-a4c8-fbdfc5c62f62 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| 25b43b3a-ca29-54e6-a901-d2a5cc13e515 | textbox | Identify hazards:
| 060dccd0-0da4-56cc-8e81-86a1e47b7e06 | button | Select action required | Eliminate, Minimise
| 7146e76e-3121-5e64-a43c-88a4e7583570 | textbox | Control methods:
| 3a0e9adb-b53e-5193-8ebf-1c50af6879d0 | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| 7940a93a-e5e3-4861-a812-aed590f22f7d | checkpoint | Signoff
| bbd26cb1-a728-5233-bdd2-4ad24dc56579 | signoff | All persons involved in this task analysis to sign here
| 67b48110-ea6d-5c84-98c7-928bea97374c | checkpoint | Task 10
| ddb31cb2-cc02-541f-8bad-d3662f96df2b | textbox | Describe steps required:
| 689289f9-80d2-5a40-b605-5721b2a5fb3a | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| df65f29b-d661-5b97-ae01-7d87b32e9c88 | textbox | Identify hazards:
| af5f648e-0c44-5dbb-b26b-33e53a702a64 | button | Select action required | Eliminate, Minimise
| 2add2296-74ed-5f26-ab43-86551f266d1c | textbox | Control methods:
| 990be898-0fcc-5aaf-84fb-9bd6280f990d | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| f850ba62-d9c6-4c87-98a5-29e63e359d7e | checkpoint | Signoff
| c473185f-0fa9-5bdc-a35c-65f1a6b7fed0 | signoff | All persons involved in this task analysis to sign here
| 1db96f2a-f91f-5c61-9c68-2a7a9da75242 | checkpoint | Reviewed
| 2c2cd428-6507-5925-a8a2-3c2d91ce1f45 | date | Date:
| 77c1056d-e39f-517a-9896-da9afa1df8dc | signoff | Reviewer to sign
| d292941a-a1cd-41f3-b874-cd83ee57b1f1 | checkpoint | Reviewed
| 67d264bf-134a-50de-8352-bbde2b316b25 | date | Date:
| 44065d37-240c-586f-982e-e7aa9bc62c1d | signoff | Reviewer to sign
| 5a31bd70-1a39-4e71-a314-8723fc83c5fc | checkpoint | Reviewed
| f322bb92-d112-559a-a3db-bd5a817f02d4 | date | Date:
| 037da3df-1401-5948-9c62-f7a96dc6dfc8 | signoff | Reviewer to sign
| d28710df-3a7d-4762-af2a-5db0c573a41d | checkpoint | Reviewed
| 9530bb8d-330b-538a-a74f-c4388c99d3d7 | date | Date:
| 15325b67-c0ce-5c60-85eb-83bce1e5f376 | signoff | Reviewer to sign
| 201928cd-130e-44f0-ab2b-f03f069d0d67 | checkpoint | Reviewed
| 1872c82d-d706-520c-9042-35402523d3e7 | date | Date:
| 83b68f24-a235-4e3e-b927-6d075197292a | signoff | Reviewer to sign
| 56438aa9-d477-487e-957b-e6fe29f162fc | checkpoint | Reviewed
| 1dc9a1cf-4a69-5b42-8345-defb514f1204 | date | Date:
| 7a1ac6ab-6f79-4ed5-a947-58df7f836cee | signoff | Reviewer to sign
| 662563cc-c1e2-4a54-bc3d-0af07540a265 | checkpoint | Reviewed
| 08482974-1a36-5807-b451-9ee1f7f790ee | date | Date:
| ddfd8fb3-1c7b-4645-bac3-c811eaff41f3 | signoff | Reviewer to sign
| f79a7225-b957-4926-8e32-53821da468d7 | checkpoint | Reviewed
| 012fdaae-1f90-5e38-8cf1-f1c0d81e41e9 | date | Date:
| cdf6cce8-f9f1-4c77-bc7c-90f1ade703f4 | signoff | Reviewer to sign
| a6c0ad47-b8fb-48cb-ba93-363690b587a1 | checkpoint | Reviewed
| 31d10681-9ee5-5d9c-a2b6-b54643938b09 | date | Date:
| 35b6dcba-3d62-4c87-a6e2-3514bd5206e0 | signoff | Reviewer to sign
| d66eecd4-06f0-4245-8fa9-c53aa0f41712 | checkpoint | Reviewed
| 19ad2559-920c-5f4c-816a-344d6a90b3a5 | date | Date:
| 5bff908d-c4e9-4e58-a730-43ebf4fcfc68 | signoff | Reviewer to sign
| 540041d6-73aa-571b-8899-0066b667fe96 | checklist | H&S - Toolbox Minutes |  | Toolbox Minutes | 77d3542b-8d57-4b9a-8a61-f75ab42e3d44
| ea9a63c4-92c3-5d97-876b-9ccec66dd923 | checkpoint | Record of attendance and discussions
| 69380e3b-75da-5514-bd16-b53aae2af9d1 | textbox | Date:
| ce87c0cc-0a62-581b-81ed-00b8c89cda75 | textbox | Location:
| 25360a18-44d8-5fef-a75f-c97bc2619529 | textbox | Attendees:
| bbd60ee6-80e4-5294-9389-967f31f9e1cf | note | (separate attendees with a comma)
| db6010bb-4977-56a4-ac3d-62695d21c92d | checkpoint | Matters arising from previous minutes
| 7fefc92c-30e7-5c70-9673-38100aea113d | textbox
| 2a1970a5-1bc0-524b-aacb-112f23d1d847 | checkpoint | Safe work practices/incidents
| 90734f5c-0b10-5947-8d2a-ac02f05b17de | textbox
| 0c313288-5a0c-59e8-86ee-f660b078ffa3 | checkpoint | New hazards discussed/reviewed
| ffbc7a38-c2fb-5bb9-90e1-89429267b55e | textbox
| e621d61d-391c-594c-b2ad-5c707517c76e | checkpoint | Training/employee concerns
| ac7eecb7-ba1d-5cea-ae8c-78eb168f48c0 | textbox
| a467bdb2-38d2-598e-8b6c-dfd1b5344031 | checkpoint | Description of today's work
| ce872cb8-820d-5f6e-b3cc-73042bb406c0 | textbox
| 308176c7-2eb5-53fd-a7d8-a458263c1750 | checkpoint | Other items
| f44afba4-fd33-5425-bb13-c246ad39c1d8 | textbox
|  | checklist | New Template |  | Roof Logic SM Membrane System | d1dfcb94-48a2-4980-b83a-9d95a64eeeea
folder-normal is not dependant but can't have own status |  | folder-normal | Base deck fixings installed
folder-normal is not dependant but can't have own status |  | folder-normal | Vapour barrier completed
folder-normal is not dependant but can't have own status |  | folder-normal | Polystyrene flute installed
folder-normal is not dependant but can't have own status |  | folder-normal | LW compressed PIR fixed off as per manufacturers specifications
folder-normal is not dependant but can't have own status |  | folder-normal | S/M Membrane installed, welded correctly & damage free
folder-normal is not dependant but can't have own status |  | folder-normal | Penetrations with diverters complete
folder-normal is not dependant but can't have own status |  | folder-normal | All flashings installed correctly, sealed & tidy
folder-normal is not dependant but can't have own status |  | folder-normal | Internal gutters installed with outlets & overflows
| 8801737a-688b-5866-8074-11773e85ea75 | checklist | QA - Ardex Butynol |  | Ardex Butynol | 9e8b8136-a177-40f7-a200-74606c6fc1fc
| a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
| c0e9bd74-e7d8-5ee9-bae7-2272d9eaa5db | checkpoint | Area Accessible
| 31ad6319-af5f-53f1-989e-ec138593f803 | checkpoint | Substrate must be dry with max 18% moisture content
| df23a83d-03a7-5cac-a9d1-6c4bf0cd82e6 | checkpoint | Sheeting laid staggered joints (brick bond), the edge of sheet supported with framing.
| 7283c2fd-ec64-5511-9c98-306e6b422ffa | checkpoint | Plywood fix S/S screw countersunk with a 3mm gap between all sheets, 150mm centre on edges & 200mm in the body.
| 45b5b43a-b387-52f0-8ace-ed751f6ca085 | checkpoint | All joints of plywood and junctions with other materials covered with 25mm release
| faec3593-fe02-5478-9c0b-b0fbb15842f5 | section | Roof QA
| bfc0e322-1d7f-57d8-b966-33dea998d144 | checkpoint | Installed so that laps facing down
| 4130d51d-265a-578c-a9cb-c5ef1054d874 | checkpoint | Correct adhesive used as per spec
| 4d67ae84-c26c-5aa5-9960-bdae3893ab2c | checkpoint | Membrane fully adhered to plywood
| e307a628-43bb-50ae-a479-7e126b931c13 | checkpoint | Adhesive evenly spread
| a7389825-b302-5225-a2d0-5fcc03125d3b | checkpoint | Overlaps at lease 50mm
| 076b8182-9818-5342-96fa-5aac8c07e412 | checkpoint | Seam tape and seam primer used
| b862ead7-5411-5add-8576-2a466e1e1d35 | checkpoint | All lap, penetrations and details fully closed and tested.
| 840e9f99-acb7-57f4-beca-fe4c8ae8bae5 | checklist | QA - Ardex Plywood Substrates |  | Ardex Plywood Substrates | 5d36edfb-617e-48d4-a5ee-14a405313af4
| a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
| b4f476ee-b727-5944-b729-9a447c79f29a | checkpoint | Edge protection/scaffold in place
| d66ba057-caeb-564c-afb7-c2cff7a8c112 | checkpoint | Safety nets installed
| bfa930e1-5be5-5088-abad-b8a6e5f4c741 | checkpoint | Purlins/battens & all necessary timberwork complete
| 8b8ba5b8-3fd9-5ed7-a733-ec529fd2b966 | checkpoint | Other trades works damage free & protected
| faec3593-fe02-5478-9c0b-b0fbb15842f5 | section | Roof QA
| 9b1790d7-833a-54d3-8e4a-37a5e8adaba9 | checkpoint | A minimum of 17mm complying with AS/NZS 2269. CD Structural Grade plywood with the sanded C face upwards, and H3 with Waterborne treatment
| bf99d03f-8d9e-57e4-84c4-0ccd1bc8908a | checkpoint | Substrates must be dry when an ARDEX waterproofing membrane is applied. The plywood and the timber substructure shall have a maximum moisture content of 18% when an ARDEX waterproofing membrane is adhered
| 43d0617c-c2ba-5fd5-a6a3-d799eea9cbce | checkpoint | Plywood panels shall be laid with staggered joints (brick bond), the edge of sheets shall be supported with dwangs or framing
| 8ee7d27e-073a-5b72-b879-5ba28ebbc4e7 | checkpoint | Plywood shall be laid with the face grain at right angles to the supports. A 20mm triangular fillet shall be used at the base of any 90° upstand. External edges shall be chamfered with a minimum radius of 5mm
| 0b326b80-da3a-5369-877f-6b30cd002722 | checkpoint | Plywood shall be fixed with 10 gauge x 50mm stainless steel countersunk head screws with 3mm gaps between all sheets, at 150mm centres on edges, and 200mm in the body of the sheets
| c17d189f-d4e0-5111-91b2-c6b80f4aeb24 | checkpoint | All joints in the plywood and junctions of plywood with other materials must have a 25mm release tape applied before application of the membrane
| c0d6cf1f-fa2a-5f0c-a85b-a6a88a4ec3ea | checkpoint | Framing supports at a maximum 400mm centres (in one direction). All plywood edges must also be supported. Do not use tongue and groove plywood. If thicker plywood is to be used support spacing needs tomeet NZBC and NZS3064, or engineer specific design
| 769f461e-c8e2-5c2c-8164-79da22320436 | checkpoint | Clarify for how long the plywood has been exposed?
| 30cd914e-4459-5211-9d4e-426f3001c02a | checkpoint | Minimum17mmF8 CCA H3.2 treated structural plywood (not LOSP treated).
| 4585285d-c93c-5da1-b3e2-03567e4202b1 | checkpoint | Minimum CD grade with the sanded C face upwards
| 73adacec-b682-54b8-98a6-4e602bad170c | checkpoint | Minimum required falls are met , Correct falls to outlets
| f13e393c-b605-5b44-8a1d-2465a2e3a122 | checkpoint | Plywood laid with face grain at right angles to supports
| e26ef676-488a-58f8-a422-cdab9fcce48a | checkpoint | Plywood is to be laid with staggered joints in a brick bond pattern with a 3mm expansion gap between plywood sheet edges. Bond breaker tape to be applied to all plywood sheet joints prior to membrane application
| b8a4f0d7-8a8b-551a-9e55-5f96181e8443 | checkpoint | All outlets and overflows fitted and rebated into the substrate
| 82f817a4-16de-52ff-a85a-fece489b9908 | checkpoint | Plywood is screwed with 10g x 50mm SS counter sunk screws at 150mmcentres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm
| c652b27b-ad8c-53ac-85ff-795ac91d11a5 | checkpoint | Provide 20mmtimber fillets at the base of all upstands
| 90d5cce2-3774-5def-9c02-d5ea0238b3e1 | checkpoint | Chamfer all external edges with aminimumradius of 5mm
| 2ce0fc42-953c-588a-8ff0-c76c6dd3b4d9 | checkpoint | Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood and framing supports to be at no more than 18% moisturecontent
| 5c5b77d1-ff0d-504a-9ffe-cf3d101b8123 | checkpoint | All drains and outlets aremembrane compatible
| a4e431ad-4dbd-56a4-bf00-991d08140624 | checkpoint | Has the installer accepted the condition of the plywood?
| 36e8c2f8-57e3-5a12-9dec-fac3778564e6 | checkpoint | Please ensure you have clearly ordered the correctmembrane, colour and thickness for your project
| 62c11d9e-dd44-56ec-a4f7-5ca892e91f36 | checklist | QA - Coloursteel Cladding |  | QA - Coloursteel Cladding | 294399c2-ffc7-4edf-a44e-e3baf7be8202
| a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
| b4f476ee-b727-5944-b729-9a447c79f29a | checkpoint | Edge protection/scaffold in place
| 8d5859bd-c4fd-528d-aede-41c168bbc57b | signoff | Raise remedial / request review
| d66ba057-caeb-564c-afb7-c2cff7a8c112 | checkpoint | Safety nets installed
| 1d9a8c5c-0ca1-53ad-a07e-b320c8bd7181 | signoff | Raise remedial / request review
| bfa930e1-5be5-5088-abad-b8a6e5f4c741 | checkpoint | Purlins/battens & all necessary timberwork complete
| 4a6910c1-42f6-5657-857d-abb94e4467c5 | signoff | Raise remedial / request review
| f4e3af4b-1762-574f-864f-5d701f847a33 | section | Wall Cladding QA
| 3a5b9ec4-1c43-5ded-b58d-7f7efb77cd7e | checkpoint | Base flashing installed & taped with correct fall
| 392a41b6-adca-5bc3-8114-d40a0d81f222 | checkpoint | Cladding installed correct sequence
| bd75ce2b-976d-5a68-80a1-000946765a13 | checkpoint | Screws uniform & intact
| 259875ba-698b-53a8-88fb-e83d80a87fc7 | checkpoint | Foam installed where required
| 0e9117d0-0465-5c2f-9bf2-6ae1b13d8f6b | checkpoint | Flashing junctions cut correctly & uniformed - as rev details
| b59103c8-7cb8-559b-977b-08d89b030856 | checkpoint | Cladding clean & damage free
| c7de0040-c441-5568-8e97-a2e7ce585abb | checkpoint | Site clean, rubbish in bin or removed
| 1d561f3f-c6c3-5d28-a247-a534b413a5ae | checklist | QA - Coloursteel Roofing Checklist |  | Coloursteel Roofing | 64f7223b-432f-4b49-a4f2-8d4c417003ea
| a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
| b4f476ee-b727-5944-b729-9a447c79f29a | checkpoint | Edge protection/scaffold in place
| 8d5859bd-c4fd-528d-aede-41c168bbc57b | signoff | Raise remedial / request review
| d66ba057-caeb-564c-afb7-c2cff7a8c112 | checkpoint | Safety nets installed
| 1d9a8c5c-0ca1-53ad-a07e-b320c8bd7181 | signoff | Raise remedial / request review
| bfa930e1-5be5-5088-abad-b8a6e5f4c741 | checkpoint | Purlins/battens & all necessary timberwork complete
| 4a6910c1-42f6-5657-857d-abb94e4467c5 | signoff | Raise remedial / request review
| ca183b70-1c75-57b6-972a-c2414aa47594 | section | Substrate Checklist : Enviroclad Plywood
| 52878a11-a4ff-5d9e-9bf3-e6292d88e22b | checkpoint | Framing supports at 400mm centres (in one direction). All plywood edges must also be supported.
| 85db5d9d-2877-487d-99d6-1850a4e741fb | note | Do not use tongue and groove plywood. Viking Roofspec can accept the maximum support spacings provided in Table 15C of CHH Ecoply Specification Guide.
| daa8e8a5-0ae2-5259-b081-091977df63d1 | checkpoint | Minimum thickness 17mm, F8, CCA H3.2 treated, structural plywood (not LOSP treated).
| a88a7607-c943-5657-a4b3-099f985a8800 | checkpoint | Minimum CD grade with the sanded C face upwards.
| 8f3e20e8-0400-59eb-b95e-da904ed996d0 | checkpoint | Plywood laid with face grain at right angles to supports.
| d1e0a570-0a5f-5cee-8fcf-0d2be56a5d30 | checkpoint | Plywood is to be laid with staggered joints in a brick bond pattern with a 3mm expansion gap between plywood sheet edges.
| 4a41c5d3-eeaf-5868-bc9d-1594634e6a99 | checkpoint | Plywood is screw-fixed with 10g x 50mm SS counter-sunk screws at 150mm centres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm.
| 048c7033-b0e1-53c6-8f1a-c527e0716782 | checkpoint | Chamfer all external edges with a minimum radius of 5mm.
| 0eba1011-abf5-414c-95d2-dcd86e6c985b | note | *Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood and framing supports to be at no more than 18%moisture content.
| e394e72e-aed4-5742-889d-7c1192d5d820 | checkpoint | For Roofs and Roof Decks over living spaces, all cavities must be ventilated and insulated in compliance with clause H1 NZBC. Cavity ventilation is not required for a Warm Roof system which meets or exceeds the minimum R value requirements.
| 2c9421c8-62be-50e0-bea1-f9e4ace34821 | checkpoint | All drains and outlets are membrane compatible.
| 9483470c-64af-4c61-ba0c-9d4294af6851 | note | Note that TPO membranes cannot be welded to Stainless Steel scuppers or sumps. Accessories must have Clamped Grates or be TPO weldable.
| 70d3bd8f-5e07-55ee-b1dc-278071b4f442 | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
| faec3593-fe02-5478-9c0b-b0fbb15842f5 | section | Roof QA
| adc4d60d-92ee-5570-a8ef-b797a21ff53c | checkpoint | Fascia straight, cut in correctly
| e88ff7c1-8dcc-5127-a83c-adb5b36ea091 | checkpoint | Spouting installed with correct falls & outlets as per plans
| f48f40e9-589b-5a30-ae33-a4ff40aae73c | checkpoint | Underlay over fascia & trimmed neatly
| db7549cf-1519-54bf-89d2-7682ec7dd0d8 | checkpoint | Valleys straight
| 61eaa4b9-34b2-5ee8-9ee1-38a491efc961 | checkpoint | Screws installed correctly & washers intact
| 7a9d1814-4f58-533b-b4a7-8230037f4bca | checkpoint | Roof clean from debris & swarf
| 43bc51d5-f09d-5c98-a168-8bc8927f81b2 | checkpoint | Flashing junctions tidy & sealed correctly
| 28ef82cc-5c7e-54aa-adf3-5b06e9f3af3f | checkpoint | Roof laid correctly & damage free
| c7de0040-c441-5568-8e97-a2e7ce585abb | checkpoint | Site clean, rubbish in bin or removed
| b967e72f-dbc5-5549-a084-5582af54b31d | checklist | QA - Coloursteel with R2.6 Insulation Checklist |  | Coloursteel with R2.6 Insulation Checklist | c6bee418-0d9c-4a07-83a5-807751e10f48
| a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
| b4f476ee-b727-5944-b729-9a447c79f29a | checkpoint | Edge protection/scaffold in place
| d66ba057-caeb-564c-afb7-c2cff7a8c112 | checkpoint | Safety nets installed
| bfa930e1-5be5-5088-abad-b8a6e5f4c741 | checkpoint | Purlins/battens & all necessary timberwork complete
| 8b8ba5b8-3fd9-5ed7-a733-ec529fd2b966 | checkpoint | Other trades works damage free & protected
| faec3593-fe02-5478-9c0b-b0fbb15842f5 | section | Roof QA
| f23f1c03-1e41-5097-b72d-78cfd197ea69 | checkpoint | Safety mesh installed correctly
| d03c3460-165e-5886-a45d-16bd295c10d8 | checkpoint | Covertex 407 installed correctly
| a5ecf3c2-00af-5654-875c-870131780433 | checkpoint | 75mm Bayonet installed correctly
| 487c842b-c270-5915-8c46-31a6750a6160 | checkpoint | 140mm Insulation installed correctly
| 9e470424-b817-5111-97cd-07672b6e1e3c | checkpoint | 20mm Cavity bat installed correctly
| 673d43a5-c5af-526c-b5be-3b32447e5900 | checkpoint | Screws installed correctly.
| 7a9d1814-4f58-533b-b4a7-8230037f4bca | checkpoint | Roof clean from debris & swarf
| 43bc51d5-f09d-5c98-a168-8bc8927f81b2 | checkpoint | Flashing junctions tidy & sealed correctly
| 28ef82cc-5c7e-54aa-adf3-5b06e9f3af3f | checkpoint | Roof laid correctly & damage free
| c7de0040-c441-5568-8e97-a2e7ce585abb | checkpoint | Site clean, rubbish in bin or removed
| dfaea186-b750-5646-9949-c9a599a56d6d | checklist | QA - Coolstore Membrane |  | QA - Membrane | 42321a8a-bd15-450f-b6d2-816ad9761af7
| a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
| b4f476ee-b727-5944-b729-9a447c79f29a | checkpoint | Edge protection/scaffold in place
| 8d5859bd-c4fd-528d-aede-41c168bbc57b | signoff | Raise remedial / request review
| d66ba057-caeb-564c-afb7-c2cff7a8c112 | checkpoint | Safety nets installed
| 1d9a8c5c-0ca1-53ad-a07e-b320c8bd7181 | signoff | Raise remedial / request review
| bfa930e1-5be5-5088-abad-b8a6e5f4c741 | checkpoint | Purlins/battens & all necessary timberwork complete
| 4a6910c1-42f6-5657-857d-abb94e4467c5 | signoff | Raise remedial / request review
| 8b8ba5b8-3fd9-5ed7-a733-ec529fd2b966 | checkpoint | Other trades works damage free & protected
| d8aeafb7-9626-5307-9e40-267b5a694d2e | signoff | Raise remedial / request review
| faec3593-fe02-5478-9c0b-b0fbb15842f5 | section | Roof QA
| e9f626c2-c78d-540f-89f2-d9dbcbc1d5a9 | checkpoint | Coolstore panel correct
| 7b5527dd-dd15-550f-a7ed-27a61bf0b60d | checkpoint | Coolstore panel clean
| 8da2ad40-9986-5aa7-8d84-87dfd896ac61 | checkpoint | Drip edge/gutter line flashing installed
| f09cb2a8-c353-51d5-b539-43c4b3faf60a | checkpoint | Membrane laid in accordance with suppliers details
| 658e874c-8d13-56f6-b4b6-bc06d15d4b8d | checkpoint | No visible damage to membrane
| 08d6b82b-c64b-57bd-94ec-e3bcfc224348 | checkpoint | All laps welded correctly
| 177ddafd-0676-54c5-aedd-eea3b7e87fe9 | checkpoint | Flashings installed where required for termination/weathertightness
| 3b26bf81-bfee-5372-903a-a762155fd1ac | checkpoint | Penetrations welded correctly
| 2de56624-0414-5945-b84c-21091946ff47 | checkpoint | Roof/Site clean of rubbish and excess materials
| 1957b410-1e69-5aee-b274-17fa803fef07 | checklist | QA - Enviroclad |  | Enviroclad | 8d5e4d88-d36d-4233-8865-3dd5824f8ef4
| a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
| 83231cd9-63fe-5477-ab42-068ae084c39b | checkpoint | Framing support at max 400mm. All plywood edges supported
| 52eb3683-95a6-52c7-b671-37eaf5015b3e | checkpoint | Plywood laid with face grain at right angles to support
| 22b2ff8f-4548-5191-949e-5a17fe914c36 | checkpoint | Plywood screwed with S/S counter sunk screws at 150mm centres on all sheet edges and 200mm through body
| d36c477c-6543-5fb8-bd0f-da3617747615 | checkpoint | Chamfer all external edges with a minimum radius 5mm
| 31ad6319-af5f-53f1-989e-ec138593f803 | checkpoint | Substrate must be dry with max 18% moisture content
| 38ab4ec9-6ff5-50ae-b45e-8a42555b4be9 | checkpoint | All drains and outleds are membrane complatible
| c9126592-d051-5ea7-adcf-4b4f17045c10 | section | Cladding QA
| bfc0e322-1d7f-57d8-b966-33dea998d144 | checkpoint | Installed so that laps facing down
| 4130d51d-265a-578c-a9cb-c5ef1054d874 | checkpoint | Correct adhesive used as per spec
| 4d67ae84-c26c-5aa5-9960-bdae3893ab2c | checkpoint | Membrane fully adhered to plywood
| e307a628-43bb-50ae-a479-7e126b931c13 | checkpoint | Adhesive evenly spread
| 0e22268f-a299-51a2-b699-ac4e897424f9 | checkpoint | Install adjoining sheets in the same manner, overlapping edges a minimum of 50mm to provide for a minimum 40mm hot air weld
| 75e17e45-7224-5a66-9b8a-b655f73d918a | checkpoint | All lap, penetrations and details fully closed and tested
| 7410a9d1-90af-4825-9585-5394c5a23488 | checklist | QA - Gutters |  | Gutters | 5480b198-34fc-420a-91e3-4a2cd129cf0c
| 67481516-e0f4-4156-b88e-9169b2792473 | section | Gutters
| 931af666-6c6e-4869-adcd-c28f47f2a50d | checkpoint | Correct fall
| 48bc5afc-752a-4be1-8061-ae92d77f167a | checkpoint | Brackets set up in correct centres
| 6ef8ab16-6e63-46ed-b493-6e87b1f0956a | checkpoint | Droppers installed and in correct location
| 76bd4e4e-de95-44ba-beab-617144c9fe63 | checkpoint | All downpipes are installed correctly
| 937a2f97-0ff6-4207-a32b-70e1cec01e2f | checkpoint | Water test completed and no ponding
| f2d34026-5652-593d-8b26-6bbb6d974a2a | checklist | QA - Hilton Roof Sheeting Checklist |  | QA - Hilton Roof Sheeting Checklist | 9244a94a-5da3-4197-bae8-2e028b208b6f
| a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
| b4f476ee-b727-5944-b729-9a447c79f29a | checkpoint | Edge protection/scaffold in place
| 8d5859bd-c4fd-528d-aede-41c168bbc57b | signoff | Raise remedial / request review
| d66ba057-caeb-564c-afb7-c2cff7a8c112 | checkpoint | Safety nets installed
| 1d9a8c5c-0ca1-53ad-a07e-b320c8bd7181 | signoff | Raise remedial / request review
| bfa930e1-5be5-5088-abad-b8a6e5f4c741 | checkpoint | Purlins/battens & all necessary timberwork complete
| 4a6910c1-42f6-5657-857d-abb94e4467c5 | signoff | Raise remedial / request review
| ee146c23-100a-5237-9190-fd14c0131265 | section | Checklist : Roof Sheeting
| f23f1c03-1e41-5097-b72d-78cfd197ea69 | checkpoint | Safety mesh installed correctly
| e64d27ac-7c46-5894-b463-3d8bdfef19bd | checkpoint | Vapour barrier installed correctly
| 950db2c7-291b-5a1e-ac7b-0add57364a30 | checkpoint | Timber batten with ventilation holes installed correctly
| a74a41d9-7e59-5dcb-ad0b-77deb5008b21 | checkpoint | 50mm Insulation installed correctly
| a5ecf3c2-00af-5654-875c-870131780433 | checkpoint | 75mm Bayonet installed correctly
| d03c3460-165e-5886-a45d-16bd295c10d8 | checkpoint | Covertex 407 installed correctly
| adc4d60d-92ee-5570-a8ef-b797a21ff53c | checkpoint | Fascia straight, cut in correctly
| e88ff7c1-8dcc-5127-a83c-adb5b36ea091 | checkpoint | Spouting installed with correct falls & outlets as per plans
| f48f40e9-589b-5a30-ae33-a4ff40aae73c | checkpoint | Underlay over fascia & trimmed neatly
| db7549cf-1519-54bf-89d2-7682ec7dd0d8 | checkpoint | Valleys straight
| 61eaa4b9-34b2-5ee8-9ee1-38a491efc961 | checkpoint | Screws installed correctly & washers intact
| 7a9d1814-4f58-533b-b4a7-8230037f4bca | checkpoint | Roof clean from debris & swarf
| 43bc51d5-f09d-5c98-a168-8bc8927f81b2 | checkpoint | Flashing junctions tidy & sealed correctly
| 28ef82cc-5c7e-54aa-adf3-5b06e9f3af3f | checkpoint | Roof laid correctly & damage free
| c7de0040-c441-5568-8e97-a2e7ce585abb | checkpoint | Site clean, rubbish in bin or removed
| e58760a7-f1e2-5b60-a482-9b7299fa9395 | checklist | QA - Kingspan Roof Checklist |  | Kingspan Roofing | 57afe919-3659-4db1-a07f-5995f468af4c
| a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
| b4f476ee-b727-5944-b729-9a447c79f29a | checkpoint | Edge protection/scaffold in place
| 8d5859bd-c4fd-528d-aede-41c168bbc57b | signoff | Raise remedial / request review
| d66ba057-caeb-564c-afb7-c2cff7a8c112 | checkpoint | Safety nets installed
| 1d9a8c5c-0ca1-53ad-a07e-b320c8bd7181 | signoff | Raise remedial / request review
| bfa930e1-5be5-5088-abad-b8a6e5f4c741 | checkpoint | Purlins/battens & all necessary timberwork complete
| 4a6910c1-42f6-5657-857d-abb94e4467c5 | signoff | Raise remedial / request review
| 5a3e7a2b-9930-57e9-b8a6-b6144f8d4dd7 | section | Kingspan Roof QA
| de6591da-5a36-500f-a4f0-8b08d0599bd8 | checkpoint | Screws tight & washers intact
| dec764b9-4a7a-5d5d-af10-b325200f4e3b | checkpoint | Roof clean of roofing debris
| a45e9fde-9439-512b-b24f-843f4f774112 | checkpoint | Roof clean of swarf. If FAIL, mark on plan areas of concern & include photos
| 0a85e97b-0d58-55aa-8b30-c0633c386f17 | checkpoint | Undamaged roofing sheet profile. If FAIL, mark on plan areas of concern & include photos
| a44a91f7-2f88-5377-85b7-35351d229dc4 | checkpoint | Scratches - mark on plan areas of concern & include photos
| c8d3798c-33c2-558a-adda-1a7d38797a8f | checkpoint | Roof laid in correct sequence
| 0efed9e9-794c-5e6b-9999-c573cecbcd70 | checkpoint | Flashing junctions sealed & tidy
| f990ee8d-89d8-59a9-8e12-608d97228cb1 | checkpoint | Lap tape installed correctly
| 13059466-a6ce-490a-a2c1-56cdbccfab8c | checklist | QA - Kingspan Roofing Checklist |  | QA - Kingspan Roofing Checklist | 6564f604-919f-4e1f-8bb5-6e1367d3d64c
| a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
| b4f476ee-b727-5944-b729-9a447c79f29a | checkpoint | Edge protection/scaffold in place
| 8d5859bd-c4fd-528d-aede-41c168bbc57b | signoff | Raise remedial / request review
| d66ba057-caeb-564c-afb7-c2cff7a8c112 | checkpoint | Safety nets installed
| 1d9a8c5c-0ca1-53ad-a07e-b320c8bd7181 | signoff | Raise remedial / request review
| bfa930e1-5be5-5088-abad-b8a6e5f4c741 | checkpoint | Purlins/battens & all necessary timberwork complete
| 4a6910c1-42f6-5657-857d-abb94e4467c5 | signoff | Raise remedial / request review
| 5a3e7a2b-9930-57e9-b8a6-b6144f8d4dd7 | section | Kingspan Roof QA
| de6591da-5a36-500f-a4f0-8b08d0599bd8 | checkpoint | Screws tight & washers intact
| dec764b9-4a7a-5d5d-af10-b325200f4e3b | checkpoint | Roof clean of roofing debris
| a45e9fde-9439-512b-b24f-843f4f774112 | checkpoint | Roof clean of swarf. If FAIL, mark on plan areas of concern & include photos
| 0a85e97b-0d58-55aa-8b30-c0633c386f17 | checkpoint | Undamaged roofing sheet profile. If FAIL, mark on plan areas of concern & include photos
| a44a91f7-2f88-5377-85b7-35351d229dc4 | checkpoint | Scratches - mark on plan areas of concern & include photos
| c8d3798c-33c2-558a-adda-1a7d38797a8f | checkpoint | Roof laid in correct sequence
| 0efed9e9-794c-5e6b-9999-c573cecbcd70 | checkpoint | Flashing junctions sealed & tidy
| f990ee8d-89d8-59a9-8e12-608d97228cb1 | checkpoint | Lap tape installed correctly
| f939b35b-7a61-5a79-bc8b-9a9f0925c9bc | checklist | QA - Nu Wall |  | Nu Wall | 9711ba3a-972c-4651-af82-e098c61c120b
| a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
| 23b6e36f-f95e-5dde-8089-f73698f7bb05 | checkpoint | Substrate - Inspected and Straight
| 077477ee-ef2d-5d45-a286-b033197e2ce0 | checkpoint | Single Castellated Batten 600mm Centres
| c13727e2-1c4d-561e-9f6f-ca20a2cfe4a6 | checkpoint | Separation Barrier Installed
| 475a2d58-0616-5893-9920-93a5978a89ec | checkpoint | Windows Installed and Set 18 - 20mm out from Batten
| c9126592-d051-5ea7-adcf-4b4f17045c10 | section | Cladding QA
| 6b9a8de3-53db-5607-926b-9b871d87f88f | checkpoint | Head flashing Installed Taped and Stop ended
| 37da922b-b4af-5835-8b7b-bd20b84df7d3 | checkpoint | Window / Door/ Base Flashing Screwed at 300mm Centres
| da0d1f9e-9f04-5ad4-a40e-0a27d05f1c69 | checkpoint | Window / Door Foam Tape Installed
| 717aa8b2-2ea0-5bf3-8c9a-fd3b2935542a | checkpoint | Plastic Soakers Installed Around Window / Door Jams
| e4eba7a1-7606-5248-83e7-f954fecc3a91 | checkpoint | Cladding Brackets Installed evry 600mm
| 4244102b-5693-55b6-85c5-d0adfc2ac85c | checkpoint | Cladding Free from Damage / Scratches
| 608905fd-d1ec-5cf4-97d1-fdc7a0ac6597 | checkpoint | Site Clean - Rubbish Removed
| 326afb36-1f37-4a3b-aa1c-9f673b9fd72d | checklist | QA - Purlins, Noggs, Plywood install |  | QA - Purlins, Noggs, Plywood install | b90d935a-b97d-4bf4-b6a9-219891ef5166
| 3a6c111c-eed1-4426-96c5-a88e818ee1c6 | section | Details
| ebd4a903-a79b-4fc4-a7b5-313ffa64797d | checkpoint | Purlins as specified, Correct fixings and spacings. Installed straight.
| d0eeed3e-2929-4572-bf12-9dd7a7e57726 | checkpoint | Nogs at correct spacings.
| 217ef630-3fec-470a-a940-cacb9de90d1e | checkpoint | Plywood correct thickness, installed correctly with specified fixings.
| 58a8cce4-5d06-55e6-a7f8-4a2f0e95bc16 | checklist | QA - Roof Logic Fibertherm MSR |  | Roof Logic Fibertherm MSR | 4d6f0dcf-1eb4-4219-a8ae-5f3d423c6c25
| 160df85e-f083-5149-8142-df030d8b2114 | section | Liner Deck
| 7aca4ffa-d55d-510a-9c32-a94f4649e2b7 | checkpoint | Liner deck correctly installed and correct lengths
| 070f96c1-f49e-5416-8f3b-6a5b64f1683a | checkpoint | Liner deck fixings as per roof logic specifications
| 9065be5a-5abc-5c36-8b4d-5d42b5f788cd | checkpoint | Profile foam installed
| d239f214-fa37-5762-b4ff-51851c4ca497 | section | Structural post and rails
| 4b33cabc-6dbf-5894-aa91-234bbe05e55c | checkpoint | Post and rails correct spacings as per Roof logic
| e2e21323-5997-5be7-8c14-fc8698729305 | checkpoint | Fixings as per roof logic specifications
| a99d3159-c615-5c99-ab30-b9d3a98ab5df | section | Butyl Tapes
| e3487aae-a009-59ce-8ceb-39d1ba2bb58e | checkpoint | Base sheet laps taped
| c0848133-b98f-5eca-8f48-80ac46b60084 | checkpoint | Under flashings / Penetrations taped
| f7b868a1-06da-5103-ae4b-0c91936ca794 | section | Elite Insulation
| 3e8f57fb-92be-556c-a03b-a9e98499e441 | checkpoint | Installed and to the specified R value
| 52828e74-0e54-52ab-82d4-aa89fa3f0b0d | section | Top Sheets
| ce6023a5-e5e1-5635-97b9-3ea5da4e6a87 | checkpoint | Top sheet installed in the correct sequence
| bcf08e49-2ea7-5ad4-b5ca-f930f941f844 | checkpoint | Fixings straight washers in tacked
| 38915ae3-30d7-5288-b8ce-d8b2dc874141 | checkpoint | Sheets correct lengths and turn ups / downs done
| 2c75e7ef-3001-5ce6-9695-f11983659bea | checkpoint | Profile foam in place
| 22479ea0-8f28-5b63-9780-e00369c3f789 | section | Flashing / Penetrations
| 2f5669bd-6bb5-55e0-aae0-a7010eed2f4d | checkpoint | Flashings correctly installed
| 3e7fd24b-6341-51c6-a959-e42078037c66 | checkpoint | Junctions neat and sealed
| e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | section | Final Inspection
| 3ec0bb9c-d646-586e-9919-aefbe34142c2 | checkpoint | Roof clean all rubbish removed
| e8c0d883-6c4d-5818-a297-4beeb0997207 | checkpoint | No damage / scratches
| 90cb6428-d055-5b68-9798-1e1afe5a5a2e | checklist | QA - Roof Logic SM Membrane System |  | Roof Logic SM Membrane System | 82bbcc99-4943-4301-add2-7dc5f1f6f03b
| 4951e42e-6be1-56e6-9bd9-d5a10efb7282 | checkpoint | Base deck fixings installed
| dfe5d3b6-d414-5c96-a077-d723b3b4ab33 | checkpoint | Vapour barrier completed
| 70249f84-a0df-527f-9b84-a21183acce63 | checkpoint | Polystyrene flute installed
| 957ea167-9b50-5ba0-81db-66f043817d25 | checkpoint | LW compressed PIR fixed off as per manufacturers specifications
| d38979f7-a0ab-53ce-94f2-efeadaf751bc | checkpoint | S/M Membrane installed, welded correctly & damage free
| 9b9c57e4-15d3-55ce-9c83-2bf56c16dd81 | checkpoint | Penetrations with diverters complete
| 6f725e57-6a3f-533d-99f2-cfb8025554c7 | checkpoint | All flashings installed correctly, sealed & tidy
| c5ef6710-ddfc-5009-88db-29cf13d222b4 | checkpoint | Internal gutters installed with outlets & overflows
| 998db05d-0c22-5ff1-befd-0de3842979ae | checklist | QA - Rooflogic UltraTherm MSR Roofing System |  | Rooflogic UltraTherm MSR Roofing System | 33e8a3cf-65dd-4f26-956e-b4f2c1a275d1
| a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
| 431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
| 695b83f0-0043-5642-8427-d674630e40b3 | signoff | Raise remedial / request review
| 999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
| bbd145ec-75af-57df-88ba-42f50005165a | signoff | Raise remedial / request review
| 9c51e892-57fc-56f4-891a-a1021b63bfd3 | checkpoint | Substrate acceptable (clean, dry and stable)
| 32594108-1836-52b6-b949-dd2b506200c6 | signoff | Raise remedial / request review
| 0928ba5b-96f3-5dc7-8d60-9a2911dae719 | section | Surface Preparation
| 9b9a75a0-9636-5b16-b1be-2c09ad4bd3a0 | checkpoint | All purlins are in place
| 862b7622-d514-5b0a-bf08-cbdc86bbf49a | signoff | Raise remedial / request review
| 0a1307d7-f803-50f9-888c-2c18396ba47c | checkpoint | Under flashings installed
| df2fc6f6-06c0-58de-a1df-c00180124eb8 | signoff | Raise remedial / request review
| d9ff5339-45ae-56fa-8ef9-6be936bc5398 | checkpoint | Sheets in good condition for roof installation
| 5793832d-2de3-50de-b8cc-684879b6b04e | signoff | Raise remedial / request review
| 16c5b34f-8cac-5015-a959-fab255ea795a | section | RL Base Deck
| 4e77911b-5903-5dd0-aa63-1536c3389e9b | checkpoint | Installed in accordance with specification
| c950976a-0318-535c-b115-abf3d739f4ba | checkpoint | Installed in accordance with project specific and Rooflogic standard details
| af8d9815-371f-5086-9b5f-850c50c99e0a | checkpoint | Correct fasteners used and installed with correct frequency (i.e. 1 fastener per trough along every purlin line
| c2d85594-faca-5d84-a86f-151a54cf252e | section | Vapour Control Layer
| a20db41f-e8ce-5d91-ba05-5fdc80238685 | checkpoint | Vapour Control Layer installed to top face of acoustic board
| c00a89af-8c21-5216-8aec-a93401ef6e2c | checkpoint | Correct side laps (80mm) and end laps (100mm)
| 3226f481-ac57-585f-a57d-b37b904d874a | checkpoint | Vapour Control Layer to be installed in accordance with project details. Ensure Vapour Control Layer is correctly terminated to ensure vapour control continuity at roof openings, transitions and at horizontal to vertical roof/cladding junctions
| 43e2aa1e-5eee-51a8-810a-a424fd2dc094 | checkpoint | Any damage to vapour control layer repaired to ensure vapour control layer 100% continuous.
| 57068517-b895-5732-84f8-3b71b2956d7a | section | RL Acoustic Board, PIR Board and FRU 36 Underlay
| c0a4c510-28e7-5abd-86c2-5094e6eeab32 | checkpoint | Acoustic Board installed over Vapour Barrier and mechanically attached to the substrate
| 1ea1a3e4-b3cf-5b89-96cb-23ebf9f1da64 | checkpoint | Correct thickness input
| d572bf04-a2fe-5393-a6f5-880f80e41cc1 | checkpoint | Any damaged insulation board has been cut out and replaced with new tightly butted piece of acoustic board (minimum 300mm x 300mm piece.)
| 469c2bdd-0021-55da-891d-da7013c6c900 | checkpoint | RL PIR Board insulation to be installed continuously over vapour control layer to roof and gutter in accordance with architectural drawings
| 12dd9cc4-b0e0-54b5-93a0-0ee393111c91 | checkpoint | Any damaged insulation board to be cut out and replaced with new, tightly butted piece of PIR Board (minimum 300mm x 300mm piece.)
| 22794620-a8db-58bd-957f-6020bf650ec1 | checkpoint | Install Dristud FRU 36 underlay with 150mm side laps and, if required, 200mm end laps
| b20eaa7c-3595-4fe9-90c1-0a4ed29d1e8d | note | NB. The underlay can be installed in line with the fall of the roof and there is no requirement to install safety netting beneath the underlay or use a self-supporting grade underlay. The underlay is fully supported by the high density rigid insulation layers and will not sag or deflect either during application or over the life of the system.
| 2d4c15fd-6e97-5775-ad52-0a012d4aa3e3 | section | Top Deck
| ca8cff62-f376-5c1d-bb13-829e54586e95 | checkpoint | Visually inspect material delivered to site. Confirm all delivered materials correspond with order and specification.
| 5b27b797-9c69-59f5-9c3f-e6c6ce63d691 | checkpoint | Fix according to specified fixing pattern to achieve required wind uplift resistance
| be907a7d-850b-5eda-99d9-aca485390c0f | checkpoint | Correct fixings/profiled washer assembly used.
| c5c6eccf-9d81-56e5-bd72-5664fe9d8fbe | checkpoint | Allowance for thermal expansion when fixing sheets
| 33a414d6-d23d-5d46-9671-99e76dd755e2 | checkpoint | Sheet set out square
| e0fe1790-c649-5eeb-8be0-476ee999bbc5 | checkpoint | Sheet length as required to achieve specified gutter overhang
| 59c14941-a721-51c4-8236-d92be1eeaad9 | checkpoint | Stop-ends and turn-downs to sheets
| e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | section | Final Inspection
| 4f6f60ea-81b2-5034-91bf-2ddeeee8db05 | checkpoint | System installation is complete
| 0d4aa82c-a06c-5501-8c9e-6b52eab2dee6 | checkpoint | Installation of fixings in accordance with specification and appropriate wind zone
| 0cd8d4cb-c053-510e-886d-0253f7c27f74 | checkpoint | All flashing details in accordance with specifications, plans and details with correct type and spacing of fixings and placement of seals and sealants
| 8f372bc7-3f55-5c8c-bbb0-0dade669c8b0 | checkpoint | All construction equipment and materials removed from roof/site
| ad9928a4-c65a-5d08-a91b-7c3cd9ee33c6 | checkpoint | Any damage to top skin or associated flashings rectified by repair or replacement
| ba941bc7-d05d-5ee2-81d9-3b4e850deb60 | checkpoint | Debris, sward and other contamination cleared/removed from roof
| 3bf8dfea-b0c7-5a26-b351-8ef698c0ecab | checkpoint | Maintenance Documents submitted to Main Contractor/Building Owner
| 7dee3fd5-e45c-5c82-9c66-9071637e87b7 | checklist | QA - Rooflogic UltraTherm Xtreme Roofing System with Fibretite Membrane |  | Rooflogic UltraTherm Xtreme Roofing System with Fibretite Membrane | 1fed0e6c-2808-4870-8d30-8b3e37da5812
| a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
| 431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
| 695b83f0-0043-5642-8427-d674630e40b3 | signoff | Raise remedial / request review
| 999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
| bbd145ec-75af-57df-88ba-42f50005165a | signoff | Raise remedial / request review
| 9c51e892-57fc-56f4-891a-a1021b63bfd3 | checkpoint | Substrate acceptable (clean, dry and stable)
| 32594108-1836-52b6-b949-dd2b506200c6 | signoff | Raise remedial / request review
| 0928ba5b-96f3-5dc7-8d60-9a2911dae719 | section | Surface Preparation
| 9b9a75a0-9636-5b16-b1be-2c09ad4bd3a0 | checkpoint | All purlins are in place
| 862b7622-d514-5b0a-bf08-cbdc86bbf49a | signoff | Raise remedial / request review
| 0a1307d7-f803-50f9-888c-2c18396ba47c | checkpoint | Under flashings installed
| df2fc6f6-06c0-58de-a1df-c00180124eb8 | signoff | Raise remedial / request review
| d9ff5339-45ae-56fa-8ef9-6be936bc5398 | checkpoint | Sheets in good condition for roof installation
| 5793832d-2de3-50de-b8cc-684879b6b04e | signoff | Raise remedial / request review
| 16c5b34f-8cac-5015-a959-fab255ea795a | section | RL Base Deck
| 4e77911b-5903-5dd0-aa63-1536c3389e9b | checkpoint | Installed in accordance with specification
| c950976a-0318-535c-b115-abf3d739f4ba | checkpoint | Installed in accordance with project specific and Rooflogic standard details
| af8d9815-371f-5086-9b5f-850c50c99e0a | checkpoint | Correct fasteners used and installed with correct frequency (i.e. 1 fastener per trough along every purlin line
| c2d85594-faca-5d84-a86f-151a54cf252e | section | Vapour Control Layer
| a20db41f-e8ce-5d91-ba05-5fdc80238685 | checkpoint | Vapour Control Layer installed to top face of acoustic board
| c00a89af-8c21-5216-8aec-a93401ef6e2c | checkpoint | Correct side laps (80mm) and end laps (100mm)
| 3226f481-ac57-585f-a57d-b37b904d874a | checkpoint | Vapour Control Layer to be installed in accordance with project details. Ensure Vapour Control Layer is correctly terminated to ensure vapour control continuity at roof openings, transitions and at horizontal to vertical roof/cladding junctions
| 43e2aa1e-5eee-51a8-810a-a424fd2dc094 | checkpoint | Any damage to vapour control layer repaired to ensure vapour control layer 100% continuous.
| 5938a466-bd4d-5f64-a003-67d1a5e47867 | section | Install RL PIR Board and RL Roof Board HD
| 469c2bdd-0021-55da-891d-da7013c6c900 | checkpoint | RL PIR Board insulation to be installed continuously over vapour control layer to roof and gutter in accordance with architectural drawings
| 12dd9cc4-b0e0-54b5-93a0-0ee393111c91 | checkpoint | Any damaged insulation board to be cut out and replaced with new, tightly butted piece of PIR Board (minimum 300mm x 300mm piece.)
| 02cd45b7-d474-5b41-8b8d-cfe4b6bf2feb | checkpoint | PIR insulation to be dry prior to application of RL Roof Board and Fibertite membrane.
| 4f871f4f-d7f2-59ad-bddd-aa145c32baca | checkpoint | Roof Board HD to be installed over PIR Board and mechanically attached to the substrate. Fasteners to be installed in accordance with the prescribed fixing pattern.
| 792b1eb7-75c4-5164-897d-479e5143bf21 | section | Adhering Fibertite Membrane
| 81e70536-1cab-5cf5-b117-f027a822f9f7 | checkpoint | Install Fibertite membrane in strict accordance with Project Specification.
| 7304fa34-e3ca-50de-ab79-126ad37457ce | checkpoint | Ensure substrate (e.g. Roof Board) is dry and free from dirt, debris or contamination.
| 169a2efa-74c7-56ad-b2c8-647e0e2b160f | checkpoint | Select adhesive as specified
| e8bb6c91-7e88-4eed-9140-a258ac5743eb | button |  | 190E, 490U, 690U,490E
| 1216659b-d839-5292-b83f-30d9dad5ea9e | checkpoint | Adhesive applied as per specification -Ref specification cl .3.13 in project specification
| 27052b6b-78b5-568e-b24a-202d8c21f2b4 | checkpoint | Take into account ambient air temperatures and humidity levels
| ba50ce50-4525-5cbe-a549-4b3ea837ce22 | section | Welding Fibertite Membrane
| 46fae741-ec52-57bf-b3ed-c777883c184b | checkpoint | Test welds carried out daily with hand-held welders
| 046230b3-3be3-5459-9f60-d5d42be72d6e | checkpoint | Test welds carried out when commencing and re-commencing welding with robotic welder (e.g. start of day, after break.)
| 19ea4380-89fd-5aeb-8a0e-80fb36eab904 | checkpoint | Seams to be welded clear of dirt, debris, moisture and adhesive residues.
| ae22c991-57fe-53d7-b042-ed2ecea1d308 | checkpoint | Seams wiped clean (both surfaces to be welded) with Acetone and clean, white cotton rag
| c888ab6a-c9e2-508d-8683-b67922eee61d | checkpoint | Hand and Robotic welding to be carried out by trained personnel familiar with equipment and membrane
| f70a3559-03e1-5d91-b25e-8f57e29d7728 | checkpoint | Daily inspections of all completed work by way of seam probing to ensure all welds are secure, fully closed and watertight
| b2c488ba-935f-5bf7-a640-c27600c3a885 | checkpoint | Any welding deficiencies rectified on the same day they are seam probed
| f7b72917-a559-5b87-8887-47cac59b0564 | checkpoint | Night joints are installed daily, as required, to ensure that no moisture is allowed to migrate under the installed membrane.
| e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | section | Final Inspection
| 4f6f60ea-81b2-5034-91bf-2ddeeee8db05 | checkpoint | System installation is complete
| 3062e849-1017-5c63-8bd6-ba45206ab93a | checkpoint | All membrane terminated with either thermoplastic weld or mechanical clamp/termination (drain clamps with no missing bolts)
| 9925e84b-ca57-5ae9-a5f7-66721f54b53f | checkpoint | No exposed membrane terminations that could allow water behind
| 0c0d1b65-f19e-55e5-b349-d175e6a217bc | checkpoint | All terminations (details in accordance with project specific and standard RL construction plans and detail drawings.
| 30f1153a-90e6-5ea8-a6b4-dd48c83666a5 | checkpoint | Any damage to system and/or membrane have been recorded/ rectified
| ef661bc0-9cb1-59f1-8208-15cac2200766 | checkpoint | All construction equipment and materials removed from roof/site.
| 3bf8dfea-b0c7-5a26-b351-8ef698c0ecab | checkpoint | Maintenance Documents submitted to Main Contractor/Building Owner
| 9c61e2be-cf27-523f-9442-0b4a4249838c | checklist | Rescue Plan Checklist |  | Rescue Plan Checklist | 8969e375-eaee-4c59-baf7-640769f29c9e
| 9d51497a-32d0-5818-9e4b-2d4cf127c673 | checkpoint | General details
| df1b2b13-eb59-59cb-856b-a15295aee280 | textbox | Location
| 193ba206-b82e-5239-919e-2b8ca01fbabe | textbox | Supervisor
| 434e85af-7570-541c-8f84-eb92215a851d | date | Date
| 93555361-1164-5ca6-a4bd-4de290d16778 | checkpoint | Team members involved
| 58b6de50-ca2b-54ca-817d-4f4335d1f592 | signoff | ALL TEAM MEMBERS TO SIGN HERE
| 3a039052-b953-51a7-b349-4eae5c126b76 | checkpoint | Rescue details
| da0f956b-d3df-57ea-9fc2-5d043dc2113c | note | Please note training competencies and responsibilities
| 779f1e63-f2a0-51fa-89c0-8f7b50e018ac | textbox | Nature of Emergency
| a9056506-9261-57dd-9126-3fac8e19c94d | textbox | Rescue Method
| 703ce2e1-951c-5db7-9c09-6aa192fe8013 | textbox | Rescue Equipment
| 3eae9dd7-1a0d-5bce-abb5-d41f0ccdcdc0 | textbox | Communication & contact numbers
| 0d4ced32-43fe-55da-801a-33981b4b620e | textbox | Medical Requirements
| c7dbde9a-949b-534a-9882-103e255c3249 | textbox | Emergency Services involvement (if applicable)
| f1f663ed-7fc7-4e13-a91f-9e56eafcd3a6 | checklist | Ultratherm Xtreme Derbigum membrane system |  | Ultratherm Xtreme Derbigum membrane system | ec3ea972-7b15-43b7-8aa3-318fe5b81152
| 0d4bdfc9-2364-4c69-81e3-579de60ca73e | checkpoint | Substrate
| b17a0c8f-7fa8-418d-bd30-cd699eeb128d | checkpoint | RL Base sheet Liner deck
| 0dbb605a-2eb3-45e5-a65e-9283d07b2558 | checkpoint | Fixings
| f8ddf59e-8d18-42e7-bee6-516d17537f7b | checkpoint | Vapour Control Layer
| b7638123-9de4-4743-ba41-2e3e29dc7b80 | checkpoint | PIR Board
| 653bd473-69c9-43f0-a5b7-2bb12f93f879 | checkpoint | Securock installed correctly
| 1283bde1-e837-4a76-ba47-1641bac4c7e8 | checkpoint | Fixings to specification
| 7a8e0128-26ab-469d-8934-d6b174a2ca86 | checkpoint | Primer is used with correct application sequences
| 94c9e922-b216-472b-b38f-17320326c089 | checkpoint | Leak Detection installed correctly
| 2d65c57d-0d47-4b25-b80b-c158fd550299 | checkpoint | RL Derbicoat HP base sheet (fully adhered)
| d115f14e-65e5-4d3a-b908-a414225fe922 | checkpoint | RL Derbicolour FR Cap sheet
| 7cf082c1-f134-4365-8a92-a632d34c1e22 | checkpoint | Penetrations
| 94e9412a-2733-44e7-8fe8-7e409044448e | checkpoint | QA (laps, damages, trade interuptions, repairs)
| 1b4a1b81-5c3a-422b-aab0-e09cccfe966f | signoff | Sign off

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Crane Lift Plan Checklist |  | Crane Lift Plan Checklist | 37f9f5a9-ea3b-4991-a5a1-524fa02747ab
| section | Lift plan details
| checkpoint-no-value | Lift plan details
b6926c0c-82df-5246-8d61-748aaa27b0eb | textbox | Customer
45a2da6c-8018-50de-b40e-e27968880adc | textbox | Site representative
f539c759-eb99-5921-b5d8-81172b55a9bd | textbox | Crane supplier
7fdbd583-ef8f-5962-962d-df88349a0f07 | textbox | Crane make/model
2a4263a4-df9d-5af4-8b9e-99e62a385ef4 | textbox | Crane operator
82dde959-7bce-50d1-9f2a-716196efac87 | textbox | Date and time of the lifts
376c909f-3546-5b5e-ac6b-9ec0b06a8256 | button | Communication | Radio, Hand signals, Other
93a57b73-9d37-50c9-9abe-a7165b58a5f4 | textbox | Specify if other
ee575260-2ed5-5719-9a33-11d8f82fa6c0 | textbox | Lift description
fcc0aaed-5512-5207-a02f-bb697e2b991d | textbox | Crane ID
c7e1289e-7350-51fe-b972-d32fa1a2f31e | textbox | First Aider
6699d035-6a04-54aa-a748-2ef99730ec13 | textbox | Dogman
a72348d4-c9e9-5c31-887f-0f89914dfc25 | textbox | Location
| checkpoint | Hazard checks
43048c4a-8aa0-5715-83a8-672da7b12b82 | tickbox | Workplace hazards
3ca62ec9-7e0d-59a7-bd24-57104563289c | tickbox | Crane Hazards
6e31246c-7746-5b46-8902-7ac57e9c0a2f | tickbox | Crane Operator ticketed
54a7e2c9-8c9f-5bb1-bdb6-869c30b7112b | tickbox | Dogman ticketed
5b4d686e-2f28-5e87-8184-fbb837935948 | tickbox | Fatigue managed
d7401911-1286-5b34-abdb-59258d1ddd74 | tickbox | PPE correct
b25e3d92-8b7f-5c9a-8291-ffbdd2a2e6ff | tickbox | Crane cert correct
f826ca4b-112f-5d26-a454-f01116c2c63f | tickbox | Lifting equip certs correct
4bd47e6f-188d-56f3-96bc-a98c660bc6fb | tickbox | Rating charts correct
a982a844-c021-5c8f-881b-b119d4c3b754 | tickbox | Counterweight correct
58e4baac-8f34-557c-bc16-1465d72ae238 | tickbox | Reeving correct
ea3eaa14-1742-5a60-a5cc-dedc205e86c8 | tickbox | Outriggers Ext/Pinned
42504207-7b7b-5be1-bb09-ec898a9ab66a | tickbox | Vision conditions checked (sun strike/bad lighting/dark/fog/obstructed/control sunglasses/lighting/radios/spotter )
56f2fa22-349e-548a-949d-348fa3d52601 | tickbox | Weather conditions checked (fine/wet/ice/wind)
e076d73e-5507-5988-88d1-d46bece93234 | tickbox | Traffic managed (people and vehicles)
99aac7f4-b0a9-58c6-a0b6-70c3e3b7053f | tickbox | Radio's checked
75b61362-8cea-58f1-89c8-4ee7352efc4a | tickbox | Airport notified
1e8e1d93-6c70-56d8-ac42-33aa37098b38 | tickbox | Hazard notification required (WorkSafe NZ: hazard notification)
b729e9e6-98bf-5112-a92f-6501e0619de9 | tickbox | Crane setup as per lift plan
72642d6c-b347-50ea-b447-79bc104d13b1 | tickbox | SLI configured and working
cc620a2e-7bf3-5337-94a2-99325cc86cc4 | tickbox | Electrical hazards (power lines/load attached to power; power lines must be at least 4m away unless you have a permit)
922f15f7-a7d9-51e0-b898-b681963ecb5e | tickbox | Crane is earthed
89876007-91cd-5349-90ef-bcf43fb29a1b | tickbox | Ground conditions checked (flat, can support crane, access without sliding etc.)
a9dcd5dd-5117-5611-920e-fe1e4063698f | tickbox | Underground services are clear (water, power, storm water, waste water, septic tanks etc.)
50507cbf-53e3-5ff9-b665-76e12f709a0c | tickbox | Obstructions checked (slew, structures, boom, overhead, buildings etc.)
c1154ff0-b6bb-52ab-a4c4-b091e3fffdda | tickbox | Rigging methodology discussed
6a5af6c2-5664-5419-abf3-c708d16c1bd6 | tickbox | Load support checked
fdea58c6-be8a-54b0-bb90-dcc2406aff5e | tickbox | The lift will use a tag line
d4c6b328-843a-59e6-986e-7fb9dc057fb6 | tickbox | Loose objects removed from load
f70b4107-e2e2-5c79-862e-59e15d109f55 | tickbox | No simultaneous operations
3965892e-8416-5396-b4b7-12df048be4db | tickbox | Mancage checks
9aaefcae-5315-55c9-a9e1-061385cc9078 | tickbox | Confined space checked
5f473559-36e9-52bb-a7a1-9558ba0310a0 | tickbox | Environment checked
| checkpoint | Lift details photographed and uploaded
| checkpoint | Lift sketch photographed and uploaded
| checkpoint | Acknowledge
cb35ceac-d2ce-5226-846f-2324dd611d6d | textbox | Crane Operator
d0a5d12a-6680-520f-964a-d49e9bb5aa6c | textbox | Dogman
f4a4709e-83d5-527a-8944-f86af736bfa5 | textbox | Site Representative / Customer
03eae6f0-aae3-433d-b5db-de61af6558ca | checklist | Site Inspection Checklist |  | Site Inspection Checklist | 49450426-70bd-4642-a230-071ac42b9c65
60afc33f-617e-4ce1-9ed3-6e7627ca0e24 | section | Site Control
f1b66757-cb95-4b97-8a07-a0c6b98587f3 | checkpoint | Hazard Board and signage up-to-date
cca0e913-3969-411c-940a-1a541c5eeb18 | checkpoint | Environmental plan - issues
184b6d6d-c19e-53eb-8786-cf7b5105d06c | textbox | Toolbox talk last date:
58c46cc7-76d7-45bb-a523-c7df83f3d37b | checkpoint | Safety inductions for all on-site
09514458-2504-4182-8c93-bd740e5244b4 | checkpoint | Safety notice board current
1f55790d-574e-4d3d-b59d-8033ccac81cd | checkpoint | Task Analysis up to date
be20a8d6-c0c7-462e-b7ba-f99fbfb24c99 | checkpoint | Procedures in Task Analysis being followed
0aba2851-55f5-4a55-802e-c61643fc3c71 | section | Site Facilities
d1501466-9003-486b-b10a-10bc254937ab | checkpoint | Offices clean, adequate & good lighting
cf002835-170f-4811-a9eb-5acb0d42182a | checkpoint | Smoko sheds - clean, portable water
ab267d51-2ed3-48da-886e-5a5782aa997a | checkpoint | Toilets - clean, washing water
bba784ba-f549-4d47-a875-5e4aea7d8868 | checkpoint | Tool /equipment sheds adequate
43cd0dc3-0bea-4d79-bbb8-54dabced2cfe | section | General Site Tidiness and Access ways
66920665-f602-4892-9e23-0e32df5d1947 | checkpoint | Clear, safe access to work areas
fd30b3cb-3131-4108-bc54-1f94f0d49f1c | checkpoint | Stairways and accessways clear
204ce79d-6291-4667-b341-50576c8dac4c | checkpoint | Hoardings /fence and gates secure
adeab3e2-d67f-4ee5-b435-fb38bd131a52 | checkpoint | Loose materials secure from wind
c24948d1-a47c-43ff-b0c1-f8df990a7d2b | section | Notice of Delay/Damage
d689eebf-2302-44fc-92ce-03eafa380309 | checkpoint | Notice of Delay/Damage
f7e5aaa3-35fc-52b4-9db0-1a06ae54e092 | textbox | Reference Point
c81b180c-3349-5cdc-ae9c-de7b02d54554 | textbox | Description
83addf41-129a-431f-9c1e-1375271fe278 | signoff | Request Review / Send for Acknowledgement
5904e1c0-6c86-40ae-bf40-5705a667fd5c | checkpoint | Delay/Damage Acknowledged
66d19e5f-5952-496b-9296-a735d37bb8d6 | section | Personal Safety Equipment
03d1ca7f-9904-4e5a-a4e3-ea8be4c01b92 | checkpoint | Signage displayed and legible
3841af3d-c39d-4050-9d1f-574d27bc59ca | checkpoint | Hardhats being worn
159c11b3-e442-4f5c-a0df-659018b72753 | checkpoint | Correct footwear being worn
66eb470b-0861-42a3-a47f-ffb29bbe47a5 | checkpoint | Glasses /gloves /ear muffs /vests /masks used
8543944f-a6f8-40f0-9cd5-b26d3dc34f5d | section | First Aid/Fire Prevention
932792d2-e58b-4027-8901-35df52c49a0b | checkpoint | First Aid Box Available
0cab6934-5d61-4706-a5e4-c5d499ef1501 | checkpoint | Accident register
f4e17b4f-2326-45ac-b95e-ada797adbb9d | checkpoint | Fire Extinguishers
1d2dc73a-e94c-5316-8e6d-fb43bb0f4ca6 | tickbox | Available
ca096386-7446-5d69-9c7d-fa02fadcf00e | tickbox | Current (12mth)
7b03e9a2-16a8-5d56-be06-86c463999e37 | tickbox | Sufficient number
75c77b92-eff1-4965-af46-6e2f73620c67 | checkpoint | Evacuation
cb29a992-17f7-575b-9ad9-442991caac8f | tickbox | Procedure current
a3094678-0225-5b61-be85-1fd1ea14460a | tickbox | All emergencies incl
796fde00-f4cc-442a-8e1c-4e304db482e5 | section | Cranes/hoist/lifting equipment
581b96f3-313c-4831-b941-0ded61b48325 | checkpoint | Proper lift assessment plan done
cfbf69e7-6f3b-4f92-ac5e-b82452bde5ab | checkpoint | Crane certification current
236d5d00-2b3f-48ad-a3f4-4cc54cdf71d9 | checkpoint | Slings/chains certified
366c86a8-e0e3-4ad0-9f9b-a7d73323fd81 | checkpoint | Operator procedures in place
8a9e5690-9bbd-4646-b5f5-c23a1ec4d881 | checkpoint | Inspections being done
2139e28d-55a1-4efe-b626-7f7ec8be6b1f | checkpoint | Man cage available
3998021f-cccd-480d-83d4-7036a32b715b | checkpoint | Emergency plan in place
6f2d6cd7-309a-4c92-b972-c71252c3a3b2 | section | Compressed air equipment
339699b7-77b9-453e-b241-a29327f86b29 | checkpoint | In good condition
cc17bf0f-9645-4eb8-9107-35dca9c7a221 | checkpoint | Appropriate guards fitted
9526f7e2-f7f0-4e09-a55f-3a61d88de258 | checkpoint | Trained user
9c5498ac-4a67-47aa-b1a2-b76df6873a43 | section | Excavations
d0277593-ea47-4fcc-b343-577077f55e67 | checkpoint | Correctly Shored
b07f54a2-c86e-4702-ac86-e88aee42c7b9 | section | Hot Works
3943b97e-6dbe-4792-9dc3-93b7a949ab1e | checkpoint | Hot work permits being issued
dc8522de-1539-4b66-b07f-3ddd22e893b3 | checkpoint | Fire extinguishers on hand
2a86e0d7-145b-4291-b0ae-cca399262225 | checkpoint | Operators using PPE
9a09a816-1ca0-4c88-b886-d65ce1dd3a7d | section | Electrical Equipment
68949b9e-4435-4d97-bee1-923d2a430a35 | checkpoint | Main board lockable /weatherproof
7efa20d2-30f7-4418-852b-0a91a487ce0d | checkpoint | Current tagged and damage-free leads
d4e489e6-8a6b-43ec-ac4a-7cabd42685a2 | checkpoint | Current tagged plant
14f9a186-9b8d-43b6-9c8f-b5124975999a | checkpoint | Current tagged lifeguards
088c8e03-7080-4965-832b-3e59df574aae | checkpoint | Leads safely placed
2e7ce64a-c0e7-4713-bc33-22969117825f | checkpoint | Equipment in good condition
7820ecdf-9403-4047-ae96-dbe37a7625d2 | checkpoint | Appropriate guards on equipment
92a8af8d-4641-4ec8-8efd-77b92c31be47 | checkpoint | Adequate temporary lighting
65532257-0331-4c6d-afe8-7678e2626ee5 | section | Chemicals
ccb71487-788d-4fcf-a3e5-aa42149305ba | checkpoint | Correctly stored
707ccf97-c254-4a3e-8684-96576fc322d3 | checkpoint | Safety Data Sheet (SDS) available
cd997028-d8ae-4458-a933-583b4a8da6ef | checkpoint | Operators using PPE
582012c1-3423-420e-a9d9-3abd0bdf8bf9 | section | Tools
179162bd-0aa4-4b9e-962c-f6db5dcf11fc | checkpoint | PAT tool WoF current and secure
692c2f2d-d606-4253-be21-c66bb28757a7 | checkpoint | Staff trained in tool use (SWPS)
76afab8b-37e9-446e-bef0-7e7d825ea031 | checkpoint | PAT signage on site
4f7a7579-e3b5-402d-85fb-f1efd2e9f0b8 | section | Scaffolding
a6b8b628-7d1b-41d0-8ecc-f3a2012b195a | checkpoint | Notifiable weekly Scaftag/current
acf65aa5-d00d-48a2-950c-c8f2624c9816 | checkpoint | Handrails/mid-rails
61457962-4576-4478-815c-e39fc8bf4c9a | checkpoint | Toe boards
1c4cf5e9-d072-4f5b-acc3-d394b739d383 | checkpoint | Platforms
9695d228-5eab-422a-a9cf-ab006f9be0b1 | checkpoint | Ladders/stairs
cca0c051-f20c-445c-bdb0-42e4a1d33fb4 | checkpoint | Base sound
0f088e1e-39e5-4c71-b687-574bf6ed1ef6 | checkpoint | Work platforms clear
a5a18db9-572d-4eec-92c5-1ca5a9d67380 | checkpoint | Platforms trip free
d6068e0d-2d6b-4409-be23-46e32e480361 | checkpoint | Planks tied down
d76eedb9-fb46-412c-bacd-c1cf94b2226d | checkpoint | Headroom clear
c000d72b-67c7-4274-9c53-64f77c253c10 | checkpoint | Ties/bracing adequate
eb8bbfe4-a1ad-4d6e-a0fc-929bb6015fa7 | section | Ladders
1c180c09-4cde-4e17-a372-5469af3f92f9 | checkpoint | Good condition
45cdfede-cae1-4658-9a17-3348098be19f | checkpoint | Secured top and bottom
02475e84-4bf9-450a-9680-72a15fc1cdb7 | checkpoint | Stays to step ladders
61c3c327-65ff-41d4-98a5-1416ff67eacb | checkpoint | Working 2 steps down
503fcfd5-79f4-465a-93b5-ae136848fa5b | section | Fall Hazards
251ead6e-4862-48f3-b6a8-f96aa788cb49 | checkpoint | Fall Hazards
ea644de7-537a-4e9b-ab21-fcc68b899835 | checkpoint | Floor openings
c4e242e4-ee49-43cb-a8a9-cd0dac2a0d3e | checkpoint | Lift shafts
c835c517-7cb9-4d61-a195-a2c1653324cf | checkpoint | Stairs
afb0f4a8-ce11-4cbd-aea4-b6caee1cab1c | section | EWP Checklist
e372ed40-1212-4ff8-8d1e-a1a70d1d0db9 | checkpoint | All below items closed out
6ecc8a12-70d0-5e44-a0ab-be549b3e1ef7 | textbox | Team member to "pass " once satisfied all below items have been addressed
063d9f4f-80f2-4cd2-86da-84ddc38faf24 | checkpoint | EWP check # 1
e9298a0c-046b-41f5-9131-fcd8b8bbe970 | checkpoint | Logbook Current
5dd2214b-fec3-5a1b-bdd8-fc3eadf48626 | textbox | Date of last logbook signature
2581165f-3199-4108-afb8-9beba40af40f | checkpoint | Machine cert current (six months )
40ec8f76-5682-4976-b715-9eaf46d2d451 | checkpoint | If in use is it being used correctly
b0dfb67a-b1a3-47c0-aa4d-8135a1f3d31c | checkpoint | If outside is it rated correctly
4fd7a41b-df7b-4f3b-a37f-5bbdc305fafb | checkpoint | Is Correct PPE being used/harness/lanyard
7f717c6c-81e7-4b22-925d-5cdf4e8e0d7c | checkpoint | If being used are the operators competent
fdbf9521-2b67-541e-9e7f-cd8b6989d989 | textbox | Action/allocated to
a8436985-c060-48cc-9159-60b37530d054 | checkpoint | Action completed