## Master List Templates
Warnings | Id | Type | Name | Values | Prompting Name | Resource Id
| a4715e4f-bfd7-53fe-b4ac-2c95038275db | checklist | Add Delay / Damage |  | Notice of Delay/Damage | cc9b07d0-57b6-4cf2-b1b4-2af67cfdc18d
| d67d1f9a-530c-5ac4-ada0-4630b559dd43 | checkpoint-no-value | Notice of Delay/Damage
| 04d652de-4dce-46c0-a1ef-3432b444bcae | textbox | Reference Point
| e72120d4-51ec-451b-856c-a513bf3b3c98 | textbox | Description
| c925a483-418b-5420-b389-591ef23eb6a5 | signoff | Request Review / Send for Acknowledgement
| 6e201a15-bcad-52b8-9179-94426a1c5170 | checkpoint-no-value | Delay/Damage Acknowledged
| 967ee202-a218-46c4-98c8-b6d773c666b2 | button |  | No,Yes
| 31f884dc-4dfa-5171-9626-9f8a1060529d | checklist | Add Variation |  | Variation Details - | 740b2e42-f0eb-4d80-bf0b-728c7110867e
| af43077e-903d-5d88-8da8-e50a24463098 | checkpoint | Variation Details Approved
| 28d26279-c304-4689-8317-1deb797dc8fe | textbox | Reference/Drawing/Instruction Number
| 2247155b-6de8-434c-a1e1-058d724a6a62 | textbox | Variation Area
| ae7fc046-dca9-4fab-98f8-374caeb044ec | textbox | Materials & labour breakdown
Invalid dependant | 822653e1-1a8d-5c1e-9229-bee00e9e7e9a | signoff | Request Variation Acknowledgement
| 8d20db40-ceeb-512f-b832-5bd4676ee2c5 | checkpoint | Variation Completed
Invalid dependant | d302c95c-762e-5e5c-a32b-f0e8b483eb06 | signoff | Request Variation Signoff
| 513602b4-a55b-4ce2-8073-0a73c8e3ae53 | checklist | Charge Up Sheet |  | Charge Up Sheet | 7fbb5c4b-73e1-46e6-bcbc-646fd93c33d1
| 45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| 7f13a2c9-c9aa-4c0e-ab2d-ac8e45d6ef20 | checkpoint | Details
| d79a2570-6909-5bb7-adae-24c2064efd7e | textbox | Project
| 331fda8f-f0e4-586a-bbc2-c89aed258607 | date | Date:
| 3c8a8191-d510-5ced-894c-bdc3fa57ee00 | textbox | Variation Description:
| efb29f45-08dd-59ab-8dc3-3b925506029e | textbox | Staff Names:
| 69a1df50-3782-5837-b593-e457661ac779 | note | Hours worked
| cb3a6fcf-63d7-5036-925a-5d3be3e64ecb | textbox | FROM:
| 8b571dd3-2412-5d0e-a805-c94c972ee65e | textbox | TO:
| 9c022897-d754-5b74-aae2-eb538285f300 | textbox | Travel (KM'S)
| c68cf2ce-5f9e-555c-9ff3-2d5e2f5d2f79 | button | Materials Ordered: | Yes,No
| f7f6793c-344d-524f-b46c-abc78ffe4192 | textbox | Please note where orders were placed OR attach the order
| a4b1fac8-ddf7-4232-90a8-cd44b35eb74b | checkpoint | Callout/Measure
| 104300e9-e956-4b86-95fc-5456f3e65a07 | checkpoint | Iron
| a5801c4e-c22d-41e5-939b-576875330a0b | checkpoint | Ridging/Flashing
| e6ed17c5-5017-44ea-be79-b46d1c56ee21 | checkpoint | Downpipes
| 2031baf7-58ef-4332-8eb7-e9d2b6ca4bc5 | checkpoint | Droppers/Bends/Brackets etc
| 78550fe2-198d-426f-b36a-482ddfd14f73 | checkpoint | Spouting/Fascia
| e533a81f-ddcc-4b05-a80b-869d565fb1db | checkpoint | Stopend/Bracket/Corners
| 64815423-39c2-4a85-9e06-b4be28f13016 | checkpoint | Screws
| a538dfbf-d000-4f36-bd8c-19cef0ca0a4d | checkpoint | Paper/Netting
| 4e1ed599-1371-46ec-a545-97d4809bffe1 | checkpoint | Sealants/Rivets/Other
| 8bbd0f58-1703-4dec-a9ca-05896c883ab6 | checkpoint | Clearlites/EPDM/Profile Washers
| 76ee89cb-fc6a-4d4e-b1c2-5b754099e556 | checkpoint | Access/Scissor
| fe611019-e07b-4ea2-90dc-53e6655eb668 | checkpoint | Edge Protection
| d6fcfd04-e5cc-4e9d-b528-b3cbeba856a5 | checkpoint | Site Manager Signoff
| eef0e216-77fc-5a5e-837c-c3b2ae520740 | textbox | Site Manager Name:
| 16d1c55f-7d32-4fe4-8073-0ace8685d22c | signoff | Site Manager Signature:
| 092a5d35-a23e-5f51-b85f-b30b695272d2 | checklist | H&S - Accident / Incident for Register |  | H&S - Incident / Accident for Register | 6a915984-006c-4684-9c22-307f7a988524
| 8111ace1-1386-5c1f-8290-3df28e3c8d3f | checkpoint | Details
| 8cda870c-753f-5137-9817-f83dbbc3ba7b | textbox | Date & time
| 43b983e5-5bf8-5976-aeca-9949de9e5682 | textbox | Name of Person
| 3ab28167-bd09-57f3-b93a-b83ce22e17f1 | textbox | Description of accident/near miss
| 0304d0fa-7d8b-5288-b869-cb4d429324e0 | textbox | Cause of harm (if any)
| 030c3127-762a-5b1e-bd08-02634d52cfd6 | textbox | Type of injury or disease
| da68050c-5bc8-5d1a-a2d0-7a12e3a4f55e | checkpoint | Immediate Action Taken
| c98e01d5-790e-5866-8e95-772c4d9b01c8 | tickbox | First Aid
| ad061492-f0ab-50bd-88c9-48c918f1ed04 | tickbox | Corrective Action
| ca667166-e882-5333-a703-8dc3824cb01f | tickbox | Review Risk Register
| 335dfac9-0b66-58be-a8f9-975d37b4c2f6 | checkpoint | Does the incident require Work Safe notification
| 53a6732a-82d9-5575-9e1c-fa232b948ab6 | button |  | Yes,No
| 76b99723-72cc-542b-82e6-3836b82ed050 | checkpoint | Is the incident the subject of a Toolbox Talk
| 880c93d9-2333-5a7e-aa2b-d78653e3ead3 | tickbox | Yes
| 683a7547-43ae-5590-bcbc-a142953938db | checkpoint | Signed Off
| 3692b921-7927-5be0-8665-655dd4671e0d | checklist | H&S - Accident / Incident Full Report |  | H&S - Accident and Incident Full Report | 649d2f73-a6b3-4b65-9687-55e6f78ecce1
| 1e73e335-4fa9-567b-a94b-c2f5490516df | section | Employee to Complete
| b44195bd-c0a4-5680-aed8-885e7c3ad764 | checkpoint-no-value | Information about the employee who had the incident
| 791e5f8b-957a-4e5c-ae2a-dbea0994ad62 | textbox | Name
| 41a7f6d6-9313-487b-8dcc-9b277dd4f16f | dropdown | Role | Client, Contractor, Visitor,Employee
| 1e2fe6ca-d24d-465b-9e4e-c50a681f2481 | textbox | Job title (if employee
| 1a039a8f-3f21-494a-b3ac-567764d019bb | textbox | Contact telephone
| 4442ebb8-f60e-50ea-8154-56309093aaa1 | checkpoint-no-value | Information about the incident
| a5d6bb9c-5e9f-49da-aa40-247c16a5cb77 | dropdown | Type of incident | Accident, Property Damage, Property Loss,Near Miss
| 4be9c3ef-228e-4be2-b5ff-fcbadcab3c31 | textbox | When did the incident happen?
| 768ccefc-717f-4f1b-911d-904dc970bc9f | textbox | Where did the incident happen?
| c4587cb6-e9b5-49cd-b5f1-20cb1d1029e7 | textbox | What happened? (Include details of any object, machine or substance involved, or property lost or damaged.)
| 4852316b-6944-45ef-b08a-4add1a45c98e | button | Was a known significant hazard involved? | No,Yes
| 6bcea14e-258b-4b74-a51a-ec00162bc35f | textbox | If YES - what was the significant hazard?
| 89279f72-6406-568d-861f-2bd1f93eef3c | checkpoint-no-value | Name(s) of any witnesses
| 0fc0fb37-5796-43f2-9c05-dd3677ab0063 | textbox | Name and contact info
| 28590cb0-b269-4805-b18e-9d3b80ad1d32 | textbox | Name and contact info
| ea53a9a7-0719-4d58-9c11-a58ca89d006f | textbox | Name and contact info
| 4301b38d-8a77-470f-8246-d945eaaa03ca | textbox | Name and contact info
| 5066017b-a70d-42e5-961b-bf70d88eb09f | textbox | Name and contact info
| a3b3f9c6-9349-5490-a06a-8766c052739d | checkpoint-no-value | What injury or injuries were sustained?
| 9326d889-dc5e-4cd2-a9f4-35d1f8ea6c64 | textbox | Body part injured (plase indicate which side of the body e.g. right or left)
| d9c2ca4b-4232-4322-be1e-415ed0b69e42 | textbox | Type of injury (e.g. break or sprain)
| f3be42c8-2f9b-44f5-809e-43344b38b4aa | button | Is this a notifiable injury? | No,Yes
| 22597bbe-e03e-4890-a68d-02ab6fddbb63 | textbox | If YES - Work Safe NZ
| c0b74e12-5bce-506c-9ff5-1e8710716bcc | checkpoint-no-value | What trearment was given?
| 501e09a6-a1ab-426d-96a1-743d129bacb3 | tickbox | First Aid
| 823f018c-9c45-45e6-9208-8a2bfd1e1f12 | tickbox | Physiotherapy
| d8135d84-9e2b-412d-84a6-e8e8998b05f4 | tickbox | Massage therapy
| c6b1f7dd-bf20-43b1-96ff-642735cb341f | tickbox | Doctor (GP)
| 29bb6b52-1a1c-42b7-9398-f288ce24fc18 | tickbox | Hospital
| 06dc9c0d-5d57-4c45-b8c0-35d2a8f0a5b4 | tickbox | Emergency services
| 3b5602b9-da77-48cf-baa5-b84994c2cc2f | tickbox | Other
| da5e368b-5e84-52f0-82d8-82be7c89aa5d | checkpoint | The above report provides a true, accurate and complete account of the accident / incident / near miss
| 6fd64a8c-5a03-4fd9-813e-d2a1ea1e1fad | note | Employee to Sign
| 6bb7806e-b892-5156-b233-c03be09eb308 | section | Manager to Complete with Employee
| 8111ace1-1386-5c1f-8290-3df28e3c8d3f | checkpoint-no-value | Details
| 42b74fe1-2e33-43bb-869c-80ff911b6249 | textbox | What (in your opinion) were the causal factors of this incident?
| 40fe19d3-b5af-532e-b4ae-6a6200913eb8 | checkpoint-no-value | Hazard identification
| 1e0b1dc2-a946-4360-84cf-228007cf2d0c | button | New Hazard Identified | No,Yes
| e34e2ae5-fde4-4cd0-83c6-95609442b7a4 | button | Significant | No,Yes
| 65447533-330f-45f1-ac14-9b11376e15aa | note | If YES identify the hazard management process to be done e.g. update hazard register and put in recommended actions below
| 3a453423-a1fd-540f-b29a-f619da71aed9 | checkpoint-no-value | Recommended Actions - Has the Hazard Management Process been undertaken
| 81cebe0c-bc93-4278-bdbe-8c13afbcf0b8 | button |  | No,Yes
| e2410cb2-0178-4ccb-a8de-52c46b875fa7 | textbox | What has been done?
| ec792840-9bfe-49f6-8271-b1ed28400b2c | textbox | Person responsible for this?
| bfbc08e2-8f7b-488e-b308-0d20f45563b4 | textbox | By when?
| 97e279d1-af6d-5137-8e10-c322e3fff906 | checkpoint-no-value | Recommended Actions - Is a review of Safety Management System required?
| 99ab7927-c71f-4898-a1d0-67df21f24d19 | button |  | No,Yes
| e792e9e7-bf45-4a64-b192-8729d6fdb682 | textbox | Which part?
| 9688f557-0559-4387-b49d-9a1c60f306a8 | textbox | Person responsible for this?
| 7437ff28-6a0b-494c-aef0-270caf445ec7 | textbox | By when?
| 5e4bdda8-248f-5658-bffc-6fa674701629 | checkpoint-no-value | Other recommended actions
| c904865d-72e1-4704-b510-dcfb8d6a04e8 | textbox | Specific actions to prevent recurrence
| b091d029-5f3c-486c-bea4-be8b9d8aa3c0 | textbox | Person responsible for this?
| 0bec84c9-7e23-4da5-be40-46a881e42227 | textbox | By when?
| 0e731c78-4c41-4127-9aff-2316ba5c5a81 | textbox | Specific actions to prevent recurrence
| 170a60de-1873-4940-a769-ec3f02eec828 | textbox | Person responsible for this?
| 5c05522e-5642-4c8b-a02f-1ebfeb6900b9 | textbox | By when?
| cc083986-69ff-52ed-9057-42a9c3a80409 | checkpoint | All relevant staff members have received information regarding the incident, changes of operation / procedures.
| 212333ca-0bcf-4192-ba6d-fa63f41df598 | textbox | Person responsible for this?
| 31833c13-0eb9-4c4a-8b36-3ef052dd0967 | textbox | By when?
| 097796a8-48f6-5ec3-bc5a-76b162b189d4 | checkpoint | If a notifiable incident has ocurred, have WSNZ (as relevant) reporting procedures been followed.
| 6236c182-4787-5f04-915b-d18709ebae57 | checkpoint | Have internal reporting systems been followed?
| 07adee93-1283-4cda-a38f-c936c1fe52ad | note | E.g. Toolbox, Close out
| 176b822c-20b3-5f7d-9210-fa00cad35d94 | checkpoint | Has the incident been recorded on the Accident Database
| 3354a6f3-5050-591c-af7d-6bb47ebc3f0a | checkpoint-no-value | Overall comments
| 91d68b65-398e-47c4-87ce-38dd20981ac3 | note | E.g. Health and Safety review actions.
| 030f26cf-68a4-5ecf-9ff3-cab9ecb17240 | checkpoint | Manager Sign Off
| c13838b3-7aaf-4883-bd80-6bad71839a26 | note | Manager to sign
| c1142197-1e98-5249-bc11-f36d998e6089 | checklist | H&S - Task Analysis |  | Task Analysis | 8dea143f-ce6e-4616-9ee9-cd635f61c346
| 45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| 8111ace1-1386-5c1f-8290-3df28e3c8d3f | checkpoint | Details
| 40427842-5edf-5c38-852f-748774fb461c | textbox | Job description:
| f8a26940-83c9-5173-9119-de3884d9db9a | textbox | Project/site:
| d4bdfc02-f6ac-5b28-b548-e16ce6dd3232 | textbox | Date:
| 4276a48e-0d28-545b-bde9-7032ff473375 | textbox | PPE required:
| 9ac26ff1-b960-5524-aed0-79ecc069db9c | textbox | Plant required:
| c20227fa-24fe-5aab-9467-071e08047cb0 | textbox | Signage required:
| 9768303f-39fb-549c-baf2-c56b3553def3 | signoff | Person completing this task analysis to sign here
| a83eac8f-b9d5-5eb0-8dc8-dc1694c6f016 | checkpoint | Task 1
| 5f39c8e8-b1f1-5b32-95d7-fb79de09df7a | textbox | Describe steps required:
| c8f656e9-1059-5d4c-8c92-86781bb0089a | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| 62cc8668-f7ef-5d2a-9824-1d7a1d72e854 | textbox | Identify hazards:
| 97086881-cfaf-5d44-bde2-0d77d059acf0 | button | Select action required | Eliminate, Minimise
| 89d9a6d6-2d7f-5883-a0a9-bd1c18eb9307 | textbox | Control methods:
| abb7ef83-c3ce-5169-a630-ae0da8642837 | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| 42c21dbd-9bff-5051-bd1f-f936237b2320 | checkpoint | Signoff
| cc191907-6808-5a08-b7e6-5d947e1865eb | signoff | All persons involved in this task analysis to sign here
| 15528ba3-d1f6-5918-a3aa-3ef338fe1ead | checkpoint | Task 2
| 13c69e11-f4af-5a03-a111-7c7fcb52451d | textbox | Describe steps required:
| daa69e9e-573c-5763-8546-9f46164345a1 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| e5e0dbec-c9b7-5c80-afa1-341b3aa72364 | textbox | Identify hazards:
| 09dfe371-002f-57fb-8253-044fe1251023 | button | Select action required | Eliminate, Minimise
| 74b4a096-f4a1-50da-b2e7-899cd2a3cc28 | textbox | Control methods:
| 24c20771-f400-56a2-91fa-e2db1d2821c5 | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| 1be8acc6-d979-4750-bf0a-a41e6b41ec6b | checkpoint | Signoff
| 3b2241a7-4391-5e74-b296-abd8081d6688 | signoff | All persons involved in this task analysis to sign here
| 80436cc7-4dbf-5cce-a6c8-7f08ccd202f9 | checkpoint | Task 3
| b94aa874-2c71-5b40-9774-2c3f0945c50e | textbox | Describe steps required:
| 53db78eb-bec9-587f-a417-9c5afa559594 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| d981a12f-564f-5477-ba27-ce3c90a640ea | textbox | Identify hazards:
| 91c09d5c-e3cc-50f8-9ade-bcd941d821cc | button | Select action required | Eliminate, Minimise
| 29f4ca79-80e6-55e2-8830-182a6bde991b | textbox | Control methods:
| 397f99cf-4219-558b-9c2f-93355accc2c9 | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| 428ce69b-de38-47c8-ba97-ad15ab45f7d4 | checkpoint | Signoff
| 20a46ba7-4201-553b-9717-c37d7fbf4bb4 | signoff | All persons involved in this task analysis to sign here
| 79d35d09-3c5b-59ae-9c63-46dff1027007 | checkpoint | Task 4
| eac8044d-2706-58e1-86fc-07655dd04e6d | textbox | Describe steps required:
| e8badd54-559e-5faf-957c-ca0b22c99d40 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| 6ab3f7a8-f670-52f3-beb4-98aad500f6f0 | textbox | Identify hazards:
| f13c9ab0-9b6b-53a6-8922-567c1a3d003e | button | Select action required | Eliminate, Minimise
| 25e5e6c9-4f3e-5883-a609-570eeb9a7786 | textbox | Control methods:
| 95b199ac-b0f1-558b-a19e-89875042615a | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| 2bdf171b-4a14-4425-80aa-e36d96e54c5d | checkpoint | Signoff
| 31c5e2e2-2eac-5cdb-8625-84bfc48087cd | signoff | All persons involved in this task analysis to sign here
| 6146adf6-9f16-515c-aa5b-6e6839d23cdf | checkpoint | Task 5
| 5cd5f2d2-eb32-5e73-8d31-9c8d8a23edd6 | textbox | Describe steps required:
| 01cc5107-54cc-5b51-8c2c-c0b5bb6377b7 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| 95ac8ec0-1b72-56a4-85e4-2e0ea871c37b | textbox | Identify hazards:
| ba52b3e3-3fc8-55cc-94ca-f83743bb3665 | button | Select action required | Eliminate, Minimise
| 6f7544c1-a398-50f6-bc30-f10c2afa2f20 | textbox | Control methods:
| 99f6629d-6ba0-5b04-acee-218fbcbfce47 | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| b0d7b6f5-8f5d-46f6-a3be-aedb2599334f | checkpoint | Signoff
| 6c175da0-a605-5cee-aba2-b37a97cbb207 | signoff | All persons involved in this task analysis to sign here
| 5f31f459-8312-4596-bfcf-2998ba9f0e26 | checkpoint | Signoff
| 1c8eb113-fc3e-59c3-bc00-a9c88ffa1697 | signoff | All persons involved in this task analysis to sign here
| c28028db-cc55-5320-ac76-ddfc80b73a42 | checkpoint | Task 6
| f2148293-360e-5d70-81af-15b3152cb9ed | textbox | Describe steps required:
| da03e97a-e4ca-5a47-b561-ad38255e238f | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| 03b89aad-a483-546c-9547-308fdc0f4672 | textbox | Identify hazards:
| af0601c9-d2f5-5d3c-a3eb-290cb45e12e4 | button | Select action required | Eliminate, Minimise
| 19eea0f4-22b3-531e-bee9-f3e6c557a047 | textbox | Control methods:
| 2d215a5a-f4b0-58af-abf5-3df8e8d5aaed | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| 21007e7b-02fd-48ed-bb5d-8e8d83934eaa | checkpoint | Signoff
| 2252213d-3085-5f96-ba54-27b3fa9fca11 | signoff | All persons involved in this task analysis to sign here
| 85e0067e-4b6d-42f5-9e39-14085cc5371f | checkpoint | Signoff
| 1e14e842-27cb-5315-b439-d64368d12a7c | signoff | All persons involved in this task analysis to sign here
| 188d0909-6098-5af6-bcd6-e2425dbd9f88 | checkpoint | Task 7
| 3ef654c4-8999-5782-b1f3-318fa06bdf2f | textbox | Describe steps required:
| 98306632-b8e4-5957-8fe7-3e8d8c877f41 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| daf4336f-e186-5e8c-ba99-6683b1a33565 | textbox | Identify hazards:
| 92939a0f-a21d-54ff-b4e5-98de9c8f0459 | button | Select action required | Eliminate, Minimise
| 47e81353-478a-59ac-a426-47e7096853f7 | textbox | Control methods:
| 23f6b1a7-a7b2-579b-91be-f6b90460847d | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| 6ba05570-90a0-45b3-94e7-2b6f10621b0c | checkpoint | Signoff
| ecb5534e-72f3-5f92-b352-c9621c5ddb51 | signoff | All persons involved in this task analysis to sign here
| 1b718dba-8340-4b65-bd3d-303f2d38abaa | checkpoint | Signoff
| 18bd7645-d99b-51ba-907a-a3de5a658315 | signoff | All persons involved in this task analysis to sign here
| 5a12e103-3d03-586b-89a1-b42fe5dfa007 | checkpoint | Task 8
| ea02dec5-28a3-5b6e-b9ac-1be280723da2 | textbox | Describe steps required:
| 4ccd39e3-1698-59f5-a7f5-422f08ca822f | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| 82b5b459-9be5-5117-9631-b8441773e83d | textbox | Identify hazards:
| e6495d0b-e788-5f74-b60a-d1a7eff325d2 | button | Select action required | Eliminate, Minimise
| 193ef846-0971-5191-b661-87a847f3a813 | textbox | Control methods:
| dea97879-10dd-5a09-ae3d-0b7ed66fa95c | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| ee27594a-3c26-4955-8e52-432d3fc47c9b | checkpoint | Signoff
| bca2b149-852b-547b-b1eb-c26858c01c90 | signoff | All persons involved in this task analysis to sign here
| ea891b3b-a1ba-4f3b-80cf-a06c41c6c809 | checkpoint | Signoff
| eb96c9a3-c398-5337-a0de-248ae563741f | signoff | All persons involved in this task analysis to sign here
| c79776d5-975a-50d9-861a-664305bc3a6a | checkpoint | Task 9
| 3856dbbe-e610-552f-befe-8a4601a7e7a0 | textbox | Describe steps required:
| 83014112-1370-5a99-a4c8-fbdfc5c62f62 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| 25b43b3a-ca29-54e6-a901-d2a5cc13e515 | textbox | Identify hazards:
| 060dccd0-0da4-56cc-8e81-86a1e47b7e06 | button | Select action required | Eliminate, Minimise
| 7146e76e-3121-5e64-a43c-88a4e7583570 | textbox | Control methods:
| 3a0e9adb-b53e-5193-8ebf-1c50af6879d0 | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| 7940a93a-e5e3-4861-a812-aed590f22f7d | checkpoint | Signoff
| bbd26cb1-a728-5233-bdd2-4ad24dc56579 | signoff | All persons involved in this task analysis to sign here
| 67b48110-ea6d-5c84-98c7-928bea97374c | checkpoint | Task 10
| ddb31cb2-cc02-541f-8bad-d3662f96df2b | textbox | Describe steps required:
| 689289f9-80d2-5a40-b605-5721b2a5fb3a | button | Select initial risk | Very Low, Low, Moderate, High, Very High
| df65f29b-d661-5b97-ae01-7d87b32e9c88 | textbox | Identify hazards:
| af5f648e-0c44-5dbb-b26b-33e53a702a64 | button | Select action required | Eliminate, Minimise
| 2add2296-74ed-5f26-ab43-86551f266d1c | textbox | Control methods:
| 990be898-0fcc-5aaf-84fb-9bd6280f990d | button | Select residual risk | Very Low, Low, Moderate, High, Very High
| f850ba62-d9c6-4c87-98a5-29e63e359d7e | checkpoint | Signoff
| c473185f-0fa9-5bdc-a35c-65f1a6b7fed0 | signoff | All persons involved in this task analysis to sign here
| 1db96f2a-f91f-5c61-9c68-2a7a9da75242 | checkpoint | Reviewed
| 2c2cd428-6507-5925-a8a2-3c2d91ce1f45 | date | Date:
| 77c1056d-e39f-517a-9896-da9afa1df8dc | signoff | Reviewer to sign
| d292941a-a1cd-41f3-b874-cd83ee57b1f1 | checkpoint | Reviewed
| 67d264bf-134a-50de-8352-bbde2b316b25 | date | Date:
| 44065d37-240c-586f-982e-e7aa9bc62c1d | signoff | Reviewer to sign
| 5a31bd70-1a39-4e71-a314-8723fc83c5fc | checkpoint | Reviewed
| f322bb92-d112-559a-a3db-bd5a817f02d4 | date | Date:
| 037da3df-1401-5948-9c62-f7a96dc6dfc8 | signoff | Reviewer to sign
| d28710df-3a7d-4762-af2a-5db0c573a41d | checkpoint | Reviewed
| 9530bb8d-330b-538a-a74f-c4388c99d3d7 | date | Date:
| 15325b67-c0ce-5c60-85eb-83bce1e5f376 | signoff | Reviewer to sign
| 201928cd-130e-44f0-ab2b-f03f069d0d67 | checkpoint | Reviewed
| 1872c82d-d706-520c-9042-35402523d3e7 | date | Date:
| 83b68f24-a235-4e3e-b927-6d075197292a | signoff | Reviewer to sign
| 56438aa9-d477-487e-957b-e6fe29f162fc | checkpoint | Reviewed
| 1dc9a1cf-4a69-5b42-8345-defb514f1204 | date | Date:
| 7a1ac6ab-6f79-4ed5-a947-58df7f836cee | signoff | Reviewer to sign
| 662563cc-c1e2-4a54-bc3d-0af07540a265 | checkpoint | Reviewed
| 08482974-1a36-5807-b451-9ee1f7f790ee | date | Date:
| ddfd8fb3-1c7b-4645-bac3-c811eaff41f3 | signoff | Reviewer to sign
| f79a7225-b957-4926-8e32-53821da468d7 | checkpoint | Reviewed
| 012fdaae-1f90-5e38-8cf1-f1c0d81e41e9 | date | Date:
| cdf6cce8-f9f1-4c77-bc7c-90f1ade703f4 | signoff | Reviewer to sign
| a6c0ad47-b8fb-48cb-ba93-363690b587a1 | checkpoint | Reviewed
| 31d10681-9ee5-5d9c-a2b6-b54643938b09 | date | Date:
| 35b6dcba-3d62-4c87-a6e2-3514bd5206e0 | signoff | Reviewer to sign
| d66eecd4-06f0-4245-8fa9-c53aa0f41712 | checkpoint | Reviewed
| 19ad2559-920c-5f4c-816a-344d6a90b3a5 | date | Date:
| 5bff908d-c4e9-4e58-a730-43ebf4fcfc68 | signoff | Reviewer to sign
| 1d561f3f-c6c3-5d28-a247-a534b413a5ae | checklist | QA - Coloursteel Roofing Checklist |  | Coloursteel Roofing | 64f7223b-432f-4b49-a4f2-8d4c417003ea
| a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
| b4f476ee-b727-5944-b729-9a447c79f29a | checkpoint | Edge protection/scaffold in place
| 8d5859bd-c4fd-528d-aede-41c168bbc57b | signoff | Raise remedial / request review
| d66ba057-caeb-564c-afb7-c2cff7a8c112 | checkpoint | Safety nets installed
| 1d9a8c5c-0ca1-53ad-a07e-b320c8bd7181 | signoff | Raise remedial / request review
| bfa930e1-5be5-5088-abad-b8a6e5f4c741 | checkpoint | Purlins/battens & all necessary timberwork complete
| 4a6910c1-42f6-5657-857d-abb94e4467c5 | signoff | Raise remedial / request review
| ca183b70-1c75-57b6-972a-c2414aa47594 | section | Substrate Checklist : Enviroclad Plywood
| 52878a11-a4ff-5d9e-9bf3-e6292d88e22b | checkpoint | Framing supports at 400mm centres (in one direction). All plywood edges must also be supported.
| 85db5d9d-2877-487d-99d6-1850a4e741fb | note | Do not use tongue and groove plywood. Viking Roofspec can accept the maximum support spacings provided in Table 15C of CHH Ecoply Specification Guide.
| daa8e8a5-0ae2-5259-b081-091977df63d1 | checkpoint | Minimum thickness 17mm, F8, CCA H3.2 treated, structural plywood (not LOSP treated).
| a88a7607-c943-5657-a4b3-099f985a8800 | checkpoint | Minimum CD grade with the sanded C face upwards.
| 8f3e20e8-0400-59eb-b95e-da904ed996d0 | checkpoint | Plywood laid with face grain at right angles to supports.
| d1e0a570-0a5f-5cee-8fcf-0d2be56a5d30 | checkpoint | Plywood is to be laid with staggered joints in a brick bond pattern with a 3mm expansion gap between plywood sheet edges.
| 4a41c5d3-eeaf-5868-bc9d-1594634e6a99 | checkpoint | Plywood is screw-fixed with 10g x 50mm SS counter-sunk screws at 150mm centres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm.
| 048c7033-b0e1-53c6-8f1a-c527e0716782 | checkpoint | Chamfer all external edges with a minimum radius of 5mm.
| 0eba1011-abf5-414c-95d2-dcd86e6c985b | note | *Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood and framing supports to be at no more than 18%moisture content.
| e394e72e-aed4-5742-889d-7c1192d5d820 | checkpoint | For Roofs and Roof Decks over living spaces, all cavities must be ventilated and insulated in compliance with clause H1 NZBC. Cavity ventilation is not required for a Warm Roof system which meets or exceeds the minimum R value requirements.
| 2c9421c8-62be-50e0-bea1-f9e4ace34821 | checkpoint | All drains and outlets are membrane compatible.
| 9483470c-64af-4c61-ba0c-9d4294af6851 | note | Note that TPO membranes cannot be welded to Stainless Steel scuppers or sumps. Accessories must have Clamped Grates or be TPO weldable.
| 70d3bd8f-5e07-55ee-b1dc-278071b4f442 | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
| faec3593-fe02-5478-9c0b-b0fbb15842f5 | section | Roof QA
| adc4d60d-92ee-5570-a8ef-b797a21ff53c | checkpoint | Fascia straight, cut in correctly
| e88ff7c1-8dcc-5127-a83c-adb5b36ea091 | checkpoint | Spouting installed with correct falls & outlets as per plans
| f48f40e9-589b-5a30-ae33-a4ff40aae73c | checkpoint | Underlay over fascia & trimmed neatly
| db7549cf-1519-54bf-89d2-7682ec7dd0d8 | checkpoint | Valleys straight
| 61eaa4b9-34b2-5ee8-9ee1-38a491efc961 | checkpoint | Screws installed correctly & washers intact
| 7a9d1814-4f58-533b-b4a7-8230037f4bca | checkpoint | Roof clean from debris & swarf
| 43bc51d5-f09d-5c98-a168-8bc8927f81b2 | checkpoint | Flashing junctions tidy & sealed correctly
| 28ef82cc-5c7e-54aa-adf3-5b06e9f3af3f | checkpoint | Roof laid correctly & damage free
| c7de0040-c441-5568-8e97-a2e7ce585abb | checkpoint | Site clean, rubbish in bin or removed
| e58760a7-f1e2-5b60-a482-9b7299fa9395 | checklist | QA - Kingspan Roof Checklist |  | Kingspan Roofing | 57afe919-3659-4db1-a07f-5995f468af4c
| a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
| b4f476ee-b727-5944-b729-9a447c79f29a | checkpoint | Edge protection/scaffold in place
| 8d5859bd-c4fd-528d-aede-41c168bbc57b | signoff | Raise remedial / request review
| d66ba057-caeb-564c-afb7-c2cff7a8c112 | checkpoint | Safety nets installed
| 1d9a8c5c-0ca1-53ad-a07e-b320c8bd7181 | signoff | Raise remedial / request review
| bfa930e1-5be5-5088-abad-b8a6e5f4c741 | checkpoint | Purlins/battens & all necessary timberwork complete
| 4a6910c1-42f6-5657-857d-abb94e4467c5 | signoff | Raise remedial / request review
| 5a3e7a2b-9930-57e9-b8a6-b6144f8d4dd7 | section | Kingspan Roof QA
| de6591da-5a36-500f-a4f0-8b08d0599bd8 | checkpoint | Screws tight & washers intact
| dec764b9-4a7a-5d5d-af10-b325200f4e3b | checkpoint | Roof clean of roofing debris
| a45e9fde-9439-512b-b24f-843f4f774112 | checkpoint | Roof clean of swarf. If FAIL, mark on plan areas of concern & include photos
| 0a85e97b-0d58-55aa-8b30-c0633c386f17 | checkpoint | Undamaged roofing sheet profile. If FAIL, mark on plan areas of concern & include photos
| a44a91f7-2f88-5377-85b7-35351d229dc4 | checkpoint | Scratches - mark on plan areas of concern & include photos
| c8d3798c-33c2-558a-adda-1a7d38797a8f | checkpoint | Roof laid in correct sequence
| 0efed9e9-794c-5e6b-9999-c573cecbcd70 | checkpoint | Flashing junctions sealed & tidy
| f990ee8d-89d8-59a9-8e12-608d97228cb1 | checkpoint | Lap tape installed correctly
| 326afb36-1f37-4a3b-aa1c-9f673b9fd72d | checklist | QA - Purlins, Noggs, Plywood install |  | QA - Purlins, Noggs, Plywood install | b90d935a-b97d-4bf4-b6a9-219891ef5166
| 3a6c111c-eed1-4426-96c5-a88e818ee1c6 | section | Details
| ebd4a903-a79b-4fc4-a7b5-313ffa64797d | checkpoint | Purlins as specified, Correct fixings and spacings. Installed straight.
| d0eeed3e-2929-4572-bf12-9dd7a7e57726 | checkpoint | Nogs at correct spacings.
| 217ef630-3fec-470a-a940-cacb9de90d1e | checkpoint | Plywood correct thickness, installed correctly with specified fixings.
| 998db05d-0c22-5ff1-befd-0de3842979ae | checklist | QA - Rooflogic UltraTherm MSR Roofing System |  | Rooflogic UltraTherm MSR Roofing System | 33e8a3cf-65dd-4f26-956e-b4f2c1a275d1
| a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
| 431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
| 695b83f0-0043-5642-8427-d674630e40b3 | signoff | Raise remedial / request review
| 999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
| bbd145ec-75af-57df-88ba-42f50005165a | signoff | Raise remedial / request review
| 9c51e892-57fc-56f4-891a-a1021b63bfd3 | checkpoint | Substrate acceptable (clean, dry and stable)
| 32594108-1836-52b6-b949-dd2b506200c6 | signoff | Raise remedial / request review
| 0928ba5b-96f3-5dc7-8d60-9a2911dae719 | section | Surface Preparation
| 9b9a75a0-9636-5b16-b1be-2c09ad4bd3a0 | checkpoint | All purlins are in place
| 862b7622-d514-5b0a-bf08-cbdc86bbf49a | signoff | Raise remedial / request review
| 0a1307d7-f803-50f9-888c-2c18396ba47c | checkpoint | Under flashings installed
| df2fc6f6-06c0-58de-a1df-c00180124eb8 | signoff | Raise remedial / request review
| d9ff5339-45ae-56fa-8ef9-6be936bc5398 | checkpoint | Sheets in good condition for roof installation
| 5793832d-2de3-50de-b8cc-684879b6b04e | signoff | Raise remedial / request review
| 16c5b34f-8cac-5015-a959-fab255ea795a | section | RL Base Deck
| 4e77911b-5903-5dd0-aa63-1536c3389e9b | checkpoint | Installed in accordance with specification
| c950976a-0318-535c-b115-abf3d739f4ba | checkpoint | Installed in accordance with project specific and Rooflogic standard details
| af8d9815-371f-5086-9b5f-850c50c99e0a | checkpoint | Correct fasteners used and installed with correct frequency (i.e. 1 fastener per trough along every purlin line
| c2d85594-faca-5d84-a86f-151a54cf252e | section | Vapour Control Layer
| a20db41f-e8ce-5d91-ba05-5fdc80238685 | checkpoint | Vapour Control Layer installed to top face of acoustic board
| c00a89af-8c21-5216-8aec-a93401ef6e2c | checkpoint | Correct side laps (80mm) and end laps (100mm)
| 3226f481-ac57-585f-a57d-b37b904d874a | checkpoint | Vapour Control Layer to be installed in accordance with project details. Ensure Vapour Control Layer is correctly terminated to ensure vapour control continuity at roof openings, transitions and at horizontal to vertical roof/cladding junctions
| 43e2aa1e-5eee-51a8-810a-a424fd2dc094 | checkpoint | Any damage to vapour control layer repaired to ensure vapour control layer 100% continuous.
| 57068517-b895-5732-84f8-3b71b2956d7a | section | RL Acoustic Board, PIR Board and FRU 36 Underlay
| c0a4c510-28e7-5abd-86c2-5094e6eeab32 | checkpoint | Acoustic Board installed over Vapour Barrier and mechanically attached to the substrate
| 1ea1a3e4-b3cf-5b89-96cb-23ebf9f1da64 | checkpoint | Correct thickness input
| d572bf04-a2fe-5393-a6f5-880f80e41cc1 | checkpoint | Any damaged insulation board has been cut out and replaced with new tightly butted piece of acoustic board (minimum 300mm x 300mm piece.)
| 469c2bdd-0021-55da-891d-da7013c6c900 | checkpoint | RL PIR Board insulation to be installed continuously over vapour control layer to roof and gutter in accordance with architectural drawings
| 12dd9cc4-b0e0-54b5-93a0-0ee393111c91 | checkpoint | Any damaged insulation board to be cut out and replaced with new, tightly butted piece of PIR Board (minimum 300mm x 300mm piece.)
| 22794620-a8db-58bd-957f-6020bf650ec1 | checkpoint | Install Dristud FRU 36 underlay with 150mm side laps and, if required, 200mm end laps
| b20eaa7c-3595-4fe9-90c1-0a4ed29d1e8d | note | NB. The underlay can be installed in line with the fall of the roof and there is no requirement to install safety netting beneath the underlay or use a self-supporting grade underlay. The underlay is fully supported by the high density rigid insulation layers and will not sag or deflect either during application or over the life of the system.
| 2d4c15fd-6e97-5775-ad52-0a012d4aa3e3 | section | Top Deck
| ca8cff62-f376-5c1d-bb13-829e54586e95 | checkpoint | Visually inspect material delivered to site. Confirm all delivered materials correspond with order and specification.
| 5b27b797-9c69-59f5-9c3f-e6c6ce63d691 | checkpoint | Fix according to specified fixing pattern to achieve required wind uplift resistance
| be907a7d-850b-5eda-99d9-aca485390c0f | checkpoint | Correct fixings/profiled washer assembly used.
| c5c6eccf-9d81-56e5-bd72-5664fe9d8fbe | checkpoint | Allowance for thermal expansion when fixing sheets
| 33a414d6-d23d-5d46-9671-99e76dd755e2 | checkpoint | Sheet set out square
| e0fe1790-c649-5eeb-8be0-476ee999bbc5 | checkpoint | Sheet length as required to achieve specified gutter overhang
| 59c14941-a721-51c4-8236-d92be1eeaad9 | checkpoint | Stop-ends and turn-downs to sheets
| e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | section | Final Inspection
| 4f6f60ea-81b2-5034-91bf-2ddeeee8db05 | checkpoint | System installation is complete
| 0d4aa82c-a06c-5501-8c9e-6b52eab2dee6 | checkpoint | Installation of fixings in accordance with specification and appropriate wind zone
| 0cd8d4cb-c053-510e-886d-0253f7c27f74 | checkpoint | All flashing details in accordance with specifications, plans and details with correct type and spacing of fixings and placement of seals and sealants
| 8f372bc7-3f55-5c8c-bbb0-0dade669c8b0 | checkpoint | All construction equipment and materials removed from roof/site
| ad9928a4-c65a-5d08-a91b-7c3cd9ee33c6 | checkpoint | Any damage to top skin or associated flashings rectified by repair or replacement
| ba941bc7-d05d-5ee2-81d9-3b4e850deb60 | checkpoint | Debris, sward and other contamination cleared/removed from roof
| 3bf8dfea-b0c7-5a26-b351-8ef698c0ecab | checkpoint | Maintenance Documents submitted to Main Contractor/Building Owner
| 7dee3fd5-e45c-5c82-9c66-9071637e87b7 | checklist | QA - Rooflogic UltraTherm Xtreme Roofing System with Fibretite Membrane |  | Rooflogic UltraTherm Xtreme Roofing System with Fibretite Membrane | 1fed0e6c-2808-4870-8d30-8b3e37da5812
| a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
| 431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
| 695b83f0-0043-5642-8427-d674630e40b3 | signoff | Raise remedial / request review
| 999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
| bbd145ec-75af-57df-88ba-42f50005165a | signoff | Raise remedial / request review
| 9c51e892-57fc-56f4-891a-a1021b63bfd3 | checkpoint | Substrate acceptable (clean, dry and stable)
| 32594108-1836-52b6-b949-dd2b506200c6 | signoff | Raise remedial / request review
| 0928ba5b-96f3-5dc7-8d60-9a2911dae719 | section | Surface Preparation
| 9b9a75a0-9636-5b16-b1be-2c09ad4bd3a0 | checkpoint | All purlins are in place
| 862b7622-d514-5b0a-bf08-cbdc86bbf49a | signoff | Raise remedial / request review
| 0a1307d7-f803-50f9-888c-2c18396ba47c | checkpoint | Under flashings installed
| df2fc6f6-06c0-58de-a1df-c00180124eb8 | signoff | Raise remedial / request review
| d9ff5339-45ae-56fa-8ef9-6be936bc5398 | checkpoint | Sheets in good condition for roof installation
| 5793832d-2de3-50de-b8cc-684879b6b04e | signoff | Raise remedial / request review
| 16c5b34f-8cac-5015-a959-fab255ea795a | section | RL Base Deck
| 4e77911b-5903-5dd0-aa63-1536c3389e9b | checkpoint | Installed in accordance with specification
| c950976a-0318-535c-b115-abf3d739f4ba | checkpoint | Installed in accordance with project specific and Rooflogic standard details
| af8d9815-371f-5086-9b5f-850c50c99e0a | checkpoint | Correct fasteners used and installed with correct frequency (i.e. 1 fastener per trough along every purlin line
| c2d85594-faca-5d84-a86f-151a54cf252e | section | Vapour Control Layer
| a20db41f-e8ce-5d91-ba05-5fdc80238685 | checkpoint | Vapour Control Layer installed to top face of acoustic board
| c00a89af-8c21-5216-8aec-a93401ef6e2c | checkpoint | Correct side laps (80mm) and end laps (100mm)
| 3226f481-ac57-585f-a57d-b37b904d874a | checkpoint | Vapour Control Layer to be installed in accordance with project details. Ensure Vapour Control Layer is correctly terminated to ensure vapour control continuity at roof openings, transitions and at horizontal to vertical roof/cladding junctions
| 43e2aa1e-5eee-51a8-810a-a424fd2dc094 | checkpoint | Any damage to vapour control layer repaired to ensure vapour control layer 100% continuous.
| 5938a466-bd4d-5f64-a003-67d1a5e47867 | section | Install RL PIR Board and RL Roof Board HD
| 469c2bdd-0021-55da-891d-da7013c6c900 | checkpoint | RL PIR Board insulation to be installed continuously over vapour control layer to roof and gutter in accordance with architectural drawings
| 12dd9cc4-b0e0-54b5-93a0-0ee393111c91 | checkpoint | Any damaged insulation board to be cut out and replaced with new, tightly butted piece of PIR Board (minimum 300mm x 300mm piece.)
| 02cd45b7-d474-5b41-8b8d-cfe4b6bf2feb | checkpoint | PIR insulation to be dry prior to application of RL Roof Board and Fibertite membrane.
| 4f871f4f-d7f2-59ad-bddd-aa145c32baca | checkpoint | Roof Board HD to be installed over PIR Board and mechanically attached to the substrate. Fasteners to be installed in accordance with the prescribed fixing pattern.
| 792b1eb7-75c4-5164-897d-479e5143bf21 | section | Adhering Fibertite Membrane
| 81e70536-1cab-5cf5-b117-f027a822f9f7 | checkpoint | Install Fibertite membrane in strict accordance with Project Specification.
| 7304fa34-e3ca-50de-ab79-126ad37457ce | checkpoint | Ensure substrate (e.g. Roof Board) is dry and free from dirt, debris or contamination.
| 169a2efa-74c7-56ad-b2c8-647e0e2b160f | checkpoint | Select adhesive as specified
| e8bb6c91-7e88-4eed-9140-a258ac5743eb | button |  | 190E, 490U, 690U,490E
| 1216659b-d839-5292-b83f-30d9dad5ea9e | checkpoint | Adhesive applied as per specification -Ref specification cl .3.13 in project specification
| 27052b6b-78b5-568e-b24a-202d8c21f2b4 | checkpoint | Take into account ambient air temperatures and humidity levels
| ba50ce50-4525-5cbe-a549-4b3ea837ce22 | section | Welding Fibertite Membrane
| 46fae741-ec52-57bf-b3ed-c777883c184b | checkpoint | Test welds carried out daily with hand-held welders
| 046230b3-3be3-5459-9f60-d5d42be72d6e | checkpoint | Test welds carried out when commencing and re-commencing welding with robotic welder (e.g. start of day, after break.)
| 19ea4380-89fd-5aeb-8a0e-80fb36eab904 | checkpoint | Seams to be welded clear of dirt, debris, moisture and adhesive residues.
| ae22c991-57fe-53d7-b042-ed2ecea1d308 | checkpoint | Seams wiped clean (both surfaces to be welded) with Acetone and clean, white cotton rag
| c888ab6a-c9e2-508d-8683-b67922eee61d | checkpoint | Hand and Robotic welding to be carried out by trained personnel familiar with equipment and membrane
| f70a3559-03e1-5d91-b25e-8f57e29d7728 | checkpoint | Daily inspections of all completed work by way of seam probing to ensure all welds are secure, fully closed and watertight
| b2c488ba-935f-5bf7-a640-c27600c3a885 | checkpoint | Any welding deficiencies rectified on the same day they are seam probed
| f7b72917-a559-5b87-8887-47cac59b0564 | checkpoint | Night joints are installed daily, as required, to ensure that no moisture is allowed to migrate under the installed membrane.
| e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | section | Final Inspection
| 4f6f60ea-81b2-5034-91bf-2ddeeee8db05 | checkpoint | System installation is complete
| 3062e849-1017-5c63-8bd6-ba45206ab93a | checkpoint | All membrane terminated with either thermoplastic weld or mechanical clamp/termination (drain clamps with no missing bolts)
| 9925e84b-ca57-5ae9-a5f7-66721f54b53f | checkpoint | No exposed membrane terminations that could allow water behind
| 0c0d1b65-f19e-55e5-b349-d175e6a217bc | checkpoint | All terminations (details in accordance with project specific and standard RL construction plans and detail drawings.
| 30f1153a-90e6-5ea8-a6b4-dd48c83666a5 | checkpoint | Any damage to system and/or membrane have been recorded/ rectified
| ef661bc0-9cb1-59f1-8208-15cac2200766 | checkpoint | All construction equipment and materials removed from roof/site.
| 3bf8dfea-b0c7-5a26-b351-8ef698c0ecab | checkpoint | Maintenance Documents submitted to Main Contractor/Building Owner
| 9c61e2be-cf27-523f-9442-0b4a4249838c | checklist | Rescue Plan Checklist |  | Rescue Plan Checklist | 8969e375-eaee-4c59-baf7-640769f29c9e
| 9d51497a-32d0-5818-9e4b-2d4cf127c673 | checkpoint | General details
| df1b2b13-eb59-59cb-856b-a15295aee280 | textbox | Location
| 193ba206-b82e-5239-919e-2b8ca01fbabe | textbox | Supervisor
| 434e85af-7570-541c-8f84-eb92215a851d | date | Date
| 93555361-1164-5ca6-a4bd-4de290d16778 | checkpoint | Team members involved
| 58b6de50-ca2b-54ca-817d-4f4335d1f592 | signoff | ALL TEAM MEMBERS TO SIGN HERE
| 3a039052-b953-51a7-b349-4eae5c126b76 | checkpoint | Rescue details
| da0f956b-d3df-57ea-9fc2-5d043dc2113c | note | Please note training competencies and responsibilities
| 779f1e63-f2a0-51fa-89c0-8f7b50e018ac | textbox | Nature of Emergency
| a9056506-9261-57dd-9126-3fac8e19c94d | textbox | Rescue Method
| 703ce2e1-951c-5db7-9c09-6aa192fe8013 | textbox | Rescue Equipment
| 3eae9dd7-1a0d-5bce-abb5-d41f0ccdcdc0 | textbox | Communication & contact numbers
| 0d4ced32-43fe-55da-801a-33981b4b620e | textbox | Medical Requirements
| c7dbde9a-949b-534a-9882-103e255c3249 | textbox | Emergency Services involvement (if applicable)

## Project Checklist Templates
Warnings | Id | Type | Name | Values | Prompting Name | Resource Id
|  | checklist | Crane Lift Plan Checklist |  | Crane Lift Plan Checklist | 43ecc3b8-1c09-4ed2-86f1-b80b9c8b5a7c
|  | section | Lift plan details
|  | checkpoint-no-value | Lift plan details
| 685b25f8-289a-5608-b88e-d380a663a625 | textbox | Customer
| f5dd04d7-3dac-5ec7-afe2-e885234ad959 | textbox | Site representative
| cfaad349-a55c-59f9-8b13-0626b2c61eff | textbox | Crane supplier
| caa0f25d-1c35-5019-9b7d-b34bd6ed5682 | textbox | Crane make/model
| 62ec9b95-fa8f-5299-bcf0-d734fdda92bd | textbox | Crane operator
| e435866c-f8d4-5b85-ab01-81b3a9e02801 | textbox | Date and time of the lifts
| b9976130-4255-50fa-b55b-0beda0bcce0a | button | Communication | Radio, Hand signals, Other
| e9bf64bb-f5c1-570d-baca-665ba4cabca4 | textbox | Specify if other
| 67b1d9fc-df2d-545a-8a2a-149af0d47a08 | textbox | Lift description
| 017c2d3c-944c-5675-9162-c68bfef13f64 | textbox | Crane ID
| 4769c0da-fe60-55c1-95a9-502a94c2b683 | textbox | First Aider
| df3e81a6-6183-584b-b7c7-7391b86452b7 | textbox | Dogman
| 23ccbe64-a35f-5e68-b35f-485a2a44ffb0 | textbox | Location
|  | checkpoint | Hazard checks
| bdbcda6e-237d-58b7-b218-be9f8e8c0d55 | tickbox | Workplace hazards
| d55b9b04-72f2-5de4-829d-f3f91d1cb33f | tickbox | Crane Hazards
| c81c3107-6dfb-59c2-9f6c-dace17e148ef | tickbox | Crane Operator ticketed
| 6695a19b-d28c-5573-bdc1-3ef9b31d4bd9 | tickbox | Dogman ticketed
| fe4cf2b8-9ce4-5397-ae3d-af1ced8352ac | tickbox | Fatigue managed
| 9ef169fe-df10-5d87-a467-38ad2bafbd30 | tickbox | PPE correct
| ddbdf7e1-a923-57f2-b36c-20c036f26784 | tickbox | Crane cert correct
| 6fdf8c9c-6137-588e-a5b8-2fc3c98d447b | tickbox | Lifting equip certs correct
| fd3810fa-fffb-5c5b-9cbc-e1babaed05cd | tickbox | Rating charts correct
| 34a1c130-bb8f-5a3f-8a68-a716560e68f2 | tickbox | Counterweight correct
| 46ba1980-9d34-536d-a4ab-90b1e204d107 | tickbox | Reeving correct
| e33711a7-1be0-51ab-b655-1812f52f9490 | tickbox | Outriggers Ext/Pinned
| fa348c22-afc5-5e56-8aa9-35c6ad234ee0 | tickbox | Vision conditions checked (sun strike/bad lighting/dark/fog/obstructed/control sunglasses/lighting/radios/spotter )
| 7182a1d7-0baa-58ca-8dd5-c61aa92d4f02 | tickbox | Weather conditions checked (fine/wet/ice/wind)
| daa2a3ad-579d-5b67-b88a-ce8e27c9af4b | tickbox | Traffic managed (people and vehicles)
| e48d5026-76c6-5628-b3d8-18c64e00be8f | tickbox | Radio's checked
| 7b747fd6-7c0d-59ab-a2f5-685dee79c76b | tickbox | Airport notified
| 1913d6d2-3411-5ba6-b30e-29938deef2aa | tickbox | Hazard notification required (WorkSafe NZ: hazard notification)
| 526dfd8a-09fe-58e3-b165-e76a5bfb1dfb | tickbox | Crane setup as per lift plan
| 42f1c2ef-1c4d-547a-9945-e33001768f9a | tickbox | SLI configured and working
| 5c0ab861-a5bd-5b74-a1b9-b81add5fd922 | tickbox | Electrical hazards (power lines/load attached to power; power lines must be at least 4m away unless you have a permit)
| 0bf1c005-34f6-50a7-9e1a-4c9e11a6280e | tickbox | Crane is earthed
| 477ba5d7-7ed2-5af1-9135-9fdd5fd1f0be | tickbox | Ground conditions checked (flat, can support crane, access without sliding etc.)
| c922e82d-7879-530e-959b-4635bcbd38ef | tickbox | Underground services are clear (water, power, storm water, waste water, septic tanks etc.)
| 53d96f06-669d-5ad1-bcfb-0ba9204d260b | tickbox | Obstructions checked (slew, structures, boom, overhead, buildings etc.)
| 59aa0d26-a0fa-5cbe-8824-22a8dc5a69dc | tickbox | Rigging methodology discussed
| e445e3fc-ded1-5ccb-bd26-94ae11ae1212 | tickbox | Load support checked
| 1d9ae1e1-eb1b-5e09-983e-89d5a15b9055 | tickbox | The lift will use a tag line
| 54dca9b5-6931-5082-ba93-19c94181c0ba | tickbox | Loose objects removed from load
| 3f107d1e-a9b2-5920-a1de-1a7da7b17033 | tickbox | No simultaneous operations
| 614b04c1-cb42-52d7-a1b5-cc469596f596 | tickbox | Mancage checks
| 7477ebb4-ca76-5d0b-aa1c-7f11e968bdf9 | tickbox | Confined space checked
| da9fac5f-909b-5ee4-ad80-645fd28201b4 | tickbox | Environment checked
|  | checkpoint | Lift details photographed and uploaded
|  | checkpoint | Lift sketch photographed and uploaded
|  | checkpoint | Acknowledge
| 823b647d-bfda-5e16-8f6c-f38e8ccf8e76 | textbox | Crane Operator
| 1b962e99-042f-53ee-8957-81326cdf4968 | textbox | Dogman
| 226c4bfc-b290-52a2-9b6b-efee81233052 | textbox | Site Representative / Customer
|  | checklist | Flood Test Record |  | Flood Testing Record | 4fd03831-71bf-4bff-a180-1897dd7c3568
|  | folder-normal | Details
folder-normal is not dependant but can't have own status |  | folder-normal | Outcome of flood test
|  | folder-normal | Roofing contractor's signature (use paperclip to sign on screen)
|  | folder-normal | Main contractor's signature (use paperclip to sign on screen)
|  | checklist | H&S - Site Safety Inspection |  | Site Inspection Checklist | 51ecc3b8-4463-4da1-bd6a-8a1032a17c0f
|  | section | Details
|  | checkpoint | Details Complete
| 8b03cbae-c408-4ae9-a756-cca7018dea83 | textbox | Site/Location :
| 52914ecc-91b7-4603-9495-6a1e5ad3bd75 | textbox | Date
| 8ff362f0-afb9-45ca-87d4-347265a7e11e | textbox | Name of Inspector :
|  | section | Site Control
|  | checkpoint | Hazard Board and signage up-to-date
|  | checkpoint | Environmental plan - issues
| cae0f94e-0878-4302-855f-50626b9940cc | textbox | Toolbox talk last date:
|  | checkpoint | Safety inductions for all on-site
|  | checkpoint | Safety notice board current
|  | section | Site Facilities
|  | checkpoint | Offices clean, adequate & good lighting
|  | checkpoint | Smoko sheds - clean, portable water
|  | checkpoint | Toilets - clean, washing water
|  | checkpoint | Tool /equipment sheds adequate
|  | section | General Site Tidiness and Access ways
|  | checkpoint | Clear, safe access to work areas
|  | checkpoint | Stairways and accessways clear
|  | checkpoint | Hoardings /fence and gates secure
|  | checkpoint | Loose materials secure from wind
|  | section | Personal Safety Equipment
|  | checkpoint | Signage displayed and legible
|  | checkpoint | Hardhats being worn
|  | checkpoint | Correct footwear being worn
|  | checkpoint | Glasses /ear muffs /vests /masks used
|  | section | First Aid/Fire Prevention
|  | checkpoint | First Aid Box Available
|  | checkpoint | Accident register
|  | checkpoint | Fire Extinguishers
| 12bab111-d5d2-4ba9-87f2-979c842a9df6 | tickbox | Available
| 61ea2b23-6ac8-44f8-9d40-86c8daf1dd62 | tickbox | Current (12mth)
| 3f3e012d-918a-4137-9689-dcced1049dcc | tickbox | Sufficient number
|  | checkpoint | Evacuation
| 7aa1d51b-82ee-46ea-a2d8-8922b951f5d1 | tickbox | Procedure current
| 62e3bbb3-5108-4954-b02d-7071877274bd | tickbox | All emergencies incl
|  | section | Cranes/hoist/lifting equipment
|  | checkpoint | Proper lift assessment plan done
|  | checkpoint | Crane certification current
|  | checkpoint | Slings/chains certified
|  | checkpoint | Operator procedures in place
|  | checkpoint | Inspections being done
|  | checkpoint | Man cage available
|  | checkpoint | Emergency plan in place
|  | section | Compressed air equipment
|  | checkpoint | In good condition
|  | checkpoint | Appropriate guards fitted
|  | checkpoint | Trained user
|  | section | Excavations
|  | checkpoint | Correctly Shored
|  | section | Welding/gas cutting
|  | checkpoint | Hot work permits being issued
|  | checkpoint | Fire extinguishers on hand
|  | checkpoint | Operators using PPE
|  | section | Electrical Equipment
|  | checkpoint | Main board lockable /weatherproof
|  | checkpoint | Current tagged and damage-free leads
|  | checkpoint | Current tagged plant
|  | checkpoint | Current tagged lifeguards
|  | checkpoint | Leads safely placed
|  | checkpoint | Equipment in good condition
|  | checkpoint | Appropriate guards on equipment
|  | checkpoint | Adequate temporary lighting
|  | section | Chemicals
|  | checkpoint | Correctly stored
|  | checkpoint | Safety Data Sheet (SDS) available
|  | checkpoint | Operators using PPE
|  | section | Tools
|  | checkpoint | PAT tool WoF current and secure
|  | checkpoint | Staff trained in tool use (SWPS)
|  | checkpoint | PAT signage on site
|  | section | Scaffolding
|  | checkpoint | Notifiable weekly Scaftag/current
|  | checkpoint | Handrails/mid-rails
|  | checkpoint | Toe boards
|  | checkpoint | Platforms
|  | checkpoint | Ladders/stairs
|  | checkpoint | Base sound
|  | checkpoint | Work platforms clear
|  | checkpoint | Platforms trip free
|  | checkpoint | Planks tied down
|  | checkpoint | Headroom clear
|  | checkpoint | Ties/bracing adequate
|  | section | Ladders
|  | checkpoint | Good condition
|  | checkpoint | Secured top and bottom
|  | checkpoint | Stays to step ladders
|  | checkpoint | Working 2 steps down
|  | section | Fall Hazards
|  | checkpoint | Fall Hazards
|  | checkpoint | Floor openings
|  | checkpoint | Lift shafts
|  | checkpoint | Stairs
|  | checklist | H&S - Toolbox Talk |  | Toolbox Checklist | 8f1a96dc-faff-4698-b02f-9d12ccb8b92b
|  | section | Details
|  | checkpoint | Details Complete
| 305f2185-4e3a-4417-ae95-885bb0b1de8a | textbox | Office location:
| b2fd07dc-8f92-4010-8a71-46e71c03ff63 | textbox | Who is running this meeting:
| 1d3d0b15-a56a-498c-b16b-2afa5f8e2573 | textbox | Company
| 88e78785-0eea-4ad8-a896-1622379eacfc | textbox | Agenda items:
| ce0224f5-54b8-47a5-b890-7a5416c69623 | textbox | Theme of the week (topic for focus):
|  | section | Health and safety issues
|  | checkpoint | 1.
| 2ec0fc9e-b14f-43a5-bb60-4df5d5ab3ab4 | textbox | Issues raised from site safety inspection:
| 1b5fcc97-f30c-4727-a783-29c22206fa41 | textbox | Actions:
| b5107b7c-d991-4507-a1a9-6180db10057c | textbox | By who and when:
|  | checkpoint | 2.
| 8978adff-e266-4646-b125-178fba33a0dd | textbox | Issues outstanding from previous briefings:
| 507afe6b-4ee7-4485-bd4b-99698d8e8f47 | textbox | Actions:
| 7d92f59d-ce24-4ec9-8428-a92c87f559e3 | textbox | By who and when:
|  | checkpoint | 3.
| 305b3039-3f3d-45b4-8536-fb028ee2010b | textbox | Employee-raised issues:
| c98f50a5-1fb4-45b7-86e0-301132ec8b7c | textbox | Actions:
| c250b53e-5070-459c-b01f-af8fcce5cdb7 | textbox | By who and when:
|  | checkpoint | 4.
| 26f6b1aa-3048-4106-a64b-dc4e2cf75ec3 | textbox | Positive safe-action observations:
| dd2ab926-5b94-46f6-a93f-eed5fa00233e | textbox | Actions:
| 464cc30b-c155-4299-b08c-242a1821bd72 | textbox | By who and when:
|  | checkpoint | 5.
| ba0166ff-1cef-49fe-a54e-fce60528feea | textbox | Incidents or injuries:
| 8f9035d5-30e5-4ea2-9ec4-4d19df05b3fd | textbox | Actions:
| 1a84fee3-7466-42bd-a3ff-39c2785201a3 | textbox | By who and when:
|  | section | Job plans reviewed
|  | checkpoint | Job/Task & Action/Outcome
| cb9c1ca7-7b79-4c62-8f74-3a1d70af5886 | textbox | 1.
| d396585a-1ce3-4d1e-b838-375ab4165dd0 | textbox | 2.
| 4657beed-8141-41c2-926d-0d7204a497a2 | textbox | 3.
| 1e162112-08ad-40c3-9d33-6c4bac52a906 | textbox | 4.
| fd629f21-4050-47b3-b236-26daf8c94903 | textbox | 5.
| a08ea05c-aa58-425b-9cb6-e2fa8951a414 | textbox | 6.
|  | section | Operational issues
|  | checkpoint | Issue & Action
| 301f9ad4-6682-45c0-aa57-7b074b0e8a13 | textbox | 1.
| 1373bee6-816f-408a-97a0-72f99b461b6e | textbox | 2.
| c487e999-fa82-493c-b540-e056d94778fb | textbox | 3.
| 5341a99d-52f8-4c86-8e11-6e8adfb0627e | textbox | 4.
| 8e55092c-df52-43d0-b019-a8e67550ae09 | textbox | 5.
| b87136a8-71c4-41f7-9cdb-74d4b55b5521 | textbox | 6.
|  | section | Other business
|  | checkpoint | Item & Action
| 2e63def1-4462-4998-b972-d5125960181e | textbox | 1.
| 044404a1-6065-4d33-8f96-7da9ab2eaf3a | textbox | 2.
| 1e321545-4537-44dd-9443-3ae2c58d572b | textbox | 3.
| e3214f18-5e4b-42bf-856b-435adffda167 | textbox | 4.
|  | section | Attendees
|  | checkpoint | Add name and Photo of attendees
|  | section | Review by management
|  | checkpoint | Reviewed and signed off
| 054479d9-523d-4c50-88ce-626d6600059d | textbox | 1.
| e1ea14ce-04e9-4c55-b0e6-131f75ee169d | textbox | 2.
|  | checklist | Membrane Checklist |  | Membrane | 7b0cca2a-e0ec-423f-b436-aff8f0d9a39d
|  | section | Prestart
|  | checkpoint | Edge protection/scaffold in place
|  | signoff | Raise remedial / request review
|  | checkpoint | Safety nets installed
|  | signoff | Raise remedial / request review
|  | checkpoint | Purlins/battens & all necessary timberwork complete
|  | signoff | Raise remedial / request review
|  | checkpoint | Other trades works damage free & protected
|  | signoff | Raise remedial / request review
|  | section | Roof QA
|  | checkpoint | Plywood substrate correct
|  | checkpoint | Substrate clean
|  | checkpoint | Drip edge/gutter line flashing installed
|  | checkpoint | Membrane laid in accordance with suppliers details
|  | checkpoint | No visible damage to membrane
|  | checkpoint | All laps welded correctly
|  | checkpoint | Flashings installed where required for termination/weathertightness
|  | checkpoint | Penetrations welded correctly
|  | checkpoint | Roof/Site clean of rubbish and excess materials
|  | checklist | QA - Coloursteel Cladding Checklist |  | Coloursteel Cladding | 279edfbb-3807-41c2-9007-65cbc957c28a
|  | section | Prestart
|  | checkpoint | Edge protection/scaffold in place
|  | signoff | Raise remedial / request review
|  | checkpoint | Safety nets installed
|  | signoff | Raise remedial / request review
|  | checkpoint | Purlins/battens & all necessary timberwork complete
|  | signoff | Raise remedial / request review
|  | section | Substrate Checklist : Enviroclad Plywood
|  | checkpoint | Framing supports at 400mm centres (in one direction). All plywood edges must also be supported.
| a071e9e8-2fb8-47c3-8ab3-facf1f1adfc2 | note | Do not use tongue and groove plywood. Viking Roofspec can accept the maximum support spacings provided in Table 15C of CHH Ecoply Specification Guide.
|  | checkpoint | Minimum thickness 17mm, F8, CCA H3.2 treated, structural plywood (not LOSP treated).
|  | checkpoint | Minimum CD grade with the sanded C face upwards.
|  | checkpoint | Plywood laid with face grain at right angles to supports.
|  | checkpoint | Plywood is to be laid with staggered joints in a brick bond pattern with a 3mm expansion gap between plywood sheet edges.
|  | checkpoint | Plywood is screw-fixed with 10g x 50mm SS counter-sunk screws at 150mm centres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm.
|  | checkpoint | Chamfer all external edges with a minimum radius of 5mm.
| 86ef0ee6-cd4e-49f6-b30c-4a3d5b5c5ac1 | note | *Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood and framing supports to be at no more than 18%moisture content.
|  | checkpoint | For Roofs and Roof Decks over living spaces, all cavities must be ventilated and insulated in compliance with clause H1 NZBC. Cavity ventilation is not required for a Warm Roof system which meets or exceeds the minimum R value requirements.
|  | checkpoint | All drains and outlets are membrane compatible.
| 555f09ff-90cd-47eb-9fc4-39069aea55d0 | note | Note that TPO membranes cannot be welded to Stainless Steel scuppers or sumps. Accessories must have Clamped Grates or be TPO weldable.
|  | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
|  | section | Wall Cladding QA
|  | checkpoint | Base flashing installed & taped with correct fall
|  | checkpoint | Cladding installed correct sequence
|  | checkpoint | Screws uniform & intact
|  | checkpoint | Foam installed where required
|  | checkpoint | Flashing junctions cut correctly & uniformed - as rev details
|  | checkpoint | Cladding clean & damage free
|  | checkpoint | Site clean, rubbish in bin or removed