## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | QA - Flashings |  | Flashings
8cdb6920-9133-49a1-8dde-bfbc31b61c54 | section | Drip edge flashings
268d7349-1ba4-4d5e-9b77-07657fff4621 | checkpoint | Correct girth as per plan
546c394a-21a1-4938-8dc4-5c6c570d1f4f | checkpoint | Overlaps are sealed and riveted
32f404de-0756-40a2-96ac-046d1208aa2c | checkpoint | Free from damages and scratches
9368e8af-865d-4615-b9e2-3e64e63e7fd0 | section | Barge flashings
16bae0b4-8e02-493f-a75d-3f570392dbe9 | checkpoint | Correct girth as per plan
1af06ae0-d267-4c48-a092-1d4cb3125fb7 | checkpoint | Overlaps are sealed and riveted
c5a31ed6-e78f-4129-a2fc-6df6d7670889 | checkpoint | Free from damages and scratches
8056179a-cf32-4590-83ef-d2925fd4b338 | section | Head flashings
c960fb4c-b145-4bb2-87b7-511f31b1092d | checkpoint | Correct girth as per plan
b8becbf8-cb36-4f8b-89ed-75d5be818f01 | checkpoint | Overlaps are sealed and riveted
b4c26303-ff39-4d80-bbdb-9d4459b103dc | checkpoint | Free from damages and scratches
a0799664-6f34-4e53-bc3a-3533778d6c39 | section | Apron flashings
8829eae8-1ae5-4a4a-b635-09a1a9705621 | checkpoint | Correct girth as per plan
1055ad26-1a37-4765-afe3-83a38189276b | checkpoint | Overlaps are sealed and riveted
d3e5e987-319a-4262-ac2d-64c2b3225b72 | checkpoint | Free from damages and scratches
16097a38-37d6-4977-81d2-9b3759b1e779 | section | Parapet caps
c1b5ab94-f665-4211-b771-8754b169cfe8 | checkpoint | Correct girth as per plan
b630e0ad-8a3c-4987-a5ae-ce12b82d6dfc | checkpoint | Overlaps are sealed and riveted
6b311a95-5fc5-4e10-954d-d7bc13bbff42 | checkpoint | Free from damages and scratches
7063be52-7c22-4f36-8a3e-b26f86a084e2 | section | Penetration flashings
402fc02e-2ccd-4f3d-984f-ac736fce056e | checkpoint | Correct girth as per plan
fc6367b4-98f1-48f2-baa6-3ee7ce51de34 | checkpoint | Overlaps are sealed and riveted
ea516c91-3439-44a7-bb42-293b8e741173 | checkpoint | Free from damages and scratches
| section | Parapets
| checkpoint | Correct size flashings
| checkpoint | Under soakers installed as per details
| checkpoint | Fixings at 300 ⌀
| checkpoint | Expansion joints installed
| checkpoint | Caps completed and damage free
| section | Heads + Barges
| checkpoint | Correct size flashings
| checkpoint | Under fixings in places + correct fixings
| checkpoint | Expansion joints installed
| checkpoint | Fibretite flashing install membrane & welded to flashing correctly
| checklist | QA - Rooflogic UltraTherm Xtreme Roofing System with Fibretite Membrane |  | Rooflogic UltraTherm Xtreme Roofing System with Fibretite Membrane
a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
695b83f0-0043-5642-8427-d674630e40b3 | signoff | Raise remedial / request review
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
bbd145ec-75af-57df-88ba-42f50005165a | signoff | Raise remedial / request review
9c51e892-57fc-56f4-891a-a1021b63bfd3 | checkpoint | Substrate acceptable (clean, dry and stable)
32594108-1836-52b6-b949-dd2b506200c6 | signoff | Raise remedial / request review
0928ba5b-96f3-5dc7-8d60-9a2911dae719 | section | Surface Preparation
9b9a75a0-9636-5b16-b1be-2c09ad4bd3a0 | checkpoint | All purlins are in place
862b7622-d514-5b0a-bf08-cbdc86bbf49a | signoff | Raise remedial / request review
0a1307d7-f803-50f9-888c-2c18396ba47c | checkpoint | Under flashings installed
df2fc6f6-06c0-58de-a1df-c00180124eb8 | signoff | Raise remedial / request review
d9ff5339-45ae-56fa-8ef9-6be936bc5398 | checkpoint | Sheets in good condition for roof installation
5793832d-2de3-50de-b8cc-684879b6b04e | signoff | Raise remedial / request review
16c5b34f-8cac-5015-a959-fab255ea795a | section | RL Base Deck
4e77911b-5903-5dd0-aa63-1536c3389e9b | checkpoint | Installed in accordance with specification
c950976a-0318-535c-b115-abf3d739f4ba | checkpoint | Installed in accordance with project specific and Rooflogic standard details
af8d9815-371f-5086-9b5f-850c50c99e0a | checkpoint | Correct fasteners used and installed with correct frequency (i.e. 1 fastener per trough along every purlin line
c2d85594-faca-5d84-a86f-151a54cf252e | section | Vapour Control Layer
a20db41f-e8ce-5d91-ba05-5fdc80238685 | checkpoint | Vapour Control Layer installed to top face of acoustic board
c00a89af-8c21-5216-8aec-a93401ef6e2c | checkpoint | Correct side laps (80mm) and end laps (100mm)
3226f481-ac57-585f-a57d-b37b904d874a | checkpoint | Vapour Control Layer to be installed in accordance with project details. Ensure Vapour Control Layer is correctly terminated to ensure vapour control continuity at roof openings, transitions and at horizontal to vertical roof/cladding junctions, under flashings installed as per detail
43e2aa1e-5eee-51a8-810a-a424fd2dc094 | checkpoint | Any damage to vapour control layer repaired to ensure vapour control layer 100% continuous.
5938a466-bd4d-5f64-a003-67d1a5e47867 | section | Install RL PIR Board and RL Roof Board HD
469c2bdd-0021-55da-891d-da7013c6c900 | checkpoint | RL PIR Board insulation to be installed continuously over vapour control layer to roof and gutter in accordance with architectural drawings
12dd9cc4-b0e0-54b5-93a0-0ee393111c91 | checkpoint | Any damaged insulation board to be cut out and replaced with new, tightly butted piece of PIR Board (minimum 300mm x 300mm piece.)
02cd45b7-d474-5b41-8b8d-cfe4b6bf2feb | checkpoint | PIR insulation to be dry prior to application of RL Roof Board and Fibertite membrane.
4f871f4f-d7f2-59ad-bddd-aa145c32baca | checkpoint | Roof Board HD to be installed over PIR Board and mechanically attached to the substrate. Fasteners to be installed in accordance with the prescribed fixing pattern.
| section | Fibertite Membrane
| checkpoint | Install Fibertite membrane in strict accordance with Project Specification.
792b1eb7-75c4-5164-897d-479e5143bf21 | section | Adhering Fibertite Membrane
7304fa34-e3ca-50de-ab79-126ad37457ce | checkpoint | Ensure substrate (e.g. Roof Board) is dry and free from dirt, debris or contamination.
169a2efa-74c7-56ad-b2c8-647e0e2b160f | checkpoint | Select adhesive as specified
e8bb6c91-7e88-4eed-9140-a258ac5743eb | button |  | 440, 220
1216659b-d839-5292-b83f-30d9dad5ea9e | checkpoint | Adhesive applied as per specification -Ref specification cl .3.13 in project specification
27052b6b-78b5-568e-b24a-202d8c21f2b4 | checkpoint | Penetrations dressed correctly and boots seals clamped
ba50ce50-4525-5cbe-a549-4b3ea837ce22 | section | Welding Fibertite Membrane
ae22c991-57fe-53d7-b042-ed2ecea1d308 | checkpoint | Seams wiped clean (both surfaces to be welded) with Acetone and clean, white cotton rag
| checkpoint | Test welds of works to be carried out on completion of works with hand- held or robotic welders
19ea4380-89fd-5aeb-8a0e-80fb36eab904 | checkpoint | Seams to be welded clear of dirt, debris, moisture and adhesive residues.
b2c488ba-935f-5bf7-a640-c27600c3a885 | checkpoint | Any welding deficiencies rectified on the same day they are seam probed
f7b72917-a559-5b87-8887-47cac59b0564 | checkpoint | Night joints are installed daily, as required, to ensure that no moisture is allowed to migrate under the installed membrane.
| checkpoint | Area left clean & free of other materials/debris to avoid damage
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | section | Final Inspection
4f6f60ea-81b2-5034-91bf-2ddeeee8db05 | checkpoint | System installation is complete
3062e849-1017-5c63-8bd6-ba45206ab93a | checkpoint | All membrane terminated with either thermoplastic weld or mechanical clamp/termination (drain clamps with no missing bolts)
9925e84b-ca57-5ae9-a5f7-66721f54b53f | checkpoint | No exposed membrane terminations that could allow water behind
0c0d1b65-f19e-55e5-b349-d175e6a217bc | checkpoint | All terminations details in accordance with project specific and standard RL construction plans and detail drawings.
30f1153a-90e6-5ea8-a6b4-dd48c83666a5 | checkpoint | Any damage to system and/or membrane have been recorded/ rectified
ef661bc0-9cb1-59f1-8208-15cac2200766 | checkpoint | All construction equipment and materials removed from roof/site.
3bf8dfea-b0c7-5a26-b351-8ef698c0ecab | checkpoint | Maintenance Documents submitted to Main Contractor/Building Owner