## Sheet1
1.01 | AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Crushing Resistance | H | 1 per 10,000 m3 | NZS4407:3.10 | CHAR(LESS) 10% passing 2.36mm sieve at 130kN | IANZ report | Contractor |  | A | I | R | 1.01 - AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Detail of Activity / Test - Crushing Resistance | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - 1 per 10,000 m3 | Inspection / Test method - NZS4407:3.10 | Acceptance Criteria - CHAR(LESS) 10% passing 2.36mm sieve at 130kN | Record documents (QCP - Quality Control Portal) - IANZ report | Responsibility - Contractor | Project Specific Notes / Instructions - | Designer - A | Eng. Rep - I | Contractor - R | 1.01 - AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production
1.02 | AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Weathering Quality Index | H | 1 per 10,000 m3 | NZS4407:3.11 | AA, AB, AC, BA, BB, CA | IANZ Report | Contractor |  | A | I | R | 1.02 - AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Detail of Activity / Test - Weathering Quality Index | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - 1 per 10,000 m3 | Inspection / Test method - NZS4407:3.11 | Acceptance Criteria - AA, AB, AC, BA, BB, CA | Record documents (QCP - Quality Control Portal) - IANZ Report | Responsibility - Contractor | Project Specific Notes / Instructions - | Designer - A | Eng. Rep - I | Contractor - R | Detail of Activity / Test - Crushing Resistance
1.03 | AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Calfornia Bearing Ratio (CBR) | H | 1 per 10,000 m3 | NZS4402:4.1.3 NZS4407:3.15 | Compaceted using NZ Vibe Hammer 4-day soaked CBR ≥ 80% | IANZ Report | Contractor |  | A | I | R | 1.03 - AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Detail of Activity / Test - Calfornia Bearing Ratio (CBR) | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - 1 per 10,000 m3 | Inspection / Test method - NZS4402:4.1.3 NZS4407:3.15 | Acceptance Criteria - Compaceted using NZ Vibe Hammer 4-day soaked CBR ≥ 80% | Record documents (QCP - Quality Control Portal) - IANZ Report | Responsibility - Contractor | Project Specific Notes / Instructions - | Designer - A | Eng. Rep - I | Contractor - R | Action (Hold, Monitor, Witness) - H
1.04 | AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Quality of Fines, PI and CI | H | 1 per 1,000 m3 | NZS4407:3.4 - PI NZS4407:3.5 - CI | PI ≤ 5 CI ≤ 3 | IANZ Report | Contractor | NZTA M04: 2024 AP40 - Class 2 PI and CI applies | A | I | R | 1.04 - AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Detail of Activity / Test - Quality of Fines, PI and CI | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - 1 per 1,000 m3 | Inspection / Test method - NZS4407:3.4 - PI NZS4407:3.5 - CI | Acceptance Criteria - PI ≤ 5 CI ≤ 3 | Record documents (QCP - Quality Control Portal) - IANZ Report | Responsibility - Contractor | Project Specific Notes / Instructions - NZTA M04: 2024 AP40 - Class 2 PI and CI applies | Designer - A | Eng. Rep - I | Contractor - R | Minimum Test Frequency - 1 per 10,000 m3
1.05 | AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Broken Faces Content | H | 1 per 1,000 m3 | NZS4407:3.14 | ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm | IANZ Report | Contractor | Waived if aggregate is from crushed hard rock quarry | A | I | R | 1.05 - AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Detail of Activity / Test - Broken Faces Content | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - 1 per 1,000 m3 | Inspection / Test method - NZS4407:3.14 | Acceptance Criteria - ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm | Record documents (QCP - Quality Control Portal) - IANZ Report | Responsibility - Contractor | Project Specific Notes / Instructions - Waived if aggregate is from crushed hard rock quarry | Designer - A | Eng. Rep - I | Contractor - R | Inspection / Test method - NZS4407:3.10
1.06 | AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Particle Size Distribution | H | 1 per 1,000 m3 | NZS4407:3.8.1 | NZTA M04:2024-Class 2 Class 2 in Table 12 for PSD Table 13 for shape control | IANZ report | Contractor |  | A | I | R | 1.06 - AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Detail of Activity / Test - Particle Size Distribution | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - 1 per 1,000 m3 | Inspection / Test method - NZS4407:3.8.1 | Acceptance Criteria - NZTA M04:2024-Class 2 Class 2 in Table 12 for PSD Table 13 for shape control | Record documents (QCP - Quality Control Portal) - IANZ report | Responsibility - Contractor | Project Specific Notes / Instructions - | Designer - A | Eng. Rep - I | Contractor - R | Acceptance Criteria - CHAR(LESS) 10% passing 2.36mm sieve at 130kN
1.07 | Optimisation of Stabilising Agent(s) (FBS only) | Blend Particle Size Distribution | H | 1 per 1,000 m3 | NZS4407:3.8.1 | Check if average of existing (from TPs) and any overlay will meet the ideal FBS / BE grading. | Report using IANZ Reports for AP40 and TP PSDs | Designer | Designer to advise if "average" blend is acceptable. | R | A | I | 1.07 - Optimisation of Stabilising Agent(s) (FBS only) | Detail of Activity / Test - Blend Particle Size Distribution | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - 1 per 1,000 m3 | Inspection / Test method - NZS4407:3.8.1 | Acceptance Criteria - Check if average of existing (from TPs) and any overlay will meet the ideal FBS / BE grading. | Record documents (QCP - Quality Control Portal) - Report using IANZ Reports for AP40 and TP PSDs | Responsibility - Designer | Project Specific Notes / Instructions - Designer to advise if "average" blend is acceptable. | Designer - R | Eng. Rep - A | Contractor - I | Record documents (QCP - Quality Control Portal) - IANZ report
1.08 | Optimisation of Stabilising Agent(s) (FBS only) | Indirect Tensile Strength, ITS | H | 1 Optimisation test per aggregate type | NZTA T/19: 2020 | Testing at 1mm/min: BSM Dry ITS: 175 kPa to 400 kPa BSM Soaked ITS: 150 kPa to 350 kPa Testing at 50.8mm/min: BSM Dry ITS: 210 kPa to 480 kPa BSM Soaked ITS: 180 kPa to 450 kPa | IANZ Report | Designer | Designer to advise on binder content(s) Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field | R | A | I | 1.08 - Optimisation of Stabilising Agent(s) (FBS only) | Detail of Activity / Test - Indirect Tensile Strength, ITS | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - 1 Optimisation test per aggregate type | Inspection / Test method - NZTA T/19: 2020 | Acceptance Criteria - Testing at 1mm/min: BSM Dry ITS: 175 kPa to 400 kPa BSM Soaked ITS: 150 kPa to 350 kPa Testing at 50.8mm/min: BSM Dry ITS: 210 kPa to 480 kPa BSM Soaked ITS: 180 kPa to 450 kPa | Record documents (QCP - Quality Control Portal) - IANZ Report | Responsibility - Designer | Project Specific Notes / Instructions - Designer to advise on binder content(s) Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field | Designer - R | Eng. Rep - A | Contractor - I | Responsibility - Contractor
1.09 | Optimisation of Stabilising Agent(s) (FBS only) | Unconfined Compressive Strength, UCS | H | 1 Optimisation test per aggregate type | CCNZ / NPTG / CETANZ Industry Guide | UCS limits set by the design engineeer | IANZ Report | Designer | Designer to advise on binder content(s) Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field | R | A | I | 1.09 - Optimisation of Stabilising Agent(s) (FBS only) | Detail of Activity / Test - Unconfined Compressive Strength, UCS | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - 1 Optimisation test per aggregate type | Inspection / Test method - CCNZ / NPTG / CETANZ Industry Guide | Acceptance Criteria - UCS limits set by the design engineeer | Record documents (QCP - Quality Control Portal) - IANZ Report | Responsibility - Designer | Project Specific Notes / Instructions - Designer to advise on binder content(s) Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field | Designer - R | Eng. Rep - A | Contractor - I | Project Specific Notes / Instructions -
1.1 | Optimisation of Stabilising Agent(s) (FBS only) | Modified Maximum Dry Density | H | Single Point DD vs WC during optimisation test | NZS 4402.4.1.3 | To determine target density | IANZ Report | Designer | Required before Stabilisation comences | R | A | I | 1.1 - Optimisation of Stabilising Agent(s) (FBS only) | Detail of Activity / Test - Modified Maximum Dry Density | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - Single Point DD vs WC during optimisation test | Inspection / Test method - NZS 4402.4.1.3 | Acceptance Criteria - To determine target density | Record documents (QCP - Quality Control Portal) - IANZ Report | Responsibility - Designer | Project Specific Notes / Instructions - Required before Stabilisation comences | Designer - R | Eng. Rep - A | Contractor - I | Designer - A
2.01 | Setout section | Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking | H | Prior to each section | Survey | Document existing furniture | Electronic survey files | Contractor |  |  | I | R | 2.01 - Setout section | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - Prior to each section | Inspection / Test method - Survey | Acceptance Criteria - Document existing furniture | Record documents (QCP - Quality Control Portal) - Electronic survey files | Responsibility - Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep - I | Contractor - R | Eng. Rep - I
2.02 | Initial granular overlay and check levels | Supply, pre-compact and trim to line and level with NZTA M/4 AP40 | H | Prior to granulisation | Use grader's machine control and inspect shape | Minimum: -10mm Maximum: +20mm | Drawing Showing levels and crossfalls | Stabilising Contractor with Main Contractor | Overlay approved AP40 M/4-2 material to the thickness specified and pre-compact. Level correctness is critical to ensure we granulate all chipseal. |  | A | R | 2.02 - Initial granular overlay and check levels | Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40 | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - Prior to granulisation | Inspection / Test method - Use grader's machine control and inspect shape | Acceptance Criteria - Minimum: -10mm Maximum: +20mm | Record documents (QCP - Quality Control Portal) - Drawing Showing levels and crossfalls | Responsibility - Stabilising Contractor with Main Contractor | Project Specific Notes / Instructions - Overlay approved AP40 M/4-2 material to the thickness specified and pre-compact. Level correctness is critical to ensure we granulate all chipseal. | Designer - | Eng. Rep - A | Contractor - R | Contractor - R
2.03 | Pre-hoe, shape and proof roll | Pre-hoe to depth specified and shape as instructed in the site specific methodology statement and/or IFC drawings and proof roll | H | Prior to stabilisation per section | Use grader's machine control and inspect shape |  | N/A | Stabilising Contractor | Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement |  | A | R | 2.03 - Pre-hoe, shape and proof roll | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site specific methodology statement and/or IFC drawings and proof roll | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - Prior to stabilisation per section | Inspection / Test method - Use grader's machine control and inspect shape | Acceptance Criteria - | Record documents (QCP - Quality Control Portal) - N/A | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement | Designer - | Eng. Rep - A | Contractor - R | 1.02 - AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production
2.04 | Pre-hoe, shape and proof roll | Pre-hoe to depth specified and shape as instructed in the site specific methodology statement and/or IFC drawings and proof roll | H | Prior to stabilisation per section | Visual check or Vibratory Roller's response meter |  | Stabilising Contractor confirm no obvious soft areas found | Stabilising Contractor | Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions |  | A | R | 2.04 - Pre-hoe, shape and proof roll | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site specific methodology statement and/or IFC drawings and proof roll | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - Prior to stabilisation per section | Inspection / Test method - Visual check or Vibratory Roller's response meter | Acceptance Criteria - | Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions | Designer - | Eng. Rep - A | Contractor - R | Detail of Activity / Test - Weathering Quality Index
2.05 | Pre-hoe, shape and proof roll | Pre-hoe to depth specified and shape as instructed in the site specific methodology statement and/or IFC drawings and proof roll | H | 1 per 50m per cut | Pilot Holes to prehoe depth. | Check that no in-tact chipseals are present after prehoe | Daily work Log | Stabilising Contractor | Existing chipseals need to be granulated throughout. Last opportunity to confirm this has been achieved. |  | A | R | 2.05 - Pre-hoe, shape and proof roll | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site specific methodology statement and/or IFC drawings and proof roll | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - 1 per 50m per cut | Inspection / Test method - Pilot Holes to prehoe depth. | Acceptance Criteria - Check that no in-tact chipseals are present after prehoe | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - Existing chipseals need to be granulated throughout. Last opportunity to confirm this has been achieved. | Designer - | Eng. Rep - A | Contractor - R | Action (Hold, Monitor, Witness) - H
2.06 | Compaction (Subbase) | Plateau Density Test | H | On first day per site and then 1 per 10,000m2 unless material or anvil conditions change | Draft NZTA T/24 (Aug-2024) | To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD | Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed | Stabilising Contractor | If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER | I | A | R | 2.06 - Compaction (Subbase) | Detail of Activity / Test - Plateau Density Test | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change | Inspection / Test method - Draft NZTA T/24 (Aug-2024) | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER | Designer - I | Eng. Rep - A | Contractor - R | Minimum Test Frequency - 1 per 10,000 m3
2.07 | Compaction (Subbase) | Maximum Dry Density | M | On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes | NZS 4402.4.1.3 | For analysis of DoC To be done at the sampled MC, at hand squeeze test MC and 1% above the hand squeeze test on site | IANZ Report | Stabilising Contractor | MDD briquette to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out. | I | A | R | 2.07 - Compaction (Subbase) | Detail of Activity / Test - Maximum Dry Density | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes | Inspection / Test method - NZS 4402.4.1.3 | Acceptance Criteria - For analysis of DoC To be done at the sampled MC, at hand squeeze test MC and 1% above the hand squeeze test on site | Record documents (QCP - Quality Control Portal) - IANZ Report | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - MDD briquette to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out. | Designer - I | Eng. Rep - A | Contractor - R | Inspection / Test method - NZS4407:3.11
2.08 | Compaction (Subbase) | Degree of Compaction (DoC) | H | 5 per 1,000m2 | NZS 4407.4.2.1 (DT full stabilising depth) | Average DoC ≥ 95% Minimum DoC ≥ 92% | IANZ Report | Stabilising Contractor |  | I | A | R | 2.08 - Compaction (Subbase) | Detail of Activity / Test - Degree of Compaction (DoC) | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - 5 per 1,000m2 | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth) | Acceptance Criteria - Average DoC ≥ 95% Minimum DoC ≥ 92% | Record documents (QCP - Quality Control Portal) - IANZ Report | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep - A | Contractor - R | Acceptance Criteria - AA, AB, AC, BA, BB, CA
3.01 | Final Granular Overlay and check levels | Supply, pre-compact and trim to line and level with NZTA M/4 AP40 | H | Prior to stabilisation per section | Survey | As per NZTA Z/16 Minimum: -5mm Maximum: +15mm | Drawing Showing levels and crossfalls | Stabilising Contractor with Main Contractor | This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to): - overlay aggregate quality / consistency - moisture content - any concerns with shape and tie in - etc. |  | I | R | 3.01 - Final Granular Overlay and check levels | Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40 | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - Prior to stabilisation per section | Inspection / Test method - Survey | Acceptance Criteria - As per NZTA Z/16 Minimum: -5mm Maximum: +15mm | Record documents (QCP - Quality Control Portal) - Drawing Showing levels and crossfalls | Responsibility - Stabilising Contractor with Main Contractor | Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to): - overlay aggregate quality / consistency - moisture content - any concerns with shape and tie in - etc. | Designer - | Eng. Rep - I | Contractor - R | Record documents (QCP - Quality Control Portal) - IANZ Report
3.02 | Production Plan | Plan showing cut lines and sequencing of works | M | Prior to each section | Daily Report | Points covered in NZTA B/5 | Daily Production Plan | Stabilising Contractor |  |  | I | R | 3.02 - Production Plan | Detail of Activity / Test - Plan showing cut lines and sequencing of works | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - Prior to each section | Inspection / Test method - Daily Report | Acceptance Criteria - Points covered in NZTA B/5 | Record documents (QCP - Quality Control Portal) - Daily Production Plan | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep - I | Contractor - R | Responsibility - Contractor
3.03 | Weather conditions | Material behind stabiliser | M | Prior to spreading | Measurement | Material after stabilisation: BE: > 20°C, FB: > 20°C and Ambient: >5 deg.C | Daily work Log | Stabilsing Contractor |  |  | I | R | 3.03 - Weather conditions | Detail of Activity / Test - Material behind stabiliser | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - Prior to spreading | Inspection / Test method - Measurement | Acceptance Criteria - Material after stabilisation: BE: > 20°C, FB: > 20°C and Ambient: >5 deg.C | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilsing Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep - I | Contractor - R | Project Specific Notes / Instructions -
3.04 | Weather conditions | Wind | M | Prior to spreading cement or lime | Local weather stations | Wind speed CHAR(LESS) 25 km/hr | Daily work Log | Stabilsing Contractor |  |  | I | R | 3.04 - Weather conditions | Detail of Activity / Test - Wind | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - Prior to spreading cement or lime | Inspection / Test method - Local weather stations | Acceptance Criteria - Wind speed CHAR(LESS) 25 km/hr | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilsing Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep - I | Contractor - R | Designer - A
3.05 | Weather conditions | Rain | M | Prior to spreading cement or lime | Local weather stations | No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material | Daily work Log | Stabilsing Contractor |  |  | I | R | 3.05 - Weather conditions | Detail of Activity / Test - Rain | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - Prior to spreading cement or lime | Inspection / Test method - Local weather stations | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilsing Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep - I | Contractor - R | Eng. Rep - I
4.01 | Stabilising Agents | Lime (if applicable - check PI delete otherwise) | M | Per Batch | TNZ M/15 | Conform to Specification | Certificate in contractor's site folder | Stabilising Contractor |  |  | I | R | 4.01 - Stabilising Agents | Detail of Activity / Test - Lime (if applicable - check PI delete otherwise) | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - Per Batch | Inspection / Test method - TNZ M/15 | Acceptance Criteria - Conform to Specification | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep - I | Contractor - R | Contractor - R
4.02 | Stabilising Agents | Cement, GP | M | Per Batch | NZS 3122 | Conform to Specification | Certificate in contractor's site folder | Stabilising Contractor |  |  | I | R | 4.02 - Stabilising Agents | Detail of Activity / Test - Cement, GP | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - Per Batch | Inspection / Test method - NZS 3122 | Acceptance Criteria - Conform to Specification | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep - I | Contractor - R | 1.03 - AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production
4.03 | Stabilising Agents | Bitumen (130/150) | M | Per Batch | M/1 | Conform to Specification | Certificate in contractor's site folder | Stabilising Contractor |  |  | I | R | 4.03 - Stabilising Agents | Detail of Activity / Test - Bitumen (130/150) | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - Per Batch | Inspection / Test method - M/1 | Acceptance Criteria - Conform to Specification | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep - I | Contractor - R | Detail of Activity / Test - Calfornia Bearing Ratio (CBR)
4.04 | Spreading of powdered stabilising agent (Cement / Lime) | Place 1m2 canvas or 0.5m x 0.5m trays along spreader run | M | every 400 m2 every 150m for a 2.4m width | Weigh mat or tray | ± 0.5kg/m2 of specified rate | Daily work Log | Stabilising Contractor |  |  | I | R | 4.04 - Spreading of powdered stabilising agent (Cement / Lime) | Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - every 400 m2 every 150m for a 2.4m width | Inspection / Test method - Weigh mat or tray | Acceptance Criteria - ± 0.5kg/m2 of specified rate | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep - I | Contractor - R | Action (Hold, Monitor, Witness) - H
4.05 | Spreading of powdered stabilising agent (Cement / Lime) | Compare area spread with weight used for each spreader load | M | On-going measurement by computer/load cells | Measurement each run | ± 2.5% of specified rate | Daily work Log | Stabilising Contractor |  |  | I | R | 4.05 - Spreading of powdered stabilising agent (Cement / Lime) | Detail of Activity / Test - Compare area spread with weight used for each spreader load | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - On-going measurement by computer/load cells | Inspection / Test method - Measurement each run | Acceptance Criteria - ± 2.5% of specified rate | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep - I | Contractor - R | Minimum Test Frequency - 1 per 10,000 m3
4.06 | Injection of bituminous stabilising agent (FBS or BE) | Flow meter and operator's display readings | M | Continous monitoring by the operator and the grounds person | Visual display reading | ± 5% of specified rate | N/A | Stabilising Contractor |  |  | I | R | 4.06 - Injection of bituminous stabilising agent (FBS or BE) | Detail of Activity / Test - Flow meter and operator's display readings | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - Continous monitoring by the operator and the grounds person | Inspection / Test method - Visual display reading | Acceptance Criteria - ± 5% of specified rate | Record documents (QCP - Quality Control Portal) - N/A | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep - I | Contractor - R | Inspection / Test method - NZS4402:4.1.3 NZS4407:3.15
4.07 | Injection of bituminous stabilising agent (FBS or BE) | Compare tonnes used (from the stabiiser's PCU) with the measured area | M | Record usage from PCU at the end of each run | Record readings at the end of each run | ± 3% of specified rate | Daily work Log | Stabilising Contractor |  |  | I | R | 4.07 - Injection of bituminous stabilising agent (FBS or BE) | Detail of Activity / Test - Compare tonnes used (from the stabiiser's PCU) with the measured area | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - Record usage from PCU at the end of each run | Inspection / Test method - Record readings at the end of each run | Acceptance Criteria - ± 3% of specified rate | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep - I | Contractor - R | Acceptance Criteria - Compaceted using NZ Vibe Hammer 4-day soaked CBR ≥ 80%
4.08 | Injection of bituminous stabilising agent (FBS or BE) | Compare tonnes used (from delivery docket) with measured area | M | For each bitumen tanker load | Dip bitumen tanker before and after | ± 2.5% of specified rate | Daily work Log | Stabilising Contractor |  |  | I | R | 4.08 - Injection of bituminous stabilising agent (FBS or BE) | Detail of Activity / Test - Compare tonnes used (from delivery docket) with measured area | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - For each bitumen tanker load | Inspection / Test method - Dip bitumen tanker before and after | Acceptance Criteria - ± 2.5% of specified rate | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep - I | Contractor - R | Record documents (QCP - Quality Control Portal) - IANZ Report
4.09 | Injection CHAR(AMP) Mixing of Water | In-situ Stabilisation process | M | On-going visual assessment | Visual and hand squeeze test | Mixed material free of pockets or streaks. Overlaps minimum of 150mm | Daily work Log | Stabilising Contractor |  |  | I | R | 4.09 - Injection CHAR(AMP) Mixing of Water | Detail of Activity / Test - In-situ Stabilisation process | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - On-going visual assessment | Inspection / Test method - Visual and hand squeeze test | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep - I | Contractor - R | Responsibility - Contractor
4.1 | Depth of stabilisation | Depth of stabilisation | M | Every 200m | Measurement | +15mm / -5mm from specified depth | Daily work Log | Stabilising Contractor |  |  | I | R | 4.1 - Depth of stabilisation | Detail of Activity / Test - Depth of stabilisation | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - Every 200m | Inspection / Test method - Measurement | Acceptance Criteria - +15mm / -5mm from specified depth | Record documents (QCP - Quality Control Portal) - Daily work Log | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep - I | Contractor - R | Project Specific Notes / Instructions -
4.11 | FBS material | Stabilised material strength - ITS | M | 3 soaked ITS + 3 dry ITS per Lot or when the material changes | NZTA T/19N: 2020 | Testing at 1mm/min: BSM Dry ITS: 150 kPa to 400 kPa BSM Soaked ITS: 120 kPa to 350 kPa Testing at 50.8mm/min: BSM Dry ITS: 180 kPa to 450 kPa BSM Soaked ITS: 150 kPa to 420 kPa | IANZ Report | Stabilising Contractor | ITS briquettes to be produced on site if travel time to lab > 30 minutes. | I | A | R | 4.11 - FBS material | Detail of Activity / Test - Stabilised material strength - ITS | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - 3 soaked ITS + 3 dry ITS per Lot or when the material changes | Inspection / Test method - NZTA T/19N: 2020 | Acceptance Criteria - Testing at 1mm/min: BSM Dry ITS: 150 kPa to 400 kPa BSM Soaked ITS: 120 kPa to 350 kPa Testing at 50.8mm/min: BSM Dry ITS: 180 kPa to 450 kPa BSM Soaked ITS: 150 kPa to 420 kPa | Record documents (QCP - Quality Control Portal) - IANZ Report | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - ITS briquettes to be produced on site if travel time to lab > 30 minutes. | Designer - I | Eng. Rep - A | Contractor - R | Designer - A
4.12 | Compaction | Plateau Density Test | H | On first day per site and then 1 per 10,000m2 unless material or anvil conditions change | Draft NZTA T/24 (Aug-2024) | To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD | Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed | Stabilising Contractor | If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER | I | A | R | 4.12 - Compaction | Detail of Activity / Test - Plateau Density Test | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change | Inspection / Test method - Draft NZTA T/24 (Aug-2024) | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER | Designer - I | Eng. Rep - A | Contractor - R | Eng. Rep - I
4.13 | Compaction | Maximum Dry Density | M | On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes | NZS 4402.4.1.3 | For analysis of DoC To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site | IANZ Report | Stabilising Contractor | MDD briqutte to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out. | I | A | R | 4.13 - Compaction | Detail of Activity / Test - Maximum Dry Density | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes | Inspection / Test method - NZS 4402.4.1.3 | Acceptance Criteria - For analysis of DoC To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site | Record documents (QCP - Quality Control Portal) - IANZ Report | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out. | Designer - I | Eng. Rep - A | Contractor - R | Contractor - R
4.14 | Compaction | Degree of Compaction (DoC) | H | 5 per 1,000m2 | NZS 4407.4.2.1 (DT full stabilising depth) | Average DoC ≥ 98% Minimum DoC ≥ 95% | IANZ Report | Stabilising Contractor |  | I | A | R | 4.14 - Compaction | Detail of Activity / Test - Degree of Compaction (DoC) | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - 5 per 1,000m2 | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth) | Acceptance Criteria - Average DoC ≥ 98% Minimum DoC ≥ 95% | Record documents (QCP - Quality Control Portal) - IANZ Report | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep - A | Contractor - R | 1.04 - AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production
4.15 | Finished Pavement | Crossfall | H | every 20m | Measurement | ± 0.5% of specified crossfall measure 2m apart | Survey | Stabilising Contractor |  |  | A | R | 4.15 - Finished Pavement | Detail of Activity / Test - Crossfall | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - every 20m | Inspection / Test method - Measurement | Acceptance Criteria - ± 0.5% of specified crossfall measure 2m apart | Record documents (QCP - Quality Control Portal) - Survey | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep - A | Contractor - R | Detail of Activity / Test - Quality of Fines, PI and CI
4.16 | Finished Pavement | Stabilised width | H | 1 every 20m | Measurement | -20mm, +100mm | Survey | Stabilising Contractor |  |  | A | R | 4.16 - Finished Pavement | Detail of Activity / Test - Stabilised width | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - 1 every 20m | Inspection / Test method - Measurement | Acceptance Criteria - -20mm, +100mm | Record documents (QCP - Quality Control Portal) - Survey | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep - A | Contractor - R | Action (Hold, Monitor, Witness) - H
4.17 | Finished Pavement | Surface Shape | H | every 20m | Measurement | CHAR(LESS) 10mm using 3m straight edge | Survey | Stabilising Contractor | Only required if the visual inspection appears unsatisfactory |  | A | R | 4.17 - Finished Pavement | Detail of Activity / Test - Surface Shape | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - every 20m | Inspection / Test method - Measurement | Acceptance Criteria - CHAR(LESS) 10mm using 3m straight edge | Record documents (QCP - Quality Control Portal) - Survey | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory | Designer - | Eng. Rep - A | Contractor - R | Minimum Test Frequency - 1 per 1,000 m3
4.18 | Finished Pavement | Surface Finish | H | Per Lot | Visual | 1. Larger aggregate held in pace with a matrix of smaller aggregate 2. Smaller aggregate held in place by fine material 3. matrix does not displace under normal trafficking and/or sweeping | Survey | Stabilising Contractor | ER to be present at pre-seal inspection |  | A | R | 4.18 - Finished Pavement | Detail of Activity / Test - Surface Finish | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - Per Lot | Inspection / Test method - Visual | Acceptance Criteria - 1. Larger aggregate held in pace with a matrix of smaller aggregate 2. Smaller aggregate held in place by fine material 3. matrix does not displace under normal trafficking and/or sweeping | Record documents (QCP - Quality Control Portal) - Survey | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - ER to be present at pre-seal inspection | Designer - | Eng. Rep - A | Contractor - R | Inspection / Test method - NZS4407:3.4 - PI NZS4407:3.5 - CI
4.19 | Finished Pavement | Roughness | H | Before Sealing | TNZ TM 7003 v1 | 100m rolling average ≤ 75 counts/km | Test Certificate | Contractor |  |  | A | R | 4.19 - Finished Pavement | Detail of Activity / Test - Roughness | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - Before Sealing | Inspection / Test method - TNZ TM 7003 v1 | Acceptance Criteria - 100m rolling average ≤ 75 counts/km | Record documents (QCP - Quality Control Portal) - Test Certificate | Responsibility - Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep - A | Contractor - R | Acceptance Criteria - PI ≤ 5 CI ≤ 3
4.2 | Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover) | Clegg Impact Value | H | 5 per 1000m2 |  | CIV ≥ 50 | CIV form - ConQA | Stabilising Contractor |  | I | A | R | 4.2 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover) | Detail of Activity / Test - Clegg Impact Value | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - 5 per 1000m2 | Inspection / Test method - | Acceptance Criteria - CIV ≥ 50 | Record documents (QCP - Quality Control Portal) - CIV form - ConQA | Responsibility - Stabilising Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep - A | Contractor - R | Record documents (QCP - Quality Control Portal) - IANZ Report
4.21 | Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover) | Degree of Saturation, DOS | M | 5 per 1000m2 | NZS 4407.4.2.2 and DOS calculation in NZTA B/5 | aim for DOS ≤ 80% | IANZ report | Contractor | Report only | I | A | R | 4.21 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover) | Detail of Activity / Test - Degree of Saturation, DOS | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency - 5 per 1000m2 | Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5 | Acceptance Criteria - aim for DOS ≤ 80% | Record documents (QCP - Quality Control Portal) - IANZ report | Responsibility - Contractor | Project Specific Notes / Instructions - Report only | Designer - I | Eng. Rep - A | Contractor - R | Responsibility - Contractor
5.01 | Pavement Layer Signoff | Assessment of all test results for conformity | H | Each Lot | Site Inspection | Reporting of any non-conforming results to Designer via NCR | NCR | Engineers Representative |  |  |  |  | 5.01 - Pavement Layer Signoff | Detail of Activity / Test - Assessment of all test results for conformity | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency - Each Lot | Inspection / Test method - Site Inspection | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR | Record documents (QCP - Quality Control Portal) - NCR | Responsibility - Engineers Representative | Project Specific Notes / Instructions - | Designer - | Eng. Rep - | Contractor - | Project Specific Notes / Instructions - NZTA M04: 2024 AP40 - Class 2 PI and CI applies
Designer - A
Eng. Rep - I
Contractor - R
1.05 - AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production
Detail of Activity / Test - Broken Faces Content
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - 1 per 1,000 m3
Inspection / Test method - NZS4407:3.14
Acceptance Criteria - ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm
Record documents (QCP - Quality Control Portal) - IANZ Report
Responsibility - Contractor
Project Specific Notes / Instructions - Waived if aggregate is from crushed hard rock quarry
Designer - A
Eng. Rep - I
Contractor - R
1.06 - AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production
Detail of Activity / Test - Particle Size Distribution
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - 1 per 1,000 m3
Inspection / Test method - NZS4407:3.8.1
Acceptance Criteria - NZTA M04:2024-Class 2 Class 2 in Table 12 for PSD Table 13 for shape control
Record documents (QCP - Quality Control Portal) - IANZ report
Responsibility - Contractor
Project Specific Notes / Instructions -
Designer - A
Eng. Rep - I
Contractor - R
1.07 - Optimisation of Stabilising Agent(s) (FBS only)
Detail of Activity / Test - Blend Particle Size Distribution
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - 1 per 1,000 m3
Inspection / Test method - NZS4407:3.8.1
Acceptance Criteria - Check if average of existing (from TPs) and any overlay will meet the ideal FBS / BE grading.
Record documents (QCP - Quality Control Portal) - Report using IANZ Reports for AP40 and TP PSDs
Responsibility - Designer
Project Specific Notes / Instructions - Designer to advise if "average" blend is acceptable.
Designer - R
Eng. Rep - A
Contractor - I
1.08 - Optimisation of Stabilising Agent(s) (FBS only)
Detail of Activity / Test - Indirect Tensile Strength, ITS
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - 1 Optimisation test per aggregate type
Inspection / Test method - NZTA T/19: 2020
Acceptance Criteria - Testing at 1mm/min: BSM Dry ITS: 175 kPa to 400 kPa BSM Soaked ITS: 150 kPa to 350 kPa Testing at 50.8mm/min: BSM Dry ITS: 210 kPa to 480 kPa BSM Soaked ITS: 180 kPa to 450 kPa
Record documents (QCP - Quality Control Portal) - IANZ Report
Responsibility - Designer
Project Specific Notes / Instructions - Designer to advise on binder content(s) Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
Designer - R
Eng. Rep - A
Contractor - I
1.09 - Optimisation of Stabilising Agent(s) (FBS only)
Detail of Activity / Test - Unconfined Compressive Strength, UCS
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - 1 Optimisation test per aggregate type
Inspection / Test method - CCNZ / NPTG / CETANZ Industry Guide
Acceptance Criteria - UCS limits set by the design engineeer
Record documents (QCP - Quality Control Portal) - IANZ Report
Responsibility - Designer
Project Specific Notes / Instructions - Designer to advise on binder content(s) Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
Designer - R
Eng. Rep - A
Contractor - I
1.1 - Optimisation of Stabilising Agent(s) (FBS only)
Detail of Activity / Test - Modified Maximum Dry Density
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - Single Point DD vs WC during optimisation test
Inspection / Test method - NZS 4402.4.1.3
Acceptance Criteria - To determine target density
Record documents (QCP - Quality Control Portal) - IANZ Report
Responsibility - Designer
Project Specific Notes / Instructions - Required before Stabilisation comences
Designer - R
Eng. Rep - A
Contractor - I
2.01 - Setout section
Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - Prior to each section
Inspection / Test method - Survey
Acceptance Criteria - Document existing furniture
Record documents (QCP - Quality Control Portal) - Electronic survey files
Responsibility - Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep - I
Contractor - R
2.02 - Initial granular overlay and check levels
Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - Prior to granulisation
Inspection / Test method - Use grader's machine control and inspect shape
Acceptance Criteria - Minimum: -10mm Maximum: +20mm
Record documents (QCP - Quality Control Portal) - Drawing Showing levels and crossfalls
Responsibility - Stabilising Contractor with Main Contractor
Project Specific Notes / Instructions - Overlay approved AP40 M/4-2 material to the thickness specified and pre-compact. Level correctness is critical to ensure we granulate all chipseal.
Designer -
Eng. Rep - A
Contractor - R
2.03 - Pre-hoe, shape and proof roll
Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site specific methodology statement and/or IFC drawings and proof roll
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - Prior to stabilisation per section
Inspection / Test method - Use grader's machine control and inspect shape
Acceptance Criteria -
Record documents (QCP - Quality Control Portal) - N/A
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement
Designer -
Eng. Rep - A
Contractor - R
2.04 - Pre-hoe, shape and proof roll
Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site specific methodology statement and/or IFC drawings and proof roll
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - Prior to stabilisation per section
Inspection / Test method - Visual check or Vibratory Roller's response meter
Acceptance Criteria -
Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions
Designer -
Eng. Rep - A
Contractor - R
2.05 - Pre-hoe, shape and proof roll
Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site specific methodology statement and/or IFC drawings and proof roll
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - 1 per 50m per cut
Inspection / Test method - Pilot Holes to prehoe depth.
Acceptance Criteria - Check that no in-tact chipseals are present after prehoe
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - Existing chipseals need to be granulated throughout. Last opportunity to confirm this has been achieved.
Designer -
Eng. Rep - A
Contractor - R
2.06 - Compaction (Subbase)
Detail of Activity / Test - Plateau Density Test
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
Inspection / Test method - Draft NZTA T/24 (Aug-2024)
Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
Designer - I
Eng. Rep - A
Contractor - R
2.07 - Compaction (Subbase)
Detail of Activity / Test - Maximum Dry Density
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
Inspection / Test method - NZS 4402.4.1.3
Acceptance Criteria - For analysis of DoC To be done at the sampled MC, at hand squeeze test MC and 1% above the hand squeeze test on site
Record documents (QCP - Quality Control Portal) - IANZ Report
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - MDD briquette to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
Designer - I
Eng. Rep - A
Contractor - R
2.08 - Compaction (Subbase)
Detail of Activity / Test - Degree of Compaction (DoC)
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - 5 per 1,000m2
Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
Acceptance Criteria - Average DoC ≥ 95% Minimum DoC ≥ 92%
Record documents (QCP - Quality Control Portal) - IANZ Report
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep - A
Contractor - R
3.01 - Final Granular Overlay and check levels
Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - Prior to stabilisation per section
Inspection / Test method - Survey
Acceptance Criteria - As per NZTA Z/16 Minimum: -5mm Maximum: +15mm
Record documents (QCP - Quality Control Portal) - Drawing Showing levels and crossfalls
Responsibility - Stabilising Contractor with Main Contractor
Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to): - overlay aggregate quality / consistency - moisture content - any concerns with shape and tie in - etc.
Designer -
Eng. Rep - I
Contractor - R
3.02 - Production Plan
Detail of Activity / Test - Plan showing cut lines and sequencing of works
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - Prior to each section
Inspection / Test method - Daily Report
Acceptance Criteria - Points covered in NZTA B/5
Record documents (QCP - Quality Control Portal) - Daily Production Plan
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep - I
Contractor - R
3.03 - Weather conditions
Detail of Activity / Test - Material behind stabiliser
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - Prior to spreading
Inspection / Test method - Measurement
Acceptance Criteria - Material after stabilisation: BE: > 20°C, FB: > 20°C and Ambient: >5 deg.C
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilsing Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep - I
Contractor - R
3.04 - Weather conditions
Detail of Activity / Test - Wind
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - Prior to spreading cement or lime
Inspection / Test method - Local weather stations
Acceptance Criteria - Wind speed CHAR(LESS) 25 km/hr
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilsing Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep - I
Contractor - R
3.05 - Weather conditions
Detail of Activity / Test - Rain
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - Prior to spreading cement or lime
Inspection / Test method - Local weather stations
Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilsing Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep - I
Contractor - R
4.01 - Stabilising Agents
Detail of Activity / Test - Lime (if applicable - check PI delete otherwise)
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - Per Batch
Inspection / Test method - TNZ M/15
Acceptance Criteria - Conform to Specification
Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep - I
Contractor - R
4.02 - Stabilising Agents
Detail of Activity / Test - Cement, GP
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - Per Batch
Inspection / Test method - NZS 3122
Acceptance Criteria - Conform to Specification
Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep - I
Contractor - R
4.03 - Stabilising Agents
Detail of Activity / Test - Bitumen (130/150)
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - Per Batch
Inspection / Test method - M/1
Acceptance Criteria - Conform to Specification
Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep - I
Contractor - R
4.04 - Spreading of powdered stabilising agent (Cement / Lime)
Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - every 400 m2 every 150m for a 2.4m width
Inspection / Test method - Weigh mat or tray
Acceptance Criteria - ± 0.5kg/m2 of specified rate
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep - I
Contractor - R
4.05 - Spreading of powdered stabilising agent (Cement / Lime)
Detail of Activity / Test - Compare area spread with weight used for each spreader load
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - On-going measurement by computer/load cells
Inspection / Test method - Measurement each run
Acceptance Criteria - ± 2.5% of specified rate
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep - I
Contractor - R
4.06 - Injection of bituminous stabilising agent (FBS or BE)
Detail of Activity / Test - Flow meter and operator's display readings
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - Continous monitoring by the operator and the grounds person
Inspection / Test method - Visual display reading
Acceptance Criteria - ± 5% of specified rate
Record documents (QCP - Quality Control Portal) - N/A
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep - I
Contractor - R
4.07 - Injection of bituminous stabilising agent (FBS or BE)
Detail of Activity / Test - Compare tonnes used (from the stabiiser's PCU) with the measured area
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - Record usage from PCU at the end of each run
Inspection / Test method - Record readings at the end of each run
Acceptance Criteria - ± 3% of specified rate
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep - I
Contractor - R
4.08 - Injection of bituminous stabilising agent (FBS or BE)
Detail of Activity / Test - Compare tonnes used (from delivery docket) with measured area
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - For each bitumen tanker load
Inspection / Test method - Dip bitumen tanker before and after
Acceptance Criteria - ± 2.5% of specified rate
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep - I
Contractor - R
4.09 - Injection CHAR(AMP) Mixing of Water
Detail of Activity / Test - In-situ Stabilisation process
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - On-going visual assessment
Inspection / Test method - Visual and hand squeeze test
Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep - I
Contractor - R
4.1 - Depth of stabilisation
Detail of Activity / Test - Depth of stabilisation
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - Every 200m
Inspection / Test method - Measurement
Acceptance Criteria - +15mm / -5mm from specified depth
Record documents (QCP - Quality Control Portal) - Daily work Log
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep - I
Contractor - R
4.11 - FBS material
Detail of Activity / Test - Stabilised material strength - ITS
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - 3 soaked ITS + 3 dry ITS per Lot or when the material changes
Inspection / Test method - NZTA T/19N: 2020
Acceptance Criteria - Testing at 1mm/min: BSM Dry ITS: 150 kPa to 400 kPa BSM Soaked ITS: 120 kPa to 350 kPa Testing at 50.8mm/min: BSM Dry ITS: 180 kPa to 450 kPa BSM Soaked ITS: 150 kPa to 420 kPa
Record documents (QCP - Quality Control Portal) - IANZ Report
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - ITS briquettes to be produced on site if travel time to lab > 30 minutes.
Designer - I
Eng. Rep - A
Contractor - R
4.12 - Compaction
Detail of Activity / Test - Plateau Density Test
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
Inspection / Test method - Draft NZTA T/24 (Aug-2024)
Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
Designer - I
Eng. Rep - A
Contractor - R
4.13 - Compaction
Detail of Activity / Test - Maximum Dry Density
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
Inspection / Test method - NZS 4402.4.1.3
Acceptance Criteria - For analysis of DoC To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
Record documents (QCP - Quality Control Portal) - IANZ Report
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
Designer - I
Eng. Rep - A
Contractor - R
4.14 - Compaction
Detail of Activity / Test - Degree of Compaction (DoC)
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - 5 per 1,000m2
Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
Acceptance Criteria - Average DoC ≥ 98% Minimum DoC ≥ 95%
Record documents (QCP - Quality Control Portal) - IANZ Report
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep - A
Contractor - R
4.15 - Finished Pavement
Detail of Activity / Test - Crossfall
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - every 20m
Inspection / Test method - Measurement
Acceptance Criteria - ± 0.5% of specified crossfall measure 2m apart
Record documents (QCP - Quality Control Portal) - Survey
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep - A
Contractor - R
4.16 - Finished Pavement
Detail of Activity / Test - Stabilised width
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - 1 every 20m
Inspection / Test method - Measurement
Acceptance Criteria - -20mm, +100mm
Record documents (QCP - Quality Control Portal) - Survey
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep - A
Contractor - R
4.17 - Finished Pavement
Detail of Activity / Test - Surface Shape
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - every 20m
Inspection / Test method - Measurement
Acceptance Criteria - CHAR(LESS) 10mm using 3m straight edge
Record documents (QCP - Quality Control Portal) - Survey
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory
Designer -
Eng. Rep - A
Contractor - R
4.18 - Finished Pavement
Detail of Activity / Test - Surface Finish
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - Per Lot
Inspection / Test method - Visual
Acceptance Criteria - 1. Larger aggregate held in pace with a matrix of smaller aggregate 2. Smaller aggregate held in place by fine material 3. matrix does not displace under normal trafficking and/or sweeping
Record documents (QCP - Quality Control Portal) - Survey
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions - ER to be present at pre-seal inspection
Designer -
Eng. Rep - A
Contractor - R
4.19 - Finished Pavement
Detail of Activity / Test - Roughness
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - Before Sealing
Inspection / Test method - TNZ TM 7003 v1
Acceptance Criteria - 100m rolling average ≤ 75 counts/km
Record documents (QCP - Quality Control Portal) - Test Certificate
Responsibility - Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep - A
Contractor - R
4.2 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
Detail of Activity / Test - Clegg Impact Value
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - 5 per 1000m2
Inspection / Test method -
Acceptance Criteria - CIV ≥ 50
Record documents (QCP - Quality Control Portal) - CIV form - ConQA
Responsibility - Stabilising Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep - A
Contractor - R
4.21 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
Detail of Activity / Test - Degree of Saturation, DOS
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency - 5 per 1000m2
Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5
Acceptance Criteria - aim for DOS ≤ 80%
Record documents (QCP - Quality Control Portal) - IANZ report
Responsibility - Contractor
Project Specific Notes / Instructions - Report only
Designer - I
Eng. Rep - A
Contractor - R
5.01 - Pavement Layer Signoff
Detail of Activity / Test - Assessment of all test results for conformity
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency - Each Lot
Inspection / Test method - Site Inspection
Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
Record documents (QCP - Quality Control Portal) - NCR
Responsibility - Engineers Representative
Project Specific Notes / Instructions -
Designer -
Eng. Rep -
Contractor -