## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1212-ITP-010 Bridge Access Ramp | itp |  |  |  |  | DN1212-ITP-010 Bridge Access Ramp Rev2
section | 1 - PRELIMINARY AND GENERAL
checkpoint | 1.1 - Method Statement Development & Safety Analysis
label | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to Construction: Document Review
label | ○ Method Statement & JSEA
label | ○ Completed & signed by relevant authority
label | Test Frequency - Once
label | QA Record - Work pack (MS,JSEA,ITP)
label | DNZ Engineer - H
label | Engineer's Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - IFC Drawings and Specification
label | Standard, Drawing or Specification Reference - ACC
label | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
label | ○ Works done in accordance with KiwiRail specification
label | Test Frequency - Once
label | QA Record - N/A
label | DNZ Engineer - R
checkpoint | 1.3 - Model
label | Standard, Drawing or Specification Reference - ACC
label | Construction Activity Description, Test Type and Acceptance Criteria - Model reviewed and confirmed with correct location; depth, height and orientation for column, headstock and staircase
label | Test Frequency - Once
label | QA Record - N/A
label | DNZ Engineer - R
checkpoint | 1.4 - Permit to Dig
label | Standard, Drawing or Specification Reference - DG-ZH-ST004 Ground Disturbance
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
label | Test Frequency - Permit issued each week
textbox | QA Record - FlowForm Permit Register/Permit Number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Lifting Permit
label | Standard, Drawing or Specification Reference - DG-ZH-ST047 Cranes and Lifting Equipment Loads
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
label | Test Frequency - Prior to Construction when required
textbox | QA Record - FlowForm Permit Register/Permit Number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
section | 2 - MATERIAL APPROVALS
checkpoint | 2.1 - Concrete Mix Design
label | Standard, Drawing or Specification Reference - NZS 3104, 3235599-SP03-ST-3253 Section 2.1
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete mix details shall be provided to the Engineer for review and approval.
label | ○ 50MPa @ 28 Day Compressive Strength.
label | Test Frequency - Once
label | QA Record - Mix Certification, Plant Certification
textbox | InEight Approval
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Reinforcing Steel
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3253: Note 2.3, AS/NZS 4671
label | Construction Activity Description, Test Type and Acceptance Criteria - As per Access Ramp Reinforcing IFC detail drawings.
label | ○ Shop Drawings shall be provided to the Engineer for review and approval.
label | ○ Reinforcing steel to be grade 500E MA.
label | Test Frequency - Once
label | QA Record - Mill Test Certificates, Delivery Dockets
textbox | Shop Drawing Approval
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Formwork
label | Standard, Drawing or Specification Reference - MDS, Temporary works drawings
label | Construction Activity Description, Test Type and Acceptance Criteria - Formwork of choice from sub-contractor, Standard panels up to 900mm wide modules
label | ○ Full range of safety features
label | ○ High Quality plywood to provide F5 finish.
label | Test Frequency - Once
label | QA Record - MDS
label | DNZ Engineer - I
label | Designer Rep - R
checkpoint | 2.4 - Formwork Curing Agent
label | Standard, Drawing or Specification Reference - Material Data Sheet
label | Construction Activity Description, Test Type and Acceptance Criteria - Chemical curing agent.
label | Test Frequency - Once
label | QA Record - MDS
label | DNZ Engineer - R
label | Designer Rep - R
checkpoint | 2.5 - RCC65
label | Standard, Drawing or Specification Reference - Material Data Sheet
label | Construction Activity Description, Test Type and Acceptance Criteria - Recycled crushed concrete 65.
label | Test Frequency - Once
label | QA Record - Test Reports
textbox | InEight Approval
label | DNZ Engineer - R
label | Designer Rep - R
checkpoint | 2.6 - Geotextile (Bidim)
label | Standard, Drawing or Specification Reference - MDS
label | Construction Activity Description, Test Type and Acceptance Criteria - Geotextile A29 or similar approved material.
label | Test Frequency - Once
label | QA Record - MDS
label | DNZ Engineer - R
label | Designer Rep - R
section | 3 - CONSTRUCTION ACTIVITIES
checkpoint | 3.1 - Survey Setout
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3100, 3235599-SP03-ST-3253
label | Construction Activity Description, Test Type and Acceptance Criteria - Survey set out Ramp position based on model. Set out to include; Centre of Ramp, height and offsets. Tolerances for insitu concrete pour taken from NZS 3109 table 5.2
label | Test Frequency - Once
label | QA Record - As-Built
label | DNZ Engineer - W
checkpoint | 3.2 - Excavation
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250: Note 3.5
label | Construction Activity Description, Test Type and Acceptance Criteria - Excavation to be 500mm below existing platform level.
label | ○ Insitu subgrade material at the base of undercut shall be inspected by the Engineer to confirm design assumptions prior to backfilling.
label | Test Frequency - Once
label | QA Record - Photos
label | DNZ Engineer - I
checkpoint | 3.3 - Subgrade Testing
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3253, 3235599-SP03-ST-3250
label | Construction Activity Description, Test Type and Acceptance Criteria - Minimum subgrade shear strength of 40kPa.
label | Test Frequency - Once
label | QA Record - Shear Vane Test Results, Photos
label | DNZ Engineer - H
label | Designer Rep - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Subgrade Undercut (If required)
label | Standard, Drawing or Specification Reference - 746-24-847-AC Tech Spec Section C0302.4.2, 3235599-SP03-ST-3250: Note 3.2
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to subgrade undercutting, the Engineer shall confirm the extent of subgrade undercut and fill requirements.
label | ○ Undercut area to be wrapped in A29, backfilled and compacted in layers of 200mm RCC65.
label | Test Frequency - Once
label | QA Record - As-Built, Photo
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Backfill & Compaction
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250, 746-24-847-AC
label | Construction Activity Description, Test Type and Acceptance Criteria - Backfill lift to be backfilled at maximum 200mm lifts.
label | ○ Each lift to be tested to a minimum of MDD of 95%
label | Test Frequency - Once
label | QA Record - NDM Test Results, Photos, As-Built
label | DNZ Engineer - H
label | Designer Rep - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Formwork Installation
label | Standard, Drawing or Specification Reference - MDS
label | Construction Activity Description, Test Type and Acceptance Criteria - As per Temporary works drawings for Access Ramp.
label | Test Frequency - Once
label | QA Record - Prepour Checksheet, Photos
label | DNZ Engineer - H
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Reinforcing Installation
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3253
label | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per IFC detail drawing & shop drawing details
label | Test Frequency - Once
label | QA Record - Pre-Pour Checksheet, Photos
label | DNZ Engineer - H
label | Designer Rep - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Concrete Pre-Pour Inspection
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3253: Note 2.2
label | Construction Activity Description, Test Type and Acceptance Criteria - Reinforcing cage as per IFC and shop drawings.
label | ○ Correct number of bars and grade.
label | ○ Correct steel lapping.
label | ○ Minimum cover to be 40mm or 75mm if casted directly on ground.
label | Test Frequency - Once
label | QA Record - Survey Check, Structural Engineer Inspection, MSQA SVR, Pre-Pour Checklist, Photos
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Concrete Pour
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3253: Note 2.1, NZS3104:2021
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete: 50MPa as approved by designer.
label | ○ Cylinder test taken at supply Yard only for 7 and 28 days.
label | Test Frequency - Each Pour
label | QA Record - Delivery Dockets, Compressive Test Results, Photos
label | DNZ Engineer - H
label | Designer Rep - W
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10 - Slab joints
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3253, Detail C
label | Construction Activity Description, Test Type and Acceptance Criteria - All joints between concrete ramp sections to have PEF rod and SikaFlex 11C grey or equivalent on outer face.
label | Test Frequency - Each Ramp section.
label | QA Record - MDS & Photos
label | DNZ Engineer - I
label | Designer Rep - W
checkpoint | 3.11 - Ramp Surface Finish
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3253: Note 2.4, NZBC D1.
label | Construction Activity Description, Test Type and Acceptance Criteria - All surfaces subjected to foot traffic to have F5 finish (Exposed Aggregate finish).
label | Test Frequency - Once
label | QA Record - Prepour Checksheet, Photos
label | DNZ Engineer - I
label | Designer Rep - I
section | 4 - FINAL RECORDS
checkpoint | 4.1 - As-Built
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per design drawings. All compliance recorded CAD files
label | Test Frequency - Once
label | QA Record - As-Built
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Redline Mark-Up
label | Standard, Drawing or Specification Reference - DN1199-PLA-0006
label | Construction Activity Description, Test Type and Acceptance Criteria - IFC Drawings mark-Up on PDF
label | Test Frequency - Once
label | QA Record - IFC Drawings Mark-Up on PDF
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Non-conformances
label | Standard, Drawing or Specification Reference - DN1199-PLA-0006
label | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
textbox | NCR Reference
label | Test Frequency - Each NCR
label | QA Record - NCR forms on InEight, DN1190-PLA-0006
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
section | ITP APPROVAL PROCESS
checkpoint-no-status | ITP APPROVAL PROCESS
label | Prepared By: Site Engineer - Moses Kaufanga
label | Reviewed By: Project Manager - Dan Trotman
label | Reviewed by: Quality Mge./Eng. - Nas Matar
label | Reviewed By: Design Engineer - Daniel Cvitanich
label | Reviewed By: AT Project Manager - Werner Nel
label | Reviewed By: AT Engineer to Contract - Mike Robertson
date | Date:
section | FINAL ITP CLOSE-OUT
checkpoint | FINAL ITP CLOSE-OUT
textbox | Downer Project/Site Engineer:
textbox | QA Mgr./Engineer:
textbox | Designers Rep(Assistant):
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature