## Sheet1
1.1.1 | Earthworks Methodology | The Contractor shall submit the construction and QA methodology, for each element of Earthworks, incl construction, Site Access, dewatering, wet weather, testing, inspection and hold points for review and approval prior to works. | Engineers Approval | Appendix V | Approved Methodology | Prior to Earthworks | HP | ENG | 1.1.1 - Earthworks Methodology | Detail - The Contractor shall submit the construction and QA methodology, for each element of Earthworks, incl construction, Site Access, dewatering, wet weather, testing, inspection and hold points for review and approval prior to works. | Acceptance / Conformance Criteria - Engineers Approval | Standard / Specification - Appendix V | Verifying Document - Approved Methodology | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks | Verification Activity: Activity - HP | Verification Activity: By - ENG | 1.1.1 - Earthworks Methodology
Detail - The Contractor shall submit the construction and QA methodology, for each element of Earthworks, incl construction, Site Access, dewatering, wet weather, testing, inspection and hold points for review and approval prior to works.
Acceptance / Conformance Criteria - Engineers Approval
Standard / Specification - Appendix V
Verifying Document - Approved Methodology
Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
Verification Activity: Activity - HP
Verification Activity: By - ENG