## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP - R - On Grade Slab Pre-Pour (per area) |  |  |  |  | Yes | ITP - R - On Grade Slab Pre-Pour (per area) | 0444bd19-0e74-4324-b0c0-b52838726d17
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Survey set out (height, location, setout) - confirmation attached.
checkpoint-status |  |  | checkpoint | Underground services installation completed
checkpoint-status |  |  | checkpoint | Backfilling completed
checkpoint-status |  |  | checkpoint | Waterproofing completed
checkpoint-status |  |  | checkpoint | DPM overlapping/taping with no tears or perforations. Council requirement
checkpoint-status |  |  | checkpoint | Reinforcing completed
checkpoint-status |  |  | checkpoint | Engineer sign off completed and approved for pour
button | 5744e146-2412-525f-8735-1618f82a6920 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved for pour
button | 493292ef-aa82-551b-8426-5e36c7c3d055 |  | button | Note remedial work needed | None, Minor, Major
text | 05d1249a-bd24-5e7c-be94-05c680c20680 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checklist-sectioned |  |  | checklist | ITP - R - Service Trenches (Common and Pulling Pits) |  |  |  |  | Yes | ITP - R - Service Trenches (Common and Pulling Pits) | 2d5c3b42-565a-4515-b4bb-a511062eec1c
checkpoint-group |  |  | section | Common Service Trenches
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Power Ducts and Comms Ducts
checkpoint-status |  |  | checkpoint | Mag slab installed
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 93610e50-bab5-5b2e-806f-c5278844a7fa |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 0dc05c28-6bd4-5ce7-8f9c-e9b9cbd85156 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 4e2f39f4-a5db-5264-a669-34763a80e18b |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Pulling Pits
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Power Ducts and Comms Ducts
checkpoint-status |  |  | checkpoint | Draw cords
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 9d3aaf32-be2d-5e2e-918c-f71e67ff7974 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | b6c9ff15-6c6d-50f3-a77d-cf8db6786be9 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 3a715be8-6730-592a-b9f0-3ac11b5b326c |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-flat |  |  | checklist | ITP - R - Tanking/Waterproofing |  |  |  |  | Yes | ITP - R - Tanking/Waterproofing | 44d1b75b-7daf-44f6-82d8-5c75b0a21499
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Verify application of waterproofing, joint laps, thickness and number of layers as is specified.
checkpoint-status |  |  | checkpoint | Monitor installation and adequacy of protective linings during backfilling operations
checkpoint-status |  |  | checkpoint | Subcontractor to provide photo evidence of applied membranes
checkpoint-status |  |  | checkpoint | Sign off completed areas as per the agreed method PRIOR TO follow-on trades commencing their work.
checkpoint-status |  |  | checkpoint | Flood test conducted
checkpoint-status |  |  | checkpoint | PS3 received from subcontractor confirming application of membrane is in accordance with manufacturers recommendations
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | cd98d4df-fd66-5da7-a898-2ca9f1a34ef0 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | a869495d-7f94-5892-b5f0-7b1ca0f514cd |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 23b00c48-e5ff-5b60-8280-d6dfe82920c4 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-sectioned |  |  | checklist | ITP - R - Apartment Structural Steel (per area/level) |  |  |  |  | Yes | ITP - R - Apartment Structural Steel (per area/level) | 545c64cb-7553-4443-bbac-05a22a6be6e3
checkpoint-group |  |  | section | SFC and Non SFC Accredited Contractors
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Accreditation confirmed as below.
button | 3346e514-9d49-5dd7-8f51-4651205cd305 |  | button | Confirm Steel Contractor's SFC Accreditation | SFC Accredited, Non-SFC Accredited
checkpoint-status |  |  | checkpoint | Subcontractor SFC certification (n/a response if non-SFC)
checkpoint-status |  |  | checkpoint | Steel source list and declaration of conformity
checkpoint-status |  |  | checkpoint | Detail of proposed markings if members and/or connections are to exposed to view. (only applicable for Architecturally Exposed Structural Steel, AESS)
checkpoint-status |  |  | checkpoint | Structural Steel installed, test results uploaded and attached. Meets specification
button | cbf52c58-b256-5b3b-bb80-a3cee7eb4cc3 |  | button | Chemical anchor tests conducted and documented | Yes, Reworked, N/A
button | c0382b40-29ba-50eb-93ec-1f7a14d91561 |  | button | Mechanical anchor tests conducted and documented | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Bolting requirements confirmed against design requirements.
checkpoint-status |  |  | checkpoint | Welding conforms to design requirements.
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | 543c61be-8ed3-5a2a-aad5-33c616f58202 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 25880649-fa87-5737-a2d0-13b755e45c8d |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Mandatory Completion for Non SFC Accredited Contractors ONLY
checkpoint-status |  |  | checkpoint | Non SFC only: Independent preparation, assembly and fabrication inspection report received and issued to subsubcontractor
checkpoint-status |  |  | checkpoint | Non SFC only: Independent welding inspection report received and issued to subcontractor
checkpoint-status |  |  | checkpoint | Non SFC only: Independent surface treatment inspection report received and issued to subcontractor
checkpoint-status |  |  | checkpoint | Non SFC only: Independent paint coatings inspection report received and issued to subcontractor
checkpoint-status |  |  | checkpoint | Non SFC only: Independent galvanised coating inspection report received and issued to subcontractor
checkpoint-status |  |  | checkpoint | Non SFC only: Final weld inspector compliance certificate received
checkpoint-status |  |  | checkpoint | Non SFC only: Final surface preparation inspector compliance certificate received
checkpoint-status |  |  | checkpoint | Non SFC only: Final paint coating inspector compliance certificate received
checkpoint-status |  |  | checkpoint | Non SFC only: Final galvanising inspector compliance certificate received
holdpoint |  |  | signoff | Raise remedial as required.
checklist-sectioned |  |  | checklist | I - C - Site Visit Report |  |  |  |  | Yes | I - C - Site Visit Report | 5779b536-3753-445e-8b36-56ba53a149d7
checkpoint-group |  |  | section | Site Visit Details
checkpoint-no-status |  |  | checkpoint | Site Details
text | 65f69954-f3b8-5edb-b70f-4c9c3bc6f4bf |  | textbox | Area of site visited:
text | 28fb2723-f954-5448-b5f3-15a2ed6fbf76 |  | textbox | Work element monitored / purpose of visit:
text | 79957183-cf05-58ad-9f30-4bed4a660696 |  | textbox | Date of site visit:
text | 794afb11-5e80-5ffe-9e06-3876e75a9113 |  | textbox | Time on site (include start and end times):
text | cc14af9d-af85-5325-8d3c-e9bcfca84cc5 |  | textbox | Weather conditions:
text | c2ac2bea-f740-58ab-bfbe-b6ecaec5d4b8 |  | textbox | Report prepared by:
text | 86db574d-ccd1-576e-9835-1d648074c737 |  | textbox | Additional personnel accompanying:
checkpoint-status |  |  | checkpoint | Consented drawings have been followed
text | 33b8ea75-bc69-541d-90c7-18202965cbf0 |  | textbox | Building Consent Number:
text | 3ffa0431-a775-5a1c-95df-e12c8869530f |  | textbox | Drawing & Revision Number(s):
checkpoint-status |  |  | checkpoint | Health and Safety acceptable
checkpoint-group |  |  | section | Site Report Summary/Closeout
checkpoint-status |  |  | checkpoint | Works accepted and may proceed
label | b6d62539-2b6a-5000-984d-a253406a195f |  | note | Select Pass if works accepted or Fail if reinspection required to defective elements
boolean | 285401b8-ea10-52ea-95e4-ca08e0d36c0f |  | tickbox | Report attached or remedials summarised below
text | 56d4d7ed-2866-502a-98af-3a8c37ec5c38 |  | textbox | Remedial(s)
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | ITP - R - Foundation Piling |  |  |  |  | Yes | ITP - R - Foundation Piling | 5bdc1c5d-0a79-4ea7-989b-551b6005d9a7
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Subcontractor piling card reviewed and meets requirements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Piles set out, surveyed, and marked.
checkpoint-status |  |  | checkpoint | Site condition acceptable for piling rig
checkpoint-status |  |  | checkpoint | Piles meet set out, heights, and correct within tolerances.
checkpoint-status |  |  | checkpoint | All piling cards received, filed, and meet requirements.
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 3bb95f66-bb97-5417-a569-80601acc6526 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 28f53f3d-b5a0-5c50-ad49-2bee8fffb9fc |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | bb370923-70c7-529c-a8b0-d4ee2b306cb0 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-sectioned |  |  | checklist | ITP - R - Services |  |  |  |  | Yes | ITP - R - Services | 693dd216-7e1c-402d-8e6a-1aaebfa0e401
checkpoint-group |  |  | section | Residential Apartment/Townhouse Unit
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Fire - Alarm, Hydrant & Sprinkler. PS3, As Builts, and O&M Manual received.
checkpoint-status |  |  | checkpoint | Nurse Call, Security, Data and Communications. PS3, As Builts, and O&M Manual received.
checkpoint-status |  |  | checkpoint | Hydraulic. PS3, As Builts, and O&M Manual received.
checkpoint-status |  |  | checkpoint | Electrical. PS3, As Builts, and O&M Manual received.
checkpoint-status |  |  | checkpoint | Mechanical. PS3, As Builts, and O&M Manual received.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 6fd5aa5c-1316-528a-b480-2b9fd761c4aa |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Common, Recreational & Service Areas
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydrant, Fire Alarms, Sprinklers. PS3, As Builts, O&M Manual, and IQP Cert received
checkpoint-status |  |  | checkpoint | Specified Systems - Alarms, Manual/Automatic. PS3, As Builts, and O&M Manual received.
checkpoint-status |  |  | checkpoint | Specified Systems - Gas Detection. PS3, As Builts, and O&M Manual received.
checkpoint-status |  |  | checkpoint | Specified Systems - Nurse Call. PS3, As Builts, and O&M Manual received.
checkpoint-status |  |  | checkpoint | Specified Systems - Access Controlled Doors. PS3, As Builts, and O&M Manual received.
checkpoint-status |  |  | checkpoint | Specified Systems - Interfaced Fire/Smoke Doors/Windows/Security. PS3, As Builts, and O&M Manual received.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydraulic. PS3, As Builts, and O&M Manual received.
checkpoint-status |  |  | checkpoint | Specified Systems - Lifts. PS3, As Builts, and O&M Manual received.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, fresh air and duct extrac system. PS3, As Builts, and O&M Manual received.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, kitchen extract + air conditioning system. PS3, As Builts, and O&M Manual received.
checkpoint-status |  |  | checkpoint | Specified Systems - Smoke Curtains. PS3, As Builts, and O&M Manual received.
checkpoint-status |  |  | checkpoint | Specified Systems - Essential Power Supply. PS3, As Builts, and O&M Manual received.
checkpoint-status |  |  | checkpoint | Specified Systems - Emergency Signage + Exits & Emergency Lighting. PS3, As Builts, and O&M Manual received.
checkpoint-status |  |  | checkpoint | Swimming Pool - Plant. PS3, As Builts, and O&M Manual received.
checkpoint-status |  |  | checkpoint | Fire Engineer inspection completed and approved
button | 180e0b34-ac35-5444-ac3a-063fa74d8070 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Electrical Engineer inspection completed and approved
button | 498980b8-d18e-5de6-b9f3-28edd6335310 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Mechanical / Hydraulic Engineer inspection completed and approved
button | efa5852e-a38e-5703-aaff-d1d4492acae7 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | dd103838-8140-5466-acfb-469a4008c15d |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-flat |  |  | checklist | ITP - R - Apartment Roofing (per area) |  |  |  |  | Yes | ITP - R - Apartment Roofing (per area) | 704da179-d617-468d-95ab-12eebc483c6f
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Verify materials supplied to site (material and fixings) are as specified or approved samples
checkpoint-status |  |  | checkpoint | Producer Statement Construction (PS3) received and attached for installation of roof abseil and/or fall arrest system
checkpoint-status |  |  | checkpoint | Construction complies with specifications
checkpoint-status |  |  | checkpoint | Obtain and upload all performance and authority certificates as required by specification or statutory regulations.
checkpoint-status |  |  | checkpoint | Council Pre-Roof Inspection completed and passed
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | a266ace1-2241-5fa6-96c0-df1b757d17fa |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 4ca069e1-25e9-52f7-8d90-e16040a2e7b8 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 75824e7b-c1d8-5ec4-bc39-dc1ad85c2a7b |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-sectioned |  |  | checklist | ITP - R - Apartment Pre Cast Floor Structure and Concrete Pour (per level/area) |  |  |  |  | Yes | ITP - R - Apartment Pre Cast Floor Structure and Concrete Pour (per level/area) | 98873e68-f446-4a5f-b531-0fee2330471a
checkpoint-group |  |  | section | Pre Commencement
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
button | c390adb5-89da-5dab-94e7-b248ee03c9f3 |  | button | Confirm construction method | Double T's, Rib & Infill, Other
text | 4e3fb26d-8c0b-50fc-9c62-489176f57323 |  | textbox | Other details:
checkpoint-status |  |  | checkpoint | Propping/Falseworks Confirmed and Accepted
button | a09a5a53-ae3a-51a8-a000-e313eb84ec43 |  | button | Propping layout confirmed as "issued for construction" | Yes, N/A
button | 6bc5248c-71bd-5af1-92b9-4a7c62ae48f6 |  | button | Floor area cleared for propping to be erected | Yes, N/A
checkpoint-status |  |  | checkpoint | Hogging of panels within design tolerances. Installed in accordance with suppliers recommendations.
checkpoint-status |  |  | checkpoint | Adequate identification, cast date and verification of inspection marked on precast element.
checkpoint-group |  |  | section | Floor Construction
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Pre-cast elements inspected upon delivery and accepted for lifting.
checkpoint-status |  |  | checkpoint | Floor structure elements landed as per layout
checkpoint-status |  |  | checkpoint | Ryman SOP followed where applicable. (Reference the document name / version)
checkpoint-status |  |  | checkpoint | Reinforcing laid as per specification
checkpoint-status |  |  | checkpoint | Service penetrations present as per specification
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved for pour
button | f53230b7-e372-54f4-b674-af601ff6d036 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | adee665b-d2b2-51b9-a9c4-09a3ac829917 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Pre Pour Planning
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | f4e75066-6ab5-56b6-8ca6-c0b56058bf3c |  | textbox | Date of pour
text | 718b1c2f-1223-5077-94e2-40f9a983a729 |  | textbox | Specified concrete strength:
text | 8bc3104c-6929-5dfd-8317-41997bf866b3 |  | textbox | Concrete strength ordered:
text | b75d655a-ab1a-537d-8add-abfe415ff88a |  | textbox | Concrete quantity ordered:
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 05167440-ffba-5bf9-993b-be9c247123b2 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Request to pour received and approved
button | edddb85d-09ff-578a-85b3-2090dd5005af |  | button | Reinforcing meets specification | Yes, Reworked, N/A
button | d16a1371-ad5d-540e-9798-bcd63396f568 |  | button | Service penetrations present and correct | Yes, Reworked, N/A
button | be63a07a-b74a-547f-a685-6e2646284b6c |  | button | Waterproofing elements present and correct | Yes, Reworked, N/A
button | e23a674b-55ad-5866-ac5a-f0dd3cc446f3 |  | button | Couplers present and correct | Yes, Reworked, N/A
button | 3abf4b79-32a8-5908-b11d-82dbdd3fce8b |  | button | Control joints/ stop ends installed accurately and correctly braced | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | 864c88b2-d430-51d5-8350-9262f2fbfed1 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | f49baf82-31d5-5d8e-9726-04200ecd1fb4 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-flat |  |  | checklist | ITP - R - Unit Benchmarking (Use at stage level) |  |  |  |  | Yes | ITP - R - Unit Benchmarking (Use at stage level) | a297da8b-e781-41d4-adee-26c91035ec87
checkpoint-status |  |  | checkpoint | Benchmark standard agreed as per Quality Management Plan
button | 7dcff55c-54e5-556c-a319-ee9e504daaaf |  | button | Project Manager or delegate present | Yes, No, N/A
button | a5cf7ab6-239d-58f9-a212-2e326c067a7b |  | button | Sales representative or delegate present | Yes, No, N/A
button | b78cfb06-b4d8-5373-8ac2-5bf5a72d3a4d |  | button | QA Advisor or delegate present | Yes, No, N/A
button | a3b541fd-612b-571e-89bd-50c2fee293ca |  | button | Design representative or delegate present | Yes, No, N/A
text | 729ef6b5-c1bd-5cfa-a7e7-0dcfc2f060a5 |  | textbox | Benchmark details (e.g. apartment number or explanation)
text | 5a9de39d-f159-51fd-9320-0edd7a4c2b36 |  | textbox | Record benchmark date
checklist-sectioned |  |  | checklist | ITP - R - Apartment Pre Cast Element Installation (per area/level) |  |  |  |  | Yes | ITP - R - Apartment Pre Cast Element Installation (per area/level) | acf3a909-90ee-49b5-a969-27a1c9342f0a
checkpoint-group |  |  | section | Pre-Cast Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Pre-cast elements inspected upon delivery and accepted for lifting.
checkpoint-status |  |  | checkpoint | Installed verticaly / aligment tolerances complies with specification (components below)
checkpoint-status |  |  | checkpoint | Stairs
checkpoint-status |  |  | checkpoint | Spandrels
checkpoint-status |  |  | checkpoint | Pre-cast panels
checkpoint-status |  |  | checkpoint | Columns
checkpoint-status |  |  | checkpoint | Stitch joints
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 06a24cdb-9f09-50e8-957c-19c2f5426ea8 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 033eb121-48d8-58b4-917e-ac730864a572 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 01743983-3d14-5f17-ade8-8838210e24dc |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Timber Framing Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Timber Framing installed
button | 438a8b6c-1369-59be-a3f0-e7762d753a7e |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | f624bc12-da11-5edf-8f61-5816fbce9ba3 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | c217f577-39b6-50e2-b8d8-170bb6a2253f |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | fee02e06-7969-5f6b-b0f8-1fbc42bc7702 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Insuti Pour Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Stitch joints - meets specification
checkpoint-status |  |  | checkpoint | Beams - meets specification
checkpoint-status |  |  | checkpoint | Panels - meets specification
checkpoint-status |  |  | checkpoint | Columns - meets specification
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 30322963-22ed-51b0-837b-80e2859f4e2e |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 9125224a-389d-50f1-8e88-1e72b465cecd |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 23777645-7f24-5c3b-b058-eab20d019a45 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Testing
checkpoint-status |  |  | checkpoint | Chemical anchor testing completed. Upload report
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
text | a3f05921-2100-57e3-8cb7-fea9329e1982 |  | textbox | Record sample size
holdpoint |  |  | signoff | Raise remedial as required.
checklist-sectioned |  |  | checklist | ITP - R - Apartment Build (per area/level) |  |  |  |  | Yes | ITP - R - Apartment Build (per area/level) | b6f4ed07-4d3a-42dd-aed1-d4d39980355a
checkpoint-group |  |  | section | Façade
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Envelope/Watertightness Completed (requirements below)
button | 2e00bf3e-9e79-54dc-bf0f-c4ed59b8a9a5 |  | button | Ecoply Board installed | Yes, Reworked, N/A
button | cd096575-f498-5702-b719-52c7555748d6 |  | button | Lintels installed | Yes, Reworked, N/A
button | dc02fea6-15f5-5dfe-9e90-504459a16ca0 |  | button | Tapes and VaproShield installed. | Yes, Reworked, N/A
button | 9e36a586-63b7-5d41-ad54-582d678d94cd |  | button | Windows and Sliders installed | Yes, Reworked, N/A
button | cd4697f4-3749-5eb3-bf11-02c47ed04b6f |  | button | Flashing installed | Yes, Reworked, N/A
button | b1ac6243-3ef7-57e9-a344-1a2b077615dd |  | button | Envelope Penetrations completed | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Council pre-wrap inspection completed and passed
button | 21c8ccf6-40ac-506f-be87-b9706b0699a7 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council brickwork 'half-high' inspection completed and acceptable
button | a94cc7d8-96d3-5b0d-b0f3-a4c1671acaa9 |  | button | Note remedial work needed | None, Minor, Major
text | 1168a2d5-41d4-587a-a6cb-1459296f7252 |  | textbox | Describe cladding type:
button | 00e19b42-661e-5295-969b-37454114ad6b |  | button | Brick Works completed | Yes, Reworked, N/A
button | 8b50e452-301f-5307-92db-103cdb17fc06 |  | button | STO Poly Plaster completed | Yes, Reworked, N/A
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Installed horizontal fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed vertical fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Eyebrow and soffit fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Boss Bulkhead Batt fire barriers as per sepecifications
checkpoint-status |  |  | checkpoint | Installed Gutter fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Concrete Pannels (under roof) fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Hatches fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Consultant Inspections Completed and Passed
button | c503cd9b-bdf8-5b4a-a0a1-fb7f7dcd8485 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 8b48d9c1-f389-52f7-a816-37b7ba5ada89 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Pre-Line
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Pre-line completed
button | 5e895fc4-ebfa-558c-a9aa-ef0d5fd4ba24 |  | button | Framing system installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Nogs Installed as below and comply
button | 534967c5-3b81-5f7c-a437-a2279e611df8 |  | button | Electrical First Fix completed and acceptable | Yes, Reworked, N/A
button | 854b9f9c-58f4-5290-a483-250f5b651ca0 |  | button | Plumbing First Fix completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Insulation installation completed and acceptable
checkpoint-status |  |  | checkpoint | Security, Comms and Data First Fix completed and acceptable
button | 009e3528-c44f-50bb-98a1-b0f60223445c |  | button | HVAC First Fix completed and acceptable | Yes, Reworked, N/A
button | 5536a335-0515-5aaf-949a-a842e72dcad9 |  | button | Fire Security First Fix completed and acceptable | Yes, Reworked, N/A
button | 561cce7a-be35-5b71-b915-af56cd9888bc |  | button | Under floor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable | Yes, Reworked, N/A
button | 803d79e3-434f-5adc-8e98-05fe1d326658 |  | button | Kitchen extract First Fix completed and acceptable | Yes, Reworked, N/A
button | c19f6d9c-62a7-58a1-be71-0d222f9c2ab8 |  | button | Passive fire installation completed and acceptable | Yes, Reworked, N/A
button | 1a41dc37-2099-5b55-987d-d7b820c602b7 |  | button | Suspended ceiling grids installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Pre-line plumbing external inspections completed and uploaded. Any remedial work signed off.
button | 0760d416-0a2e-5fa0-8b45-2110281f8d6c |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Pre-line building external inspections completed and uploaded. Any remedial work signed off.
button | c2a8ce51-2f6c-54d1-9596-0c99f53ff357 |  | button | Note remedial work needed | None, Minor, Major
text | 795a7829-2a20-5379-80c0-193a56cc5b77 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed
checkpoint-status |  |  | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Consider bracing, adhesive/sealant & lining layer(s) requirements (including fire stopping between layers)
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Services/penetrations, correctly formed & located (consider cut-out tolerances where applicable)
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Correct fixing pattern/sealant (including fire)/adhesive/layers installed to align with consented design and specifications
checkpoint-status |  |  | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | 5c809249-d8e6-5fbe-8a72-5609bcc72c3f |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Balustrade Testing
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Balustrade Anchor Bolt Pull Testing
label | a4998ce2-b6b2-596c-9df2-8afad11a0d7d |  | note | Test results to be uploaded
checkpoint-status |  |  | checkpoint | Balustrade Lateral Load Testing
label | 8bc53c51-1b9a-5b0d-bbbd-221d4618f49a |  | note | Test results to be uploaded
checkpoint-status |  |  | checkpoint | Consultant Inspections Completed and Passed
button | c786f264-4b46-5419-8663-e4ece162af5e |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 80c07156-fba1-52e2-a304-b5ea821ca7c7 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-flat |  |  | checklist | ITP - R - Fitout (per unit) |  |  |  |  | Yes | ITP - R - Fitout (per unit) | bc1193c8-c5d2-4733-ac7f-324863b03203
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Finishing completed, meets benchmark standard. Refer separate checklist. Full response to the items below needed.
button | a40f588e-7c14-511c-b2ce-40e7c7cce575 |  | button | Hardware/Fittings | Yes, Reworked, N/A
button | 38f4c701-6b1a-50a8-bfe3-8285b324bca8 |  | button | Plumbing completed and acceptable | Yes, Reworked, N/A
button | 9dbd4ca4-4471-58b3-8eab-99bb094b3420 |  | button | Electrical completed and acceptable | Yes, Reworked, N/A
button | 1e99b54e-80b0-51d5-9dd4-9ecc98bf51c1 |  | button | Joinery/Doors completed and acceptable | Yes, Reworked, N/A
button | 4aa23148-5785-52df-8175-71113c008c88 |  | button | Decorating completed and acceptable | Yes, Reworked, N/A
button | a21546ac-9859-5289-baa6-4c0f1a0648b7 |  | button | Flooring completed and acceptable | Yes, Reworked, N/A
button | 1f8ad32d-0898-5965-95be-6ddd4069e8c3 |  | button | Other works completed (inc. client extras) and acceptable, state below. | Yes, Reworked, N/A
text | b26a1316-e447-54d5-b8cf-4c5e11efe3e6 |  | textbox | Details:
checkpoint-status |  |  | checkpoint | Upload Related Ryman Fitout quality inspection record (QT-012)
holdpoint |  |  | signoff | Raise remedial as required.
checklist-flat |  |  | checklist | ITP - R - Project Manager Handover to Operations (per unit) |  |  |  |  | Yes | ITP - R - Project Manager Handover to Operations (per unit) | c14c0cfd-32b1-48f8-bef9-85f2f434ef1c
checkpoint-status |  |  | checkpoint | No outstanding defects/snag list items
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Chattels confirmed as operational
checkpoint-status |  |  | checkpoint | Chattel manuals provided.
checkpoint-status |  |  | checkpoint | Unit meets benchmark standards and expectations
checkpoint-status |  |  | checkpoint | Resident "Welcome Letter" completed by PM and left in property.
checkpoint-status |  |  | checkpoint | Formal handover to Sales/Operations conducted by PM.
checklist-sectioned |  |  | checklist | ITP - R - Pipe Laying (Mains Water, Storm and Waste) |  |  |  |  | Yes | ITP - R - Pipe Laying (Mains Water, Storm and Waste) | c18ca821-72e6-4aaf-bf85-2ca25871a2fa
checkpoint-group |  |  | section | Storm Water
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Set-out completed
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Ground conditions
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Pipework
checkpoint-status |  |  | checkpoint | Levels and Gradients
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | dbc83026-beee-5cad-8629-fd456a27298a |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | ef587f1d-2c5e-5876-b5a1-b64c48d5755f |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | b8c336f9-12cf-570e-bb32-352d100d03af |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Storm Water
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Set-out completed
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Ground conditions
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Pipework
checkpoint-status |  |  | checkpoint | Levels and Gradients
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 775c3e42-a10a-58f9-b705-67ece6a87b01 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 240f00e6-66db-532e-b4a3-c2fd5411e444 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 8b65445c-6ad5-5901-9027-62cc34d34680 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Waste Water
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Set-out completed
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Ground conditions
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Pipework
checkpoint-status |  |  | checkpoint | Levels and Gradients
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Air/water test completed
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 3b50c5b7-c637-5ada-b997-f7c8eb82b054 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | ff3e6422-c60b-5ef1-bdd9-ba04401a7685 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 028adb8b-0f8e-59e2-9df1-caa8659a1cee |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-flat |  |  | checklist | ITP - R - Contractor Allocation (Use at stage level for each subcontractor on the stage) |  |  |  |  | Yes | ITP - R - Contractor Allocation (Use at stage level for each subcontractor on the stage) | c9977c85-e60f-4973-90e7-9acf5057e187
checkpoint-status |  |  | checkpoint | Contractor Allocated
text | 9cf79b80-2033-536e-9388-fea1d7d80f31 |  | textbox | Record Subcontractor Company Name
text | f7cc3f41-a2ed-52f2-8fa3-e9d03845de34 |  | textbox | Record scope of works
checkpoint-status |  |  | checkpoint | Specifications confirmed with subcontractor management
checkpoint-status |  |  | checkpoint | Programme milestones confirmed with subcontractor management
checkpoint-status |  |  | checkpoint | All subcontractor ITPs (inspection test plans) attached and agreed.
checkpoint-status |  |  | checkpoint | Quality expectations and requirements discussed and confirmed as understood.
holdpoint |  |  | signoff | Escalate concerns to QA Advisor
checklist-sectioned |  |  | checklist | ITP - R - Excavation (Bulk and Detailed) |  |  |  |  | Yes | ITP - R - Excavation (Bulk and Detailed) | d665c164-2aa0-4ac7-9611-3e26bda44e97
checkpoint-group |  |  | section | Bulk Excavation
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Excavation depth determined using appropriate RL's (Check relevant drawings and revisions)
checkpoint-status |  |  | checkpoint | Confirm location and isolation of relevant services
checkpoint-status |  |  | checkpoint | Batters formed correctly
checkpoint-status |  |  | checkpoint | Trenches/ pits / hazardous areas appropriately isolated
checkpoint-status |  |  | checkpoint | Soft spots identified and appropriate remedial completed
checkpoint-status |  |  | checkpoint | Hardfill/ blinding installed correctly to required specification
checkpoint-status |  |  | checkpoint | Static Rolled (2 photos required)
checkpoint-status |  |  | checkpoint | Scala Test and results upload (including supporting documents)
checkpoint-status |  |  | checkpoint | Excavation completed - Correct locations and RL's achieved
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 70f69d1d-9ae2-5bb4-a2ec-bfd63bc829b0 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 653319eb-b1bd-5686-b23f-5f5533664789 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 4b376fd3-ff2d-5a9d-bfdc-29c02aeda003 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Detailed Excavation
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Grids/profiles/set out completed, clearly marked and accurate
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Services (overhead / below ground) considered and isolated where required before excavation commences
checkpoint-status |  |  | checkpoint | Placement of Geotextile (2 photos required)
checkpoint-status |  |  | checkpoint | Placement of hardfill
checkpoint-status |  |  | checkpoint | Placement of Geo-grid (2 photos)
checkpoint-status |  |  | checkpoint | NDM test and report (supporting documents incl. photos)
checkpoint-status |  |  | checkpoint | Completed level of hardfill (completion NDM test with report and supporting documents (incl. photos) and uploaded into QA system)
checkpoint-status |  |  | checkpoint | Sand blinding and check final RL. (completion required to handover to the next stage-townhouses only)
checkpoint-status |  |  | checkpoint | Excavation for services is completed and accurate
checkpoint-status |  |  | checkpoint | Excess material cleaned up and removed as required
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 9d658784-a89a-56cf-bc9c-8cd0cfe3fd52 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | db2fe806-e034-5b8a-a213-1780b192a1ec |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 5702aacb-95c7-506b-9ef2-94789ab3fef5 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-sectioned |  |  | checklist | ITP - R - Concrete - Planning and Pour (per area) |  |  |  |  | Yes | ITP - R - Concrete - Planning and Pour (per area) | f1ffd667-28b2-4c7a-822e-babb5364c5ba
checkpoint-group |  |  | section | Pre Pour Planning
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | fbac267b-d1e2-5199-9765-416977c7e778 |  | textbox | Date of pour
text | cdda315e-823a-561f-8a1d-4d4809d0e20a |  | textbox | Specified concrete strength:
text | 1e2f349f-5120-54c2-8a7d-bafd8e184bd2 |  | textbox | Concrete strength ordered:
text | 6f2514cf-5b9e-501b-81e6-fbddcdb6e0b1 |  | textbox | Concrete quantity ordered:
text | 151dfde5-61f9-5fc7-9503-94769c3d826c |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Request to pour received and approved
button | fae3fdac-d041-5843-80c4-9150d0e68618 |  | button | Reinforcing meets specification | Yes, Reworked, N/A
button | 468b285a-fef6-58bb-bb90-d9664a837ead |  | button | Service penetrations present and correct | Yes, Reworked, N/A
button | b73c34a2-dac0-5483-a073-e7f718ff3a99 |  | button | Waterproofing elements present and correct | Yes, Reworked, N/A
button | e078721e-47a8-539f-aea6-87cb956ed532 |  | button | Couples present and correct | Yes, Reworked, N/A
button | 9f76ed3d-aff3-5b8a-8511-337aff6db9c0 |  | button | Control joints/ stop ends installed accurately and correctly braced | Yes, Reworked, N/A
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | 1f7afe36-f57d-55fe-9abe-34efff6fd4a3 |  | button | Note remedial work needed | None, Minor, Major
text | 8b648a38-8c34-5ee3-823c-5f8928296824 |  | textbox | Inspected by and date:
holdpoint |  |  | signoff | Raise remedial as required.