## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | d8be49e7-7ee5-4802-89a6-38cd716a7ae8 |  | checklist | Windows Installation Checklist |  |  |  |  | Yes | Windows Installation Checklist | 1ca346cc-61a6-41e5-ab62-ac31a70b5941
checkpoint-group | 2a34f421-b937-4487-9bc6-42e46128a9db |  | section | Pre-Install
checkpoint-status | f370a20c-cc67-4e1d-a1bb-c788ca7985a8 |  | checkpoint | Area clean/ clear & substrate acceptable
label | 4fe4b27a-b7fe-5a35-8825-7d8d61551645 |  | note | Window received in good condition
button | 76188eea-82f1-5ad9-af7d-dc610f6b7bf7 |  | button | Site measure completed - Opening size correct | Yes, No, N/A
button | 447a93d6-204c-5dff-91bd-99ca22f69df6 |  | button | Waterproofing in place where applicable (i.e rebate) | Yes, No, N/A
checkpoint-group | 755bc85a-e3e4-4685-80d5-a6df7a4cec38 |  | section | Installation & Handover
checkpoint-status | 71190784-82b2-4e8a-933a-d51432f5dedc |  | checkpoint | All windows installed in correct location according to drawing provide
checkpoint-status | 09a5c242-91bb-443f-9e94-f83a5dd2ce84 |  | checkpoint | Sub-head and sub-sill install correctly and fully seal on sub-sill photos as below
button | 67e9e590-073f-58d6-9415-580cb03a2d6e |  | button | Level plumb & correct height | Yes, No, N/A
button | 441ae5a6-8463-5f44-97fe-43abbadd93a4 |  | button | Fixings as 500mm spacing | Yes, No, N/A
checkpoint-status | 1d0da682-1c38-4575-85b5-b130ae35a1ec |  | checkpoint | Window - opening/closing freely & latching correctly
checkpoint-status | c03c4b92-c946-4bfe-b844-edfd44268228 |  | checkpoint | WINDOW JOCKEY SASH INSTALL AND CHECK opening/closing freely & latching correctly
checkpoint-status | bd0f0975-d8db-431e-a146-84c7da9d213f |  | checkpoint | All Windows and small infill Installed and hardware correctly & area left clean/tidy - Attach photos below
button | 12341f0a-cff9-5b10-90f4-047746cc2f04 |  | button | Glass protection applied | Yes, No, N/A
checkpoint-status | b543d7db-8ad2-49ed-9bcb-931909e8c99b |  | checkpoint | External Caulking (Photo Require)