## Sheet1
Inspection & Test Plan (ITP)
Process: Bottom Driven Piles ITP No.: SDC – ITP – J7*** Date: 23-04-2023 1
THIS INSPECTION & TEST PLAN COMPRISES THE FOLLOWING DOCUMENTS AND IS APPROVED FOR USE:
PART 1 Inspection and Test Plan
PART 2 Quality Control Checklist/s
PART 3 Lot Verification Checklist
Scope:
This ITP is to cover the installation of the 762mm Bottom driven piles associated with the abutment and pier foundations for the replacement of bridge 217 in Napier on the Palmerston North – Gisborne rail line. ITP Derived from Novare Projects Project No. 3364/62.
Reference Documentation:
Specification and Standards
AS/NZS 1554.1 Structural steel welding - Welding of steel structures AS/NZS 1554.3 Structural steel welding - Welding of reinforcing steel
AS 2159 Piling - Design and installation
NZS 3101 The design of concrete structures
NZS 3104 Specification for concrete production
NZS 3109 Concrete construction
NZS 3404.1: 1997 Steel structures Standard
AS/NZS 1554.1 Structural steel welding - Welding of steel structures SESOC Construction Specification Bored & Driven Piles rev. I June 2022
Page 1 of 12

## Sheet2
DRAWINGS
| DRAWING NUMBER | DRAWING TITLE
Subsequent additions to or revisions of these drawings
Page 2 of 12

## Sheet3
Name: | Signature | Date
Prepared By: Max White
Reviewed By:
Reviewed By:
Approved By:
Project may add additional Reviewer and Approver rows as necessary
Approved By:
Approved By: (See NOTE)
Revision:
Project Doc. No.: SDC-ITP-J7*** Revision: 01
Page 3 of 12

## Sheet4
Inspection and Test Plan
PART 1 OF INSPECTION & TEST PLAN
Contractor Name: Spiral Drillers Process: Bottom Driven Piles ITP No: SDC-ITP-J7***
No. |  |  |  | Responsibility | [5 empty] | Frequency
[7 empty] | Conformance Criteria summary |  | Method |  |  | Hold/Witness
[12 empty] | Requirements |  |  |  |  | Records or
|  |  | Inspection / Test Point |  |  | Spec Reference
[15 empty] | N P |  | Checklist
[14 empty] | UC |  |  | Reference
[12 empty] | C |  | C
1.0 - Preliminary Inspections and Tests
1.1 |  | Design and Drawings are of 100% Detail Design Status |  | Spiral Drillers Engineer | N.A |  | Latest Issue Design Drawings issued via email |  | Document review/ document control | Prior to Start of work | HP |  | IP |  |  | SD Quality Control Checklist
1.1. 1b |  | Submittal of construction methodology |  | Spiral Drillers | Project Memo Section 2.1.iii |  |  | Include: Equipment, Pile construction methodology, delivery and storage of | Document review | Prior to Start of work | HP |  | HP |  | HP | Approved ITP
material, safe work area, pile concrete & sand placement.
Approved Materials
Page 4 of 12

## Sheet5
No. | [5 empty] | Conformance Criteria summary |  |  | Frequency
|  |  | Responsibility |  |  |  |  | Method |  |  | Hold/Witness
[11 empty] | Requirements |  |  |  |  | Records or
|  | Inspection / Test Point |  |  | Spec Reference
[14 empty] | N P |  | Checklist
[13 empty] | UC |  |  | Reference
[11 empty] | C |  | C
2.1 | Reinforcing Cages |  | Spiral Drillers |  |  |  Mill Certifications |  | Detail Sheets approved by structural engineer prior to manufacture Mill certificates for reinforcing cages used. Engineer to inspect constructed cages. | Per pile type intended to be construct ed Prior to manufact ure Once arrived on site | HP |  | RR |  | RR | Delivery Dockets SD Pile cards Reinforcing Mill cert testing
[6 empty] |    | Send notice in advance request for inspections 7.8.3 Micro-Alloying MA 300E or Grade 500E steel Reinforcing as per approved detail sheets.
 Reinforcing to comply with AS/NZS 4671
[6 empty] |  | & NZS3109. Any cutting, bending or welding of reinforcing on site to be approved in writing by the design engineer.
2.2 | Steel Pile Casing |  | Spiral Drillers | SESOC Section 2.2.4 |  |   | Sizing to be 762mm x 16mm WT Pile casing to comply with the requirements in the project drawings. | Steel casing mill certs, heat no. and material testing. | Tests/ certs for steel casings rolled from different steel coils. | RR |  | RR |  | RR | Delivery Dockets, Heat Number and Mill certs.
 Deviation from straightness shall not be greater than 1/600 longitudinally.
Page 5 of 12

## Sheet6
No. | [7 empty] | Method | Frequency
|  |  | Responsibility |  |  | Conformance Criteria summary |  |  |  |  | Hold/Witness
[11 empty] | Requirements |  |  |  |  | Records or
|  | Inspection / Test Point |  |  | Spec Reference
[14 empty] | N P |  | Checklist
[13 empty] | UC |  |  | Reference
[11 empty] | C |  | C
2.3 | Concrete mix design |  | Spiral Drillers |  |  |  Submit proposed concrete mix design in advance of concrete been placed on site  Concrete batching plant will keep records to prove ongoing suitability of plant and mix design, production tests and delivery.  Concrete mix design to comply with NZS3104.  Maximum permittable aggregate size to be 19mm.  Mixing design intended strength to be XXMPa and meeting the requirements for exposure classification XX. |  | Concrete mix design Submitted to the engineer prior to concrete being placed. | Prior to concrete being placed | HP |  | HP |  | RR | Written confirmation for acceptance of mix deisng. SDC QA - Concrete pile schedule Certificates, testing records
2.4 | Welding on site |  | Spiral Drillers | AS/NZS 1554.1. NZS 4781. |  |  | Welders WPS form in AS/NZS 1554.1 | Welding WPS Certification of each welder | Prior to Start of work | HP |  | HP |  | RR | Welding records and certificates Current welding qualification
 Individual welders qualified to the WPS, AS/NZS 2980 Welder Certificate
2.5 | Piling Hammer & Equipment |  | Spiral Drillers |  |  |  Weigh bridge docket to verify the |  | Weigh bridge dockets Driveability analysis document | Prior to start of work | HP |  | HP |  | RR | Driveability analysis
[6 empty] |  | weight of the piling helmet. Driveability analysis to determine the drop height, Set and temporary compression requirements.
Page 6 of 12

## Sheet7
No. |  |  |  | Responsibility |  | Reference | Conformance Criteria summary |  | Method | Frequency | Hold/Witness Requirements
Records or
Inspection /
Checklist
|  |  | Test Point | [7 empty] | SDC | UCC | N P
Reference
3.0 - Setting Out
3.1 |  | Set out and survey |  |  | United Civil Construction | Project drawings ASG Piling Specificati on Rev G – Section 1.13 | UCC to set out pile centre lines on guide frames installed by SDC. Set out requirements will vary from location but will be required on multiple occasions. Setout gridlines to be within +- 3mm of design position. UCC to provide several benchmark pegs along the alignment that are checked frequently to ensure accuracy. SDC will be responsible for offsets taken from the pile set out location. |  | Registered surveyor Inspection and Set out | Each Pile position. | HP | IP | IP | SD Quality Control Checklist Set out report for tolerance As-built Survey Monitoring of benchmarks.
4.0 Construction stage
4.1 |  | Reinforcing Cages |  |  | Spiral Drillers | SESOC Section 1.10 |  | Stack reinforcing cages on suitable supports on firm ground, in a manner to eliminate excessive handling stresses or other damage. | Each delivery | Each delivery | HP | IP | IP | Structural engineer inspection of reinforcing cages SD Pile QA sheet Delivery dockets.
 Reject and replace reinforcing cages that are not as per the detail sheets.  Compile delivery dockets for reference to mill certs.
4.2 |  | Concrete Dockets |  |  | Spiral Drillers | Approved Mix design document. |  Mix design on delivery docket matches |  | Slump Tests & Concrete dockets. | Each Concrete truck. | HP | RR | RR | SD Concrete pour QA Sheet Concrete testing report.
[7 empty] |  | the approved mix design. On site material testing to confirm mix design characteristics are achieved.
Page 7 of 12

## Sheet8
No. |  |  | Responsibility |  | Reference | Conformance Criteria summary |  | Method | Frequency | Hold/Witness Requirements
Records or
Inspection /
Checklist
|  | Test Point | [7 empty] | SDC | UCC | N P
Reference
4.3 | Bottom Driving Plug Material |  |  | Spiral Drillers | SESOC Section 4.12.1 |  Aggregate to conform to table 4.12-1 of |  | Material grading cert. Pile measurem ents. | Daily | HP | RR | RR | SD Polymer Checklist.
[6 empty] |  | SESOC Rev I (Sealing Chip). Plug Length shall not be less than 1.5x casing diameter at commencement of
piling and shall not exceed 4.0m unless approved by the Engineer. 
4.4 | Pile installation/ founding level. |  | Spiral Drillers/ UCC |  |  | Tolerances The centre of the pile head at the design level of the head shall be within 75mm of its lateral position and 25mm of its vertical position. The pile shall be within 1:75 of its design. Do not force incorrectly placed piles into their correct position after they have been placed. Pile as built survey to be completed by United Civil Construction Founding Capacity: Pile locations to be driven to their required founding capacity verified using either Hiley or PDA. Driving Records All Piles will have the drop height & no. of drops recorded at the following intervals. 1.0m -> Up to 20m deep. 0.5m -> To founding depth. Set/ temporary compression recorded over 10No. consecutive blows using either a manual set card or a Pile Driving Monitor. |  | Position of pile: 75mm horizontal, 25mm vertical and 1:75 of its design Piles shall achieve a minimum founding resistance Outlined in IFC Drawings Cut off level to be +25, - 25mm | Each pile | HP | HP | RR | SD Pile Card Geotechnical Engineer inspection record. PDA Record review
Page 8 of 12

## Sheet9
No. |  |  | Responsibility |  |  | Conformance Criteria summary |  | Method | Frequency | Hold/Witness Requirements
Records or
|  | Inspection / |  |  | Spec
Checklist
|  | Test Point |  |  | Reference |  |  |  |  | SDC | UCC | N P
Reference
4.5 | Welding process |  | Spiral Drillers | AS/NZS 1554.1 NZS 3404.1 and AS/NZS 5131. AS/NZS 1554.1, clause 1.8.2. SESOC Section 2.2.6 |  |   | Welds to be carried out to the WPS form in AS/NZS 1554.1 Splicing will be a single bevel full strength butt weld, Flux-cored arc, | Document review and on-site inspections (Radiograp hy or ultrasonic) Independe nt testing report. | Weld testings: 10% non destruction examinatio n testing (UT testing) | HP | RR | RR | Independent test report
self-shielded, welded one side with backing strip. Weld testings:  10% Ultrasonic testing completed on Pile casing welds.
4.6 | Concrete placing |  | Spiral Drillers |  |  | Each pile is to be checked before each pour pfor any groundwater or contaminates in the ile Daily concrete pour record to approved checklist Concrete docket to be submitted each pour Testing  Carry out 7 and 28 days testing |  | Concrete dockets, Test results And Pile cards | Every 50m3 or minimum of 1 per day Each pile to be inspected before pouring concrete | HP | IP/RR | IP/RR | Concrete dockets and laboratory test results SD Concrete QA Card.
[6 empty] |  | Standard cylinders for each 50m3. 1 at 7 days, 2 at 28 days.
 1 slump test per load Concrete to be poured in a manner that avoids hitting the reinforcing cage. Poured central down the pile hole. Concrete to be tested in an IANZ Accredited lab. Depth to top of concrete, placement time and method to be recorded for each truck.
Completion
Page 9 of 12

## Sheet10
No. |  |  | Responsibility |  | Conformance Criteria summary | Method | Frequency | Hold/Witness Requirements
Records or
|  | Inspection / |  | Spec
Checklist
|  | Test Point |  | Reference |  |  |  | SDC | UCC | N P
Reference
5.1 | As- built pile survey |  | United Civil/ Spiral Drillers |  | All piles installed are within the required tolerances as shown in the construction specification and drawings. +-75mm horizontal tolerance +- 25mm vertical tolerance | As-built survey completed by a registered surveyor | Upon completio n of pile installatio n |  |  |  |  | Complete As-built document referring position to design positions.
5.2 | Warranty and code of compliance |  | Spiral Drillers |  | Documented evidence Certificate, warranty or Producers statement Warranty meets spec requirements Commence warranty from date of practical completion Spiral Drillers will issue a Producer Statement for the entirety of their contracted works upon completion. | Record review | once | HP | HP | RR | RR
Hold/Witness Requirements HP-Hold Point , IP- Inspection point , RR- Records review, WP-Witness Point
Comments:
Page 10 of 12

## Sheet11
Quality Control Checklist Spiral Drillers
PART 2 OF INSPECTION & TEST PLAN
Process: Bottom Driven Piles
Location: Bridge 217 - Napier |  |  |  | J7*** - Bottom Driven piles |  |  |  |  | Date opened:
No. | Inspection / Test Point | [10 empty] | NCR # (if reqd)
Contractor Hold / Witness Point Release
Result* /
Hold Point /
|  |  | Witness |  | Result
Point
|  |  | Number |  |  |  | CONTRACTOR SIGN OFF |  |  | UCC SIGN OFF
[6 empty] | Initials |  | Date |  | Initials | Date
1 |  | Preliminary Inspections and Tests
1.1 | Design and Drawings are of 100% Detail Design Status | HP
1.2 | Construction methodology | HP
2 |  | Approved Materials
2.1 | Reinforcing Cages | HP
2.2 | Steel Pile Casing | HP
2.3 | Welding | HP
2.4 | Concrete Mix Design | HP
2.5 | Welding On-Site | HP
2.6 | Piling Hammer & Equipment | HP
3 |  | Set-out
3.1 | Set out and survey | HP
4 |  | Construction Stage
4.1 | Reinforcing cages | RR
4.2 | Concrete Delivery | RR
4.3 | Bottom Driving Plug Material | HP
4.4 | Pile Installation/ Founding level | HP
4.5 | Welding Process | HP
4.6 | Concrete Placing | RR
5 |  | Completion Inspections and Tests
5.1 | Warranty and producer statements requested in specs compliance information | HP
5.2 | Complete set of As-built information | RR
Page 11 of 12

## Sheet12
Comments:
Work Completed:
The above items have been inspected and are in accordance with the drawings and specifications. All documentation as required by Specification is included in this Lot.
|  | Contractor | Ormat/ Delegate
Name:
Position Title:
Company
Signature
Date:
Page 12 of 12