## Sheet1
|  | APPENDIX : 400.07.01 | [9 empty] | Document No |  | ITP# J3161
[9 empty] | Notes: 1.Reference to Eastbridge ITP No. J3161 Revision A 2.Technical Specification Revision - Novare Spec |  |  | Revision |  | 0
|  | PROJECT NAME | [9 empty] | Author |  | B. Guild
|  | J3161 BR217 | [9 empty] | Date |  | 6/04/2023
[12 empty] | Reviewed By |  | D.Basire
[12 empty] | Date |  | 6/04/2023
[12 empty] | Approved By |  | J. Mellsop
Item | Task | RI | Acceptance Criteria | [5 empty] | Applicable Standard and/or Technical Requirement | Inspection Test |  | Verification Activity By |  |  | Verifying Record |  | Completion Sign-Off
[10 empty] | Method | Frequency | Eastbridge | Contractor | Client Rep.
1 | Preliminaries
1.1 | Method & Documentation
1.1.1 | Shop Drawings | PM | Submit electronic copies of shop drawings, providing complete details of each assembley with respect to the steelwork fabrication, surface treatment and erection. | [6 empty] | Review | Per Assembley | H | H | H | Notice to Contractor: Permission to Fabricate
1.1.2 | Independent Welding Inspector | PM | Submit Third Party welding inspection entity, appropriately qualified in the welding inspection required by the Project. | [6 empty] | Review | Once | H | H | H | Approved Independent Welding Inspector
1.2 | Material Compliance
1.2.1 | Structural Steel Grades | PM | Project Specification | [5 empty] | AS/NZS 3678 AS/NZS 3679.1 | Review | Per Material Order | H | H | R | Shop Drawings & Mill Certificates
1.2.2 | Structural Bolts | PM | Bolts will be sourced in accordance with NZS 1252:2016 All bolts are to be high strength steel bolts of grade 8.8 or higher, uno. | [5 empty] | NZS 1252:1996 | Review | Per Material Order | H | H | R | Material Conformance Certificates
1.2.3 |  | PM | All shear studs be produced in accordance with AS/NZS 1554.2:2003, with the relevant mill | [5 empty] | AS/NZS 1554.2:2003 | Review | Per Material Order
| Shear Studs |  | certificates and testing records, including mill certificates to which they will be connected
proving prequalification of welds.
1.2.4 | Structural Steel Supply Traceability | PM | Refer Project Specification All Plates are to be produced in accordance with NZS 5131 will mill certificates meeting the relevant grades given in 1.2.1. | [5 empty] | AS/NZS 5131 | Review | Per Material Order | H | H | H | ACRS or JAS-ANZ Mill Certificatoin Certificates
1.2.5 | Verified Mill Certificates | PM | [6 empty] | Project Specification | Review | Per Mill Certificate | H | H | H | ILAC Endorsment
1.2.6 |  | PM | [6 empty] | Project Specification | Material Test | Per Batch | H | H | H
| Structural Steel & Bolt Third Party Testing |  | 3 No. samples from each batch of structural steel tested for mechanical and che properties at a certified IANZ lab in NZ, and the results submitted to the Engineer |  |  |  | mical | [7 empty] | IANZ Laboratory Test Report
1.3 | Welding Procedures & Certification
1.3.1 | Welding Personnel Qualifications | PM | Review of proposed welders and their welding certificates and qualifications | [5 empty] | AS/NZS ISO9606.1:2017 | Review | Per Welder | H | R | R | Personnel Welding Qualification Certificates
1.3.2 | Welding Procedure Specification (WPS) | PM | Pre-qualified to AS/NZS 1554.1:2014 as a minimum. | [5 empty] | AS/NZS 1554.1:2014:2014 | PQR | Per WPS | H | R | H | Procedure Qualification Record
1.3.3 | Independent Review of WPS | PM | Review by nominated IWI of WPS and PQR | [6 empty] | Review | Per WPS | R | R | R | Independent Review Record
1.4 | Corrosion Protection System
1.4.1 |  | PM | [7 empty] | Review | Once | H | H | H
| Coating Applicator |  | Contractors are r Program (PCCP) | equired to be accredited under the Australian Paint Contractors Certification | [10 empty] | Coating Applicators Accreditation Certificate
1.4.2 |  | PM | Qualification to one of the following: | [6 empty] | Review | Once | H | H | H
|  |  | - NACE Protective Coating Special |  | ist
| Coating Specifier |  | - Australasian Corrosion Association |  |  | (ACA) Technician or Technologist with successful | [8 empty] | Coating Specifier Qualification Certificate
|  |  | completion of the ACA's Coating Selection and Specification Course and/or certified to N |  |  |  |  | ACE
Coating Inspection Program (CIP) Level 2
1.4.3 |  | PM | Painting specification approved by an independent paint inspector. | [6 empty] | Review | Once | H | H | H
| Coating Specification |  | Note, only coatings approved by an independent body such as APAS, NEPCOAT or NORSOK | [11 empty] | Approved Inspector | Paint Specification from Independent Paint
shall be used.
2 | Receiving & Storage of Parent Metals
J3161 BR217 Project ITP Page 1 of 4 Printed: 6/04/2023

## Sheet2
|  | APPENDIX : 400.07.01 | [5 empty] | Document No |  | ITP# J3161
|  |  |  | Notes: 1.Reference to Eastbridge ITP No. J3161 Revision A 2.Technical Specification Revision - Novare Spec |  |  |  | Revision |  | 0
|  | PROJECT NAME | [5 empty] | Author |  | B. Guild
|  | J3161 BR217 | [5 empty] | Date |  | 6/04/2023
[8 empty] | Reviewed By |  | D.Basire
[8 empty] | Date |  | 6/04/2023
[8 empty] | Approved By |  | J. Mellsop
Item | Task | RI | Acceptance Criteria | Applicable Standard and/or Technical Requirement |  | Inspection Test |  | Verification Activity By |  |  | Verifying Record | Completion Sign-Off
[6 empty] | Method | Frequency | Eastbridge | Contractor | Client Rep.
2.1 | Material Receiving into Store | PM | All incoming mateials shall be inspected for conformance to the requirements of the Project and heat numbers checked against mill certificates | PQP "Material Receiving" NZS3404.2:2009, 2.2.2 |  | Inspection | Per Material Order | I | R | R | Material Receipt Certification
2.2 | Storage PM |  | Materials shall be kept free from dirt, grease and other foreign matter and protected from corrosion as far as possible and shall be stored above ground on platforms, skids or other supports.
3 | Fabrication: Cutting, Holing & Bending
3.1 | Sharp Edges | FSUP | Rounded to a 2 mm radius by grinding after fabrication to ensure that a protective coating of normal thickness will adhere to the edges | AS/NZS 5131:2016 - Sect 6.5.4 |  | Inspection | Per Section | I | R | R | Eastrbidge Standard Fabrication Checksheet
3.2 | As-Cut Surfaces | FSUP | Australian Welding Research Association Class 2 surface | AS/NZS 5131:2016 - Sect 6.5.2 Table 6.5 |  | Inspection | Per Section | I | R | R | Eastrbidge Standard Fabrication Checksheet
3.3 | Re-Entrant Corners | FSUP | Shaped notch free to a minimum radius of 10 mm unless specifically indicated otherwise by geometry detail or as indicated on the drawings | AS/NZS 5131:2016 - Sect 6.5.3 |  | Inspection | Per Section | I | R | R | Eastrbidge Standard Fabrication Checksheet
3.4 | Holing | FSUP | Standard holes for bolts shall be D+2mm unless otherwise noted. Slotted holes shall be D=2mm wide and 2.5D long unless otherwise noted. Standard holes for pins shall be D+1mm unless otherwise noted. In the event of misalignment of bolt holes at any joint, reaming or drilling to more than 1.5mm larger than the bolt diameter will not be permitted unless specifically approved by the Engineer | AS/NZS 5131:2016 - Sect 6.7 |  | Inspection | Per Section | I | R | R | Eastbridge Standard Fabrication Checksheet
3.5 | Shaping | FSUP |  | AS/NZS 5131:2016 - Sect 6.6 |  | Inspection | Per Section | I | R | R | Eastbridge Standard Welding Checksheet
3.6 | Markings & Identification | FSUP | Steelwork markings and indentification is correct as per shop drawings | NZS 3404.1 |  | Inspection | Per Section | I | R | R | Eastbridge Standard Fabrication Checksheet
4 | Welding
4.1 | Check Welding Consumables | EBWI | Consumables to be stored in accordance with the manufacturers specification | AS/NZS 1554.1:2014 AS/NZS 5131:2016 Sect 7.5.2 |  | Review | Once | W | R | R | Approved Weld Testing Regime
4.2 | Welding Plan | EBWI | Considerations for all welding to made in respect to Section 7.2.2 for all welding related matters | AS/NZS 1554.1:2014 AS/NZS 5131:2016 Sect 7.2 |  | Inspection | Once | R | R | R | Visual Scanning Weld Report
4.3 | Allocate welders to specific welds | EBWI | Welders to be qualified in accordance with AS/NZS ISO9606.1:2017 | AS/NZS 1554.1:2014 AS/NZS ISO9606.1:2017 |  | Inspection | 100% | R | R | R | Visual Examination Weld Report
4.4 | Pre-weld inspections | IWCI | Pre-weld inspections shall be made in accordance with Section 7.5.4 | AS/NZS 1554.1:2014 AS/NZS 5131:2016 Sect. 7.5.4 |  | Inspection | 100% | R | R | R | Non-Destructive Testing Weld Report
4.5 | Welder traceability | IWCI | Welders to be traceable in accordance with Table 7.4 - CC4 | AS/NZS 1554.1:2014 AS/NZS5131:2016 Sect 7.4.3 Table 7.4 |  | Review | 100% | S | R | R | Ultrasonic Weld Report
4.6 |  | EBWI |  | AS/NZS |  | Review | 100% | H | R | R
| Stud Welding |  | Welders to be selected in accordance with AS/NZS 1554.2:2003 |  | AS/NZS 1554.2:2003 5131:2016 Sect. 5.6 & 7.5.11 | [5 empty] | Eastbridge Standard Welding Checksheet
5 | Welding Inspection & NDT
5.1 | Weld Testing Regime | PM | Generally, spread across all weld types, all welders and multiple welds of the same type. | AS/NZS 1554.1:2014 |  | Review | Once | H | R | R | Approved Weld Testing Regime
5.2 | Weld Integrity: Visual Scanning | EBWI | Weld location is as per shop drawing for each section | AS/NZS 1554.1:2014 |  | Inspection | 100% | H | R | R | Visual Scanning Weld Report
5.3 | Weld Integrity: Visual Examination | EBWI | Table 6.2.2: Permissible levels of imperfections in butt and fillet welds as determined by visual, magenetic particle and liquid penetrant examination of the weld zone | AS/NZS 1554.1:2014 |  | Inspection | 100% | H | R | R | Visual Examination Weld Report
5.4 | Weld Integrity: Magnetic Particle Inspection | IWCI | Structural fillet welds only Table 6.2.2: Permissible levels of imperfections in butt and fillet welds as determined by visual, magenetic particle and liquid penetrant examination of the weld zone | AS/NZS 1554.1:2014 |  | MPI | 25% | H | R | R | Non-Destructive Testing Weld Report
5.5 | Weld Integrity: Ultrasonic Testing | IWCI | Structural butt welds only Table 6.2.1: Permissible levels of imperfections as determined by radiograpic or ultrasonic examination for welds of category SP | AS/NZS 1554.1:2014 AS 2207 |  | UT | 25% | H | R | R | Ultrasonic Weld Report
J3161 BR217 Project ITP Page 2 of 4 Printed: 6/04/2023

## Sheet3
|  |  | APPENDIX : 400.07.01 |  |  |  |  | Document No |  | ITP# J3161
[5 empty] | Notes: 1.Reference to Eastbridge ITP No. J3161 Revision A 2.Technical Specification Revision - Novare Spec |  |  | Revision |  | 0
|  |  | PROJECT NAME |  |  |  |  | Author |  | B. Guild
|  |  | J3161 BR217 |  |  |  |  | Date |  | 6/04/2023
[8 empty] | Reviewed By |  | D.Basire
[8 empty] | Date |  | 6/04/2023
[8 empty] | Approved By |  | J. Mellsop
Item | Task |  | RI | Acceptance Criteria | Applicable Standard and/or Technical Requirement | Inspection Test |  | Verification Activity By |  |  | Verifying Record | Completion Sign-Off
[6 empty] | Method | Frequency | Eastbridge | Contractor | Client Rep.
5.6 |  |  | EBWI | "Ring" sound of stud when tapped with a 3kg hammer in the direction of the beam. | AS/NZS 1554.2:2003 | Ring Test | 100% | H | R | R
| Stud Welds: Ring Testing | [9 empty] | Eastbridge Standard Welding Checksheet
If stud gives a "'dead' sound, the test is failed.
5.7 |  |  | EBWI | No evidence of fracture under bending 15 degrees from original axis | AS/NZS 1554.2:2003 | Bend Test | 1 in 50 | H | R | R
| Stud Welds: Bend Testin | g | [8 empty] | Eastbridge Standard Welding Checksheet
First and second for each production weld set-up followed by specified frequency
5.8 | Fabricated Condition |  | EBWI | Ensure slag, spatter, scale and flux has been removed and general appearance is acceptable | AS/NZS 1554.1:2014 | Inspection | Per Section | I | R | R | Eastbridge Standard Fabrication Checksheet
5 | Corrosion Protection
Please refer to the Protective Coating Inspection and Test Plan
6 | Post Fabrication
J3161 BR217 Project ITP Page 3 of 4 Printed: 6/04/2023

## Sheet4
|  |  |  | APPENDIX : 400.07.01 | [6 empty] | Document No |  |  |  | ITP# J3161
[7 empty] | Notes: 1.Reference to Eastbridge ITP No. J3161 Revision A 2.Technical Specification Revision - Novare Spec |  |  |  | Revision |  |  |  | 0
|  |  |  | PROJECT NAME | [6 empty] | Author |  |  |  | B. Guild
|  |  |  | J3161 BR217 | [6 empty] | Date |  |  |  | 6/04/2023
[11 empty] | Reviewed By |  |  |  | D.Basire
[11 empty] | Date |  |  |  | 6/04/2023
[11 empty] | Approved By |  |  |  | J. Mellsop
Item | Task |  |  | RI | Acceptance Criteria |  | Applicable Standard and/or Technical Requirement |  | Inspection Test |  | Verification Activity By |  |  |  |  | Verifying Record | Completion Sign-Off
[9 empty] | Method | Frequency | Eastbridge |  | Contractor |  | Client Rep.
6.1 | Final Inspection |  |  | PM | Ensure all inspections and tests are completed, all reports and documentation are available and all results comply with the requirements |  | - |  | Review | Per Dispatch | H |  | H |  | H | Final Inspection Checksheet
6.2 | Dispatch |  |  | PM | Inspect delivery dockets and ensure that each item on packing list has been packed and in the correct quantity inclusive of weights |  | - |  | Review | Per Dispatcj | H |  | R |  | R | Dispatch Docket
Responsible Inspectorate (RI) | [7 empty] | Verification Activity |  |  |  | ITP Sign Off |  | Description
PM - Project Manager |  |  | SUR - Surveyor |  |  |  |  | SC - Subcontractor |  |  |  | H - Hold Point |  | Work shall not proceed past the Hold Point until released by the party imposing the Hold Point. Should be signed-off by relevant parties, immediately after the inspection/review.
CM - Construction Manager |  |  | SMR - Safety Management Representative |  |  |  |  | S - Supplier |  |  |  | W - Witness Point |  | A Quality Control point, that is at the discretion of the relevant party whether they attend. Witness to sign relevant check sheet section when works are complete
CR - Client Representative |  |  | FSUP - Fabrication Supervisor |  |  |  |  | C - Contractor |  |  |  | R - Review |  | A review of records supplied by the contractor. Not a hold point.
QMR - Quality Management Representative |  |  | EBWI - Eastbridge Welding Inspector |  |  |  |  | ENGR- Client Representative ( Engineer) |  |  |  | S - Surveillance |  | A routine construction activity where the relevant party, may choose to provide records of this inspection point, either by signing the checklists or other means, ie. observation reports.
EMR - Environment Management Representative |  |  | IWI - Independent Welding Inspector |  |  |  |  | D- Design (Aurecon) |  |  |  | I - Inspection |  | Formal inspection activity to be undertaken and recorded.
ITP Sign Off for Construction
Project Engineer:
Signature:
Date:
All works completed, records attached and work conforming
Site Engineer: |  | Project Engineer: |  |  |  | Quality Manager:
Signature:
Date:
J3161 BR217 Project ITP Page 4 of 4 Printed: 6/04/2023