## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Shear Bracket Installation |  |  |  |  | Yes | Shear Bracket Installation Checklist | 2e3bbe68-5b03-4207-ba28-f4ce7e382c4b
checkpoint-status |  |  | checkpoint | Surface Roughned to Minimum 2mm Amptitude
checkpoint-status |  |  | checkpoint | Drilled hole Depth Min Ø135mm
checkpoint-status |  |  | checkpoint | Drilled hole Clean and Dry
checkpoint-status |  |  | checkpoint | Sikadur UA31 Applied to bracket before Installation
checkpoint-status |  |  | checkpoint | Approved Chemical Epoxy installed as per Manufacturer's specification
checkpoint-status |  |  | checkpoint | Minimum Number of required Threded rods installed per brackets
checkpoint-status |  |  | checkpoint | Nuts Tightened after epoxy cured
checkpoint-status |  |  | checkpoint | Any exposed cut end of threded anchors painted with ArmourZinc110
folder-normal |  |  | checklist | ITP 001 - 7000 - Contract 7674 SH10 Parapara Bridge Strengthening |  |  |  |  | Yes | ITP 001 - 7000 - Contract 7674 SH10 Parapara Bridge Strengthening | 4b51961e-5df9-44ea-a188-af544e13b7cc
folder-normal |  |  | folder-normal | Preliminary
folder-normal |  |  | folder-normal | Shear Brackets
folder-normal |  |  | folder-normal | Post Tensioning
folder-normal |  |  | folder-normal | Backfill or Reinstate Pavement
checklist-flat |  |  | checklist | Document: |  |  |  |  | Yes | Project Documentation | a09ab147-3cc2-44aa-bef3-e0c2d5db54a4
checkpoint-no-status |  |  | checkpoint | Document Attached
checklist-sectioned |  |  | checklist | Concrete Inspection |  |  |  |  | Yes | Concrete Inspection | b45663ea-57bb-4be8-ac1a-2bcb9ce437fb
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | Adequately braced and supported
checkpoint-status |  |  | checkpoint | Grout tight
checkpoint-status |  |  | checkpoint | Correct dimensions
checkpoint-status |  |  | checkpoint | Cleaned and oiled
checkpoint-status |  |  | checkpoint | Formed surfaces straight
checkpoint-status |  |  | checkpoint | Major penetrations located
checkpoint-status |  |  | checkpoint | Embedded items located
checkpoint-status |  |  | checkpoint | Correct for specified surface finish
checkpoint-status |  |  | checkpoint | Adequate seating Pre Cast units
checkpoint-status |  |  | checkpoint | Permit to Load Obtained
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | Reinforcement Content and size
checkpoint-status |  |  | checkpoint | Confirm correct grade markings
checkpoint-status |  |  | checkpoint | Placement, tolerance, clearance
checkpoint-status |  |  | checkpoint | Rigidity and cover
checkpoint-status |  |  | checkpoint | Clean steel
checkpoint-status |  |  | checkpoint | Lap location and lengths
checkpoint-status |  |  | checkpoint | Starters/dowels correctly located
checkpoint-group |  |  | section | Construction Joints
checkpoint-status |  |  | checkpoint | Location
checkpoint-status |  |  | checkpoint | Roughened
checkpoint-status |  |  | checkpoint | Clean
checkpoint-status |  |  | checkpoint | Water bar placed if specified
checkpoint-group |  |  | section | Post Pour
checkpoint-status |  |  | checkpoint | Correct mix ordered
checkpoint-status |  |  | checkpoint | Independent Survey – Check off critical survey points
checkpoint-status |  |  | checkpoint | Engineer’s Rep Notified
holdpoint |  |  | signoff | Pre-Pour Checked and Accepted
checkpoint-group |  |  | section | Wet Concrete Checks
checkpoint-status |  |  | checkpoint | Correct mix delivered
checkpoint-status |  |  | checkpoint | Slump/flow Target
checkpoint-status |  |  | checkpoint | Compliance Cylinders Taken
checkpoint-status |  |  | checkpoint | Site Cured Cylinders Taken
checkpoint-status |  |  | checkpoint | Concrete Vibrated
checkpoint-status |  |  | checkpoint | Mandrels drawn through all ducts to verify no leakage / disconnection
checkpoint-status |  |  | checkpoint | Finished Level: Finished to grout check / angle fillet worked to
checkpoint-status |  |  | checkpoint | Surface to required finish eg U2, U4
checkpoint-status |  |  | checkpoint | Retarder applied at end of the pour
checkpoint-status |  |  | checkpoint | Curing applied (specify type)
checkpoint-status |  |  | checkpoint | Concrete Supply Dockets collected
checkpoint-group |  |  | section | Post Concrete Inspection
checkpoint-status |  |  | checkpoint | Curing correctly carried out
checkpoint-status |  |  | checkpoint | Concrete Strength for Striking
checkpoint-status |  |  | checkpoint | Concrete Strength for backfilling
checkpoint-status |  |  | checkpoint | Preparation of Construction Joints Completed
checkpoint-status |  |  | checkpoint | Blow holes, tie bar holes filled
checkpoint-status |  |  | checkpoint | Inspection of surface/s & any authorised repairs have been completed
checkpoint-status |  |  | checkpoint | As-Built complete
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Pre-Pour Checked and Accepted
text | 48513fa4-beca-5b1a-93a6-f5d5b57046d7 |  | textbox | Contractor Name
text | f39933d9-8d12-5f14-bfbb-b589e08b7fe7 |  | textbox | Date
text | 9c7a0efd-ef54-5039-b577-68d8b70ae14b |  | textbox | Engineer Name
text | d0332bcb-dd67-5dbb-ba9e-c5bf48927d5e |  | textbox | Date