## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Subgrade |  |  |  |  | Yes | Subgrade | 07431e2b-a0c6-4f37-a6ee-8194bf29436b
checkpoint-status |  |  | checkpoint | 2.1 - Proof Roll
label | 109dc978-5bb9-5858-9d6e-0364a8fec7ee |  | note | Activity Task: Proof roll with loaded log lifter
label | bf380f58-375a-5a3b-b52a-5e3a25d8297d |  | note | Acceptance Criteria: Principal supplied log truck, loaded. Covering 80% of the entire surface area being proof rolled
label | 7524ddf8-1c55-51df-bf6b-d01f4ce57353 |  | note | Frequency: After first layer of base course of thickness ≥190mm. After Scala testing
label | d192ba43-1b7c-5aaa-93d7-2b5526d9a8bb |  | note | Certifying Documentation, Record or Checksheet: Check sheet. Signed by Engineer/Engineer Rep/Engineer Rep Assistant
label | 60af6b26-825e-5b9f-8802-5dd0433489af |  | note | Internal Verification Authority or Responsibility: Witness by Supervisor
checkpoint-status |  |  | checkpoint | 2.2 - Surface Level
label | 1c0b08f7-535b-5ef2-a2c9-4fdf3c60f2e4 |  | note | Activity Task: Shape of subgrade surface
label | a0885f3f-95fc-5368-af5b-f9d8c396038c |  | note | Acceptance Criteria: 470-500mm below finished surface height
label | 031220f0-7e4a-5da1-8ff3-27a4e7c85f16 |  | note | Frequency: Each area, prior to base course.
label | a0848f0c-0a09-5bb0-ae29-504c101f0ae3 |  | note | Certifying Documentation, Record or Checksheet: 10x10m survey grid plan, report supplied to Engineer
label | 7d0824e2-2c95-5750-ad3a-b34b6bbe53fb |  | note | Internal Verification Authority or Responsibility: Surveyor
label | 95181dbd-cb99-5094-b05b-d1f1eda06546 |  | note | Critical Hold Point Authority: Hold Point
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.3 - Scalas to Subgrade through subbase
label | 8f7ca8a6-8f2b-55e3-9bbc-3e754a3245ee |  | note | Activity Task: Prove subgrade strength with Scala testing
label | 2a5e2937-58e3-5915-a17a-78866bf37ab1 |  | note | Acceptance Criteria: Scala Results as follows from table 9.1. 0-200mm = ≥6blows/50mm. 200-600 = ≥7blows/50mm
label | 3f39db78-d3a6-5b91-92e0-2aaf9be84c08 |  | note | Frequency: 1 test per 250m2 . After first layer of base course of thickness ≥190mm.
label | 1f159f01-70c0-582a-95fd-e39337c80c48 |  | note | Certifying Documentation, Record or Checksheet: Scala check sheets
label | 4bac006e-8686-5e5b-913b-37770b246aae |  | note | Internal Verification Authority or Responsibility: Supervisor
label | 52c3abc6-0884-59cc-b642-33a2a0e34e89 |  | note | Critical Hold Point Authority: Hold Point
holdpoint |  |  | signoff | HOLD POINT
checklist-flat |  |  | checklist | Basecourse Stabilization And Production Properties – AP40/Lime Basecourse | itp |  |  |  | Yes | Basecourse Stabilization And Production Properties – AP40/Lime Basecourse | 2e5f6c9e-18d1-4bb8-bc9e-6f2c6d8ee386
checkpoint-status |  |  | checkpoint | 6.1 - CBR Test AP40 Lime stabilized
label | 979d3c0c-dfbe-5f8e-b4d7-a0b238e7a291 |  | note | Activity Task: NZ Vibrating Hammer Test
label | 0a4efd72-6039-53ef-8dba-e10affe346f0 |  | note | Acceptance Criteria: NZS 4407:1991 Test 3.15. >200 CBR
label | 3b067616-4a1b-50ae-a9e8-ffda004fb2b7 |  | note | Frequency: Before supply.Test ≤1 months old. 1 test per 1000m3 stockpile measure, from stockpile.
label | 4e1786f5-360a-5668-b8b8-d03038c51f8d |  | note | Certifying Documentation, Record or Checksheet: IANZ certified laboratory results.
checkpoint-status |  |  | checkpoint | 6.2 - Lime Quantity
label | c386137b-9d71-5b44-a0bb-4b59ef7a5d50 |  | note | Activity Task: Record of lime quantities and adjusting feed rate.
label | 76e6eb9b-2121-5e27-915c-3ce09ecc53a4 |  | note | Acceptance Criteria: Lime supply vs tonnes of basecourse produced to show min 2% CaO.as a percentage of MDD of the base. Lime tolerance ≥2% - ≤3.5%
label | 3d3a2968-a4ec-5dec-a796-9c6010ee9161 |  | note | Frequency: Daily during basecourse stabilization
label | 28cd41fc-06f9-5544-badf-5021aea4c0ee |  | note | Certifying Documentation, Record or Checksheet: Calculate average %CaO on check sheet. Pug Mill check sheet
checkpoint-status |  |  | checkpoint | 6.3 - Mixing
label | f0ad6673-508a-51b7-aa21-92b3666a0369 |  | note | Activity Task: Lime and AP40 basecourse mix in pug mill
label | c72c6189-755b-5092-b215-9351313ed41e |  | note | Acceptance Criteria: Hydrated lime and aggregate mixed and uniform in appearance and moisture content.
label | f523ea47-650f-58c2-be18-af9ca51cbcc9 |  | note | Frequency: Ongoing visual checks.
label | 0888bfa1-4d49-58f7-8050-0124892c0f24 |  | note | Certifying Documentation, Record or Checksheet: check sheets
checkpoint-status |  |  | checkpoint | 6.4 - Clay Index
label | 4878b1bd-f7cd-525d-b321-6aef2ee5a3d3 |  | note | Activity Task: NSZ 4407: Test 3.5”Clay Index
label | c78bfbbf-953b-5c58-abf7-d02ca08df362 |  | note | Acceptance Criteria: Clay index ≤5%
label | f7167846-ea2d-50d0-943d-1bd87afc4dac |  | note | Frequency: 1 test per 2500m3
label | daf5de27-f5ba-5017-938f-127e51bb78d8 |  | note | Certifying Documentation, Record or Checksheet: IANZ test results
checklist-flat |  |  | checklist | Preliminaries + General |  |  |  |  | Yes | Preliminaries + General | 3f485d8d-17f7-4901-87b7-676de75e4f47
checkpoint-status |  |  | checkpoint | 1.1. - Quality Plan
label | 6b7ddc98-b4ec-58b4-a38e-0019a0eaa1f8 |  | note | Activity TASK - Contract Plan to be prepared and submitted to Engineer prior to any works commencing on site.
label | 593a72d4-60d5-51db-98d6-a5334b945e5a |  | note | Acceptance Criteria - Acceptance by Engineer.
label | 4959da33-5014-5a32-961b-f46d69c04e3f |  | note | Frequency - Prior to the commencement of site works.
label | db731169-c529-550f-b58a-af49bbf743a2 |  | note | Certifying Documentation, Record Or Checksheet - Approved Contract Plan.
label | dd0bb74a-37a6-5492-a568-cd9c131e0ff8 |  | note | Internal Verification Authority Or Responsibility -
label | 836c1580-db77-5ffc-90cb-c6182805fc48 |  | note | Critical Hold Point Authority - Contract Hold Point
checkpoint-status |  |  | checkpoint | 1.2. - Construction Programme
label | 31fe2994-de68-5cf2-a424-8d249e74bf50 |  | note | Activity TASK - The contractor shall submit to the Engineer a programme showing how the key aspects of the project will be programmed, resourced, and coordinated to meet the required contract completion dates.
label | 539744e8-f206-5fdf-b2de-85307956f8be |  | note | Acceptance Criteria - Acceptance by Engineer
label | 1fa52cdb-a400-51f4-824a-e1bcc9571a0d |  | note | Frequency - Prior to the commencement of works. Updated weekly.
label | f546a18c-6856-5f38-984b-231b4c818712 |  | note | Certifying Documentation, Record Or Checksheet - Approved Construction Programme.
label | ad44ac05-4a28-5540-a5e1-3617697d7145 |  | note | Internal Verification Authority Or Responsibility -
label | 4f2d04a6-1ce4-5964-96b1-479ad3da8478 |  | note | Critical Hold Point Authority - Contract Hold Point
checkpoint-status |  |  | checkpoint | 1.3. - HDG Coated Steel Items
label | 9ef2da52-73ab-5dc0-9981-beeffab4dcbb |  | note | Activity TASK - Fabrication and coated as per drawings
label | e096fa0e-7208-5f6b-bc15-13bef5e17201 |  | note | Acceptance Criteria - HDG600 with min thickness 600g/m2 to AS/NZS 4680
label | 9c1e6605-1f61-5554-839b-da6a06ce56c9 |  | note | Frequency - Once, prior to casting in concrete structures
label | bdf427ab-5dd1-5f18-956d-1814dc81a053 |  | note | Certifying Documentation, Record Or Checksheet - HDG600 galv certification
checkpoint-status |  |  | checkpoint | 1.4. - Survey Set out
label | 2e5d54ae-ac4f-5dbc-9cd2-74ab6b88206c |  | note | Activity TASK - Light Mast bases set out as per construction drawings
label | dd82f900-4769-5b08-b3a2-d090ef5676e1 |  | note | Acceptance Criteria - Confirmation by surveyor by email including records of survey with off sets.
label | e17d3da6-7c07-59ee-88e1-3469aa6ba539 |  | note | Frequency - Each high mast base location.
label | 24b7e50e-85f7-5de0-8040-d5852c6fbb16 |  | note | Certifying Documentation, Record Or Checksheet - Record of survey set out by email with off set records.
label | dea9834b-a77f-5d7a-9d6d-2794b5863699 |  | note | Internal Verification Authority Or Responsibility - Surveyor
checkpoint-status |  |  | checkpoint | 1.5. - Use of Concrete Suppliers technicians and lab
label | 11aca512-443b-56f4-b199-d8a20ee004b2 |  | note | Activity TASK - Slump tests and taking cylinders for compression testing.
label | 98520309-c687-52e6-9de6-381ca16c8411 |  | note | Acceptance Criteria - Acceptance by Engineer. NTE application pending for compression testing by concrete supplier . For slumps of range 110+ . Witness by Engineer/Engineer’s Rep/Engineer’s Rep Assistant
label | c327fa2f-fc9e-567a-87c4-8c42397f374a |  | note | Frequency - Prior to commencement of work. Once or as dictated by the Engineer
label | 94bacf8d-cfbc-539e-ada7-30034686e2d6 |  | note | Certifying Documentation, Record Or Checksheet - Acceptance via NTC/Email. Sign off on concrete pre pour checklist.
label | 3b8a58b8-237b-5673-899a-fc6057e9ccdc |  | note | Internal Verification Authority Or Responsibility -
label | c393d15f-311a-5f4a-8d37-9c0b26ca1585 |  | note | Critical Hold Point Authority - HOLD POINT
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5. - Atlas Concrete Mix Designs - for light mast base insitu pours.
label | c9a606f1-c55e-5965-a96d-e44069419786 |  | note | Activity TASK - 006 – 30MPa STD 19mm –
label | c89d31f5-14b8-5967-8195-e60796604836 |  | note | Acceptance Criteria - Acceptance by Engineer 30MPa @ 28 days
label | 4730a437-b3d2-5724-b567-980d7f9d90dc |  | note | Frequency - Once, before concrete commences
label | 789991d3-7a4c-56f9-bcb0-f3d7a90ed9a5 |  | note | Certifying Documentation, Record Or Checksheet - Approved Mix design by way of NTC
label | 120cdd7b-baed-5ed2-b433-697c2c68bc50 |  | note | Critical Hold Point Authority - HOLD POINT
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6. - Atlas Concrete Mix Designs - For back fill around mast bases in lieu of compacted aggregate
label | 468d3aaf-65d5-591d-bc5b-ba2b2d1f6010 |  | note | Activity TASK - SP0064M – 4MPa pump flowable fill 7mm. –
label | 839334e2-4938-5228-b47a-2b8c232c9dad |  | note | Acceptance Criteria - Acceptance by Engineer 4MPa @ 28 days
label | b50833e8-038a-521d-9c7b-f4a995e8320d |  | note | Frequency - Once, before concrete commences
label | 910feadc-d67e-55cc-af58-16b6597891f7 |  | note | Certifying Documentation, Record Or Checksheet - Approved Mix design by way of NTC
label | d536da67-17f1-5c1a-98bb-78adc600d355 |  | note | Critical Hold Point Authority - HOLD POINT
holdpoint |  | Data not allowed on signoff: Activity TASK - AP3019W – 30MPa 19mm std pump(33a962fa-ad7c-56e4-bbd0-c1c20e9eb1f5), Acceptance Criteria - Acceptance by Engineer 30MPa @ 28 days(1fb42760-327f-5f80-be4d-5bedfdcf4342), Frequency - Once, before concrete commences(26741e0b-7bd8-5c5b-9e6e-30cf054caca7), Certifying Documentation, Record Or Checksheet - Approved Mix design by way of NTC(a7bcc7c7-c88a-5892-87f3-24f225ffaa57), Critical Hold Point Authority - HOLD POINT(2c27d9e8-c47f-55da-b801-f73a0f217334) Multiple signoffs are not allowed | signoff | HOLDPOINT
holdpoint |  | Multiple signoffs are not allowed | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8. - Firth Concrete Mix Designs – For back fill around mast bases in lieu of compacted aggregate
label | b94dbabd-6a0d-5b8c-8b2f-568016a5d82d |  | note | Activity TASK - AA0207A – 2MPa 7mm flowable fill
label | 259b8e80-8b6d-5c1d-ad00-fb555900e1b1 |  | note | Acceptance Criteria - Acceptance by Engineer 2MPa @ 28 days
label | 90449c1e-ff72-5d85-90c2-b42ecc9979df |  | note | Frequency - Once, before concrete commences
label | af97a772-9d16-5742-ab4e-82956203cf89 |  | note | Certifying Documentation, Record Or Checksheet - Approved Mix design by way of NTC
label | dcce8062-c07f-5df0-8e8a-9f2902b21134 |  | note | Critical Hold Point Authority - HOLD POINT
checklist-flat |  |  | checklist | AP40 Basecourse Supply – Source Properties | itp |  |  |  | Yes | AP40 Basecourse Supply – Source Properties | 51f239f0-9454-46b4-b27f-10b7101c2ed0
checkpoint-status |  |  | checkpoint | 3.1 - Crushing Resistance
label | db42ce7f-41e6-5dde-8f96-67c0ae048438 |  | note | Activity Task: Test to NZS 4407:1991 3.10
label | db3185a5-04ba-56d9-9bc6-781c44e91f53 |  | note | Acceptance Criteria: ≤10% fines under 130kN load passing 2.36mm sieve.
label | 0e54eaaa-6c04-5888-a061-e63c4afd892e |  | note | Frequency: Before supply. Test ≤3 months old. 1 test per 5000m3 stockpile measure, from stockpile. 3 test/per material type
label | f8bd785b-8944-5eee-91bf-58d92a4f7c1a |  | note | Certifying Documentation, Record or Checksheet: IANZ certified laboratory results
label | bf1a61b9-63f5-5138-8c4a-15cf1c17edce |  | note | Critical Hold Point Authority: Hold Point
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.2 - Weathering Quality Index
label | 73e8c21f-0d1a-5c21-8e3b-02929ee3d09c |  | note | Activity Task: Weathering Test. AP40
label | c603909c-23c7-5fbc-a719-c685b115cf0b |  | note | Acceptance Criteria: NZS 4407:1991 Test. 3.11, shall have a quality index of AA, AB, AC, BA, or BB
label | e90ad871-3cf4-5e2d-9703-f285c7b752f2 |  | note | Frequency: Before supply. Test ≤3 months old. 1 test per 5000m3 stockpile measure, from stockpile. 3 test/per material type
label | f6732349-42dd-562e-bf12-40d00c9281d7 |  | note | Certifying Documentation, Record or Checksheet: IANZ certified laboratory results.
checkpoint-status |  |  | checkpoint | 3.3 - CBR
label | ccfd6406-dd21-580e-a3f1-a1a6f56bfdba |  | note | Activity Task: NZ Vibrating Hammer Test
label | 0d84639c-3de8-5e98-b658-3f2126624cfc |  | note | Acceptance Criteria: NZS 4407:1991 Test 3.15, For the aggregate without the addition of lime, section 3.3.3 of TNZ M/4 shall apply, with the CBR to be a soaked CBR using two surcharge weights.
label | 4224aafb-6e4a-5c0b-8ead-ae96009d87fc |  | note | Frequency: Before supply. Test ≤3 months old. 1 test per 5000m3 stockpile measure, from stockpile. 3 test/per material type
label | 93603102-aaa6-56b3-8637-6d8ce75f4904 |  | note | Certifying Documentation, Record or Checksheet: IANZ certified laboratory results.
checklist-flat |  |  | checklist | Precast Base Cone |  |  |  |  | Yes | Precast Base Cone | 55a2ce70-15f0-40ce-bc01-875416bbf438
checkpoint-status |  |  | checkpoint | 2.3. - On site Slump testing
label | f5a71beb-63e8-59e7-8c09-81f23fdd906d |  | note | Activity TASK - Slump testing of every concrete truck prior to use.
label | a0ad6da6-08e6-57d9-a438-aae111e05977 |  | note | Acceptance Criteria - For slumps of range 70-110, Nominated slump +/- 30mm., For slumps of range 110+, Nominated slump +/- 40mm., (As per table 9.1 NZS 3109:1997)
label | 768be0a4-67ca-5411-a301-52da46cc7972 |  | note | Frequency - Every ready-mix concrete delivery
label | 2ee4f658-827a-5ffc-8de5-e11f0781a055 |  | note | Certifying Documentation, Record Or Checksheet - Delivery docket
label | cf0a8d91-60cd-55a7-8d7d-5c5276b8f6e4 |  | note | Internal Verification Authority Or Responsibility - Witness by UCCL Engineer or Supervisor
checkpoint-status |  |  | checkpoint | 2.4. - Compression testing of concrete specimens
label | 32e55ed9-7d75-5643-966d-12fa8f4b5d26 |  | note | Activity TASK - 3No. test cylinders taken on site and subsequently tested at 28 days.Additional test cylinders as advised by UCCL for striking of pre cast forms and lifting at minimum strengths
label | ce6335d3-b4f7-5bf9-9077-24ec068e6d42 |  | note | Acceptance Criteria - Min 40MPa @ 28 days.Min 20MPa for striking. forms.Min 25MPa for lifting.
label | 3fbb7631-ac52-58b7-8c29-c2e86b0363d2 |  | note | Frequency - Each mix design, each day, every 65m3 of part thereof.
label | d12807b2-e1eb-560b-9f98-87cb80c191ef |  | note | Certifying Documentation, Record Or Checksheet - Delivery docket and qualifying.Lab test results.
label | 219026fc-c41f-5513-a82a-574bb3709fa1 |  | note | Internal Verification Authority Or Responsibility - Review by UCCL Engineer
checkpoint-status |  |  | checkpoint | 2.6. - Reinforcing Supply and Bend
label | 7ebb9b14-e75f-5e4b-bec8-825b5a5110b6 |  | note | Activity TASK - Reinforcing supplied and bent.All reinforcing to comply with AS/NZS 4671:2019.
label | 3097e51c-f50b-5fec-86b5-39df7e336ca0 |  | note | Acceptance Criteria - GRADE300 unless noted otherwise.Min bend diameters as per table NZS3109 table 3.1.Bent to shape and dimensions shown on the drawings.
label | 8e807592-92c1-5c56-828c-67bd5b80f371 |  | note | Frequency - Each pre cast structure
label | c2a04d84-a8e1-5ee9-a3d4-f9ce5965ad38 |  | note | Certifying Documentation, Record Or Checksheet - Reinforcing check sheet
label | 7d1d4561-20ab-554c-bbda-03fa69f2aa7d |  | note | Internal Verification Authority Or Responsibility - UCCL Engineer or Supervisor
label | 440155a6-43d2-50b7-a938-0e0314540153 |  | note | Critical Hold Point Authority - Hold Point
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7. - Reinforcement Placement
label | 481786ff-5731-5c23-bc5f-b07f79897703 |  | note | Activity TASK - In situ placement of reinforcing
label | 877e808d-6ea6-5a6a-882b-0e36a6069011 |  | note | Acceptance Criteria - Tolerances: Hoops and stirrups. +0,-5mm All other steel +0, -10mm Black tie wire Ø1.25mm – 2.0mm. Cover 50mm min UNO Plastic Reinforcing chairs as appropriate but not spaced greater than 1800 Cover as 60mm UNO on drawings
label | 52c4ffcf-e9bf-5278-bbc3-2d8d6993a0f6 |  | note | Frequency - Each pre cast structure
label | 2770475d-5b29-59b3-9b5b-2b45049e718d |  | note | Certifying Documentation, Record Or Checksheet - Reinforcing check sheet
label | dc9fcc13-f449-5d7b-a27f-00b7b6b48212 |  | note | Internal Verification Authority Or Responsibility - UCCL Engineer or Supervisor
checkpoint-status |  |  | checkpoint | 2.8. - Lifting Points
label | 3eb60bb4-7107-5729-ada4-0d123826b104 |  | note | Activity TASK - Installation of lifting points
label | 38987040-c2df-5398-a3e8-0209601fa37f |  | note | Acceptance Criteria - As per REID design fixed into position.
label | d26f9991-e4f9-5a66-8e67-b6c3b1b478e4 |  | note | Frequency - Each pre cast structure
label | 6711c840-0c84-52d5-a0ca-dce6bdbd75c9 |  | note | Certifying Documentation, Record Or Checksheet - Reinforcing check sheet
label | 9e6f91de-1051-57a0-8ce0-84ea89ff5363 |  | note | Internal Verification Authority Or Responsibility - UCCL Engineer or Supervisor
checkpoint-status |  |  | checkpoint | 2.9. - REID Bar
label | 2d86edf2-26a0-515a-bbe1-e305339edc6f |  | note | Activity TASK - RB bar and coupler joint
label | dd6b40b6-dd10-599c-9d1b-c8faaff944d3 |  | note | Acceptance Criteria - Epcon c8 epoxy, 6 injections into each side of RB25 coupler
label | 18ed0cd1-2e9f-5132-bc51-4ea6e5c7072e |  | note | Frequency - Each RB25 coupler
label | 264717a8-1641-5d0c-aaae-9eb25827caba |  | note | Certifying Documentation, Record Or Checksheet - Pre pour inspection check sheet
label | d6443e85-d1df-5064-8bbc-04057cb55f20 |  | note | Internal Verification Authority Or Responsibility - Supervisor
checkpoint-status |  |  | checkpoint | 2.10. - Reinforcement Inspection
label | 666003da-56f3-5e47-b835-f8e671596a1c |  | note | Activity TASK - Inspection by the Engineer/Engineer’s Rep/Engineer’s Rep Assistant
label | b10add0f-3eeb-5127-9183-1f688874899a |  | note | Acceptance Criteria - Approval by the engineer
label | 44baf94c-8bef-5b52-9b57-8491cc55067e |  | note | Frequency - Each pre cast structure
label | 17185bab-7b91-5c91-ac36-839eab8aa0d5 |  | note | Certifying Documentation, Record Or Checksheet - Engineer sign off.
label | 2518f3d0-7186-5bad-90c0-cd69c3a13611 |  | note | Internal Verification Authority Or Responsibility - Engineer/Engineer Rep
label | 2e4b17b6-9cd9-5987-96b4-bc1b7454ce70 |  | note | Critical Hold Point Authority - HOLD POINT
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.11. - Concrete Pour
label | c1a01c03-e699-52c1-929a-bc69c60402d6 |  | note | Activity TASK - Pre Pour Inspection
label | 32546d09-7cc5-561a-85ae-9b187aa30a72 |  | note | Acceptance Criteria - Approval from the Engineer/Eng Rep Forms covered in bond release agent. Forms clear of debris and sealed where appropriate. Reinforcing as per drawings and within tolerance. Concrete cover maintained All ducting in place as agreed. Earth wire installation complete and terminal bolted to internal form. Application of Rugasol C Extra to CJ. Delivery dockets reviewed, accepted and appended to check sheet.
label | dc0f1a20-dba6-5e4a-9031-75d9d49c396e |  | note | Frequency - 24hours notice. Prior to each concrete pour. Pre pour inspection check sheet.
label | 175dcf5f-ff83-5d22-9dc6-e511e8fb3b84 |  | note | Certifying Documentation, Record Or Checksheet - Engineer sign off.
label | ac9ef8bf-5a12-5679-bb14-c0274cddfec9 |  | note | Critical Hold Point Authority - HOLD POINT
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.12. - Striking Forms and Curing
label | 931318aa-3b85-5ea2-b868-19c234f95e86 |  | note | Activity TASK - Post pour inspection
label | 73cf3cb8-61ea-5c47-9799-3f5f6f39c579 |  | note | Acceptance Criteria - Striking forms after 2 days or 20MPa. Internal Surface finish F4 External surface finish F5 Application of Antisol A to surface concrete. Construction joint water blasted, exposed aggregate finish.
label | bcbb2c94-8af0-5d4c-83a6-dde2052a3c04 |  | note | Frequency - Each structure
label | 1d42d5f5-d289-5dcb-be77-2a177f463d6c |  | note | Certifying Documentation, Record Or Checksheet - Post Pour Check Sheet
label | 4f498398-135a-5cd6-8e36-5768c3638710 |  | note | Internal Verification Authority Or Responsibility - Supervisor
checkpoint-status |  |  | checkpoint | 2.13. - Precast cone lifting
label | 995c28ec-d15a-58d1-85a1-ce3e76592bf2 |  | note | Activity TASK - Moving Precast cone from casting mould
label | cdc5b894-7c13-58b7-b038-84a64cfc56f3 |  | note | Acceptance Criteria - Lifting after 25MPa. Based on compression tests initially then time frames for strength development are known and followed.
label | 2ec12de4-217e-552a-93f4-96b27cfa8d24 |  | note | Frequency - Each structure
label | 5830fc22-f369-5d6b-a608-a4f34746d601 |  | note | Certifying Documentation, Record Or Checksheet - Lift Plan
label | 51e2d66d-517d-523d-85cc-0adacfb2fc2c |  | note | Internal Verification Authority Or Responsibility - Supervisor
checklist-flat |  |  | checklist | Supply and apply of tack coat & Grade 5 chip seal |  |  |  |  | Yes | Supply and apply of tack coat & Grade 5 chip seal | 8e05419f-6a5c-473b-b34c-3069c1733a35
checkpoint-status |  |  | checkpoint | Area swept and clear of deleterious materials
label | 8e2c2e07-1120-52ad-8101-7d4f83c07803 |  | note | Visual inspection
checkpoint-status |  |  | checkpoint | Testing of CAT 60
label | 7d2885f3-d2eb-582d-9ce6-3d7b62265d2d |  | note | Test certificate from Supplier
checkpoint-status |  |  | checkpoint | Apply the Tack Coat (CAT 60)
label | 869e6943-9d81-535b-9aa8-736ec186a018 |  | note | 0.25 — 0.401/m2 residual binder
checkpoint-status |  |  | checkpoint | 7 days Curing period for the Tack Coat applied area
checkpoint-status |  |  | checkpoint | G5 Chip Seal Aggregate
label | 392215f5-d522-5e90-9ec4-6f286efc6aea |  | note | NZTA M6
checkpoint-status |  |  | checkpoint | Inspection of Tack Coated area, ensuring that it is clean.
label | f870630b-6962-5ab4-baf4-a6c287b8125a |  | note | Visual inspection
checkpoint-status |  |  | checkpoint | Apply of 180/200 Bitumen
label | a67c73c0-7dd4-58a0-b10f-001052693459 |  | note | 1.2L/m2 net binder
checkpoint-status |  |  | checkpoint | Testing of the 180/200 Bitumen
label | a98661af-81a8-5a2c-adc4-415e549caf66 |  | note | Test certificate from Supplier
checkpoint-status |  |  | checkpoint | Apply of G5 chips
label | 1dd5d5a4-f7d1-5ae7-84e0-4db9aaa338dd |  | note | No shoulder-to-shoulder contact
checklist-flat |  |  | checklist | In-situ Mast Base |  |  |  |  | Yes | In-situ Mast Base | b1f263db-9469-405c-bfe3-a62aa16e4056
checkpoint-status |  |  | checkpoint | 3.1. - Base Excavation
label | 9faac2f5-c8d6-52c1-a2e2-07dc153dc36b |  | note | Activity TASK - Dig out to underside of base.
label | 5adaf94a-4450-58da-a741-04a2eebc6752 |  | note | Acceptance Criteria - Dimensions and depth as per drawings and measured to surveyed offsets.Heights taken with dumpy level from surveyed bench mark.
label | 70f23f0d-eeb9-5ce6-8d2d-4802c1d7bf04 |  | note | Frequency - Each mast base
label | fc75bb29-19c9-50a0-81ae-f53c112960be |  | note | Certifying Documentation, Record Or Checksheet - Excavation Check Sheet
label | 69659be7-c709-577d-a0cc-ee2a412aebf7 |  | note | Internal Verification Authority Or Responsibility - UCCL Engineer/Supervisor
checkpoint-status |  |  | checkpoint | 3.2. - Foundation verification
label | c2b46b9c-4155-5e88-9e16-bceb0ff59017 |  | note | Activity TASK - Scala Penetrometer testing
label | 5fb9dc44-ef9e-5f22-8666-38b94c3cd030 |  | note | Acceptance Criteria - 5No. test to a depth of 4m below underside of excavation. Results verified with the engineer.
label | 70e0c624-da3a-5169-844a-5fc88bff1aa0 |  | note | Frequency - Each mast base
label | 443e0b0c-841f-59b6-b28b-3ddd2baa5b3d |  | note | Certifying Documentation, Record Or Checksheet - Scala Record sheet. Engineers Approval/sign off.
label | 7f13d27a-05db-568f-b956-48b73ed8f94e |  | note | Internal Verification Authority Or Responsibility -
label | 0b9a8b5b-c864-55d1-a31d-43a313f6f191 |  | note | Critical Hold Point Authority - HOLD POINT
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3. - Base foundation
label | 739cebf1-d8ef-51ad-85c4-1467fe7e528e |  | note | Activity TASK - Place geotextile, fill and Compact AP40
label | 4d2e5652-c896-5e0c-9f54-589c3830097b |  | note | Acceptance Criteria - A19 bidim placed over level, compacted excavation base AP40 minimum 150mm thick, level as per drawings. Sufficiently compacted using plate compactor or jumping jack.
label | 401f73d1-ca03-54ac-ba06-9a42deb14f84 |  | note | Frequency - Each mast base
label | 1b94aea3-f106-5615-aae8-64705734b133 |  | note | Certifying Documentation, Record Or Checksheet - Excavation Check Sheet
label | 39f6de31-5780-5eb1-9bc8-90b1e00dd0bc |  | note | Internal Verification Authority Or Responsibility - Supervisor
checkpoint-status |  |  | checkpoint | 3.4. - Flowable fill
label | 2756f841-929f-57fe-b428-96780985b5a4 |  | note | Activity TASK - Flowable fill placed in lieu of compacted aggregate at vertical faces of excavation.
label | 11b3b2e7-23b3-503b-9fbb-13fe0bd53809 |  | note | Acceptance Criteria - Placed and compacted. Mix design approved. Same thickness as AP40 wall detail in drawings.
label | 7558414b-e0b0-5676-9829-8bf3535ad2d0 |  | note | Frequency - Each mast base
label | 2714a92c-fd78-5aa9-8980-84123692b799 |  | note | Certifying Documentation, Record Or Checksheet - Excavation Check Sheet
label | 7a952359-e893-50b1-b944-242eb5c5cec6 |  | note | Internal Verification Authority Or Responsibility - Supervisor
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.9. - On site Slump testing
label | 007692b8-0308-54e5-83f2-4bc0f0415928 |  | note | Activity TASK - Slump testing of every concrete truck prior to use.
label | 1c016c93-c12c-5ecb-824a-257a0c4b5b8d |  | note | Acceptance Criteria - Nominated slump +/- 30mm. (As per table 9.1 NZS 3109:1997)
label | 76da5020-fa57-5752-8947-796503159dca |  | note | Frequency - Every ready mix concrete delivery
label | dd59c56e-377e-5b53-8ce6-6184bbf0e614 |  | note | Certifying Documentation, Record Or Checksheet - Delivery docket
label | ed3ba1ed-563f-588a-82f4-b85a618533da |  | note | Internal Verification Authority Or Responsibility - Witness by UCCL Engineer or Supervisor
label | 570acb38-8bea-53cd-b184-fe5d064f8dd3 |  | note | Critical Hold Point Authority - HOLD POINT
checkpoint-status |  |  | checkpoint | 3.10. - Compression testing of concrete specimens
label | 665ed80f-604d-5a70-bfb9-045079bf9230 |  | note | Activity TASK - 3No. test cylinders taken on site and subsequently tested at 28 days.Additional test cylinders as advised by UCCL for placing pre cast cone on stool supports.
label | 6ba04730-ac4c-58a0-9708-1189bd354b2d |  | note | Acceptance Criteria - Min 30MPa @ 28 days.Min 25MPa for placement of cone precast onto support stools.
label | 347ffe48-65e4-52cf-a260-da1e066e9e5b |  | note | Frequency - Each mix design, each day, every 65m3 of part thereof.
label | 8c6d2222-d296-51bb-ae90-7e4b467ccf28 |  | note | Certifying Documentation, Record Or Checksheet - Delivery docket and qualifying
label | 925fdf8f-5020-5294-a652-344589ab75a0 |  | note | Internal Verification Authority Or Responsibility - Review by UCCL Engineer
checkpoint-status |  |  | checkpoint | 3.11. - Reinforcing Supply and Bend – Detail Sheets
label | 942695b1-72ad-5dd5-bc57-3aed4ac034a5 |  | note | Activity TASK - Detail sheets provided prior to fabrication for review by UCCL
label | 1d722dbb-0c81-5bcc-b8f4-e4fb31fa4721 |  | note | Acceptance Criteria - Review by UCCL
label | 077a0ac1-698d-5fbd-a8fd-9d11b652d671 |  | note | Frequency - Once, prior to fabrication
label | 30946bed-57d9-54aa-aac6-c8e267f0478a |  | note | Certifying Documentation, Record Or Checksheet - Reinforcing check sheet
label | 5b2a22ec-50ae-595b-ac1f-c63f275502bb |  | note | Internal Verification Authority Or Responsibility - Review
checkpoint-status |  |  | checkpoint | 3.12. - Reinforcing Supply and Bend
label | 397f439b-34b6-5a13-b2c5-b9c86e5a1af4 |  | note | Activity TASK - Reinforcing supplied and bent. All reinforcing to comply with AS/NZS 4671:2019
label | a6b24c43-4ab0-5aa5-8b51-81eb5e481394 |  | note | Acceptance Criteria - GRADE300 unless noted otherwise Min bend diameters as per table NZS3109 table 3.1 Bent to shape and dimensions shown on the drawings
label | 7ad9f3a2-493f-5db6-ba8a-eb93c63ea2a8 |  | note | Frequency - Each base structure
label | 93fd75b8-0ce4-5381-bee9-c13861202779 |  | note | Certifying Documentation, Record Or Checksheet - Reinforcing check sheet
label | a5122733-e3e8-5f03-a5cd-53200d848b6b |  | note | Internal Verification Authority Or Responsibility - UCCL Engineer or Supervisor
label | 42f33cc4-1e1d-599a-b366-1082b19f3baf |  | note | Critical Hold Point Authority - Hold Point
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.13. - Reinforcement Placement
label | 2eea0d20-5b62-5793-bd65-c3c26b5749f3 |  | note | Activity TASK - In situ placement of reinforcing
label | 01cf21f3-23b2-5e62-ab3d-70cc35cd0d82 |  | note | Acceptance Criteria - Tolerances: Hoops and stirrups +0,-5mm All other steel +0, -10mm Black tie wire Ø1.25mm – 2.0mm. Cover 75mm min UNO (150 cover on base) Plastic Reinforcing chairs as appropriate but not spaced greater than 1800
label | 10942f9b-caf3-59a5-82ac-254702e19dae |  | note | Frequency - Each base structure
label | bd223ce0-9848-5372-b2f0-03b5ea72cdf1 |  | note | Certifying Documentation, Record Or Checksheet - Reinforcing check sheet
label | 86816bb8-65c0-5580-86ba-03fc0feaf461 |  | note | Internal Verification Authority Or Responsibility - UCCL Engineer or Supervisor
checkpoint-status |  |  | checkpoint | 3.14. - Levelling Supports
label | 3845f461-7460-5e2d-900a-e7f5cb3eb58a |  | note | Activity TASK - Installation of cast in levelling supports
label | 2025a129-0cde-508f-9bd3-e172a6a3410a |  | note | Acceptance Criteria - As per drawings, measured from surveyed offsets
label | eb176e54-8cf9-5d20-8313-68e5eac18e67 |  | note | Frequency - Each base structure
label | 2d9d59f1-7d8a-5cdd-9f01-2bee04e5f72c |  | note | Certifying Documentation, Record Or Checksheet - Reinforcing check sheet
label | 737cdcef-7e58-5e96-8c77-2ff10c5e8f76 |  | note | Internal Verification Authority Or Responsibility - UCCL Engineer or Supervisor
checkpoint-status |  |  | checkpoint | 3.15. - Reinforcement Inspection (Base Pour)
label | 8d2b080f-8867-5c71-bb7b-4d2693cfe281 |  | note | Activity TASK - Inspection by the Engineer/Engineer’s Rep/Engineer’s Rep Assistant
label | 33ec534f-735e-53db-948d-4015886846aa |  | note | Acceptance Criteria - Approval by the engineer
label | fbebe7eb-b2ea-529a-85cf-39431cda737d |  | note | Frequency - Each base structure
label | 48d12ea9-3e5a-5bbf-803d-313949e1b202 |  | note | Certifying Documentation, Record Or Checksheet - Engineer sign off.
label | 6429c5af-c188-52d8-af4b-584b149a4a9b |  | note | Critical Hold Point Authority - HOLD POINT
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.16. - Concrete Base Pour
label | 086785d8-2f51-57f7-8686-73afb61f4b48 |  | note | Activity TASK - Pre Pour Inspection
label | fa343845-1849-599e-82c3-aa0d56e07d2f |  | note | Acceptance Criteria - Approval from the Engineer/Eng Rep Any form or ply block outs covered in bond release agent. Forms clear of debris and sealed where appropriate. Reinforcing as per drawings and within tolerance. Concrete cover maintained All ducting in place as agreed. Earth rod duct installed. Rugasol C Extra applied to top of concrete for CJ
label | f1ce7fbf-4211-5a1c-8f1e-7687c9d1f00e |  | note | Frequency - 24hours notice. Prior to each concrete pour
label | ded7d344-917a-5702-8daf-c7aaf66b06e4 |  | note | Certifying Documentation, Record Or Checksheet - Engineer sign off.
label | 237c5086-8289-5d21-86e6-d176a5eaedb1 |  | note | Critical Hold Point Authority - HOLD POINT
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.17. - Striking Forms and Curing
label | 7060bdd2-01b9-5ce1-ad3a-7a0f5e10369b |  | note | Activity TASK - Post pour inspection
label | 10117083-5d88-551e-af55-b1688348d8b8 |  | note | Acceptance Criteria - Striking forms after 2 days or 20MPa. Waterblast of CJ and subsequent application of Antisol A to surface concrete
label | 11dd2ad3-042a-5a23-b681-b78c0fd16ada |  | note | Frequency - Each structure
label | 4033f771-3515-5f19-9921-571037af816e |  | note | Certifying Documentation, Record Or Checksheet - Post Pour Check Sheet
label | b10acf2a-8c26-5eac-9925-834edb041c42 |  | note | Internal Verification Authority Or Responsibility - Supervisor
checkpoint-status |  |  | checkpoint | 3.18. - Reinforcement Inspection (Foundation Top Pour)
label | 15e4f9a4-57ca-5148-bbc6-e909c8b3adb4 |  | note | Activity TASK - Inspection by the Engineer/Engineer’s Rep/Engineer’s Rep Assistant
label | f2f69892-447b-5bf0-9def-f56a505deb5e |  | note | Acceptance Criteria - Approval by the engineer
label | 72198e00-10d4-54f1-a88d-c39c86ecf10f |  | note | Frequency - Each base structure
label | 23ad1292-84c1-5131-a40a-462daa9e1ae9 |  | note | Certifying Documentation, Record Or Checksheet - Engineer sign off
label | 430032a7-0b56-518a-a44a-97411701ef97 |  | note | Critical Hold Point Authority - HOLD POINT
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.19. - Concrete Base Pour #2
label | aa22168a-3f77-5c01-ba78-e76ac9fd80c8 |  | note | Activity TASK - Pre Pour Inspection
label | 3a78aa00-1e9a-5fcb-9254-04e4f24c6c7f |  | note | Acceptance Criteria - Approval from the Engineer/Eng Rep Any form or ply block outs covered in bond release agent. Forms clear of debris and sealed where appropriate. Reinforcing as per drawings and within tolerance. Concrete cover maintained All ducting in place as agreed. Earth rod duct attached to toby box. Cast in galv items correctly installed Pre cast cone section installed correctly, support legs adjusted as required and position accepted.
label | 8722ef42-5945-5f4a-8a89-a5f488a6053e |  | note | Frequency - 24hours notice. Prior to each concrete pour
label | 46ca20cb-ed55-5a9e-a93d-17f3c421e921 |  | note | Certifying Documentation, Record Or Checksheet - Engineer sign off.Post Pour Check Sheet
label | a5239970-4f82-5703-85ec-d7cf6e8a0b15 |  | note | Critical Hold Point Authority - HOLD POINT
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.20. - Post Pour completion activities
label | bb5f86d4-3578-5fe6-a422-e9a29db0e86c |  | note | Activity TASK - Post pour inspection
label | 1ec0e049-aed5-542d-9728-ce1dac193de1 |  | note | Acceptance Criteria - Striking forms after 2 days or 20MPa. Antisol A to surface concrete Ply block out removed and Ladder installation complete
label | 442fb496-b258-5b01-991f-f7b9badaae20 |  | note | Frequency - Each structure
label | 939b3b2a-464f-5dc5-8814-2a7342073402 |  | note | Certifying Documentation, Record Or Checksheet - Post Pour Check Sheet
label | f6e42df1-75b2-580d-95d2-8927e2520835 |  | note | Internal Verification Authority Or Responsibility - Supervisor
checklist-flat |  |  | checklist | AP40 Production Properties | itp |  |  |  | Yes | AP40 Production Properties | b4b20956-b0e3-4937-a3b4-fa8023cfb804
checkpoint-status |  |  | checkpoint | 4.1 - Particle Size Distribution AP40
label | 45c22570-d694-5afb-a279-8d2242facdb9 |  | note | Activity Task: Tested to NZS 4407:1991, Test 3.8.1 “Wet Sieving Test”
label | babbfcd0-d9a9-573f-ad61-c6d7b91c0653 |  | note | Acceptance Criteria: Conform to envelope limits within Principals spec. C9.4.5 Table 10.1 and Table 10.2 , 3 test/per material type
label | ec031285-3bcc-53b2-a51c-e0b81b0a0324 |  | note | Frequency: Before supply. Test results ≤4 weeks old. 1 test per 1000m3 from stockpile.
label | a8f16feb-08ff-557b-8a5a-3dd305f1dec2 |  | note | Certifying Documentation, Record or Checksheet: IANZ certified laboratory results
checkpoint-status |  |  | checkpoint | 4.2 - Sand Equivalent
label | 915550f9-cdc9-5663-94ea-43ee7309ba79 |  | note | Activity Task: NZS 4407:2015 Test 3.6
label | 3ed66f34-ceee-5e7e-816a-50a5931f776b |  | note | Acceptance Criteria: Not more than 40 not less than 20.
label | ba026781-db49-5441-9efe-f633e1e9d461 |  | note | Frequency: Before supply. Test results ≤3 months old. 1 test per 2500m3 from stockpile.
label | 805d6fbb-b4d6-5479-930c-caf565dc2aab |  | note | Certifying Documentation, Record or Checksheet: IANZ certified laboratory results
checkpoint-status |  |  | checkpoint | 4.3 - Clay Index
label | f7a5a0d1-11ee-53b3-9045-d36f201b214a |  | note | Activity Task:
label | 76981fa7-0bf9-52a5-9558-739c081696ca |  | note | Acceptance Criteria: TNZ M/4:1995 , Except 2.5 ≤ Clay ≤ 8.0 Index
label | 29ee89da-84cf-5b02-b06a-3529e62cef5c |  | note | Frequency: Before supply. Test results ≤3 months old. 1 test per 2500m3 from stockpile.
label | 9672b56c-56d0-5f58-80f1-250acd1680c6 |  | note | Certifying Documentation, Record or Checksheet: IANZ certified laboratory results
checkpoint-status |  |  | checkpoint | 4.4 - Broken Faces
label | 46c31faa-3578-5a44-9e2b-46d9b88b55d8 |  | note | Activity Task: NZS 4407; Test 3.14 “Broken Faces Content of Aggregate”.
label | 1e9e9017-f364-5f42-96ad-77a7046bc8bd |  | note | Acceptance Criteria: aggregate broken faces content in each of the four aggregate fractions of Table. 3.14 of NZS 4407; Test 3.14 shall have not less than 80% with two or more broken faces. Engineers’ acceptance to verify no further testing required.
label | f853da82-50b6-57c6-a4bb-71d09ab1b383 |  | note | Frequency: Once. (Pending engineers acceptance of initial test result)
label | 78fdaa67-2942-5d01-ae50-8f70b7cfc08b |  | note | Certifying Documentation, Record or Checksheet: Email or NTC
checklist-flat |  |  | checklist | Supply and apply of Mix 25 asphalt |  |  |  |  | Yes | Supply and apply of Mix 25 asphalt | bb0ee871-82c2-41bc-9e1e-a0aad4b9b323
checkpoint-status |  |  | checkpoint | Area clear of deleterious materials and all surplus chips are removed
label | 8538f502-f8eb-5eb5-8bc9-c738ef1d2318 |  | note | Visual inspection
checkpoint-status |  |  | checkpoint | Determining pre leveling thickness
label | dfd36bdf-e2a2-553d-8030-86d98a6b990b |  | note | Determining any area outside the -10mm, +10mm tolerance measured with a 5m straight edge
checkpoint-status |  |  | checkpoint | Mark paving lanes/longitudinal joints
label | a36ac684-581c-587f-b8b8-847f940aeb05 |  | note | Minimize paver joints under wheel track
checkpoint-status |  |  | checkpoint | Transverse joints
label | 206c53f1-88cb-5324-b718-6bbd8ef61474 |  | note | Check with 5m straight edge to nearest level and cut back with diamond saw
checkpoint-status |  |  | checkpoint | Temperature testing of asphalt
label | c690e0f5-7d84-51cc-992d-aa9966420e17 |  | note | ≥ 145 deg, to ≤ 170 degree Celsius
checkpoint-status |  |  | checkpoint | Fine Aggregate Moisture Content
label | 185ceb1a-d9d9-59c1-b7bc-5c10a229e1e7 |  | note | Not to vary by more than 2%
checkpoint-status |  |  | checkpoint | Hot Asphalt Mix Moisture Content
label | 882319c4-3f15-57f3-95cb-83b5a368bccb |  | note | Not to exceed 0.5%, measured once daily
checkpoint-status |  |  | checkpoint | Mass Balance
label | e723a341-1dbc-59d0-b58a-b718602a4ca6 |  | note | Each truck
checkpoint-status |  |  | checkpoint | Surface Levels
label | b0f4a925-0882-5712-9c1a-c828719cfedd |  | note | Reduced level of any point on the surface of the asphalt shall be within -0 to +20mm of the finished surface level for that point from the drawings
checkpoint-status |  |  | checkpoint | Inspect for thickness before compaction
label | ba893a56-56ec-5253-9781-9314ba25e31b |  | note | Check thickness by hand prodder (84mm prior to compaction)
checkpoint-status |  |  | checkpoint | Inspect for thickness after compaction
label | 037a9eaa-24b5-5dc0-9c50-db2f7c88a892 |  | note | Thickness shall be within -0 to +10mm of the specified thickness at any point - Measure Cores
checkpoint-status |  |  | checkpoint | NDM testing
label | 39d5b54b-07bd-5d7b-9532-9241e66f7408 |  | note | Adequate compaction
checkpoint-status |  |  | checkpoint | Paving Lanes
label | a306754e-3cff-5b95-874c-c2f2819dda16 |  | note | Stagger longitudinal joints if possible
checkpoint-status |  |  | checkpoint | Mat Density (Core testing)
label | 564772f2-55c3-5361-a572-21c51176b742 |  | note | 3 cores per 1,000m2 Minimum of 3 cores per day’s paving (2.5% - 6.5%)
checkpoint-status |  |  | checkpoint | Joint Density (Core testing)
label | b0f78f36-17e6-5822-9174-6e7a34704d7c |  | note | 1 test per 100m of joint - Minimum of 3 cores per day’s paving (2.5% - 8%)
checkpoint-status |  |  | checkpoint | Bond to basecourse
label | 88818551-0af6-576e-b2a6-a53f8957db00 |  | note | Comment from cores
checkpoint-status |  |  | checkpoint | Asphalt Test Results
label | 997efda6-1382-5369-909c-4a9f2a25e3b5 |  | note | Collect samples prior to dispatch. Results to conform to table 12.3 & 12.4
checkpoint-status |  |  | checkpoint | Bitumen
label | ee7b5a2b-c772-5e46-94b2-011770fd4d95 |  | note | Comply M/1 Independent evidence bitumen complies with TNZ M/1 1995
checkpoint-status |  |  | checkpoint | % Retained Tensile strength
label | bb302cc5-40a7-5635-960c-9886f238d1fd |  | note | ≥ 80%
checkpoint-status |  |  | checkpoint | Surface Shape
label | 4d3bd416-529d-5464-bfeb-39eb8378cf58 |  | note | 6mm over a 5m with straight edge
checkpoint-status |  |  | checkpoint | Surface Texture Measurement
label | 6f0ca84d-efb8-5d7f-a308-ad3cabdcd0d9 |  | note | Six (6) tests for daily production
checklist-flat |  |  | checklist | Lime Supply – Source Properties |  |  |  |  | Yes | Lime Supply – Source Properties | ca635d45-194c-4663-a699-e9d767a963da
checkpoint-status |  |  | checkpoint | 5.1 - Lime Quality
label | 9791442f-98f4-50bb-bff8-935518e7f33c |  | note | Activity Task: Available lime Index testing from supplier
label | a1e6a9e5-de61-58aa-8c2f-e0c2a34f2143 |  | note | Acceptance Criteria: Available lime Index. NZTA M15. Available Lime Index ≥85. From Lime Producer 2% CaO based on MDD of the basecourse source material AP40.
label | d3f2e253-4ad7-5a43-82f0-7c1a7307ff10 |  | note | Frequency: One test per 200t burnt lime
label | 931d07e2-b8d3-5405-9cf7-c2788017d0b2 |  | note | Certifying Documentation, Record or Checksheet: Test results from supplier.
checklist-flat |  |  | checklist | As-built Records |  |  |  |  | Yes | As-built Records | dcd487f4-e0a6-4ef6-bfee-2e88c5f072ec
checkpoint-status |  |  | checkpoint | 4.1. - AS Built Data
label | 61279ba9-ebc9-5a7d-940b-2fa5ad10fd55 |  | note | Activity TASK - As built location of structure including ducts and services surveyed and generated in an electronic format. Either DWG or DXF
label | b3502d43-3e25-56b7-874f-e5b371e3e63f |  | note | Acceptance Criteria - As built co ordinates to an accuracy of 100mm in plan and 10mm for level. Draft copy of as built drawings and info for review. As built sheets certified by a Chartered Engineer, Registered Surveyor or other suitably qualified person approved by the Engineer
label | 632c1a0b-632d-55cd-89ba-27bf8bbc1ca3 |  | note | Frequency - One draft copy One final copy.
label | d92a60bd-26cd-54ff-aea8-7389cbd56aa5 |  | note | Certifying Documentation, Record Or Checksheet - Set of paper plan as builts. Set of DXF/DWG electronic file.
checklist-flat |  |  | checklist | Base Course Pavement Construction Requirements | itp |  |  |  | Yes | Base Course Pavement Construction Requirements | de984265-23f9-4874-9d2a-e12e4d7e8738
checkpoint-status |  |  | checkpoint | 7.1 - Density Testing
label | 2d5db4e7-929d-5b0d-982f-d787d234ca72 |  | note | Activity Task: NDM testing (IANZ testing)
label | 7593a789-94f5-549a-8adf-1124e1c5cd20 |  | note | Acceptance Criteria: Total Voids. Mean ≤18% total voids. Maximum ≤20% total voids. Using NZS 4407, Test 4.2.1 Nuclear surface moisture – density gauge – direct transmission mode. Test on each layer
label | 7fe67b81-e6ba-5f01-8426-c70f8f0031d1 |  | note | Frequency: 5 tests/10000m2.
label | 784a6e0b-a513-54ec-bf2c-010ccf90cf42 |  | note | Certifying Documentation, Record or Checksheet: IANZ certified site test results
checkpoint-status |  |  | checkpoint | 7.2 - Density Testing
label | c3d980d9-affc-5a9d-b621-25ce50aced65 |  | note | Activity Task: NDM testing (Contractors testing)
label | 223e19a5-94dc-5536-b93f-701671526eea |  | note | Acceptance Criteria: Total Voids. Mean ≤18% total voids. Maximum ≤20% total voids. Using NZS 4407, Test 4.2.1 Nuclear surface moisture – density gauge – direct transmission mode. Test on each layer
label | 122bc169-7228-5a07-be3e-41a6f5f55123 |  | note | Frequency: Every 1000m2
label | dc14dca4-0c53-5f0f-80bc-b882d5bd4a58 |  | note | Certifying Documentation, Record or Checksheet: NDM record sheets.
checkpoint-status |  |  | checkpoint | 7.3 - Water Supply
label | c3745a94-6354-53bc-95e3-71474d2856d0 |  | note | Activity Task: Water added to basecourse
label | 4018f2f5-4250-56bf-a1c6-511566402031 |  | note | Acceptance Criteria: Water supplied by a local authority for public supply purposes
label | 79d9eabb-cb07-5bed-8ef3-3a6044313707 |  | note | Frequency: NA
label | e97ccd47-777e-512f-bbe4-89ef5243da97 |  | note | Certifying Documentation, Record or Checksheet: Email acceptance/NTC by the Engineer.
checkpoint-status |  |  | checkpoint | 7.4 - Clegg Hammer
label | 4b0a8785-90b9-5460-94af-cec536795888 |  | note | Activity Task: Test upper compacted surface of base course
label | 68c5039a-25e5-53a9-a37c-3b0432346820 |  | note | Acceptance Criteria: CIV Record of 4th drop: Mean CIV of ≥50, No CIV <45
label | b29c748c-1fae-5a0a-9435-7d6ae87860c4 |  | note | Frequency: One test per 100m2
label | 8b820a04-3654-57d4-a49c-9b0169dc63ff |  | note | Certifying Documentation, Record or Checksheet: Check sheet record
label | 4b782683-7c0b-59af-91bb-818c1f4051a1 |  | note | Critical Hold Point Authority: Hold Point (Prior to sealing)
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.5 - Pre-Paving Proof Roll
label | 9b2e3db2-5ec6-5d5a-b7c9-560eec986dce |  | note | Acceptance Criteria: Proof rolling of the entire surface area of the constructed basecourse. No movement of the pavement shall be visible under the vibrating drum of a roller of static weight not less than 7 tonne.
label | b5ea3dad-9d3a-5d24-bed2-ffd2bbe6259d |  | note | Frequency: Entire Area
label | f6e32adc-4a54-56c8-b7f6-052826807283 |  | note | Certifying Documentation, Record or Checksheet: Check Sheet
label | 417e3ca9-1b8d-587b-8f48-4be20fa967db |  | note | Internal Verification Authority or Responsibility: Engineer Option to View
label | 82079953-8724-5701-9141-05d63e0dd961 |  | note | Critical Hold Point Authority: Hold Point (Prior to sealing)
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.6 - Pavement Thicknesses
label | 076d91b9-27ec-5991-abaa-9f86f843be8b |  | note | Acceptance Criteria: First Lift: 185mm to 210mm. Second lift: Total of both lifts not less than 400mm. 10 x 10m grid pattern surveyed
label | d14f646e-fe62-5ff0-a1f0-4d13c02e45e5 |  | note | Frequency: Each area of pavement
label | 069b5728-79b5-5eb7-a16d-514b49944497 |  | note | Certifying Documentation, Record or Checksheet: Survey Record
checkpoint-status |  |  | checkpoint | 7.7 - Surface Level
label | 13030f49-be77-5b8a-ad7c-a1f997e0a5e5 |  | note | Activity Task: Survey
label | 3684a04a-f7b2-5245-80a3-2255e6fb14cd |  | note | Acceptance Criteria: Survey to show minimum 400mm base course. Vertical tolerances as per C10.13.2. At any individual point on the completed basecourse: Next to concrete or existing AC: -5mm ,+0mm . Elsewhere: -15mm, +5mm . Average vertical tolerances for level as an average of any 10 or more consecutive levels on a grid shall be: Next to concrete or existing AC: -5mm, +0mm. Elsewhere: -7mm, +3mm. Cross fall not to vary by more than 0.2% between any 2 points 5m apart when compared to the design surface
label | 9754c66a-8df3-5805-8e72-b97379c916a1 |  | note | Frequency: Per Area constructed.
label | df7eff5f-2a5a-59d5-ba2d-efa46ff64d9a |  | note | Certifying Documentation, Record or Checksheet: Survey report
checkpoint-status |  |  | checkpoint | 7.8 - Surface Tolerances
label | 58c27425-389d-5565-9239-6b09f5a62acb |  | note | Activity Task: Survey
label | bdf54fe4-c240-5098-bf66-916bc64acb3e |  | note | Acceptance Criteria: Unconstrained: -20mm,+100mm, Constrained: Zero
label | 5d14acec-e79d-51f2-bae8-782d59b40005 |  | note | Frequency: Per Area constructed
label | 1b17ae89-67d1-511c-9962-b4507b6d4344 |  | note | Certifying Documentation, Record or Checksheet: Survey report
checkpoint-status |  |  | checkpoint | 7.9 - Surface Finish
label | 86ca0e5b-8b88-523e-bdea-736e2afa1ffa |  | note | Acceptance Criteria: Surface shape to conform with section 7.7 TNZ B/02. Smoothness such that no depression greater than 10mm over 3m straight edge. Finish to conform with section 7.8 TNZ B/02. Swept and large aggregate held in place by a mosaic of smaller aggregates