## Precast Concrete Materials ITP
Precast Concrete Materials ITP
Project: Homer Tunnel
Number and Revision: DS2676-DOW-ITP-CV-0001-Rev B
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | Concrete Materials and Approvals
4.01.01 | Shop Drawing Tolerances | The Contractor shall check all tolerances and clearances between precast elements to ensure a satisfactory fit between all elements and shall notify the Engineer of any locations where tolerances or clearances need to be increased to ensure satisfactory construction procedures. | PS 27.6.6.2 | Shop Drawings | Prior to Submission to the Engineer | R | PE
4.01.02 | Shop Drawings | The Contractor shall make available the shop drawings to the Engineer for review, at least 14 days prior to manufacture. Acceptance of the drawings must be obtained from the Engineer prior to the units being cast. | PS 27.6.6.2 | Shop Drawings | At least 14 days prior to manufacture. | HP | ENG
4.01.03 | Lifting Design | The lifting design specifying the lifting eyes shall be incorporated into the fabrication drawings. | PS 27.6.6.17 | Datasheets | With Shop Drawings | HP | ENG
4.01.04 | Concrete Plant | The Concrete Plant shall have a Current Certificate of Audit | PS 27.4.1 | Certificate of Audit to NZS 3104:2003 | With Mix Design and Upon Revalidation | HP | ENG
4.01.05 | Concrete Aggregate Reactivity Testing | When required, the Concrete producer is to confirm the proposed aggregates are non-reactive as defined in clause 6.1 of CCANZ TR3. | PS 27.4.2.3 | Supplier Statement | With Mix Designs Submissions | HP | ENG
4.01.06 | Precast Columns Concrete Mix Design | The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification | PS 27.4.3.3 / 27.3.1 | Concrete supplier mix designs | Submitted least 14 days in advance of concrete supply | HP | ENG
4.01.07 | Precast wall Concrete Mix Design | The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification | PS 27.4.3.3 / 27.3.1 | Concrete supplier mix designs | Submitted least 14 days in advance of concrete supply | HP | ENG
4.01.08 | Link Slab Concrete Mix Design | The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification | PS 27.4.3.3 / 27.3.1 | Concrete supplier mix designs | Submitted least 14 days in advance of concrete supply | HP | ENG
4.01.09 | Footing Concrete Mix Design | The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification | PS 27.4.3.3 / 27.3.1 | Concrete supplier mix designs | Submitted least 14 days in advance of concrete supply | HP | ENG
4.01.10 | Footing Shear Key Concrete Mix Design | The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification | PS 27.4.3.3 / 27.3.1 | Concrete supplier mix designs | Submitted least 14 days in advance of concrete supply | HP | ENG
4.01.11 | Precast Hollow Core Roof Beams Concrete Mix Design | The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification | PS 27.4.3.3 / 27.3.1 | Concrete supplier mix designs | Submitted least 14 days in advance of concrete supply | HP | ENG
4.01.12 | Precast Torsion Beam Concrete Mix Design | The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification | PS 27.4.3.3 / 27.3.1 | Concrete supplier mix designs | Submitted least 14 days in advance of concrete supply | HP | ENG
4.01.13 | MSE Approach Wall Panels Concrete Mix Design | The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification | PS 27.4.3.3 / 27.3.1 | Concrete supplier mix designs | Submitted least 14 days in advance of concrete supply | HP | ENG
4.01.14 | Precast Facia Panels and Precast Upper Retaining Wall Concrete Mix Design | The Engineer shall be provided with the Concrete Mix design for each mix comply with the requirements of the Project Specification | PS 27.4.3.3 / 27.3.1 | Concrete supplier mix designs | Submitted least 14 days in advance of concrete supply | HP | ENG
4.01.15 | Reinforcement Supplier | The contractor shall provide the name of reinforcement supplier before delivering any reinforcement | PS 27.7 | Supplier Details | Before delivering any reinforcement | R | PE
4.01.16 | Reinforcement | Reinforcing bars and mesh shall comply with AS/NZS4671:2001. Test certificates shall be obtained from the manufacturer for all strand, cable and bar to be used in the work and copies shall be forwarded to the Engineer at least one week before the programmed commencement of any work incorporating these materials. Test certificates shall be traceable to the batch of material supplied to the work. | PS 27.7.1 / 27.7.9 | Mill Certs | At least one week before incorporating these materials. | R | PE
4.01.17 | Bar Bending Schedules | The Contractor shall prepare reinforcing bar schedules in accordance with BS 8666 with due allowance for bending tolerance and associated drawings, two copies of which shall be supplied progressively to the Engineer for comment at least 14 days before the start of placing the corresponding reinforcing bars. | PS 27.7.8 | Bar Bending Schedules | At least 14 days before the start of placing the corresponding reinforcing bars. | HP | ENG
4.01.18 | ITP Inspector approval | The Contractor shall supply the details of the proposed Third Party Inspector to the engineer prior to welding | PS 27.7.6 | TPI Details and Qualifications | Prior to Welding | HP | ENG
4.01.19 | Welding of Reinforcement | The welding shall be inspected by the Contractor’s Third Party Inspector who shall meet the “Qualifications of Inspectors” requirements of AS/NZS 1554.3 Clause 10.2. Inspections of the welding shall be in accordance with AS/NZS 1554.3. | PS 27.7.6 | TPI Report | Prior to be encased. 100% Visual, 10% Ultrasonic, and 10% of Fillet by Magnetic. | HP | ENG
4.01.20 | Mechanical couplers and anchors in reinforced concrete | Mechanical couplers and anchors for the jointing of reinforcing steel shall satisfy the requirements of NZS 3101 clauses 8.7.5 and 8.9.1.3, and ISO 15835-1 Steels for the reinforcement of concrete. Only steel Reidbar components meeting the above requirements shall be accepted. | PS 27.7.12.1 | System Certification or Batch Verification. | Prior to use | R | PE
4.01.21 | Fibre Reinforcement | The following proprietary fibres and doses shall be used: • iNFORCE Microforce19 polypropolene fibres – 1.8 kg/m3 • iNFORCE Ultrafiber500 cellulose fibres – 1.8 kg/m3 | PS 21.7.4 | Datasheets | With Mix Designs Submissions | R | PE
4.01.22 | Void Formers | The Contractor shall submit to the Engineer details of the proposed method of forming the voids, including the method of securing the formers in position. | PS 27.5.3.7 | Datasheet and Method | Prior to Pour | HP | ENG
4.01.23 | Permeant Formwork Certification (Void Formers) | Design details, construction drawings and a formwork certificate (PF-T-442) shall be supplied to the Engineer prior to the formwork assembly and at least 14 days prior to concreting of the component, for review, for all permanent formwork proposed to be used. | PS 27.5.3.5 | PF-T-442 Certificate | Prior to Pour | HP | ENG
4.02 | Methodology
4.02.01 | Precast Methodology Submissions | Details of the proposed method of casting, curing, storing, transportation, and erection shall be submitted to the Engineer before commencing manufacture of the mould and precast units. | PS 27.6.1 PS 27.6.6.7 PS 21.5.3 | Methodology and Programme | Prior to Precast | HP | ENG
4.03 | Precast Test Pannels
4.03.01 | Precast Test Panels | The Contractor shall prepare precast test panels for: 1. Fascia with sandblasted design, tinted concrete and fibre reinforcement 2. Column with tinted concrete and fibre reinforcement 3. MSE Wall | PS 21.5.1.1 PS 22.16.5 | Test Panel Approval | Prior to the commencement of the permanent work | HP | ENG
4.04 | Precast Vapour Blasting Materials
4.04.01 | Precast Vapour Blasting Test Panel | A 1.8x1.8m test panel is to be produced for landscape architect and cultural artist approval prior to construction. | PS 21.7.2.1 | Notice | prior to construction | HP | ENG
4.04.02 | Vapour blasted permacolour approval | Vapour blasted area to have permacolour clear concrete sealer or approved alternative. | PS 21.7.2.1 | Notice | prior to use | HP | ENG

## Precast Unit ITP
Precast Unit (Pre, Post, Delivery) ITP
Project: Homer Tunnel
Number and Revision: DS2676-DOW-ITP-CV-0001-Rev B
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 5 – CONSTRUCTION ACTIVITY – PRECAST CONCRETE
5.01 | Concrete Pour
| General Details |  |  | Site Records
Item Name
Pre Pour Date
Concrete Strength (mPa)
Volume (m3)
Mix Design
Additives
5.01.01 | Reinforcement Pre Pour Inspection | Complete a comprehensive Reinforcing inspetion including: Bar Size & Grade, Lap Lengths, Lap Locations, Bar Supports, Anchor embedmen, Steel coating, Bar Spacing, Cover, Steel condition / clean, Starter positions, Anchor position etc. | PS 27.7.10 | Site Records | Each Pour | R | PE
| Formwork has been checked and conforms to the drawings included: | Overall location, Straightness , Bracing & supports , Grout tightness , Cleanliness , Surface finish, Construction joints (position and preparation), Rebate , Contraction joints , Penetrations , Plan dimensions , Formwork oiled , Pour thickness , Angle fillet , Diagonals , Divi nuts tight etc. |  | Site Records
5.01.02 | Pre-Pour Inspection | Complete a comprehensive pre-pour inspection and obtain approval (Inspection or Verbal) from the Engineer prior to pouring. Sign as WP when WSP not inspecting unit and note in comments. | PS 27.6.1 | Signed Pre-Pour | 24 hours’ Notice prior to the casting of any unit | HP / W | ENG
Items to be rectified prior to pour
5.01.03 | Delivery Dockets | The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size. | PS 27.7.11 | Dockets | Each Pour | R | PE
5.01.04 | Slump Testing | Slump tests shall be taken for each delivery of concrete and the results recorded by the Contractor. Slump that that exceeds the tolerance limit in NZS 3109 cl 9.4.2 shall be liable to rejection. | PS 27.4.4.4 | Site Records | Each Pour | R | PE
5.01.05 | Compression Testing | For repetitive small pours undertaken on a regular basis, three standard cylinders shall be made for each of the first five pours of any one type, and thereafter three standard cylinders shall be made for every fifth pour of that type for testing of 28 day compressive strength in an approved laboratory. | PS 27.4.4.3 | Test Results | First five pours of any one type, and thereafter shall be made for every fifth pour of that type | R | PE |  |  | Four Cylinders if one is needed at 7 days
5.01.06 | Precast Prestressed Accelerated Concrete Compression Test | Compression test cylinders, for precast prestressed units subject to accelerated curing by applying heat to the concrete, shall be cast in moulds preheated to the same temperature as the main moulds. After casting the test cylinders shall be placed in a heated enclosure monitored and controlled such that the test cylinder concrete follows the same time - temperature curve as that of the precast units. | PS 27.4.4.8.2 | Test Results | Each Occurrence | R | PE
5.01.07 | Air Content Tests for Air Entrained Concrete | Where air content tests for air entrained concrete is required by this specification, unless otherwise directed by the Engineer, each day during the manufacture and placing of concrete, for each 50m3 of concrete or part thereof produced, one sample shall be taken and subjected to air content testing in accordance with section 9 of NZS 3112: Part 1. All Air Entrained concreted to be tested, as per Table 27.2 | PS 27.4.4.7 | Test Results | Each day, one Set per 50m3 (or part thereof) for each mix placed. | R | PE
5.02 | Post Pour
5.02.01 | Post Pour Inspection | Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, Inserts, Reliefs, Curing, membrane application, and Finish against the drawings. | PS 27.6.6.14 | Site Records | Each Pour Prior to delviery | R | PE
Items to be rectified
5.02.02 | Membrane Curing | The Curing Membrane shall be applied as per the methodology with the approval of the Engineer. | PS 27.4.8.2 | Site Records | Each Occurrence | R | PE
5.02.03 | Stripping and Lifting | No formwork shall be stripped or the panel lifted until the minimum strength has been reached as per the drawings and methodology. Alternativly an approved curing time can be used | PS 27.4.4.8.1 | Schmitt Hammer or Apporved Curing Time | Prior to Stripping and Lifting | R | PE
5.02.04 | Defective Concrete Finishes | Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer. | PS27.4.9.1 / NZS 3114 | NCR | Prior to non Minor Repair | HP | ENG
| McIntosh Precast QA | Attach McIntosh Precast QA |  |  |  | R | PE
5.04 | Delivery
5.04.01 | Delivery Inspection | Following delivery, each precast item shall be inspected for conformance and delivery damage. | PS 27.6.6.14 | Delivery Record | Each Delivery | R | PE
Items to be rectified

## Precast Vapour Blasting ITP
Precast Vapour Blasting ITP
Project: Homer Tunnel
Number and Revision: DS2676-DOW-ITP-CV-0001-Rev B
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 5 – CONSTRUCTION ACTIVITY – PRECAST CONCRETE
5.03 | Urban design feature on fascia panel
5.03.01 | Vapour Blasting Method Statement | Contractor to provide method statement and shop drawings to landscape architect, cultural artist and Engineer for approval prior to commencing work | PS 21.7.2.1 | Methodology | Prior to Commencing Work | HP | ENG
5.03.02 | Blasting depth | Blasting depth not to exceed 5mm in order to avoid compromising reinforcing cover. | PS 21.7.2.1 | Site Records | Each Panel | R | PE
5.03.03 | Permacolour Application | Vapour blasted area to have permacolour clear concrete sealer or approved alternative applied within the blasted area only. | PS 21.7.2.1 | Site Records | Prior to sealing | R | PE
5.03.04 | Panel Cleaning | Prior to sealing of pattern and application of anti-graffiti coating, blasted areas are to be cleared of blasting agent before sealants applied, surface to be washed and free of marks. | PS 21.7.2.1 | Site Records | Prior to sealing | R | PE