## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Module Assembly |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Module Assembly | 0673fb12-2d02-46c3-99c9-aca3360e16a1
checkpoint-group |  |  | section | Module Assembly Inspection
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Locate floor cassette on the podium
text | 9030277f-fecd-5673-ab13-192642003f24 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Install all external walls, internal walls, and ceiling cassette as per Manufacture plan. Support/Prop necessary.
checkpoint-status |  |  | checkpoint | Fire sealant/acoustic installed as per approved plan and manufacturer specification, all edges to wall, floor and ceiling and provide photo. Part of Passive Fire System
text | 480a2f0f-afe9-5641-8245-f67730318115 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify installed floor, ceiling, and walls as per Manufacture plan.
checkpoint-status |  |  | checkpoint | Check and verify all structural fixings as per Manufacture plan.
checkpoint-status |  |  | checkpoint | Hold point: photo required an signed off by Team leader before going to next step
holdpoint |  |  | signoff | Hold point: photo required an signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_20.03.23_Structure - Roof Assembly |  |  |  |  | Yes | EGM_Ver1.0_20.03.23_Structure - Roof Assembly | 0b5d2df9-a7e6-4eeb-a4ee-230939ef9806
checkpoint-group |  |  | section | Roof Assembly Inspection
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install roof framing/trusses/purlins as per Manufacture plan
text | bffa5c2f-1770-5d23-abe9-becab650ddfd |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Install all structural fixings as per Manufacture plan
text | dd1df8fb-1e6f-5fa0-b093-a55882d001f9 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify roof framing treatment and grade as per plan
checkpoint-status |  |  | checkpoint | Check and verify bracing as per plan: roof plane braces, fixings and tensioners, roof space braces and fixings
checkpoint-status |  |  | checkpoint | Check and verify roof pitch, overhang and truss/rafter sizes & spacings as per plan
checkpoint-status |  |  | checkpoint | Check and verify roof ply sheet, centres and fixings as per plan
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Exterior - Waterproof Membrane |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Exterior - Waterproof Membrane | 103861d6-2c81-4067-b616-e925589e8b72
checkpoint-group |  |  | section | Internal - Waterproof Membrane
checkpoint-status |  |  | checkpoint | Check and review approved plan & specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Check ply roof substrate prior to application of waterproofing membrane, as accepted
checkpoint-status |  |  | checkpoint | Install waterproofing membrane as per manufacturer specification, provide photo
text | 39c6e1cf-b5fb-5f8f-a462-73031a8ca7a8 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by waterproofing membrane applicator
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Document/Record Collection |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Document/Record Collection | 1cc2ac1b-33d4-461e-b016-4da1f51c5677
checkpoint-group |  |  | section | Document / Attachment / Link / Photo
checkpoint-status |  |  | checkpoint | Records
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_ Electrical & Mechanical - Distribution Board |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_ Electrical & Mechanical - Distribution Board | 1f19de6e-92f5-48c1-8600-d7e73a130215
checkpoint-group |  |  | section | Electrical & Mechanical Distribution Board Inspection
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install Distribution Board as per approved electrical services plan
checkpoint-status |  |  | checkpoint | Install all electrical cabling as per approved electrical services plan
checkpoint-status |  |  | checkpoint | Check and verify installed switchgear valves as per plan
checkpoint-status |  |  | checkpoint | All cables are noted correctly
checkpoint-status |  |  | checkpoint | Ensure all screws are torqued to correct specification
checkpoint-status |  |  | checkpoint | Visual inspection: Cable protection/Support/Fixing are in good condition without obvious damage
text | 36252189-99e8-5914-8ce5-d3b792a67e9b |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_08.09.23_CEILING & ITEMS IN MODULE PHOTOS/Record Collection/ |  |  |  |  | Yes | EGM_Ver1.0_08.09.23_CEILING & ITEMS IN MODULE PHOTOS/Record Collection/ B | 2447312b-a6c1-4045-a31c-aeb745ab2768
checkpoint-group |  |  | section | Document / Attachment / Link / Photo
checkpoint-status |  |  | checkpoint | Records
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Second fix electrical and mechanical_Module Assembly |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Second fix electrical and mechanical_Module Assembly | 368f8306-dd08-4d95-85c5-f23f875ad6ac
checkpoint-group |  |  | section | Second fix Electrical & Mechanical
checkpoint-status |  |  | checkpoint | Check and review as per electrical and mechanical services Plan and provide picture of the respective services plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Installed distribution board.
text | fa17c8ea-fe5b-5911-8bc1-5608840a4914 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Install all power points and light switches.
checkpoint-status |  |  | checkpoint | Install all lights.
checkpoint-status |  |  | checkpoint | Install heat pumps.
checkpoint-status |  |  | checkpoint | Install heat towel rail.
checkpoint-status |  |  | checkpoint | Install mechanical ventilation/Bathroom/Laundry/Kitchen.
checkpoint-status |  |  | checkpoint | Install oven/hob.
checkpoint-status |  |  | checkpoint | Install wall heaters.
checkpoint-status |  |  | checkpoint | Check, by contractor smoke alarm, installed - completed
checkpoint-status |  |  | checkpoint | Check, by contractor sprinkler system, installed - completed
text | 63f54192-4ea0-5f98-8eb0-b052057806a1 |  | textbox | Operator Name:
checkpoint-group |  |  | section | Electrical Testing (Inform electrician to carry out the required electrical testing for all above installation)
checkpoint-status |  |  | checkpoint | Electrical Testing-Earth Resistance and Continuity, Insulation Resistance, Polarity and Phase, Correct Circuit connection, etc.
checkpoint-status |  |  | checkpoint | Visual inspection: Cable protection/Support/fixing and damages
checkpoint-status |  |  | checkpoint | RCD's Test
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_11.09.23_POST LANDED MODULE PHOTOS/Record Collection/ |  |  |  |  | Yes | EGM_Ver1.0_11.09.23_POST LANDED MODULE PHOTOS/Record Collection/ | 39e0cb99-02d7-4034-a26e-f10eefeb3080
checkpoint-group |  |  | section | Document / Attachment / Link / Photo
checkpoint-status |  |  | checkpoint | Records
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Exterior - Wraps, penetrations, windows/doors and flashings |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Exterior - Wraps, penetrations, windows/doors and flashings | 484c417a-2554-4638-80e1-0670eec0b7f4
checkpoint-group |  |  | section | Wrap (RAB)
checkpoint-status |  |  | checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install balance RAB.
text | e8c43f90-1791-576d-872f-f9bde27a1676 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Penetration
checkpoint-status |  |  | checkpoint | Locate and cut out all penetrations as per approved plans and specifications.
checkpoint-status |  |  | checkpoint | Install all penetrations.
text | ad341b41-6cc6-5312-95ff-6970310d4918 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Windows and doors
checkpoint-status |  |  | checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install all windows and doors as per approved plans and manufacture specifications.
text | 4efa796f-e0be-50e1-b556-958fc8b6dbdc |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Flashings and tapes
checkpoint-status |  |  | checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install all flashing tapes/Sealants to RAB joints, windows, doors, penetrations, etc., as required.
text | f220fed9-c685-5145-820b-f1c0a8bf2f78 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-status |  |  | checkpoint | Install all flashings: Interstorey, Int/Ext corner, cavity closer.
text | 31673056-72a4-5159-b00f-236226d9c9ee |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Structure ITP |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Structure ITP | 4ee23f52-555c-4d84-a7ff-9ac7ee57ff09
checkpoint-group |  |  | section | 1 - ITP Review and Approval Inspection
checkpoint-status |  |  | checkpoint | ITP reviewed, approved and attached
checkpoint-group |  |  | section | 2 - Preparation
checkpoint-status |  |  | checkpoint | Drawings review and approval
checkpoint-status |  |  | checkpoint | Project specification review and approval
checkpoint-status |  |  | checkpoint | Equipment calibration
checkpoint-status |  |  | checkpoint | Personnel certifications & Licenses
checkpoint-status |  |  | checkpoint | Staff training
checkpoint-status |  |  | checkpoint | Manufacture record and inspection report template
checkpoint-group |  |  | section | 3 - Material Management
checkpoint-status |  |  | checkpoint | Material list review and approval
checkpoint-status |  |  | checkpoint | Incoming material check
checkpoint-status |  |  | checkpoint | Material storage
checkpoint-status |  |  | checkpoint | Material Handling and traceability
checkpoint-group |  |  | section | 4 - Manufacture
checkpoint-status |  |  | checkpoint | 4.1 - Floor Cassette
boolean | 62ba38a0-881b-5553-b529-832d703b38a8 |  | tickbox | Structural Framing & Fixings
boolean | fe76ef3b-3703-524d-babd-f53befd1b32d |  | tickbox | Floor sheeting
checkpoint-status |  |  | checkpoint | 4.2 - External Wall / Marriage Wall / Intertenancy Wall
boolean | fe3202b5-6020-5083-a8d1-f1ac2ae5b894 |  | tickbox | Structural Framing & Fixings
boolean | 2a149c56-b2a7-5005-a60b-6ad05f1b5a57 |  | tickbox | Structural Sheet Bracing
boolean | 6d25e04e-73e2-54a8-baab-818d7d3341f1 |  | tickbox | Fire Lining 1st Layer
boolean | b2dc72a3-932b-587c-94da-648655b18102 |  | tickbox | Fire Lining 2nd Layer
checkpoint-status |  |  | checkpoint | 4.3 - Internal wall
boolean | 2bfeb47c-fedb-5d3e-a42a-8906d1b5ef7d |  | tickbox | Structural Framing & Fixings
boolean | 45c1e4aa-4d62-5653-bc42-202238fe6c12 |  | tickbox | Standard/Single Layer Gib board
checkpoint-status |  |  | checkpoint | 4.4 - Ceiling cassette
boolean | b9c3096d-e897-52f9-a4e0-77716d3d49c5 |  | tickbox | Structural Framing & Fixings
boolean | fa345759-dcdb-5e79-bba8-3d2a6941be79 |  | tickbox | Structural Sheet Bracing as required
boolean | be075a6c-b1d4-5fb5-8467-80e308125208 |  | tickbox | Fire Lining 1st Layer
boolean | 881ee9c3-6172-565d-8f0a-58d0738b6016 |  | tickbox | Fire Lining 2nd Layer
checkpoint-status |  |  | checkpoint | 4.5 - Module Assembly
boolean | b4fac07e-7892-58bb-88d2-540bdbbc63b8 |  | tickbox | Module Assembly
boolean | 605b51ce-f9da-5f36-8c8f-bfa18d7521f3 |  | tickbox | Structural Fixing & Services as per manufacture plan
checkpoint-status |  |  | checkpoint | 4.6 - Roof Assembly
boolean | 4328f145-dfc2-5d13-966c-fbd4748eb495 |  | tickbox | Roof Assembly
boolean | 7d917dfb-b099-54bd-a785-b60e3c1394df |  | tickbox | Structural framing/trusses and Fixing
checklist-sectioned |  |  | checklist | EGM_Ver1.1_17.04.23_ Pre-Assembly_Lining Materials |  |  |  |  | Yes | EGM_Ver1.1_17.04.23_ Pre-Assembly_Lining Materials | 5a9b5333-9b0f-4cf0-b4bc-aadd561caa4f
checkpoint-group |  |  | section | Pre-Assembly Inspection Inspection
checkpoint-status |  |  | checkpoint | Check and review as per approved Lining Plan Ply & Plasterboard GIB Plan, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Station - Mark up correct, as per approved Manufacture Plan
checkpoint-status |  |  | checkpoint | Station - lining sheet 1 (typically Ply), as per approved Lining Manufacture Plan
checkpoint-status |  |  | checkpoint | Station - lining sheet 2 (typically Gib Plasterboard), as per approved Lining Manufacture Plan
checkpoint-status |  |  | checkpoint | Check nailing pattern - framing as per specification
text | ab2174c3-338c-5a57-b0cd-75861687d9b4 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Passive Fire Module Assembly |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Passive Fire Module Assembly | 5f3c96ea-a275-4134-aa4b-4e87cba3b3f0
checkpoint-group |  |  | section | Module Assembly
checkpoint-status |  |  | checkpoint | Check and review as per approved passive fire report, and provide picture of the respective report which clarify shows page number
checkpoint-status |  |  | checkpoint | Install fire dampers, collars and sealants as per manufacturer specifications.
text | 433c6683-f087-5a0c-9d05-61554d7f8dba |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by fire penetration contractor, tags, before going to next step
checkpoint-group |  |  | section | Fire Seal Inspection
checkpoint-status |  |  | checkpoint | Install fire sound and seal to perimeter as per approved plan, manufacturer system specification and provide photos
checkpoint-status |  |  | checkpoint | Check and verify the Fire Sealant installed, as per approved plans
text | c2f958eb-1ac8-55cd-b5d8-1157bb97b03b |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check fire rated linings; materials and passive fire protection measures as per GIB Fire rate system GWTLE 60A
checkpoint-status |  |  | checkpoint | Check fire rated linings; materials and passive fire protection measures as per GIB Fire rate system GBUW 30A
checkpoint-group |  |  | section | Fire Door Inspection
checkpoint-status |  |  | checkpoint | Fire Door install as per approved plan and manufacturer specification and provide photos
text | 7c64de8c-2f2b-54a7-892d-be1ba2b51e51 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by fire door contractor, tags, before going to next step
checkpoint-group |  |  | section | Final Passive Fire Inspection
checkpoint-status |  |  | checkpoint | Visual inspection to check installation installed to match manufacture specifications and approved design
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by fire contractor before going to next step
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.1_17.04.23_ Saw Cut Production |  |  |  |  | Yes | EGM_Ver1.1_17.04.23_ Saw Cut Production | 63da7bab-d349-49e6-a02b-f588fbf059ed
checkpoint-group |  |  | section | Saw Cut Production Inspection
checkpoint-status |  |  | checkpoint | Check and review as per approved Saw Cutting List Plan, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Station - Correct Cutting File, as per approved manufacture plan
checkpoint-status |  |  | checkpoint | Station - Cutting lot completed, checked, and as per approved manufacture plan
text | 5132c23d-8d75-55fa-8a28-e6338135b1e5 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_ Electrical & Mechanical - First Fix |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_ Electrical & Mechanical - First Fix | 6953a05d-da32-4b5e-9402-3b0aa83edecf
checkpoint-group |  |  | section | Electrical & Mechanical Penetrations
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Locate and cut out all penetrations as per fabrication plan
text | 143bf4fb-8e22-5618-9725-6bf36c4ec0fb |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify all penetrations as per fabrication plan
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_RFI_Corrective Action |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_RFI_Corrective Action | 6cbe255a-1948-407c-ba74-9b0541c8c59c
checkpoint-group |  |  | section | RFI_CA Reporting
checkpoint-status |  |  | checkpoint | Refer to approved plan & specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Report Issue, description
text | 49be6b29-5521-59a5-bbf8-a1a89e2f7405 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team Leader
checkpoint-status |  |  | checkpoint | Outcome & solution implemented
text | f30c7bda-32f1-5b25-9a87-dc48a1154b0d |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team Leader
checklist-sectioned |  |  | checklist | EGM_Ver1.3_01.06.23_Structure - EW / MW / CW / IW / TW |  |  |  |  | Yes | EGM_Ver1.3_01.06.23_Structure - EW / MW / CW / IW / TW | 6f0e4fc7-9506-4f39-a906-900df3abaada
checkpoint-group |  |  | section | Structural Framing and Preline Inspections
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install all wall framing elements and fixing as per Manufacture plan
text | 55160e75-408a-51eb-adc3-6cf364f03b89 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and Verify sizes, spacings, treatment, grade as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | 3e7bd58a-171e-5bab-a9fd-862ea5c3e280 |  | textbox | Diagonal #1:
text | f5d13af3-3e0e-50ec-bb22-d48f0c204d3e |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify installed elements as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify installed structural fixings as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify installed nogs/blockings as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check RothoBlaas bracket is lining up with pre-drilled holes in the bottom plate, as accepted
checkpoint-status |  |  | checkpoint | Check RothoBlaas bracket is lining up with pre-drilled holes in the top plate, as accepted
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | signoff
checkpoint-group |  |  | section | Structural Sheet Bracing
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install bracing and fixing as per Manufacture plan
text | be9c360a-eee4-523a-9a7c-5615df97cccf |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | 3aa38a18-eb0a-5877-8287-86ad598b1941 |  | textbox | Diagonal #1:
text | 6f6a378b-b196-56d0-98f5-53adcce7af83 |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify installed bracing as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check RothoBlaas bracket in the top & bottom plate pre-drilled hole has NO screw or nail passing through, as accepted
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Fire Lining 1st Layer
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install 1st Layer and fixing as per Manufacture Plan
text | 7361bb75-e0f9-5cd9-a5f1-ceeb70de7731 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify installed layer edges in correct locations as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per Manufacture plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Module Assembly - Penetrations |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Module Assembly - Penetrations | 7070dccf-65e4-4db5-91b1-c08031d6ab24
checkpoint-group |  |  | section | Module Assembly - Penetrations
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Locate and cut out all penetrations as per Manufacture plan
text | 564c107d-9bc0-5327-b49a-b4b79bb1945a |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify all penetrations as per Manufacture plan
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.1_17.04.23_ Pre-Assembly_Pilot Holes |  |  |  |  | Yes | EGM_Ver1.1_17.04.23_ Pre-Assembly_Pilot Holes | 7099f88c-8a0d-410d-9c92-0b78a404faf9
checkpoint-group |  |  | section | Pre-Assembly Inspection Inspection
checkpoint-status |  |  | checkpoint | Check and review as per approved template pilot hole manufacture Plan, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Station - Mark up correct, as per correct template
checkpoint-status |  |  | checkpoint | Station - Pilot Holes, as per specification and tolerance
text | 3b4fa4f7-967d-5a68-96e4-0e6970e80227 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_29.03.23_Internal - Gib Stopping & Painting Inspection |  |  |  |  | Yes | EGM_Ver1.0_29.03.23_Internal - Gib Stopping & Painting Inspection | 7899b12f-cede-4c8e-854c-3da53702533d
checkpoint-group |  |  | section | Gib stopping & Painting
checkpoint-status |  |  | checkpoint | Install internal Gib stopping as per approved plans
text | 94453bb8-2bd7-516f-a131-48abe257985e |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify the installed GIB stopping as per approved plans
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | 1st and 2nd Painting
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Complete the 1st and 2nd internal painting as per approved plans and manufacture specifications
text | 9aaff05c-2284-5382-8e8e-b4190488337f |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check the painting
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Interior - Waterproof Membrane & Tiling_Module Assembly |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Interior - Waterproof Membrane & Tiling_Module Assembly | 7bd49b42-fe2f-4f9b-8c2b-da8542132baa
checkpoint-group |  |  | section | Internal - Waterproof Membrane
checkpoint-status |  |  | checkpoint | Check and review approved plan & specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Check substrate wall and floor prior to application of waterproofing membrane, as accepted
checkpoint-status |  |  | checkpoint | Install waterproofing membrane as per manufacturer specification, provide photo
text | b33766ec-0c91-5e05-9995-2cab41d87685 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by waterproofing applicator before going to next step
checkpoint-status |  |  | checkpoint | Install tiling and grout to areas as per approved plans
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.1_21.04.23_Plumbing & Drainage - Floor Cassette/ Assembly Area |  |  |  |  | Yes | EGM_Ver1.1_21.04.23_Plumbing & Drainage - Floor Cassette/ Assembly Area | 898798ae-6836-4b57-ae53-993e6a8e309f
checkpoint-group |  |  | section | Plumbing & Drainage Inspection
checkpoint-status |  |  | checkpoint | Check and review as per approved plumbing and drainage services Plan, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install verified pipework as per approved plans and manufacture instructions
text | 01f47780-66f2-51bd-86b4-f930e00df1ca |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify foul water pipe are gradients compliant
checkpoint-status |  |  | checkpoint | Complete air test to AS/NZS3500
checkpoint-status |  |  | checkpoint | Complete water test to AS/NZS3500
text | 28ae73ca-77fc-5e97-8fb6-9649d033261d |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by before going to next step
checkpoint-group |  |  | section | First Fix Plumbing and Drainage
checkpoint-status |  |  | checkpoint | Install pipes as per approved plans and manufacture instructions.
text | 439e9921-83c0-5d33-808a-e2dca085dc24 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Visual inspection to check Pipe lengths horizontal and vertical spacing as per approved plans
checkpoint-status |  |  | checkpoint | After installation of inner wall water pipework, complete water test to 500Kpa for 30mins (Provide Photo)
checkpoint-status |  |  | checkpoint | After plasterboard (GIB) installation, complete pressure test water pipework to 500Kpa for 30mins (Provide Photo)
checkpoint-status |  |  | checkpoint | Hold point: photo required on digital level of all pipes' runs and signed off by Plumbing team leader before going to next step
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checkpoint-group |  |  | section | Plumbing and Drainage Final Inspection
checkpoint-status |  |  | checkpoint | Check and review as per approved plumbing and drainage services Plan, refer to as per previous EGM_Plumbing & Drainage Inspection- Floor Cassette/ Assembly Area
checkpoint-status |  |  | checkpoint | Station - Pressure test completed Module with mains pressure to 500Kpa Max.
text | 3fafac83-4258-5431-87cb-a05b9a23e066 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | SW pipework flood test, visual check under floor of module for any leaks, provide photos.
checkpoint-status |  |  | checkpoint | Mains Pressure water test all fixtures and fittings for correct operation and visual check for any leakage, (provide photos as or if required)
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_29.03.23_Internal/Doors & Trims/Hardware/Kitchen & Bathroom Joinery - Module Assembly |  |  |  |  | Yes | EGM_Ver1.0_29.03.23_Internal/Doors & Trims/Hardware/Kitchen & Bathroom Joinery - Module Assembly | bbf8d21b-bdc7-42b5-8a5f-52b9ada2656f
checkpoint-group |  |  | section | Internal - Doors & Trims/Hardware/Kitchen & Bathroom Joinery
checkpoint-group |  |  | section | Door and trims
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications
checkpoint-status |  |  | checkpoint | Install all internal doors and trims
text | a0aff9c0-918b-5340-9846-bcd01168a6f7 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Install all internal doors and trims as per approved plans and manufacture specifications.
checkpoint-status |  |  | checkpoint | Hold point
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Hardware
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Complete all hardware as per approved plans and manufacture specifications.
text | 39191a73-1789-5863-b41d-b8a746389230 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Kitchen and bathroom joinery install
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install kitchen and bathroom joinery as per approved plans and manufacture specifications.
text | d39059c8-932c-58ae-b3f2-9b8e391bbc01 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Electrical First Fix Part 2_Module Assembly |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Electrical First Fix Part 2_Module Assembly | bd368837-7022-4611-8a14-46239c084b76
checkpoint-group |  |  | section | First Fix Part 2 Electrical and Mechanical
checkpoint-status |  |  | checkpoint | Check and review as per electrical and mechanical services Plan and provide picture of the respective services plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install all flush boxes as per electrical services plan
text | e173b003-14e8-5991-8100-cdbd0534d634 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Confirm the fire rated pads of flush boxes have been installed properly
checkpoint-status |  |  | checkpoint | Install all electrical conduit and draw wires as per electrical services plan
text | 6f637137-1977-5078-8c43-a8705a7d189a |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Install all electrical cablings as per electrical services plan
text | ba697d91-7671-5d31-92da-d303a6f2075f |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Apply fire sealant around cut-outs if needed
text | d1c29d9a-6a6a-5e1b-b0bd-47cd35c969e9 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify installed elements as per electrical services plan
checkpoint-status |  |  | checkpoint | Visual inspection: Cable protection/Support/fixing and damages
checkpoint-status |  |  | checkpoint | Check and verify fire sealants have been applied
holdpoint |  |  | signoff | Hold point: photo required and signed off by Electrical team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_29.03.23_Floor Covering - Module Assembly |  |  |  |  | Yes | EGM_Ver1.0_29.03.23_Floor Covering - Module Assembly | ca75988c-bf58-4bff-a59d-fcf6361e82d2
checkpoint-group |  |  | section | Contractor - Floor Covering
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install all floor coverings as per approved plans and manufacture specifications.
checkpoint-status |  |  | checkpoint | Install floor protection, completed (as required)
text | 2dbc3aa8-a6c2-5ed8-b650-4e79bc842eeb |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Plumbing & Drainage - Module Assembly |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Plumbing & Drainage - Module Assembly | d02a870c-f3e4-4d99-9a08-77cd88e37076
checkpoint-group |  |  | section | Plumbing and Drainage Inspection - Module Assembly
checkpoint-status |  |  | checkpoint | Check and review as per approved plumbing and drainage services Plan, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install pipes as per approved plumbing and drainage services Plan
checkpoint-status |  |  | checkpoint | Install connections as per approved plumbing and drainage services Plan
checkpoint-status |  |  | checkpoint | Station - Pressure test wingback as per AS/NZS 3500, provide photo
checkpoint-status |  |  | checkpoint | Station - Pressure test after plasterboard install, as per AS/NZS 3500, provide photo
text | 5c89fd80-7bf3-5d79-a718-43f34a74221f |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | SW pipework flood test, provide photo
checkpoint-status |  |  | checkpoint | Hot and Cold Water test for 30mins at 1550KPa as per AS/NZS 3500
checkpoint-status |  |  | checkpoint | Hold point: photo required of pressure gauge and signed off by Plumbing team leader before going to next step
checkpoint-status |  |  | checkpoint | Pressure gauge will be kept until second fix
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.1_17.04.23_Structure/Module Assembly |  |  |  |  | Yes | EGM_Ver1.1_17.04.23_Structure/Module Assembly | d09952e1-fe4d-4c1b-9f92-64285a76f561
checkpoint-group |  |  | section | Module Assembly Inspection
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Locate floor cassette on the podium
text | 36054082-14e3-5365-9909-77c1bd3b682f |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Install all external walls, internal walls, and ceiling cassette as per Manufacture plan. Support/Prop necessary.
checkpoint-status |  |  | checkpoint | Fire sealant/acoustic installed as per approved plan and manufacturer specification, all edges to wall, floor and ceiling and provide photo. Part of Passive Fire System
text | 60d05e65-fb26-5183-a669-e35ef635689c |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify installed floor, ceiling, and walls as per Manufacture plan.
checkpoint-status |  |  | checkpoint | Check and verify all structural fixings as per Manufacture plan.
checkpoint-status |  |  | checkpoint | Check RothoBlaas bracket is lining up with pre-drilled holes in the bottom plate, as accepted
checkpoint-status |  |  | checkpoint | Check RothoBlaas bracket is lining up with pre-drilled holes in the top plate, as accepted
checkpoint-status |  |  | checkpoint | Check RothoBlaas bracket in the top & bottom plate pre-drilled hole has NO screw or nail passing through, as accepted
text | 63589952-89bc-5461-845b-95ae1803efd7 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required an signed off by Team leader before going to next step
holdpoint |  |  | signoff | Hold point: photo required an signed off by Team leader before going to next step
checkpoint-group |  |  | section | Module Assembly - Penetrations
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Locate and cut out all penetrations as per Manufacture plan
text | c441eff9-ddb7-58ef-9c4e-01ad46c56e88 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify all penetrations as per Manufacture plan
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_ Electrical & Mechanical - Smoke Alarm_Sprinkler System |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_ Electrical & Mechanical - Smoke Alarm_Sprinkler System | d11c2a22-be7c-43e2-85aa-510c517eff64
checkpoint-group |  |  | section | Electrical & Mechanical Smoke Alarms/Sprinkler System Inspection
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install smoke alarms as per approved electrical services plan
checkpoint-status |  |  | checkpoint | Install all smoke alarm cabling as per approved electrical services plan
text | 6fe65c83-6ebb-5170-a72b-5e410831530c |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Electrical Contractor before going to next step
checkpoint-status |  |  | checkpoint | Install sprinkler system as per approved Engineer design plan
text | f82e3f6d-8cd5-5e4c-8416-b019fc4c78f0 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.1_29.03.23_Interior Fitout - Module Assembly |  |  |  |  | Yes | EGM_Ver1.1_29.03.23_Interior Fitout - Module Assembly | d4868e3d-6b66-4063-89c0-94365c328d05
checkpoint-group |  |  | section | Interior Fit Out Inspection
checkpoint-group |  |  | section | Plumber to confirm first fix plumbing complete
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Plumbing team leader before going to next step
holdpoint |  |  | signoff | Hold point: signed off by Team leader before going to next step
checkpoint-group |  |  | section | Electrician to confirm first fix electrical complete
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
holdpoint |  |  | signoff | Hold point: signed off by Team leader before going to next step
checkpoint-group |  |  | section | Complete internal wall lines
checkpoint-status |  |  | checkpoint | Complete all internal wall lines as per approved plans and manufacture specifications.
text | 3661846f-04c2-5b2b-8584-97448a6e63bf |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Postline inspection photos required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Complete all passive fire requirements
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by passive fire contractor
holdpoint |  |  | signoff | Hold point: signed off by Team leader before going to next step
checkpoint-group |  |  | section | Mechanical ducts and ventilation
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
holdpoint |  |  | signoff | Hold point: signed off by Team leader before going to next step
checkpoint-group |  |  | section | False ceiling and bulkheads
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install all false ceiling and bulkheads as per approved plans and specifications.
text | 2a695486-5154-5a7d-b307-04cb4684bb4f |  | textbox | Operator Name:
checkpoint-group |  |  | section | Acoustic floor
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install acoustic floor as per approved plans and manufacture specifications.
checkpoint-status |  |  | checkpoint | Install all batten and cradles and sound proofing as per manufacturer's specification
checkpoint-status |  |  | checkpoint | Install Fire fire sealant to perimitter
text | ba53d0dc-bacf-5123-896f-aa72abf993df |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Tiling and waterproofing: bathroom laundry Kitchen
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Complete all waterproofing membrane to tile areas as per approved plans and manufacture specifications.
text | 1075bfec-9e41-59ea-ac06-7b567726ac1f |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Plumbing
checkpoint-status |  |  | checkpoint | Plumber to confirm second fix plumbing complete
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Plumbing team leader before going to next step
holdpoint |  |  | signoff | Hold point: signed off by Team leader before going to next step
checkpoint-group |  |  | section | Electrical
checkpoint-status |  |  | checkpoint | Electrician to confirm second fix electrical complete
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
holdpoint |  |  | signoff | Hold point: signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.1_28.03.23_Structure - / CE / Ceiling Cassette Inspection |  |  |  |  | Yes | EGM_Ver1.1_28.03.23_Structure - / CE / Ceiling Cassette Inspection | d62f8213-2b37-49af-9daf-a060a52467a0
checkpoint-group |  |  | section | Structural Framing and Preline Inspection
checkpoint-status |  |  | checkpoint | Check and review correct manufacture plan and provide picture of the respective manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install all ceiling framing elements and fixings as per manufacture plan
text | 4b005796-2c81-5a7f-84d3-ea6c85d59bf3 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and Verify sizes, spacings, treatment, grade as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | 7ccb4c4b-21bd-5efe-bb57-171e744c518e |  | textbox | Diagonal #1:
text | 3b00d59e-bf2e-5332-b682-33fb1a5a7ffd |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify installed structural fixings as per manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify installed nogs/blockings as per manufacture plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | signoff
checkpoint-group |  |  | section | Fire Lining 1st Layer
checkpoint-status |  |  | checkpoint | Check and review correct manufacture plan and provide picture of the respective manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install 1st Layer and fixing as per Manufacture plan
text | 4344f1cb-84d2-56e4-aab4-ca4ef0361519 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify installed layer edges in correct locations as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per Manufacture plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | signoff
checkpoint-group |  |  | section | Fire Lining 2nd Layer
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install 2nd Layer and fixing as per Manufacture plan
text | 732f3925-d800-555f-ab2a-76212e22c5b7 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify installed layer edges in correct locations as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per Manufacture plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | signoff
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.02.23_Structure - / F / Floor Cassette Inspection |  |  |  |  | Yes | EGM_Ver1.0_22.02.23_Structure - / F / Floor Cassette Inspection | d8fc0431-f7ef-462f-aef0-08f219089266
checkpoint-group |  |  | section | Structural framing and Preline Inspection
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install all floor framing elements and fixings as per Manufacture plan
text | 690768ee-2a69-5845-a47c-84aad6ea30c0 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and Verify sizes, spacings, treatment, grade as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | 1a8c3d65-db02-50a9-a6cc-221c7dfb7c02 |  | textbox | Diagonal #1:
text | 1278bfab-ea04-5ebd-8845-625e5531f91f |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify installed elements as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify installed structural fixings as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify installed nogs/blockings as per Manufacture plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | signoff
checkpoint-group |  |  | section | Floor sheeting
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install floor sheeting and fixing as per Manufacture plan
text | 05e6d62f-3761-565d-9fb4-45601adfdf31 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | 7722d850-9542-5f78-bdb7-559f560545f1 |  | textbox | Diagonal #1:
text | 4a58799a-1d0e-51ef-9cd9-f77fdadd84c8 |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify sheet edges in correct locations as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify installed fixings as per Manufacture plan
checkpoint-status |  |  | checkpoint | Hold point: Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | signoff
checklist-sectioned |  |  | checklist | EGM_Ver1.1_29.03.23_Exterior - RAB, Insulation, penetrations, windows/doors & Opening Flashings |  |  |  |  | Yes | EGM_Ver1.1_29.03.23_Exterior - RAB, Insulation, penetrations, windows/doors & Opening Flashings | ecf16cdc-9b89-4677-a745-fe3f377f9133
checkpoint-group |  |  | section | Wrap (RAB)
checkpoint-status |  |  | checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install balance RAB and install fixings as per manufacturer specification.
checkpoint-status |  |  | checkpoint | Install all RAB joint tapes/Sealants to RAB joints, windows, doors, penetrations, etc., as required.
text | d5ea7b52-f4c3-531e-b91a-9824e622aa60 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install as per manufacture plan.
checkpoint-status |  |  | checkpoint | Attach Insulation Certificate.
text | 41bfbcba-89a2-56a3-9620-3d1012368c29 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Opening Flashing Tapes & Sill Support
checkpoint-status |  |  | checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install opening flashing tapes to Sill, Head, Jamb, window/door etc., as required.
text | 3e9bb681-6403-5bed-b7d5-cc88b92443e0 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-status |  |  | checkpoint | Install with SS screw fixing all sill supports window/door etc., as required.
text | ee6e4a03-8213-5d7a-a421-60c3ed0b636c |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Penetration
checkpoint-status |  |  | checkpoint | Locate and cut out all penetrations as per approved plans and specifications.
checkpoint-status |  |  | checkpoint | Install all penetrations, as required.
text | c3d3bfd6-5fe0-5cc8-897d-1bbfd1e4bfee |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Windows and doors
checkpoint-status |  |  | checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install all windows and doors as per approved plans and manufacture specifications.
text | bbe4e1a1-da5f-51ad-9634-6c591384d782 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Packaging & Shipping |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Packaging & Shipping | ed362f65-87ce-4418-96cf-70259757a8a7
checkpoint-group |  |  | section | Internal Fixtures and Fittings Packaging
checkpoint-status |  |  | checkpoint | Toilet: Cistern fixed by using PET fridge tape
checkpoint-status |  |  | checkpoint | Shower: Shower head protected by wrapping it with EPE foam sheet membrane
checkpoint-status |  |  | checkpoint | Cabinets and Doors: All cabinet doors, mirror cabinet doors and drawers fixed using PET fridge tape.
checkpoint-status |  |  | checkpoint | Bathroom: Bathroom door and Shower door will be fixed with PET fridge tape.
checkpoint-status |  |  | checkpoint | Place Desiccant and Hygrometer inside the module.
text | 3aafe19b-0865-54af-9f77-285bb7bb9289 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required an signed off by Team leader before going to plumbing
checkpoint-group |  |  | section | External Protective Cover
checkpoint-status |  |  | checkpoint | Use protective film to cover a module completely
checkpoint-status |  |  | checkpoint | Use heat Gun to seal the protective film.
text | 3c00d722-7a52-5c9d-95cc-3b73503581f9 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Make sure there are no gaps in the film
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before moving a Module to a Storage area.
checkpoint-group |  |  | section | Lifting and loading
checkpoint-status |  |  | checkpoint | 18-24T Forkhoist will be used to load a module onto a Specialised Transport Vehicle
checkpoint-status |  |  | checkpoint | Tie the module to the Transport Vehicle, using strops or with the equipment attached to the Vehicle
text | 72523434-5a47-5f08-bdd8-08872c6341cf |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Make sure the module is correctly sitting on the Transport vehicles
checkpoint-status |  |  | checkpoint | Make sure the Module has been secured with the correct ties
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step.
checkpoint-group |  |  | section | Shipment
checkpoint-status |  |  | checkpoint | A Specialised Transportation Vehicle will be used to transport the module to Site
text | b9431d35-e98c-5421-9b25-e1bd10369b5f |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check if the Transport Company meet the approved transport criteria
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before transporting a Module.
checklist-flat |  |  | checklist | EGM_Ver1.0_20.03.23_Final Sign Off |  |  |  |  | Yes | EGM_Ver1.0_20.03.23_Final Sign Off | f180a8d0-8ba8-4206-aced-5fb07222bb50
checkpoint-status |  |  | checkpoint | Module Sign off by Licensed Building Practitioner
holdpoint |  |  | signoff | signoff: SIGNED OFF BY LICENSED BUILDING PRACTITIONER
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_P/D - Wall Panels |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_P/D - Wall Panels | f4678068-b804-4ad5-be67-235c57a626fd
checkpoint-group |  |  | section | First fix plumbing and drainage
checkpoint-status |  |  | checkpoint | Check and review as per approved plumbing and drainage services Plan, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install pipes as per approved plans and manufacture instructions.
text | 2cf6bef2-37fe-5065-ae1a-563101113604 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Visual inspection to check Pipe lengths horizontal and vertical spacing as per approved plans
checkpoint-status |  |  | checkpoint | Hold point: photo required on digital level of all pipes' runs and signed off by Plumbing team leader before going to next step
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Passive Fire - Ceiling_Module Assembly |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Passive Fire - Ceiling_Module Assembly | ffce33e0-3bf4-49f0-ab37-cd7e9e1fba94
checkpoint-group |  |  | section | Passive Fire - Ceiling
checkpoint-status |  |  | checkpoint | Check and review as per approved passive fire report, and provide picture of the respective report which clarify shows page number
checkpoint-status |  |  | checkpoint | Install fire dampers, collars and sealants as per manufacturer specifications.
text | a8d4bc31-e761-5e25-a20a-f9394411670d |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check fire rated linings; materials and passive fire protection measures, as per GIB Fire rate system GBUC 60
checkpoint-status |  |  | checkpoint | Visual inspection to check installation installed to match manufacture specifications and approved design
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by fire contractor before going to next step
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step