## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - Clearing and Grubbing, Earthworks - Cut, Fill and Subgrade Preparation | itp |  |  |  | Yes | ITP - Clearing and Grubbing, Earthworks - Cut, Fill and Subgrade Preparation Rev0 | 1e64980d-ee61-492d-9c1e-0ef4bf1ab3ce
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | 4697d8ef-e4f9-5437-8723-289aedabf6bc |  | note | FREQUENCY: Prior to commencing any activity
label | 2dbee994-b549-500a-9a61-3f5484528b69 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 66bcd28a-30a7-556c-8d84-aaedbd3a8c2f |  | note | – using Issued for Construction (IFC) drawings
label | 4a9f8d59-0a85-5ede-ba40-84220c25b429 |  | note | – using the correct and complete set of drawings
label | 6cba5fff-ea87-5986-89b4-8dedad13000c |  | note | – all drawings are the latest revision
label | 060694ac-d5ec-5fc5-91f8-c0381eadeeb1 |  | note | REFERENCE DOCUMENTS: IFC drawings and drawing registers
label | 338494cf-baa3-5c7d-8116-7d1a62fba917 |  | note | INSPECTION/TEST METHOD: Document Review / Visual inspection
label | be93404b-6059-5cb1-b047-4dc02bb060d5 |  | note | RECORD OF CONFORMITY: This ITP signed
label | fd8b9869-6f8f-58fc-9515-dd793185429d |  | note | HP*
label | d216e2d2-ec22-5968-8103-eb08166f52f9 |  | note | RESPONSIBILITY: Site Engineer
text | e491cd57-fe6f-51bb-b6af-3c417a2fac22 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures and controls
label | 5979b04a-e37e-5cc1-812c-2f32cb4572df |  | note | FREQUENCY: Prior to commencing any activity
label | d332b54f-19bf-5ec7-8944-0029021374e1 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSMP, EMP, TMP, SWMS & WP. Access and egress inspected and assessed for stability.
label | 415b6dad-e1ab-55e7-9021-e84d015a9210 |  | note | REFERENCE DOCUMENTS: OHSMP, EMP, TMP, SWMS, WP
label | b841764e-edaa-514b-a916-97acc2ebe6fa |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 574acb9d-0df2-5fc6-b530-7f95bae2b7fe |  | note | RECORD OF CONFORMITY: This ITP signed
label | e43a0735-61e9-53ab-9638-1334c905da46 |  | note | HP*
label | 23ef4dbd-dc13-51ae-99d4-29ae7ca49aa8 |  | note | RESPONSIBILITY: Site Engineer
text | bbb3a54d-b868-5728-adcf-5bf3c599c2f9 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 1.3 Ground Penetration Permit
label | db33a5e3-88ec-5358-b0d3-b7516b74246d |  | note | FREQUENCY: Each Lot
label | 58514e03-ad0d-5548-bbaf-3a650d10fbe6 |  | note | ACCEPTANCE CRITERIA: A ground penetration permit must be issued prior to excavation commencing.
label | c637d226-2366-53a7-99de-275523824425 |  | note | ○ Plant and equipment must be appropriate for the task.
label | 257be77b-69e0-5c68-b678-fab6c6762481 |  | note | ○ Excavation operations shall not disturb areas outside the limit of excavation.
label | ba1cf984-e3f1-5593-82fe-2f1f572bf364 |  | note | REFERENCE DOCUMENTS: Ground Penetration Permit
label | a6597e1e-7181-559c-b58f-13a94fe157df |  | note | INSPECTION/TEST METHOD: Verify
label | d107bd96-81f2-55b2-a4ca-495680b4f0f0 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 01ed6253-70bd-544a-8d5d-359eb4db2b5a |  | note | IP
label | 195879a2-e545-5a30-8ea4-f97743e41dbb |  | note | RESPONSIBILITY: Site Engineer
text | 4135521d-9c02-5cb7-8802-479f890f0dfb |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 1.4 Implementation of environmental measures and controls
label | 1062cb88-f9d6-50a3-aae5-f0b705412e90 |  | note | FREQUENCY: Prior to commencing any activity
label | 06bcead7-ff5a-5f3e-b1ca-eee7466e561b |  | note | ACCEPTANCE CRITERIA: EMP meets the requirements of the specification and all controls have been implemented as per approved EMP
label | ac6b6efe-ad3e-5c04-b360-941b8a2562c9 |  | note | REFERENCE DOCUMENTS: Project Spec Cl176.A3, EMP
label | e0829591-0e29-546c-b69d-c6eeedff2aab |  | note | INSPECTION/TEST METHOD: Verify
label | fc2a11bd-767b-5015-ad63-55e0512b1214 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 892cff1c-a526-58cf-b73a-667698e61a81 |  | note | IP
label | 4bf3b5ee-d31a-5c50-b413-6ea451959fa4 |  | note | RESPONSIBILITY: Site Engineer
text | ba4f8d72-981c-56f1-bb71-363069cd2834 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 1.5 Flora and Fauna
label | d3cb9d44-e0cf-5d74-a654-89a42e3c60f1 |  | note | FREQUENCY: Prior to removing vegetation
label | 18f2a0ad-6804-509b-a453-49c9ce8e486b |  | note | ACCEPTANCE CRITERIA: Hold Point
label | fe40be87-05ae-5407-beb8-3e8fafed5dde |  | note | ○ Vegetation to be removed clearly marked and agreed. All removal consistent with contract drawings and permits. Shall fence and sign all sites nominated as No-Go Zones.
label | 8dc734c4-c4b6-5c59-ab05-2e12fcfbc5e6 |  | note | REFERENCE DOCUMENTS: Cl176.I1
label | 0c6fb762-1414-52c8-abe9-f0014888b139 |  | note | INSPECTION/TEST METHOD: Verify
label | 9dc65eeb-9cbb-59b3-88e8-588b3ad208bf |  | note | RECORD OF CONFORMITY: This ITP signed
label | 2a44a7d1-5c06-5077-a228-05b8dba8c8cc |  | note | HP
label | 0d37ed5b-7775-58dd-a4c6-61d13fe28dca |  | note | RESPONSIBILITY: Site Engineer / QAV
text | 6bd32a66-9764-5057-85e9-244b4dfe86d3 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 Protection of Existing Vegetation
label | 308e7ef2-73a8-54fd-8e44-ba40b475b38c |  | note | FREQUENCY: Prior to comencement of any work
label | b192e8d7-1db9-5cb8-a2d5-2083d918e8f5 |  | note | ACCEPTANCE CRITERIA: Prior to the commencement of any work, the Contractor and the Superintendent shall conduct a joint inspection of the site to identify vegetation to be retained and protected.
label | e39abb96-8bee-5e19-bb69-59e8d876f082 |  | note | ○ If directed by the Superintendent, existing trees, shrubs, native grasses and groundcovers and other areas of existing vegetation shall be protected by temporary fencing and incorporated into the works by the Contractor.
label | 15926809-d6a1-59a1-9add-2164197a4ad8 |  | note | ○ Protective fencing shall consist of, as a minimum, star pickets with three strands of wire and parawebbing.
label | ba177d4b-4b39-550c-aa6b-25ef39e3253f |  | note | REFERENCE DOCUMENTS: EMP Cl201.1
label | 92be53f5-0979-517a-9185-2c9fc67ddbfa |  | note | INSPECTION/TEST METHOD: Visual inspection
label | db98958b-6816-5415-ad64-751efabe043e |  | note | RECORD OF CONFORMITY: This ITP signed
label | 990aef22-9c21-544f-b95a-ff3b9b177aa8 |  | note | IP
label | 6dc4e52c-f4a7-54cc-bc69-422979143dd4 |  | note | RESPONSIBILITY: Site Engineer / Superintendent
text | fa76ea9c-ce03-5af7-8ac5-dfd0bd6d82d3 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 1.7 Flora and Fauna
label | 8d721452-6ce6-539a-a10c-2bd8d83849aa |  | note | FREQUENCY: Prior to removal of vegetation
label | 5966aae2-fb9a-5fb5-9f5f-b9013bd2f8c7 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | ecccacdd-f028-5a3f-8fe5-1be4f85425b7 |  | note | ○ Nominated sites of archaelogical and / or heritage significance inspected on-site and clearly identified and protected as No-Go zones
label | ce323897-0cdd-5f81-a11b-e8e0e7aef600 |  | note | REFERENCE DOCUMENTS: EMP Cl176.J1
label | df75a468-f797-50ea-86b5-881d635fbc81 |  | note | INSPECTION/TEST METHOD: Verify
label | 86cf5ae3-6ded-526b-a0a6-75c3865c5cb7 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 9122b3ca-7513-584f-abbf-560f7765067a |  | note | HP
label | 6dfca3c3-04a1-5566-b9f7-952da01c374a |  | note | RESPONSIBILITY: Site Engineer / QAV
text | a19191af-998a-5246-bc1a-3a57ec5eb006 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.8 Authorisation for works
label | f3071709-503d-583d-bf6a-a17e22a06fd7 |  | note | FREQUENCY: Prior to commencing works
label | 1d7b8258-e258-5859-8378-a38c399e90da |  | note | ACCEPTANCE CRITERIA: Check that all relevant approvals have been granted including verification of the works area
label | 2fde4608-e1ad-514a-a3fb-22d5b4c4a2af |  | note | ○ Ensure work pack is reviewed & signed
label | d16f0295-d60c-5e7e-9cce-09d84ece65cf |  | note | REFERENCE DOCUMENTS: Work Procedure
label | 442740d1-fa21-5c67-9993-3a688ad50b71 |  | note | INSPECTION/TEST METHOD: Verify
label | c57684bc-0fea-576b-9417-86748af70d22 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 03e72ab6-0492-5b01-bb3b-10cedc12bb62 |  | note | HP*
label | c1fc1994-0280-57a2-9728-4c612f88d7ef |  | note | RESPONSIBILITY: Site Engineer
text | c8960ae8-406d-5b30-a031-9c9097ec5760 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 1.9 Utilities
label | beb17436-a078-5742-ae71-2ab04e91b7e1 |  | note | FREQUENCY: Prior to commencing works
label | 7e4473da-e1d8-5bd2-a95c-07647aad2d5e |  | note | ACCEPTANCE CRITERIA: DBYD - locate and mark all existing services and confirm clearance from proposed work
label | b9aa9841-6e9f-5741-a5b4-a0975e995c5e |  | note | REFERENCE DOCUMENTS: DBYD Records, Plan Mark-Ups
label | 506686a6-c190-5e78-ada3-7d9bdb4d11f3 |  | note | INSPECTION/TEST METHOD: Verify
label | 66433410-b2d7-59d9-9f81-c8f78a193235 |  | note | RECORD OF CONFORMITY: This ITP signed
label | d23a1009-f212-5135-a3e1-837d6d4de6d9 |  | note | IP
label | 49a7de83-6de3-5ac8-886a-65cd25235080 |  | note | RESPONSIBILITY: Site Engineer
text | b63e06af-2224-5c1c-914c-a8029e16d14b |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 1.10 Traffic Management
label | 2f05719a-93b1-5bc6-9046-2254a6405692 |  | note | FREQUENCY: Prior to commencing works
label | 8c8f925a-f3a9-5e95-b10e-4ebbd326ccfc |  | note | ACCEPTANCE CRITERIA: Consider the requirements for traffic management, ensuring all works comply with required TMS, TMP and TGS.
label | f39a9132-3e59-5dfe-a9bc-e0e2570a9cff |  | note | REFERENCE DOCUMENTS: TMS
label | 42cb4f87-f95f-5cc0-acd1-445d1e610063 |  | note | INSPECTION/TEST METHOD: Verify
label | 0df30367-ae71-5162-b5ff-692108b24da4 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 1cb633db-927d-51a6-bb72-988fbacfdb1a |  | note | IP
label | 696272b3-bc0c-537a-9064-edb139d9dc77 |  | note | RESPONSIBILITY: Site Engineer
text | 796e4c9c-e3f8-5253-a168-eea9347b22bf |  | textbox | DATE:
checkpoint-group |  |  | section | 2 - Clear & Grub
checkpoint-status |  |  | checkpoint | 2.1 Limits of work
label | c6d3ff3b-8ada-56cb-9705-602f0df68f2e |  | note | FREQUENCY: Each Lot
label | 102e8685-aed3-58cb-9b42-8e2657e30d1d |  | note | ACCEPTANCE CRITERIA: Limits of clearing and grubbing shall be the whole length between the following chainages:
label | 80e613ab-32ef-5076-bbb6-81fc6333edf0 |  | note | REFERENCE DOCUMENTS: Cl201.03
label | ed6b915d-886b-50c5-8f71-b33fa26fe431 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 0382a92f-3ff2-517d-89ad-5011d3c18e8f |  | note | RECORD OF CONFORMITY: This ITP signed
label | 9cfc573a-cad0-5b37-b8ba-b973468f8282 |  | note | IP
label | 1f822853-20a6-5f90-9baa-3b3d2b750096 |  | note | RESPONSIBILITY: Site Engineer
text | 38d55c68-294e-547f-a90c-348193148ad9 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.2 Clear and grub trees and vegetation
label | 3c277018-b62d-5489-a8f4-a4af6a7408fa |  | note | FREQUENCY: Each Lot
label | 51ca4a32-2870-5e65-bdb6-0bccda7b82e9 |  | note | ACCEPTANCE CRITERIA: The area within the specified limits shall be cleared of all vegetation, refuse and obstructions down to natural surface. The Contractor shall not undertake any clearing work or any type of disturbance outside of the specified limits of work unless approved by the Superintendent.
label | df597c68-a989-5b24-bd35-a339539a161f |  | note | REFERENCE DOCUMENTS: Cl201.04
label | d1cdf927-79a1-58f7-90d1-a320b6bab5a0 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 77327e6c-5184-5645-bc1a-a6b53bff9568 |  | note | RECORD OF CONFORMITY: This ITP signed
label | e7d99a84-905b-5017-abb4-bd6a175bb4c2 |  | note | IP
label | 75bccae7-6585-530b-a846-0a758b5469cb |  | note | RESPONSIBILITY: Site Engineer
text | 6d0c4e27-a7bc-5c2c-a610-187c3f535980 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.3 Clear and grub trees and vegetation
label | 95daa640-5a5b-5d20-92d2-32e5ffb9bb4e |  | note | FREQUENCY: Each Lot
label | fe373f82-aaa8-5f60-ad1a-38cac41d4318 |  | note | ACCEPTANCE CRITERIA: In areas where excavation is to occur: all vegetation, refuse and obstructions totally grubbed or grubbed > 0.3m below subgrade and batters (whichever is the lesser treatment)
label | ca94952e-dea6-577d-813d-a27c7fafeb56 |  | note | REFERENCE DOCUMENTS: Cl201.05
label | 4d64c4bd-3dd7-5837-b3c9-b816b3f06f74 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 604317e0-e293-5517-b2ae-7e9d7f1fcbd7 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 81c8d421-a9d0-57da-af3f-9198cb82ad10 |  | note | IP
label | 171cc5fe-2693-5593-b6c0-99087885134a |  | note | RESPONSIBILITY: Site Engineer
text | 45aaf1d9-790f-5a9f-bca3-4d5204003e55 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.4 Clear and grub trees and vegetation (embankment areas)
label | d4b404f1-0001-5c43-b88b-d6972489a7d8 |  | note | FREQUENCY: Each Lot
label | ea50190a-8f31-52b0-aead-431dfcd814b2 |  | note | ACCEPTANCE CRITERIA: In areas to be covered by embankments < 1.0m in height: all vegetation, refuse and obstructions grubbed > 0.3m below stripped surface OR > 0.6m below subgrade level (whichever is the lesser treatment)
label | 180eea01-278e-5a53-8d6d-683dd3eedca3 |  | note | ○ In areas to be covered by embankments > 1.0m in height: foundations may remian if located or cut off not more than 0.4m above natural surface but not less than 1.0m below subgrade
label | b73fe662-d329-583c-8e8d-5f23dad06afe |  | note | REFERENCE DOCUMENTS: Cl201.05
label | 5ccea926-02ad-5eef-aed3-9f0eb9a7753a |  | note | INSPECTION/TEST METHOD: Visual inspection
label | c5177601-a69d-5c39-9ac6-8e514533aec5 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 21ca3932-5018-5cae-825b-6108d5deab25 |  | note | IP
label | 54909bb7-f88b-5664-82e5-c2855d6fb881 |  | note | RESPONSIBILITY: Site Engineer
text | 0f1dce4a-62a6-5580-9bfc-534ff4896640 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.5 Clear and grub trees and vegetation at culvert sites
label | 8911ee6e-f3e0-5f99-ac68-184e9b8017fd |  | note | FREQUENCY: Each Lot
label | 2fa952c0-efd8-5fd8-99ff-a486a047dca4 |  | note | ACCEPTANCE CRITERIA: Clear and grub trees and stumps within 10m of any proposed bridge or culvert having a waterway area > 6 m2 (unless otherwise shown on drawings)
label | 05f2954d-561c-5ecd-a06c-dbfbc6dcb389 |  | note | REFERENCE DOCUMENTS: Cl201.06
label | 68f052f6-c21c-560e-942c-1cac8446cc2b |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 0519ba6b-f144-588e-a0ea-ec1993eece79 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 8408b76b-7c74-5983-8ab4-0a2fe9851c12 |  | note | IP
label | ea55dac2-8e5d-5498-a4cb-b7a5e30fd54b |  | note | RESPONSIBILITY: Site Engineer
text | 7f8451c9-fdf0-55f2-a015-64332e25e2c7 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.6 Backfill holes
label | 272e1d6f-76f5-54dc-aaa7-c81776a4efcb |  | note | FREQUENCY: After clearing
label | a3eb35d5-9c98-5753-821e-c07145cd23ce |  | note | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material and compacted to the same degree as the surrounding material
label | b633a77e-9d10-5317-8fd7-1762c3e78c34 |  | note | REFERENCE DOCUMENTS: Cl201.05
label | 1216b105-5be9-53c0-8e73-e009cefe412b |  | note | INSPECTION/TEST METHOD: Verify
label | 7d697a47-3dbf-53f9-a564-a35aa3e6d23f |  | note | RECORD OF CONFORMITY: This ITP signed
label | c77d0e92-1927-5ad2-8da8-ea888c716d44 |  | note | TP
label | e4a7a61a-9b03-5559-9633-7d388d3b6afa |  | note | RESPONSIBILITY: Site Engineer
text | d3a443f9-bba4-5409-8d82-0a573f12fd5b |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.7 Dispose of Trees and vegetation
label | bc6e22f1-2303-5664-98db-c3bc31158553 |  | note | FREQUENCY: After clearing
label | 4e90e7eb-5cfa-52ef-bd35-2bbe28fe7933 |  | note | ACCEPTANCE CRITERIA: Tree trunks and large branches shall be removed from site. Small tree branches, weeds and shrubs shall be disposed of by chipping and mulching.
label | 759af751-e92e-549b-a0fd-5d02e5143dce |  | note | REFERENCE DOCUMENTS: Cl201.07 (b)
label | f9a184d2-65dc-5651-9cfa-8f8f3a86114c |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 9a0395ae-37e7-5915-8369-a7d629c25ac3 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 0118d36a-e0e1-5903-9768-cb2e84664ac7 |  | note | IP
label | 54074fab-fd4e-51d1-9f4e-81efb33cc471 |  | note | RESPONSIBILITY: Site Engineer
text | cb7281e1-aea2-534b-bfc9-7b8a79d6ad9e |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.8 Damage to Fencing
label | fbb10b1e-e7fa-5c57-80bb-f950455f9a63 |  | note | FREQUENCY: During Clearing
label | 487d1f05-4483-56ba-83ab-030882080a1d |  | note | ACCEPTANCE CRITERIA: Immediately repair any damage to fences to a condition at least equal to that before damage
label | c95c0571-2f22-575c-b3d0-98f49649fad3 |  | note | REFERENCE DOCUMENTS: Cl201.09
label | 0b0e9749-c0f2-561d-8e99-bb7e68b6c5d4 |  | note | INSPECTION/TEST METHOD: Verify
label | 2ee3d0a8-7fe0-5c59-9bce-f4c76feaaa96 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 02bc3d66-8ed1-5053-a94b-c175c573a250 |  | note | IP
label | 391dd438-f05c-57d3-9811-7000515669af |  | note | RESPONSIBILITY: Site Engineer
text | 9143ac9d-5692-50e2-ab76-058a6bc360b6 |  | textbox | DATE:
checkpoint-group |  |  | section | 3 - Earthworks
checkpoint-status |  |  | checkpoint | 3.1 Material Categorisation
label | 1ef93d08-d7dd-52b5-ab28-70d499201abd |  | note | FREQUENCY: Each Lot
label | e8790b67-4c18-52c3-99ba-4087f65f3be6 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | 0e37ef1e-28ec-53da-a23b-ae23f3fd27fd |  | note | ○ Prior to commencing excavation in any area and during excavation work, the contractor and Superintendent shall inspect and agree upon the type / category of material encountered
label | c8655e99-8571-5220-8e34-bcc5aa773001 |  | note | REFERENCE DOCUMENTS: Cl 204.06c
label | 7a4efca0-58b4-5814-b0e2-bc05131e6e61 |  | note | INSPECTION/TEST METHOD: Verify
label | 3ba8f1c9-e5fd-5e9e-8cbc-2ab19640dc44 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 3619c5a0-325e-5abe-bd2e-8b797924cbc6 |  | note | HP
label | d6a65e0e-46f0-586c-ae0b-a08fbe7303f3 |  | note | RESPONSIBILITY: Site Engineer / QAV
text | b8c81bf2-a79a-5346-8ed8-b6f97f41edd9 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Stripping of Topsoil
label | de12b902-5c84-542f-a15f-05dc7d45d885 |  | note | FREQUENCY: Each Lot
label | 233dcce9-58d8-5b30-8f75-f43eae8c4968 |  | note | ACCEPTANCE CRITERIA: Topsoil stripped to full width of the formation and placed in approved stockpile location. Stockpile shaped to shed water and stripped surfaces graded to be self draining. Topsoil shall not be removed from site unless approved by the superintendent.
label | d57b637f-b881-5c74-b095-b597fac8b8b0 |  | note | REFERENCE DOCUMENTS: Cl 204.05
label | 874e28c8-369b-5a3d-b7f2-57e0a49e0dce |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 1d3ee8fc-ac85-5c10-88a2-0b4bb4eec061 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 9862f159-1fd3-51e7-9256-9e9ba6bbf545 |  | note | IP
label | 8b6e952a-348e-587a-8512-65a7e37e9393 |  | note | RESPONSIBILITY: Site Engineer
text | 434d5351-6b77-59b6-822c-d15100069c31 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 3.3 Unsuitable Material
label | 1d8e33d3-f179-563b-99d1-abe354d8c445 |  | note | FREQUENCY: Each Lot containing unsuitable material
label | 2b1b7500-88b3-50cc-9b1d-37fca0471ed1 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | 38c9d08e-42ab-5d3f-b346-513c4560bd5a |  | note | ○ For unsuitable material, the proposed in-situ treatment or extent of excavation submitted to the Superintendent for review.
label | 52005f9a-fcad-5ae6-8b25-937a6ab2a629 |  | note | ○ Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Superintendent
label | 231f7927-68e6-5276-8315-95728fe54d4e |  | note | REFERENCE DOCUMENTS: Cl 204.04b, Cl 204.07d
label | d26a1f23-ef6b-58e6-957b-4c0651092822 |  | note | INSPECTION/TEST METHOD: Verify
label | bbe37570-218e-50b2-8dbc-7c005822b7a1 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | acff03fc-a873-59dc-b52d-945d7ba541e0 |  | note | HP
label | b0456a4d-1866-52ca-9b74-4ec2f332456a |  | note | RESPONSIBILITY: Site Engineer / QAV
text | 8f000e5f-88c7-5b18-b5ad-c31142e83721 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Subgrade Fill Material
label | 45bfd860-be3a-5a8a-b7e3-980cea75817b |  | note | FREQUENCY: Each Lot
label | 40338cb6-f2ad-5777-8126-1912b7c4f72d |  | note | ACCEPTANCE CRITERIA: Fill material free of topsoil, deleterious and/or perishable matter.
label | cc83f878-7ad8-56a1-aab8-db55bff74869 |  | note | ○ Type A material shall comply with the requirements of Table 204.041
label | bae5f51e-a7f5-5ee1-a11f-695cb9f5431d |  | note | ○ Type B material shall have minimum Assigned CBR of 4% and Assigned swell less than 2.5%. Materials with swell greater than 2.5% can only be used as Type B material if approved by the superintendent.
label | 18eb71e6-3de1-5bc6-abe4-c7b1b9ca3429 |  | note | ○ Type C material shall be capable of being spread in layers of not more than 500mm
label | ad00e01b-f51e-5f8e-8e61-8b86a20f6afd |  | note | REFERENCE DOCUMENTS: Cl 204.04, Table 204.041
label | b057f573-5c10-5368-9589-5f2cca8517fe |  | note | INSPECTION/TEST METHOD: Verify
label | e9d813bf-260c-58bf-98ae-c862204b9560 |  | note | RECORD OF CONFORMITY: Test Report
label | 4125b45c-93a1-5e85-ad6a-2f692aa7648f |  | note | TP
label | d379f13e-4981-502d-89a4-d546d22cb8ac |  | note | RESPONSIBILITY: Site Engineer
text | 339e6deb-99d2-5129-81d6-f8f3f8c1281c |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 3.5 Treatment of Rock Subgrade
label | 4c0b3065-fc97-5f9f-a720-8776c0f86c46 |  | note | FREQUENCY: Each Lot (prior to construction of regulating layer)
label | f98a8a45-f9e8-546c-9e53-852d1187b90a |  | note | ACCEPTANCE CRITERIA: Hold Point
label | d510b405-7acc-536a-89e9-ac4c88a78ef2 |  | note | ○ Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | 6ae0f138-2c76-5fb5-ace5-e4111633897e |  | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | b2f045b3-6a77-5690-be5b-16f244ddf352 |  | note | REFERENCE DOCUMENTS: Cl 204.06f
label | 756704fe-8477-5abe-a8e7-6eefb78ce036 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 92a1de4f-06cb-52bd-9c9f-8a17096baab2 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 7ac0292d-4541-55e6-a42b-73159d444e62 |  | note | HP
label | a4b8ee0e-cbc8-5a38-9b7e-6ff1f4aa996f |  | note | RESPONSIBILITY: Site Engineer / QAV
text | a3990976-2a89-5c63-b5df-7847f313e501 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Groundwater
label | 24364cd4-83d7-5dc9-864c-09455c4ab489 |  | note | FREQUENCY: Each Lot
label | df9b2630-3f9d-5d10-b360-b55c315c8ed8 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | f640ae66-3438-52ed-a32e-a5a3735b8765 |  | note | ○ Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | 4e263379-1250-53b0-aba4-d4ea4cefbdfb |  | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
label | ad089605-68f9-5ce1-aac0-6ef18befe1a1 |  | note | REFERENCE DOCUMENTS: Cl 204.06h, EMP
label | 7126a602-7ac5-5fa0-bb6a-2891c73f4063 |  | note | INSPECTION/TEST METHOD: Verify
label | 3069f1ba-5193-5398-b11a-2dcfa0795472 |  | note | RECORD OF CONFORMITY: Water Authorities and Superintendent Approval, This ITP signed
label | a9511b15-daff-5555-89a5-6c4bbb03ac77 |  | note | HP
label | af9c3e1a-33a6-5208-8fac-5a031ce2efd8 |  | note | RESPONSIBILITY: Site Engineer / QAV
text | e6ea1b6e-15f5-58fd-9a6b-0db2a7fdf1d5 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Surface finish of batters
label | 4dee9a41-9254-56b6-9d1f-67eb83965f15 |  | note | FREQUENCY: Each Lot
label | f11eba1e-121c-5714-9713-304b7ffcd626 |  | note | ACCEPTANCE CRITERIA: Surface of cut and fill batters to be topsoiled and textured by scarifying or horizontal grooving
label | 4fec51b4-9dcd-5ea8-8276-ae073f3429bc |  | note | REFERENCE DOCUMENTS: Cl 204.06i
label | f4020b68-48c7-55b9-99b5-79298e5eabf7 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 13828e6c-75f7-56f6-b1de-96afa4ca6464 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 4403fdb5-5da2-544b-a775-c16a10569698 |  | note | IP
label | 04ccf5ab-31a1-5cbf-afc3-a3a035a1bdc0 |  | note | RESPONSIBILITY: Site Engineer
text | 79f1ee93-85da-5293-9291-203338477791 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 3.8 Borrow Excavation
label | f31486d9-a5aa-5a67-be40-cc4d5b9da336 |  | note | FREQUENCY: Each Lot
label | e5daed98-4ade-508a-9cba-303480a257a3 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | c611780f-002e-5ad5-9eab-b32b6c139508 |  | note | ○ Borrow Excavations within the road reservation are not permitted without prior approval of Superintendent
label | 8f06f4df-dc30-53f3-b6af-b07fdb052ce8 |  | note | REFERENCE DOCUMENTS: Cl 204.09
label | 692f974e-4e95-57b4-8977-14588634d9ed |  | note | INSPECTION/TEST METHOD: Verify
label | 20116fbd-fe42-5fc6-9d77-d4366ad274ef |  | note | RECORD OF CONFORMITY: This ITP Signed, Correspondance with superintendent
label | 15fec9d9-dd15-50ab-926d-3917769b5434 |  | note | HP
label | ed5da856-afb5-5e5f-b0aa-4cf7f09f2bd4 |  | note | RESPONSIBILITY: Site Engineer / Superintendent
text | 2777c354-42ab-5b1d-b98d-15abb7cccd69 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.9 Areas upon which fills are to be constructed
label | 2466d2a2-9de3-5e83-a6db-42271d9324ca |  | note | FREQUENCY: Each Lot
label | 32c4061d-c978-5f1f-8d6c-c4b10fea7dd3 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | 1204f096-2101-52cd-a2a0-a8062f6bcba6 |  | note | ○ Areas where fill is to be constructed must be reviewed by the superintendent prior to the placement of any fill in the area
label | 6f164885-4ecf-5a24-9c64-43ce7e3d880e |  | note | REFERENCE DOCUMENTS: Cl 204.10b
label | e1d014a7-329b-559c-b1be-f1420f22956c |  | note | INSPECTION/TEST METHOD: Verify
label | 825ae403-9040-51e3-97b6-a7aa22c5a33b |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 4fd0e002-2f96-597e-a677-f66a10e6c172 |  | note | HP
label | fc32ace0-4489-59cb-8063-a8233612ba29 |  | note | RESPONSIBILITY: Site Engineer / QAV
text | 63b345ac-d336-5be2-b1c0-9821be3e2819 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 3.10 Placing of Fill
label | 3e598659-1500-5b27-b171-6756db3a2f28 |  | note | FREQUENCY: Each Layer
label | 222adf5d-a18f-543c-83b2-a158cd17cb3c |  | note | ACCEPTANCE CRITERIA: Fill placed and spread in uniform layers. Each layer keyed into the next with a textured surface. Any rocky material uniformly distributed throughout the layer.
label | 55b393b3-3e0c-5815-95df-0dd1a290360a |  | note | ○ Compacted layers do not exceed specified maximum thicknesses:
label | b37311e6-a9cb-559e-83a9-04432a1c109f |  | note | ○ Type A: Maximum compacted thickness 200mm (can be used in locations specified for Type B material)
label | 7d3ced9e-1ffe-5118-833b-e804b27b8b29 |  | note | ○ Type B: Maximum compacted thickness 200mm (can be used in locations specified for Type C material). Where > 25% rock by volume, loose layer thickness may equal 125% of typical maximum particle dimension up to max 500mm. No rocks > 80% of loose thickness of the layer.
label | 298a41e1-cd76-568c-9afd-9c6d25f68306 |  | note | ○ Type C: Maximum compacted thickness 300mm. Where > 25% rock by volume, loose thickness of each layer may equal the maximum particle dimension of the rock up to max 500mm. Reference table 204.111
label | 5afba42d-ce18-5742-9a09-3cd7da2d12d7 |  | note | REFERENCE DOCUMENTS: Cl 204.10d
label | 89b3ffa9-7a58-5c5c-9c6b-48761e1be026 |  | note | INSPECTION/TEST METHOD: Visual Inspection / Measure
label | c6508bb3-dc2c-5e12-92b8-5c51c8ff4c95 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 5c350927-b278-56ae-a6f6-505272ebafa5 |  | note | IP
label | a25d1c5f-4aff-5f14-ad7d-975488f11104 |  | note | RESPONSIBILITY: Site Engineer
text | 9751f35c-d002-5ef5-a211-9daf840e3bf3 |  | textbox | DATE:
checkpoint-group |  |  | section | 4 - Testing and Surface Preperation
checkpoint-status |  |  | checkpoint | 4.1 Test Rolling
label | ef66119f-ca66-5539-91d3-a2dcecba52f2 |  | note | FREQUENCY: Each layer
label | 2dc9b1af-5478-567f-9b86-a83a2fd56ed2 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | 8298fd18-5064-5cfa-ab47-6aa9f4328bd9 |  | note | ○ Areas upon which fills are to be constructed, all layers of fill, material within 150 mm of the cut floor level in cuts, and all stabilisied material shall be test rolled in accordance with Section 173.
label | 9899a689-0843-5658-8891-d32d8f748346 |  | note | REFERENCE DOCUMENTS: Cl 173.03, Cl 204.12
label | e9d78503-616d-5d58-a9b3-c3d83b6c070e |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 6198c5b1-0a5a-5f0e-bf90-3927f7ae019d |  | note | RECORD OF CONFORMITY: This ITP signed
label | b0e7089e-aa06-5bd5-bc7b-412738cf7f9c |  | note | HP
label | 33c39fee-b039-5825-b7f6-27b1e28bc116 |  | note | RESPONSIBILITY: Site Engineer / QAV
text | df132dd0-0ee6-5577-ac96-37f2d1078651 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 Cut and Fill Tolerances
label | c87e2176-6058-5420-886d-7ab8b4c23abf |  | note | FREQUENCY: In accordance with Table 204.031. Lots < 4,000m²
label | 8fb2b6a8-8503-5dfc-9b55-48fe1610de71 |  | note | ACCEPTANCE CRITERIA: Formation width and alignment: not less than the widths specified or shown on the drawings
label | 62d043c9-f8a3-533a-b242-a3f760389a4a |  | note | ○ Formation level and shape: Verges match FSL at outer edge of shoulder or pavement (± 50mm from design level)
label | 693407cb-bdbf-5b6e-803f-6ec7019c1b4d |  | note | ○ Boxing width and alignment: not less than specified or design levels & no deviation > 50mm from designed offset from the centreline or design line.
label | 29b5e85f-12dd-5d69-85b9-47dc1b9111ac |  | note | ○ Type A Material: thickness and width not less than specified at any point.
label | 8f4a1d75-9cf0-5ba4-8d64-a882d1390138 |  | note | ○ Type B material (immediately below capping / selected material): +15mm -30mm specified level
label | 9224abf9-b1e1-5f8e-9ddb-9e456ba5d8c6 |  | note | ○ Cut floor level (when capping layer required): +15mm -30mm specified level
label | 5cdb36ab-e726-5bfd-849b-ba7d9ad3b614 |  | note | ○ Cut floor level (no capping layer): same as subgrade tolerance
label | 1ac0541f-80fd-5141-9fa2-e9089e5f2ee8 |  | note | ○ Subgrade Scale A & B: random levelling Cl204.03(h). No point > 20mm below a 3m straightedge laid in any direction.
label | b69d88b8-3757-5c90-bc7b-f7c0edf8326b |  | note | ○ Batter and slope: Not steeper than specified at any cross section.
label | 1d8f41f4-f981-55ba-a6ed-7e9fca334f0f |  | note | ○ Batter line: Batter point < 10% of the batter height outside the calculated batter line.
label | 41ca6a2a-d978-5cf3-ab64-2e828c90e4f6 |  | note | ○ Surface Drains: Invert levels and side slopes ±50mm and free from depressions capable of retaining water.
label | 8330f5c8-add3-53dd-acfc-17f9dab43ddb |  | note | ○ The contractor shall establish a procedure to verify that compacted layers do not exceed the specified thickness. Verification records must provide evidence of measurements taken every three layers.
label | 4df86f7e-71a5-5d48-a6c4-94dd954eed5c |  | note | REFERENCE DOCUMENTS: Cl 204.03, Table 204.031,
label | d6b0ba2a-11b9-5316-8d09-4b4ae006054e |  | note | INSPECTION/TEST METHOD: Verify
label | 63949e27-e4e3-5256-af19-84b7ee28e0b3 |  | note | RECORD OF CONFORMITY: This ITP signed
label | b90bd893-efbe-565d-a2c1-af59020164a5 |  | note | SCP
label | c4bcb6f3-251a-596a-8948-67f2eb96e79c |  | note | RESPONSIBILITY: Site Engineer
text | 3edf5b06-4726-561c-a3b1-8c0be84a8455 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 4.3 Subgrade level conformity
label | 817dd15c-2c8c-51ef-9e67-650a01259148 |  | note | FREQUENCY: Each Lot
label | b2a250c1-41c3-5706-a2fc-85cf4e4915bc |  | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | e5693f74-c1c7-522d-a9d4-81f0c8ff0810 |  | note | ○ Level tolerances:
label | 182a8b20-7f45-53b8-b778-2491c996458c |  | note | ○ Scale A - 80 measurements per lot
label | 3432df84-2fa7-55e9-98b0-dd80967bbcaf |  | note | • Range = +5, -15mm
label | e891a4ed-9808-52ef-8413-1d39929108f0 |  | note | • Max S = 12 mm
label | e66cdb7e-bf86-55e0-b5a5-a61602189958 |  | note | ○ Scale B - 40 measurements per lot
label | 16aaacc4-b207-53a0-9a33-38c6c5899d5f |  | note | • Range x = +5, -25mm
label | f1ffcfb6-fbf9-520f-b869-41e808f592cc |  | note | • Max S = 15 mm
label | 92990e31-29c2-5822-8d25-8268d947908b |  | note | REFERENCE DOCUMENTS: Cl 204.03
label | 1862514e-9f0c-5e97-8211-72dc83c1c7f7 |  | note | INSPECTION/TEST METHOD: Verify
label | 8962925b-9ab8-51be-96d2-6f8e53654581 |  | note | RECORD OF CONFORMITY: This ITP signed, Survey report
label | 273d9475-d1a4-558f-b493-4df3e10278ce |  | note | SCP
label | 4764ced7-e31b-5504-9ae0-c8bfb9ce6d59 |  | note | RESPONSIBILITY: Site Engineer
text | 8677b533-8c26-5879-bad2-4368cb4a87b9 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 4.4 Fill Material Compaction & Moisture Content Requirements
label | c5d1b6bf-473f-5e86-ae05-bce2d4c5f590 |  | note | FREQUENCY: Each Lot as defined in Table 204.142.
label | e545b837-b580-5248-ad26-650f1eb89bd3 |  | note | ○ 6 tests per lot.
label | 63161164-a285-59c7-aa0e-e6637a9f0f99 |  | note | ○ Small area lots (<500m2) as per Cl173.04d.
label | 6f911715-8065-578f-9996-d6d80abeb088 |  | note | ○ 3 test mean lots.
label | 90f6993f-98eb-5dca-bcd2-6d8c5250af5d |  | note | ○ +2% compaction req.
label | f41ae95c-6a3c-546c-ab33-4307b9078794 |  | note | ACCEPTANCE CRITERIA: Refer to Reference Documents for particular Tolerances, Properties and Testing Scales and subsequent Requirements.
label | 2f613b95-ad37-51f8-ad7d-266122fc1b42 |  | note | ○ Table 204.161 for Project Specific Scales for each applicable Road Name or Area.
label | a59f8d3b-da5a-5e08-b655-90fdd9d419b3 |  | note | REFERENCE DOCUMENTS: Cl 204.13, Table 204.131, Table 204.161
label | 834efbc2-6087-5c51-9e2a-f49553b7b2bb |  | note | INSPECTION/TEST METHOD: Verify
label | 2adcb7bd-a0f9-5c74-ba62-c02d87963c1a |  | note | RECORD OF CONFORMITY: This ITP signed
label | 4eb11f99-6c7a-5cc0-931e-d484d1c5e151 |  | note | TP
label | 6c6e94f7-5832-519e-83cc-c825c5b6134a |  | note | RESPONSIBILITY: Site Engineer
text | 7cdec5ec-b1ee-5427-9297-4d0f37a475d7 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 4.5 Material Properties Testing (Scale B)
label | e4f68924-f12e-5189-8401-14c46e19cb17 |  | note | FREQUENCY: Once per lot or per material change, as per Table 204.141
label | f08cbd24-afdb-5013-87e6-3fa86acc14ac |  | note | ACCEPTANCE CRITERIA: Refer to Reference Documents for particular Frequency of Testing and Material Properties Testing Requirements.
label | bdc15a1b-e9c8-5980-b265-e56c1000bd36 |  | note | ○ Table 204.161 for Project Specific Scales for each applicable Road Name or Area.
label | bd67b500-fcf4-5eaf-8c13-317f4117635f |  | note | REFERENCE DOCUMENTS: Cl 204.14, Table 204.041, Table 204.161
label | b97854cc-7afe-54f5-bcd4-532dbfbb5afa |  | note | INSPECTION/TEST METHOD: Verify
label | 3eabd4b3-defc-5bf5-89a9-26e6825b7c21 |  | note | RECORD OF CONFORMITY: This ITP signed
label | fcf43dbc-3a08-5164-875e-978f65de7d20 |  | note | TP
label | 29d2a9e2-ad73-5014-8839-ea561ca401c9 |  | note | RESPONSIBILITY: Site Engineer
text | d82d9c76-7568-57aa-8b8e-63395b18f00a |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 4.6 Preparation and Maintenance of Final Earthwork Surface and Subgrade
label | 65616b45-bcdf-58b0-b9ff-e169b598a37f |  | note | FREQUENCY: Each Lot (Final Layer only)
label | 23aab174-4ddb-5ec4-a473-08e94a5a2bed |  | note | ACCEPTANCE CRITERIA: Smooth, hard, tightly bound surface presented. Free from depressions capable of holding water.
label | ac7e0ca5-7c07-53f1-a42d-753363af1890 |  | note | ○ Material within 150mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to placement of pavement layer.
label | 052810b6-198a-5a96-a6c9-3a033dabf8bb |  | note | REFERENCE DOCUMENTS: Cl 204.15
label | 8d49688d-2f4d-50fd-b70e-96897694af64 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 8608a11c-2b1e-5028-84c8-af65bb8681fc |  | note | RECORD OF CONFORMITY: This ITP signed
label | a53748f2-e041-56bc-8cb5-8ecd559d955a |  | note | IP
label | 2b7206b9-4bcb-5a9f-b2ae-635748ea555d |  | note | RESPONSIBILITY: Site Engineer
text | 5d773911-5fca-5924-8207-4308ce6560e6 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 1178da32-7383-5eff-ab96-72a280a4956f |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | fad571bc-9ee7-57a5-8bfd-c0dc83ad17bb |  | textbox | Print Name:
text | cb2b6e2e-f79a-54c6-b99c-36e8e62dfa5e |  | textbox | Position:
text | c44fd6d8-60ae-5e60-a18e-d1aec3a380aa |  | textbox | Date:
holdpoint |  |  | signoff | Add Signature
checkpoint-no-status |  |  | checkpoint | Table 204.031 Minimum Number of Level Measurements and Tolerances
label | 27d4100d-1178-56ac-b962-8e7e948a5180 |  | note | Scale of Surface Level Measurement ¦¦ Minimum Number of Measurements per Lot ¦¦ Tolerance: x̅ Range (mm) ¦¦ Tolerance: Maximum S (mm)
label | df28c92f-43c1-5bd1-861e-a279d088b454 |  | note | – – – – – – – – – –
label | 951cffda-df4b-5e6b-99b5-5ba44f7dafee |  | note | Scale A ¦¦ 80 ¦¦ +5 to -15 ¦¦ 12
label | c37cfbd9-a39d-5fab-b766-bd805c7b63f2 |  | note | Scale B ¦¦ 40 ¦¦ +5 to -25 ¦¦ 15
label | e4331167-0ddd-5116-9160-20cbd9386c24 |  | note | – – – – – – – – – –
label | be1ec9b9-733e-5ec6-9fea-19f0a26f8b8b |  | note | Notes:
label | 59e64809-ac59-5288-b31b-cbd367103d43 |  | note | 1. x̅ is the mean value of all level readings taken in the lot
label | 18fa5f30-2875-5ee2-baa9-1efdf4cf8d3c |  | note | 2. S is the standard deviation of all level readings taken in the lot
label | 04281dbe-52ef-5033-93a1-b1523f6cc678 |  | note | 3. A negative value designates a measured departure below the design level and positive value designates a surface level above the design level
checkpoint-no-status |  |  | checkpoint | Table 204.041
label | 161e3c70-49f1-570e-80f4-ab15ac5b4903 |  | note | Location and Use of Type A Material ¦¦ Physical Properties: Assigned CBR (min) % (1) ¦¦ Physical Properties: Swell % (1) ¦¦ Physical Properties: Permeability (max) m/s (2)
label | 1141da00-fab2-5f91-887b-e31fd897c5a7 |  | note | – – – – – – – – – –
label | 76bc71cf-be37-5cd2-94bb-5e00f0cc6fd5 |  | note | Capping Layer ¦¦ ##:6 ¦¦ ≤ 1.5 ¦¦ 5 x 10^-9
label | 2e0f0ac8-e12a-5970-b887-2cd31e6cedb3 |  | note | Selected Material ¦¦ ##:6 ¦¦ ≤ 1.5 ¦¦ Not Applicable
label | 1e251918-7826-5dfe-a4c9-8fa9c75f281d |  | note | Verge Material ¦¦ ##:6 ¦¦ ≤ 1.0 ¦¦ 5 x 10^-9
label | 22e75b9e-09ba-5443-884c-5ce0968842f6 |  | note | Structural Material ¦¦ ##:6 ¦¦ ≤ 1.5 ¦¦ Not Applicable
label | 40ef2bb1-05cb-5b51-9a91-b4ce9e6c80a7 |  | note | Other Type A Material ¦¦ ##:6 ¦¦ ≤ 1.5 ¦¦ Not Applicable
label | 6689d942-125b-51fd-9e7b-869c749e991f |  | note | – – – – – – – – – –
label | d197d909-2823-5fec-b775-19ccc6b9dfd0 |  | note | Location and Use of Type A Material ¦¦ Limits of Grading (% passing by mass) :: Post Compaction Sieve Size AS (mm)
label | b223ac62-aed5-5e56-82a9-6c529a14a50b |  | note | – – – – – – – – – –
label | 439cf970-24d9-5d61-b7fb-6bb4fcaeed42 |  | note | Capping Layer ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
label | c556b160-ca14-5fd9-822d-24d4103e79c2 |  | note | Selected Material ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
label | 8438b9a4-3a08-5dac-a8ef-9ad3e1ade52f |  | note | Verge Material ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
label | 37e84180-8f79-5236-9199-79287d8d5da3 |  | note | Structural Material ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
label | 4372f7a5-7804-56f4-a652-0218b0f3c0ed |  | note | Other Type A Material ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
label | 98926c89-d449-5efa-9017-8814e8242a4e |  | note | – – – – – – – – – –
label | ac3c0ac3-96dc-5a79-9cd5-0ab480a7250a |  | note | Notes:
label | 7e1a86bb-4da4-5f3e-84c3-537a7ab1cdc3 |  | note | (1) The Assigned CBR and percentage swell values are to be determined in accordance with VicRoads Code of Practice RC 500.20. Sampling for CBR testing shall be undertaken after field compaction.
label | 2d19d017-776d-5fc4-bfdd-f38eea3de8c6 |  | note | (2) The permeability value is to be determined in accordance with VicRoads Code of Practice RC 500.16. The permeability value is to be determined on specimens manufactured from that fraction of material which passes a 19.0 mm AS sieve, compacted at optimum moisture content and 98% of maximum dry density as determined by testing using standard compactive effort for CBR and swell.
checkpoint-no-status |  |  | checkpoint | Table 204.111 Fill at Structures
label | 36e67ec8-10b4-5fe4-9657-060cd2df5b63 |  | note | Non Vibrating Rollers - Static Weight * (tonne) ¦¦ Vibrating Rollers - Total Applied Force ** (kN) ¦¦ Minimum Distance from Compaction Plant to Abutments, Retaining Walls and Wing Walls (m) ¦¦ Minimum Cover over Top of Culverts (m)
label | c5af55fe-4461-5e26-a68b-753162c62166 |  | note | – – – – – – – – – –
label | 48060762-e4ab-583c-93a6-0a0bc42e8223 |  | note | Less than 2 ¦¦ Less than 20 ¦¦ 0.15 ¦¦ 0.15 ¦¦ 0.15
label | bec49816-4088-5e27-88a2-a52ea56ef375 |  | note | 2 - 5 ¦¦ 21 - 50 ¦¦ 0.3 ¦¦ 0.3 ¦¦ 0.15
label | 82a4933a-76ab-528e-9dbe-56a51118a68f |  | note | 6 - 10 ¦¦ 51 - 100 ¦¦ 1.2 ¦¦ 1.2 ¦¦ 0.4
label | 1f0e85da-fd80-584b-a916-965c5a81d2c6 |  | note | 11 - 20 ¦¦ 101 - 200 ¦¦ 2.4 ¦¦ 1.2 ¦¦ 0.4
label | 5b97d085-e339-5975-a828-a27c3a628230 |  | note | 21 - 35 ¦¦ 201 - 350 ¦¦ 2.4 or height of structure (whichever is greater) ¦¦ 1.2 or height or structure (whichever is greater) ¦¦ 0.7
label | b1f37a23-530d-5d24-a9e6-63591831e098 |  | note | – – – – – – – – – –
label | ba5070cf-ab3b-58c7-bbfd-102285dadbc4 |  | note | * Includes vibrating rollers operating in non-vibrating mode.
label | f294a98d-2100-5512-a068-38f767845853 |  | note | ** Total Applied Force is the sum of the static weight and the vertical component of centrifugal force.
checkpoint-no-status |  |  | checkpoint | Table 204.131 Compaction Requirements
label | ff4a5693-0cd9-54e2-90da-59755029cd19 |  | note | Material Type and Location ¦¦ Scale A: Minimum Characteristic Value of Density Ratio (%) ¦¦ Scale B: Minimum Characteristic Value of Density Ratio (%) ¦¦ Scale C: Minimum Characteristic Value of Density Ratio (%)
label | 31ea86d2-6940-5f39-8f27-b5e9ddac5656 |  | note | – – – – – – – – – –
label | 75d455c6-915c-5dd3-8bf2-da19eebf4c86 |  | note | All Type A Material ¦¦ 99.0 ¦¦ 98.0 ¦¦ 100.0
label | 2dcad875-a547-55bf-9351-fafd6318ef5e |  | note | Type B Material placed within 400 mm of top of Type B Material ¦¦ 99.0 ¦¦ 98.0 ¦¦ 100.0
label | 20201e20-4e38-5cf7-b597-105f1a205730 |  | note | Ripped and re-compacted material below Cut Floor Level ¦¦ 99.0 ¦¦ 98.0 ¦¦ 100.0
label | ecf4d795-6ff3-5e0e-acc6-f868b1c6c96e |  | note | Type B Material placed more than 400 mm below top of Type B Material ¦¦ 97.0 ¦¦ 95.0 ¦¦ 95.0
label | 9cfad10b-0f78-5dd7-b800-c6bc601b2531 |  | note | The top 150 mm of areas where fill is to be constructed ¦¦ 97.0 ¦¦ 95.0 ¦¦ 95.0
label | 22e1ff4b-f7b4-5715-8be8-862f51704cc1 |  | note | Type C Material ¦¦ 97.0 ¦¦ 95.0 ¦¦ 95.0
checkpoint-no-status |  |  | checkpoint | Table 204.142 Minimum Frequency of Testing for Compaction and Moisture Content
label | 5c563a35-866e-56fe-8d94-02be4fa51a09 |  | note | Material ¦¦ Acceptable Lot Size in a Single Layer of Work ¦¦ Minimum Testing Frequency
label | 6349b566-ab05-51d3-aa95-ddfe65d19d2b |  | note | – – – – – – – – – –
label | 97b35233-5f6b-5c00-827d-f95e4fba7bb1 |  | note | Type A Material ¦¦ One day's production or 5,000 m^2, whichever is the lesser ¦¦ Every second lot of like material and work
label | ce09b80c-8eb6-5636-bf02-e547943a1cc7 |  | note | – – – – – – – – – –
label | 4534f2a1-fc4b-5c61-b2a0-5d9f45db743b |  | note | Type B Material
label | 9dfec5c5-f6d1-5d5d-a98f-039f57ae0f40 |  | note | • Ripped and re-compacted below Cut Floor Level ¦¦ One day's production or 10,000 m^2, whichever is the lesser ¦¦ Every sercond lot of like material and work
label | 24148d89-ca64-5c47-a8e5-bbca5f251379 |  | note | • Placed within 400 mm of top of Type B Material ¦¦ One day's production or 10,000 m^2, whichever is the lesser ¦¦ Every second lot of like material and work
label | 7fbfdc06-841d-5a00-b682-336c267aab3f |  | note | • Placed more than 400 mm below top of Type B Material ¦¦ One day's production ¦¦ Every third lot of like material and work
label | 224d1535-ed9c-5104-a3a9-975e4e2b9f39 |  | note | – – – – – – – – – –
label | 731b4eb4-3917-5111-afdc-49cea01e8e83 |  | note | Type C Material ¦¦ One day's production ¦¦ Every sixth lot of like material and work
checkpoint-no-status |  |  | checkpoint | Table 204.161 Schedule for Surface Tolerance, Material Properties and Compaction Testing
label | bce0d8f6-3969-528b-94a8-7867ce47bf46 |  | note | Road Name ¦¦ Chainage / Location ¦¦ Scale of Surface Level Measurement (A, B or C) ¦¦ Scale of Material Property Testing (A or B) ¦¦ Scale of Compaction (A, B or C)
label | 8314b308-84a8-5271-b211-f493261aa24a |  | note | – – – – – – – – – –
label | d5144c75-bcf2-5e20-8136-ef5a8a69e42f |  | note | Bruny Island Main Road ¦¦ Within Limits of Works ¦¦ B ¦¦ B ¦¦ B
label | bded77fe-481a-562e-a29b-1431e4007590 |  | note | – – – – – – – – – –
label | b8066a02-a2bc-5b90-a79b-3cf8f8df4ad5 |  | note | Note: Where no level of testing is nominated, Scale A applies.
checklist-sectioned |  |  | checklist | ITP - Stormwater and Subsurface Drainage | itp |  |  |  | Yes | ITP - Stormwater and Subsurface Drainage Rev1 | 924e129d-ceed-4632-9c89-d8fdcb5ad08c
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | 74eb50ae-3733-5d52-901b-9fa131dd8e2c |  | note | FREQUENCY: Prior to commencing any activity
label | ad55bc5c-e747-5292-9e7f-bf97d402d2b2 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 9107e19c-06c1-59ec-8ccd-aa1eebd7a6a4 |  | note | – using the correct and complete set of drawings
label | f53dd5ac-39a0-522a-9977-aa14bf01d47c |  | note | – all drawings are the latest revision
label | 48c6d6f3-3651-5f16-951f-8b84a2312b9c |  | note | – Conflicting documents will be referenced to the hierarchy of documents listed in Section 175.03
label | 2c77751c-c59b-55c0-9790-da1059629c05 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers, Cl 175.03
label | 62b88d56-1d43-5547-b6da-ae9d68f122ba |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 6268c10b-fe81-583f-bb1a-21126339161f |  | note | RECORD OF CONFORMITY: This ITP Signed
label | b5878f5e-2c70-521b-8709-a6b535812105 |  | note | HP*
label | ae134cb1-58b2-50ee-b282-baabcce7bb68 |  | note | RESPONSIBILITY: Site Engineer
text | 877d4aee-1bfb-5dbb-91b9-4682c031d511 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures and controls
label | a1aa2218-f795-5c93-af5b-530a97f3dc57 |  | note | FREQUENCY: Prior to commencing any activity
label | 5d32329f-54b0-5bc1-8e0b-78a28f4f4cad |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 9150653d-d0e7-51f4-a95b-16c9963f283d |  | note | REFERENCE DOCUMENTS: OHSMP, EMP, TMS, SWMS, WP
label | 3054104c-7e6c-55b2-83fd-0e7b87fa8fed |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 00101d52-6a67-53f1-a1a4-ec032dc0ab27 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | c359678a-9a03-58e1-94c2-a977d2268277 |  | note | HP*
label | 8dc66744-d1dc-530d-b743-594628946ca1 |  | note | RESPONSIBILITY: Site Engineer
text | 2838a912-b933-55fe-aead-5113d962e79f |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 1.3 Material Classification
label | e8b45373-758e-5973-b6ac-39f4202f39bd |  | note | FREQUENCY: Each Lot
label | 3e371dea-d28e-50d7-9519-399de1217141 |  | note | ACCEPTANCE CRITERIA: Pipes supplied shall be of the category and diameter shown on the drawings or specified in clause 702.12 and shall comply with the requirements of the appropriate Australian Standard in accordance with Section 175 or as follows:
label | 43ea0f6c-2da1-5f24-9ad4-60fb5791b0ff |  | note | ○ Category 1: Perforated plastics Class 1000;
label | 67503756-5686-5061-8f4e-cac021947479 |  | note | ○ Precast concrete Class "2"
label | bdd020b8-98b8-58aa-a69b-41761e370056 |  | note | ○ Category 2: Perforated plastics Class 400
label | 5399e99c-4b01-5dd9-9dd1-b2b940ab4f34 |  | note | ○ Category 3: Geocomposite drains
label | 2a1830d3-4e77-5fd4-a87a-4baa0faa1edf |  | note | ○ Granular material as per clause 702.05, Geotextile material as per clause 702.06
label | e475c979-ce2d-5e58-871d-64a771ffb306 |  | note | REFERENCE DOCUMENTS: Cl 702.04, Cl 702.05, Cl 702.06
label | 30402610-65eb-5fe5-9c9a-35736ad056a4 |  | note | INSPECTION/TEST METHOD: Verify
label | 1ec79632-3bee-51df-a4f8-cb3975383226 |  | note | RECORD OF CONFORMITY: Order acceptance certificate, This ITP signed off
label | 77b83d5a-597f-59c0-ba19-0e89648d832c |  | note | IP
label | 32930fd0-c5c9-5857-bb21-5d837888f997 |  | note | RESPONSIBILITY: Site Engineer
text | 05732e12-b30f-59e3-b86f-03c532555fe0 |  | textbox | DATE:
checkpoint-group |  |  | section | 2 - Procurement of Materials
checkpoint-status |  |  | checkpoint | 2.1 Precast Reinforced Concrete Pipe Supply
label | 4cd42d2a-16cd-5913-8302-3bb492fb3d7d |  | note | FREQUENCY: Prior to works commencing
label | 31fbc796-6129-571d-a58e-66d22505b57e |  | note | ACCEPTANCE CRITERIA: Pipe class and size and endwall type as per drawings and Cl 701.05
label | f67c2b3a-6615-50bd-a39d-512556b0b7d2 |  | note | REFERENCE DOCUMENTS: Cl 701.05, Drawings
label | 16daac94-d101-5991-b9f3-849afd3e0625 |  | note | INSPECTION/TEST METHOD: Verify
label | d7536c8b-b1db-5c2c-93d4-f62bd003acce |  | note | RECORD OF CONFORMITY: This ITP Signed, Order acceptance certificate
label | 233f70e1-21d4-59eb-8168-00200933e17c |  | note | HP*
label | 537b44b8-b49c-5fab-977c-447543dd2b05 |  | note | RESPONSIBILITY: Site Engineer
text | e2b78960-9fac-5ee5-be82-0ea15a558296 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.2 Precast Reinforced Concrete Inlet and Outlet Structures supply
label | b923c973-5aa4-52ff-954c-d14283b6e29f |  | note | FREQUENCY: Prior to works commencing
label | 23df31ed-3fc9-51a3-9a6d-bdc831518531 |  | note | ACCEPTANCE CRITERIA: The supply of precast inlet and outlet structures shall conform with D.S.G standard drawings
label | bd8aef2c-d453-5d65-9009-904d48493348 |  | note | ○ Concrete supply shall conform with Section 610 and reinforcement supply shall comply with Section 611.
label | 494f6825-e59a-5299-8ade-f662ae81137e |  | note | REFERENCE DOCUMENTS: 610, 611, standard drawings
label | fa9183cd-1205-5f91-b3d6-f46cebb1e696 |  | note | INSPECTION/TEST METHOD: Verify
label | 7f840b1c-f07b-5f48-a3ab-f8435774eaeb |  | note | RECORD OF CONFORMITY: This ITP Signed, Recievable Inspection Checklist
label | 599047fe-2358-5457-96fe-9c219a04dd6b |  | note | HP*
label | c07e0e70-f20b-5638-a357-bcf2d4497486 |  | note | RESPONSIBILITY: Site Engineer
text | 67096968-6442-55de-b0a3-beb488103eb6 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.3 Bedding and Backfill Material Specification
label | 36b0cf37-1592-52f4-b555-c6e20edc2909 |  | note | FREQUENCY: Grading 1 test per 1,000t
label | 71193509-a5bf-513e-bb9c-d0c1a8c16a87 |  | note | ACCEPTANCE CRITERIA: Bedding and Backfill materials free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092
label | df74fb99-ea47-5e43-9427-6d1dc791e962 |  | note | ○ Ordinary backfill shall be free from perishable matter and shall conform with the requirements of Table 701.091
label | e49e0e11-1b89-504a-bda8-f582a8f923cb |  | note | REFERENCE DOCUMENTS: Cl 701.09(d), Table 701.091, Table 701.092
label | da11d8c8-fb65-5f84-8bb6-833c5a8d69d4 |  | note | INSPECTION/TEST METHOD: Verify
label | c946415b-c8a5-546a-bc5b-95ab0cd1bd60 |  | note | RECORD OF CONFORMITY: This ITP Signed, Quarry test report
label | 9f3af720-4121-54fa-b759-b3ec42affda0 |  | note | TP
label | b53bb76f-8402-573d-b3c6-af690b25b467 |  | note | RESPONSIBILITY: Site Engineer
text | 4740869e-df1e-55d3-90dc-9cb51b083c6b |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.4 Setout of Works
label | 95a38a41-7158-557d-84b6-1f0e0697cc55 |  | note | FREQUENCY: Prior to works commencing
label | 84bb35a2-2d59-50b3-946d-2862b95b1e22 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | 55a23454-0ad8-5acc-b1a5-502769652a82 |  | note | Prior to commencement of excavation for the culverts the contractor shall confirm the position of all culverts with the Superintendent
label | 203db647-f9de-5e12-9c44-af5188f347f2 |  | note | REFERENCE DOCUMENTS: Cl 701.10
label | 6596337e-0bd6-5c06-947b-dab1e619a372 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 8a0f066e-8fbe-560c-ae86-36bea157cf11 |  | note | RECORD OF CONFORMITY: Survey records, pegs on ground & this ITP Signed
label | fafe70c2-11a7-58aa-bffe-37ad76f9dbfa |  | note | HP
label | 0339524f-9a3d-52c6-9f4e-520e855d190a |  | note | RESPONSIBILITY: Site Engineer / QAV
text | 4c0db22e-7509-5dd6-b43d-e73cba33abe4 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Installation of Underground Stormwater Drainage
checkpoint-status |  |  | checkpoint | 3.1 Excavation Permit
label | 93c03dc5-cdab-5d84-b9c3-676a61e32162 |  | note | FREQUENCY: Each lot
label | 18dca1c1-6d43-562a-a005-46836722e6ae |  | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | cb200873-7d97-5ce2-9486-986e4c9d5305 |  | note | ○ Plant and equipment shall be appropriate for the task.
label | de89d9cc-0e15-5e9e-a20e-0432647f589a |  | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | 48fdd000-b41e-5159-a3fc-d61de28f1466 |  | note | REFERENCE DOCUMENTS: Excavation permit
label | d90058e9-c7ae-53ca-bb2d-0624d9633092 |  | note | INSPECTION/TEST METHOD: Verify
label | 49f5e834-92d5-51ca-9930-a8c6cc8126e0 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 6aa2c15d-d8c0-579f-b044-f61e498dd101 |  | note | HP*
label | 31f4eea5-7c00-5ac3-bc71-20fd1ec32f05 |  | note | RESPONSIBILITY: Site Engineer
text | f76cd31b-6aba-54b6-bfee-1907119a30f2 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 3.2 Excavation for trench
label | 3732a03b-ecae-5c4e-8b42-970c4d6892b8 |  | note | FREQUENCY: Each Lot
label | 5a5e24c8-7a04-510f-a007-5318e96cd555 |  | note | ACCEPTANCE CRITERIA: Excavation for the installation of pipes shall allow for the clearance from the outside of the pipe to the wall of the trench between 300mm and 600mm;
label | 5e926bd0-3864-5ed2-90c8-0c0068b5ad47 |  | note | ○ The base of the trench shall be inspected to verify compliance with the requirements in this clause prior to placing bedding in comleted exacavations.The Superintendent shall be notified at least 24 hours prior to the inspection.
label | 83fb9ad2-cc2a-5065-bbe3-aab13ecd0b17 |  | note | REFERENCE DOCUMENTS: Cl 701.15 Table 701.151, Cl 702.08
label | 668b12e6-6c1b-5e9a-ad50-6e6d35e5cc4e |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 223430a1-41a8-5aeb-ab70-e0dafe7602b3 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | b1e63937-9d8f-5da1-b227-989b1af86732 |  | note | HP
label | 7d1f08f3-8241-5d11-a84d-a9932d2aaba2 |  | note | RESPONSIBILITY: Site Engineer/ Superintendent
text | 915f9965-ae9c-5137-b39a-f0fc4f36d28d |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Trench Base Preparation / Bedding
label | 8dec3789-6deb-506c-b3e9-3ce7471dbe2f |  | note | FREQUENCY: Each Lot
label | 64f9fdbf-6ff3-5355-924e-9739226e39ae |  | note | ACCEPTANCE CRITERIA: Bedding material placed in full width of trench and compacted to at least 100mm thick, or; where the culvert is to be placed without trenching, to a width of 0.8m greater than the overall width of the culvert.
label | 6e6b9cd4-2bc6-5f71-baf5-847b101fe69a |  | note | ○ Bedding of granular filter material of thickness between 25 mm and 50mm shall be placed across bottom of trench and shall be tamped and screeded or graded to level.
label | 4cfa9e27-6678-5468-9407-1a4943310d26 |  | note | REFERENCE DOCUMENTS: Cl 701.16, Cl 702.09 (c)
label | 6b3dc1ea-2eae-5bed-a00f-c83a1e1caa44 |  | note | INSPECTION/TEST METHOD: Visual inspection / Measure
label | 146fd257-76c3-5f3e-9b66-ae94c3802536 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 0bced4c2-5170-526c-ba10-608cebbdc4cf |  | note | IP
label | 8ce903e4-6e92-5ba8-a4e0-4c1bfe754a7c |  | note | RESPONSIBILITY: Site Engineer
text | 16b9b954-b7c1-5c49-8663-8d6503a7f6eb |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 3.4 Laying/ Placing of pipes
label | e3773416-0384-551d-b470-989c73e8a05f |  | note | FREQUENCY: Each Lot
label | 04956ff2-0fce-5c31-a5e3-17c0f5315ffe |  | note | ACCEPTANCE CRITERIA: Laying of pipes to commence from the downstream end. Pipes to be laid with rebate or socket end facing upstream and be fully entered. Departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250.
label | 5db9c4d5-c5e3-5f9a-9ee6-3aa013cc274b |  | note | ○ Pipes shall be placed centrally in the trench on the prepared bedding and held firmly in place
label | 974b9229-8fe2-5820-84e6-8b8d7cba065c |  | note | REFERENCE DOCUMENTS: Cl 701.10d Cl 701.17, Cl 702.09 (d)
label | 7ebdddaf-ccd1-552b-83e1-8e36f762b8bc |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 1617a33e-0a59-55f3-83f8-e28e65cdb601 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 49338a25-1717-551a-8ec0-2a9f2db8c97d |  | note | IP
label | 25e4a9b5-3238-5269-a316-c7f486d5251c |  | note | RESPONSIBILITY: Site Engineer
text | 43e90cbd-5787-5902-a293-6703af2139f3 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 3.5 Jointing
label | 655538b3-b94e-5fa6-8d1f-c53ff8cd7810 |  | note | FREQUENCY: Each Lot
label | ca12a046-4df8-5857-9e7c-4c500a2a8b47 |  | note | ACCEPTANCE CRITERIA: Rubber ring joint pipes shall be jointed with rubber rings. Rubber rings shall be kept undisturbed, clean, and free from dirt and other foreign materials and shall be stored undercover if pipes are not to be installed immediately.
label | 345d56b4-95ea-502f-9ebb-7231a26a598d |  | note | REFERENCE DOCUMENTS: Cl 701.18
label | be4a6e40-8fd9-5306-b970-2f6a62fc08fc |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 074a5e99-315d-5dc8-9b80-e9c94b31652f |  | note | RECORD OF CONFORMITY: This ITP Signed
label | e175911b-eb59-53ea-a383-6f9403e71635 |  | note | IP
label | 5b038257-8757-54a9-ab29-46dbe924a369 |  | note | RESPONSIBILITY: Site Engineer
text | 7a386856-b58d-550f-a358-2a9985cf2cc4 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 3.6 Tolerance
label | 4aeca74e-3435-5035-a8cd-a7e7ef3e77e2 |  | note | FREQUENCY: Each Lot
label | d21040ba-e13d-571a-8e14-7547a6d27f6c |  | note | ACCEPTANCE CRITERIA: Location of each culvert run verified by survey prior to backfilling and recorded in as-constructed drawings.
label | ee13344f-07ca-52e3-8167-e4c66e2449d2 |  | note | ○ Tolerance:
label | c5c912a9-06cb-5062-9586-04676db006d0 |  | note | • Invert level of pipes at pits ± 50mm
label | 07252418-fd0f-5532-bb7e-bb89cf7a6086 |  | note | • Departure from design grade of pipe runs ± 10mm in 10m provided min grade > 1:250
label | 4ac347d0-2e31-5a73-ada1-088042703ab0 |  | note | REFERENCE DOCUMENTS: Cl '701.10
label | 8bf9daff-1007-56e2-a543-388ba72a292b |  | note | INSPECTION/TEST METHOD: Verify
label | c27e7db0-d1cc-5d1a-bf46-29977894f980 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 9e97071b-1ad8-58bb-8653-d7bbcb4bd2e0 |  | note | SCP
label | ae294bfb-d231-5b7e-881f-eb32e05df4c3 |  | note | RESPONSIBILITY: Surveyor, Site Engineer
text | 3e63e1fb-e505-5c7e-ae29-93c976f5671b |  | textbox | DATE:
checkpoint-group |  |  | section | 4 - Backfilling of Stormwater
checkpoint-status |  |  | checkpoint | 4.1 Filling
label | 97ae0d70-0d8f-5b5a-82d2-fb79f06af895 |  | note | FREQUENCY: Each Lot
label | cb74581e-47d0-5266-92d7-cccf3735dd26 |  | note | ACCEPTANCE CRITERIA: (i) Culvert Under Area to be Paved
label | b3d0ce94-a7b5-5474-8850-ae2f2e147853 |  | note | • The trench shall be backfilled to design subgrade level with selected material.
label | 40c2287b-e60e-568c-8ab2-90cebdf8c67c |  | note | (ii) Culvert Under Area not to be Paved
label | 60b1e28e-0e67-5177-ad91-bccdaa1c8c4c |  | note | • The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level.
label | 322d39c9-824f-506a-a93a-971ae5398954 |  | note | REFERENCE DOCUMENTS: Cl 701.19
label | 9f4631ed-0aec-5aca-b2eb-a81e303b8301 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | ef817b67-558d-52d6-b134-b657d683efcc |  | note | RECORD OF CONFORMITY: This ITP Signed
label | e1578691-9386-5a16-beab-252f188ce99d |  | note | IP
label | 4e84d121-59da-509c-a64a-6467c4eccdcd |  | note | RESPONSIBILITY: Site Engineer
text | eaace962-a756-5d3e-9442-ca9541947c67 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 4.2 Placement of granular backfill
label | b6fecf25-368d-5462-85d3-3bacc1fab415 |  | note | FREQUENCY: Prior to backfilling
label | 0a140f76-c0f9-50dd-af55-bec01a3c8c61 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | dd7b8b31-04be-55df-9220-525decadcc6f |  | note | ○ Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the submitted quality procedures
label | ff4e177d-688b-5d6e-9361-f7b383031c50 |  | note | REFERENCE DOCUMENTS: Cl 702.09 (g)
label | 29984a7a-357b-59d6-9ed6-b49e56d32d57 |  | note | INSPECTION/TEST METHOD: Verify
label | c00b3f51-5eb4-5616-81bc-36fc46eb5d73 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 3a501268-6cf7-5030-8a9c-d82ad836bd96 |  | note | HP
label | ea8e9c9d-e02b-5df0-823d-c7a1bee8262c |  | note | RESPONSIBILITY: Site Engineer/ Superintendent
text | 8a07d7db-9c6e-50ee-868e-355e259a840f |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 Placement of no fines backfill
label | dd5f59cf-8f73-5419-85e7-530ae9ebb34a |  | note | FREQUENCY: Each Lot
label | 8b4c0374-6814-51cf-a415-00c819b3c8b4 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | c2aee799-ab03-5a3e-a009-2533607219d8 |  | note | ○ Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete to prevent segregation and the formation of a slurry layer at the surface of the concrete which may prevent the passage of water into the filter material.
label | a00ed959-4892-5511-bc63-c0c578aeb794 |  | note | REFERENCE DOCUMENTS: Cl 702.09 (g)
label | 745fa7de-ac09-5d89-970f-ad5dd3073064 |  | note | INSPECTION/TEST METHOD: Verify
label | 41361243-7428-59d6-a25a-5633af85e133 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 653747e7-fddf-56c7-a4cf-85129bde8326 |  | note | HP
label | 7184e0c5-c336-57a7-ad9d-f70566e52598 |  | note | RESPONSIBILITY: Site Engineer/ QAV
text | 8082636b-6247-5645-9bb9-e59e0986e6be |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 Testing and Acceptance of Fill Materials
label | 72785751-b6a9-5f01-8649-a0d727ab34c4 |  | note | FREQUENCY: 3 Tests per Lot tested with 20% of all Lots tested
label | d44c62f6-c101-5f65-92e3-2613f1580b9a |  | note | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150mm loose thickness and shall be assessed for compaction and moisture content.
label | 547a4c51-868a-59aa-9027-0443a8343005 |  | note | Bedding shall be compacted to refusal using hand held mechanical equipment.
label | 2719bdc8-4aaf-599f-bf15-a936e98389cd |  | note | Backfill material with nominal size < 40mm after compaction shall be compacted to a mean density ratio of not less than 97% CDR.
label | 1f70f4ad-d873-529c-9f2e-0e712584855a |  | note | Backfill material with a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | 7a59655e-439d-5953-a57c-34bd7fe0e4e7 |  | note | REFERENCE DOCUMENTS: Cl '701.20
label | 00bf2b71-0552-5a4d-be80-88e0b5773701 |  | note | INSPECTION/TEST METHOD: Verify
label | 10b44adf-4544-584d-9ec3-30875024e5b2 |  | note | RECORD OF CONFORMITY: Compaction Test Result OR This ITP Signed
label | 412ad1d3-c72c-5c07-b205-23287cd4933e |  | note | TP
label | d020ce67-e9b1-59f2-b4e2-7cc3b3045561 |  | note | RESPONSIBILITY: Site Engineer
text | f425410a-f8ee-5ca2-980f-3e8e380ac57f |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 4.5 Access Points and Flushouts
label | 5c49e877-c145-5751-ac8a-cc0c5d1d1cec |  | note | FREQUENCY: Each Lot
label | 67491d41-14b8-5b95-a562-dc4624372612 |  | note | ACCEPTANCE CRITERIA: Access point installed at the beginning and end of the drainage run and inspection openings at intervals between 100m and 150m. Flushout risers have same diameter as pipe.
label | b64c8179-15e5-5de3-b6af-93d860764209 |  | note | REFERENCE DOCUMENTS: Cl 702.10
label | b0ada4f8-e4b1-57f3-b5b6-6498173d90d6 |  | note | INSPECTION/TEST METHOD: Verify
label | 529293ca-95e8-50b3-bc9d-50bee22c921c |  | note | RECORD OF CONFORMITY: This ITP signed
label | 1b34c626-cd5e-542d-86d7-7be6dba031df |  | note | IP
label | c4c040eb-7398-5fd5-8a2d-4b6484d24056 |  | note | RESPONSIBILITY: Site Engineer
text | 896931e0-0840-505b-804e-be900bd91073 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 4.6 Flushing Test
label | 39eccfa6-ec81-561f-8404-d8f4e951c8e7 |  | note | FREQUENCY: At completion of stage
label | 91459a86-123a-5f5f-b450-b4e0dd1e65eb |  | note | ACCEPTANCE CRITERIA: Flushing test undertaken on each subsurface drainage line after completion of the drains, flushers and risers, and after completion of barriers and road furniture. The test should be witnessed by a representative nomitated by the superintendent. Record of flushing tests must be kept.
label | 8e3d9799-8b48-5704-895d-7ac1ab93146a |  | note | REFERENCE DOCUMENTS: Cl 702.09(h)
label | 7490baf5-1dfa-5c48-815a-d66b8cb12294 |  | note | INSPECTION/TEST METHOD: Site inspection
label | 8255fe91-acac-5dee-b76d-01f55c5ed8db |  | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | 877a7f9a-69e5-5f60-89ce-a4dbaa187b0a |  | note | TP
label | c1e1b3c9-f78a-5509-a123-eddb149d1135 |  | note | RESPONSIBILITY: Site Engineer / QAV
text | a539a749-0149-5c72-9603-f65b15d0d463 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 4.7 Installation of Inlet or Outlet Structure
label | 94c198df-8765-5d01-8064-63ea15e8a4ba |  | note | FREQUENCY: Each Lot
label | b54e5501-2c45-5bb7-850e-b1c759962392 |  | note | ACCEPTANCE CRITERIA: Inlet and outlet structures shall be installed to a tolerance of +-20mm where matching kerbs or barriers or +-100mm in all other areas.
label | 96d99a37-b49a-5b75-b6d0-a31dcf138307 |  | note | REFERENCE DOCUMENTS: Cl '701.10 Cl 701.25
label | 9771600e-afa0-5b3d-b747-18ffebda7038 |  | note | INSPECTION/TEST METHOD: Verify
label | 3d3d7cda-2f15-5b8e-909c-75564c6d9b79 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | b5361c4d-483c-584f-9f17-4c768cbfad2b |  | note | IP
label | 28227446-d453-5742-829a-39fc2213bd6c |  | note | RESPONSIBILITY: Site Engineer
text | 3468fc5e-6a39-5377-985e-84a23e77b1a8 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 4.8 Culvert Coverage
label | 45f97e0a-876d-56c8-852e-ecdc7c213b76 |  | note | FREQUENCY: Each Lot
label | f0348a26-37e1-5eb5-9095-44ba1f4d57ac |  | note | ACCEPTANCE CRITERIA: Until the minimum compacted thickness of cover in Table 701.141 for axle or track loading has been provided, construction traffic shall not be permitted to cross the culvert.
label | ceb7bc5e-0962-5a10-b7ba-babd723558c0 |  | note | REFERENCE DOCUMENTS: Cl 701.14 Table 701.141
label | f2bddd72-928d-5c51-8cf5-74b7e5cf2835 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | c285f403-2d6d-5f33-bd3b-af61b1297585 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | a3cb9c23-f28c-5540-ae20-9b72e12f6591 |  | note | IP
label | dcb2c9b6-44f5-5c5a-9146-fc58e7dd04a6 |  | note | RESPONSIBILITY: Site Engineer
text | 357f91a0-4beb-594b-9735-586c983fb35a |  | textbox | DATE:
checkpoint-group |  |  | section | 5 - Subsurface / Subsoil Drainage
checkpoint-status |  |  | checkpoint | 5.1 Excavation Permit
label | 9e29d980-6153-57fb-adee-d18c036c4445 |  | note | FREQUENCY: Each lot
label | cf3c094a-369f-523a-91bf-8961bb820dfe |  | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | dbe83c8e-f80a-5384-936b-e287551466cd |  | note | ○ Plant and equipment shall be appropriate for the task.
label | 4fe40cfd-7ba8-5ed6-93f9-06dbca630a5b |  | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | 7d9146f8-0cd5-5b4c-aef4-d15c6bd45f15 |  | note | REFERENCE DOCUMENTS: Excavation permit
label | 4b6dbe09-993b-5684-8924-d360db1e24f4 |  | note | INSPECTION/TEST METHOD: Verify
label | 3938077e-4768-5988-abf5-08444337f655 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 474508ad-6163-51c7-a9f4-da3115f51da5 |  | note | HP*
label | 6fbde1b0-f784-58a0-b1e9-6d9287aa5ca2 |  | note | RESPONSIBILITY: Site Engineer
text | eeebe49e-92b6-5a9b-af59-f76078ada0e6 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 5.2 Excavation of Trench
label | 5429e05d-c740-563d-9a2e-947c2cf6d518 |  | note | FREQUENCY: Each Lot
label | 46262f7d-1287-58a1-846e-423fab9837a6 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | 75322f9f-67a2-5471-8eaa-e03d2519f64c |  | note | ○ Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by Superintendent
label | 59efb801-60e2-5b34-a01c-fe544852093c |  | note | REFERENCE DOCUMENTS: 702.08
label | e4cbffff-a790-5142-b95b-1fee3768a2ff |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 98610fe7-1a7a-5426-aa71-862b4d3086da |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 3b2497f9-5ece-5c59-99bc-20da170d7cfa |  | note | HP
label | fb2e7202-7717-5145-bf85-20b5a4a8c957 |  | note | RESPONSIBILITY: Site Engineer/ Superintendent
text | 74d89796-b753-5ebe-90ba-84a156ba46ec |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 Placement of bedding
label | e3eda897-4e8e-54c1-a925-d3fa1e25d185 |  | note | FREQUENCY: Each Lot
label | 7efd636d-9bde-5e2b-ab60-ea2f327d3b42 |  | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
label | 50284215-4fba-5721-b1ea-58c75eb540c3 |  | note | REFERENCE DOCUMENTS: 702.09 (c)
label | b51adcd3-e316-574d-9e42-9b86eee9fad7 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | f5c253ef-e157-51fc-830e-e79aaabac8c8 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | f0ef134e-bb94-5bc4-8f63-5538c1a99242 |  | note | IP
label | f433611a-8502-5d08-8a12-9ace0806b796 |  | note | RESPONSIBILITY: Site Engineer
text | c12d6227-e4c9-5661-8abd-aab01202fb8a |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 5.4 Placing pipes and geofabric (if required)
label | fdb550c3-2068-5d18-a58c-e0cf0bc02e0e |  | note | FREQUENCY: Each Lot
label | d7cd3a70-ff29-5bf3-bec3-319d98c96830 |  | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
label | 7fccd54b-a5d7-5369-a055-227c10d78e6c |  | note | ○ If geofabric required (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
label | 3797438f-b0ab-55de-8a29-2a5603ffb10a |  | note | REFERENCE DOCUMENTS: 702.09
label | aaf67160-d86e-59fd-a763-25baba7c1255 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 97ccdab3-1ddb-5b0b-a907-66d7814a2158 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 901e9eed-8815-57ac-8719-073d86bfe753 |  | note | IP
label | 3d56f938-2a97-50a1-bdc9-d4d59edf0f22 |  | note | RESPONSIBILITY: Site Engineer
text | 49247281-76f9-5a7d-ab89-a28f804f66e0 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 5.5 Placement of granular backfill
label | fcb58712-0cdd-501d-8472-b786dcaa0b78 |  | note | FREQUENCY: Prior to backfilling
label | 69da5f1e-6474-5776-8ad7-bee381f22622 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | 2b554fff-5c3b-567f-a498-d1d8299a455d |  | note | ○ Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the procedures and reviewed by the Superintendent.
label | b2e6f925-d894-5a2c-8d41-697e86f70324 |  | note | REFERENCE DOCUMENTS: 702.09
label | 655a7905-b035-5607-94c2-17d0dcb915d0 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 12572cd8-8390-5b17-98e9-01b84c2bcb39 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 22a0d7ef-3f65-5156-890d-5038dd57132d |  | note | HP
label | 4e9273df-fdf6-517a-8b52-ce8f6cf17de8 |  | note | RESPONSIBILITY: Site Engineer/ Superintendent
text | 5ddeb622-9532-587b-bac2-a854ec1bb7c6 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 Placement of backfill
label | 91c56e5a-ef3b-5f55-89cc-2064bedab323 |  | note | FREQUENCY: Each Lot
label | 0997ebc0-0402-532e-a213-60bf9ddf41c6 |  | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
label | f10dc322-d130-59fe-97a8-61406964e1bf |  | note | REFERENCE DOCUMENTS: 702.09 (g)
label | 009f5848-aa00-533e-bb69-7f49da7dbb8f |  | note | INSPECTION/TEST METHOD: Visual inspection
label | c55dfc30-f442-5899-b013-a3c8489d0e60 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 4f559db2-62ef-5554-b063-9c4e4a679798 |  | note | IP
label | 8e256635-f95d-5c21-9936-a3623ac07896 |  | note | RESPONSIBILITY: Site Engineer
text | 74f0dd45-d925-5c13-9ffb-bcc95a6eec64 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 5.7 Install Pits and Flushouts
label | 07cef956-c21d-5d69-ae39-f82e5367a027 |  | note | FREQUENCY: Each Lot
label | 3e70f235-e44e-52c2-93a2-8082a2fef8d6 |  | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
label | 35c9fd37-3d28-5c14-af0c-b3215923247f |  | note | REFERENCE DOCUMENTS: 702.1
label | 007cff71-00bc-5fd6-8e4c-e727ccecb870 |  | note | INSPECTION/TEST METHOD: Verify
label | a08a5a8e-acd9-581e-b706-f89547a5112b |  | note | RECORD OF CONFORMITY: This ITP signed off
label | b0c8f947-6b61-55a9-9157-a98351b33c47 |  | note | IP
label | 9c2446d3-7fc3-5a8a-9bdc-aab530cec3d0 |  | note | RESPONSIBILITY: Site Engineer
text | 1dcb49e8-d91c-53ef-8bbc-adf2e3aa598b |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 5.8 Flushing Test
label | 337c19a3-8761-577d-a058-ff62f1760618 |  | note | FREQUENCY: At completion of stage
label | bf01126d-7607-5288-a013-e97d0d4199cd |  | note | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction. To be complete after installation of kerb and channel, barriers and road furniture.
label | 8bf677de-1bed-555b-ae65-9524b6a90bec |  | note | REFERENCE DOCUMENTS: C702.09(h)
label | 6d8bf069-9357-5597-8d98-60576d0b3a10 |  | note | INSPECTION/TEST METHOD: Site inspection
label | fe448b9a-c033-590b-ad0c-78113fd50df7 |  | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | 9413ec1d-e836-57da-968b-03322b616099 |  | note | WP
label | 1534c1de-71da-520f-a8ec-18ed8c35fe21 |  | note | RESPONSIBILITY: Site Engineer
text | bc1ec6a1-be25-54c4-9487-80705387e504 |  | textbox | DATE:
checkpoint-group |  |  | section | 6 - Finishing and Commissioning
checkpoint-status |  |  | checkpoint | 6.1 Finishing and Rendering Pipes
label | 6c305cfc-f7e6-58f4-9911-53941fa92660 |  | note | FREQUENCY: Each Lot
label | 1f85ec99-de24-5941-bd25-115dbcccffe2 |  | note | ACCEPTANCE CRITERIA: All stormwater inlet and outlet connections shall be cut trimmed neat and finished with cementitious mortar.
label | 8d814618-9678-5df0-afcb-4db64376907e |  | note | REFERENCE DOCUMENTS: Work Procedure
label | 5b3c68ad-e493-58e2-9e69-09834413ad19 |  | note | INSPECTION/TEST METHOD: Verify
label | d3826b93-5f73-564c-b533-c43be0819e2c |  | note | RECORD OF CONFORMITY: This ITP Signed
label | ba629e69-987e-5a10-8d9e-ca5852dfd35e |  | note | IP
label | ed553ade-9b51-5476-8086-2563e2577778 |  | note | RESPONSIBILITY: Site Engineer
text | d2f9bf07-2271-5c36-a203-98edca5af222 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 6.2 Inspection of subsurface drainage lines
label | 1f302ad0-aacf-5c6c-8b60-e0a5a73f5c03 |  | note | FREQUENCY: At completion of stage
label | 4b09cc5e-eb42-5e63-a466-b87e27c6b4a6 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | b7a77a03-10d2-5080-8790-52d78aa8d091 |  | note | ○ All subsurface drainage lines constructed shall be inspected, after completion of the flushing test and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | e0a61067-e736-50ad-adbb-945e8e1890b6 |  | note | REFERENCE DOCUMENTS: Cl 702.09(i)
label | 0cacc017-b64f-557f-be16-15c1b8d38ccf |  | note | INSPECTION/TEST METHOD: Site inspection
label | acea6c50-6d67-5461-a801-1f648f3a1ed4 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 6bf4d9c4-f110-5597-b1b6-9bb508503f72 |  | note | HP
label | 8c1e2a96-b5e6-50eb-a6f3-af8fd2016753 |  | note | RESPONSIBILITY: Site Engineer / QAV
text | b3b974d0-88c4-5e26-bd2c-6c6f0919697a |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.3 Repair of Damaged Pipes
label | 76031384-15ac-5a58-ab83-2befac3aba4e |  | note | FREQUENCY: Each Lot
label | db21e5ab-488a-5fe6-bed7-99f2214faadb |  | note | ACCEPTANCE CRITERIA: Damaged pipes shall be repaired in accordance with 701.31 of the Specification, no repairs shall be undertaken without the Superintendent's approval of the repair materials and procedures.
label | df285bb9-b140-517e-8a25-52b06093877e |  | note | REFERENCE DOCUMENTS: Cl 701.31
label | f5c57d57-fc5e-5178-9f07-0d661e31861c |  | note | INSPECTION/TEST METHOD: Verify
label | cf99e051-ce03-5190-9c78-b581f3a0d543 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | e6855386-7ec5-51f5-a05a-9ea04ce62a72 |  | note | HP
label | 36953131-b45a-54fd-a4a4-7e71a8524d19 |  | note | RESPONSIBILITY: Site Engineer / Superintendent
text | f7e91d7a-0313-5645-8893-88c5b9e52ed0 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4 CCTV
label | d5750a93-f775-5ef5-9331-c60acada34ce |  | note | FREQUENCY: Each Lot
label | a5edefa9-7df3-5949-b4ab-2944efa814cc |  | note | ACCEPTANCE CRITERIA: Hold Point
label | 5ac1003e-0dd9-5d9e-9628-b16c735d215a |  | note | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | a7045fc5-3efb-5cca-82df-307d8feb47c4 |  | note | REFERENCE DOCUMENTS: Cl 701.30 WSA 05-2013
label | 5935044e-b573-5162-85e5-ebd87155cd85 |  | note | INSPECTION/TEST METHOD: Verify
label | 6beb0d6b-310d-540b-be2c-d32138ab857b |  | note | RECORD OF CONFORMITY: This ITP Signed
label | f9c7a317-75b1-5d50-996b-6df221e90f93 |  | note | HP
label | 7a0238cc-9cfc-59b2-8ceb-1f79e059e13d |  | note | RESPONSIBILITY: Site Engineer / QAV
text | b2ac13df-6405-5d23-9de1-e46610398bcf |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | 080acae7-2585-5881-a7e5-91aaec64d97b |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 362181f0-b8f9-5278-9502-6de41df5a3a1 |  | textbox | Print Name:
text | d6a56f72-d415-548d-bdc9-335424a78329 |  | textbox | Position:
text | 1094ce10-6441-513a-9c3e-acea4cc1bc37 |  | textbox | Date:
holdpoint |  |  | signoff | Add Signature
checkpoint-no-status |  |  | checkpoint | Table 701.091
label | 44e3eb34-146c-527d-b14e-2ed8836043fd |  | note | Sieve Size - AS (mm) ¦¦ Percentage Passing (by mass)
label | 401ac8c5-68d1-531e-a6a4-0bb2293f2dad |  | note | – – – – – – – – – –
label | 49007691-df1c-574a-8822-2aed625196ab |  | note | Material: Backfill
label | e530eab1-5703-50e6-afaa-acfd08843751 |  | note | 75.0: - ¦¦ 37.5: - ¦¦ 19.0: 100 ¦¦ 2.36: - ¦¦ 0.075: 5-40
label | 7c67ea02-5ed2-5a5b-9bdc-5981d1d82c98 |  | note | Material: Selected Backfill
label | f90852d2-ff8e-5d87-85b2-9a7e31751556 |  | note | 75.0: - ¦¦ 37.5: 100 ¦¦ 19.0: - ¦¦ 2.36: - ¦¦ 0.075: 5-40
label | abdc3adf-25d4-5369-a20b-bf43c5599013 |  | note | Material: Ordinary backfill
label | 58a013d5-c532-5f2b-9170-0750d0dd654d |  | note | 75.0: 100 ¦¦ 37.5: - ¦¦ 19.0: - ¦¦ 2.36: 40-100 ¦¦ 0.075: -
checkpoint-no-status |  |  | checkpoint | Table 701.092
label | f1ea284b-7459-5cc2-a40b-d0eded594ebb |  | note | Test ¦¦ Test Value
label | d570d795-5d9b-54f3-b032-df0ad8bb26ec |  | note | Plasticity Index (Max.) ¦¦ 20
checkpoint-no-status |  |  | checkpoint | Table 701.141
label | fd25471e-6dab-5284-ac32-cb7cd66c0d5c |  | note | Required Cover Thickness (Metre) (Min.)
label | ef3d5a97-1860-5c00-b3de-9b365a1a3910 |  | note | Type, Size, and Class of Culvert
label | 59c5927a-f21f-5fbe-9d00-4e6b009ed056 |  | note | – – – – – – – – – –
label | 343ea4a4-e3aa-5438-929a-2945efeed3e6 |  | note | Range of Axle or Track Loading (tonne): 0 - 9
label | 512fafb5-5e86-5610-90ba-9d727b0a36a5 |  | note | • Pipe 2
label | 7c8420ba-1878-5379-9d97-9f06efc35f48 |  | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 6f2106f0-7f3f-5e94-9040-54bd25afdf0d |  | note | 0.4 ¦¦ 0.4
label | 2b5e1522-a4f4-5b0d-9301-76a02ab258fe |  | note | • Pipe 3
label | 5956c403-5107-56ed-a042-7efb71fb9e69 |  | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 3a4e582f-55d5-5181-b419-e0f0f13acbcb |  | note | 0.4 ¦¦ 0.4
label | 6f8ac181-dd16-5071-9080-6f038edc4fe0 |  | note | • Pipe 4
label | 79b58afa-c05d-5408-8f69-dbe1afaa3264 |  | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 55a83863-1dc3-5e59-b000-62341caccbe9 |  | note | 0.4 ¦¦ 0.4
label | c42beb8f-fb67-58a2-8668-868f7d3ed956 |  | note | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
label | b313d162-2b15-5a8a-8ca3-ee4bb3d7c106 |  | note | - ¦¦ 0.1
label | 466a36ab-df23-590d-adee-c70b29311464 |  | note | – – – – – – – – – –
label | b4d8f5e9-9bcf-55b3-b0b2-3c3b7c4f9c5b |  | note | Range of Axle or Track Loading (tonne): 9 - 20
label | ce691f80-9a7f-51e9-a7a8-9833ede78ee0 |  | note | • Pipe 2
label | 853de347-3df5-5680-832c-18fe038122ef |  | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 671a0073-34c2-5aac-a362-0b7f706fdf92 |  | note | 0.4 ¦¦ 0.4
label | 6788f832-324e-5929-bc36-949ce6bddbc0 |  | note | • Pipe 3
label | 70290e84-3951-5f70-be6c-a14dbc3f92fb |  | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 673cefb5-6fb3-5c7e-9f1c-040c0cbe2a4c |  | note | 0.4 ¦¦ 0.4
label | 9ae0b9f7-b2b3-5489-a86e-37325a80ba88 |  | note | • Pipe 4
label | d5565b37-8a54-5777-a765-b52525e917ae |  | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 705ec9b0-5667-54ab-8524-1eaf698c2615 |  | note | 0.4 ¦¦ 0.4
label | 99af11f2-5cbc-589c-99ed-63fb2df8971a |  | note | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
label | f0844821-7798-5759-b055-f3c709c7dc2a |  | note | 1.2 ¦¦ 0.6
label | 2a9f086a-4c19-5419-87ab-f86d685a5c1a |  | note | – – – – – – – – – –
label | 91ce825a-a8dc-599b-8ba7-ff29f049af11 |  | note | Range of Axle or Track Loading (tonne): 20 - 35
label | ba296bd6-140f-5ef1-b23d-cd57b51db251 |  | note | • Pipe 2
label | 05b4b319-fd64-5e67-832f-5904f6e1d13b |  | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | d6b956e1-0905-5fac-99eb-f0b196843522 |  | note | 0.7 ¦¦ 0.4
label | 012ded7b-3dbc-562c-9eda-9c1e98b85d3b |  | note | • Pipe 3
label | 4c94b5a5-218f-5518-882a-73c87ffba165 |  | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 7f788c21-7f7a-590c-bdad-313aca381713 |  | note | 0.4 ¦¦ 0.4
label | e0fb3d00-1e6d-54a2-a425-50c6f4689b64 |  | note | • Pipe 4
label | 55b3ad81-d61c-5d9b-9782-8c8bf0dda68f |  | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 8056497b-4b2b-5fc8-bf6a-43d08d5d7c95 |  | note | 0.4 ¦¦ 0.4
label | 7736bb84-d457-5d82-8605-ac7bb49492a0 |  | note | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
label | d5794322-29ce-55c2-b602-05a1e675abe9 |  | note | 1.5 ¦¦ 0.9
label | c36ceaa7-3a5c-5e97-804f-925c1d6d50e2 |  | note | – – – – – – – – – –
label | f1071193-bc3d-5f3e-bac6-69bc74aa4ff0 |  | note | Range of Axle or Track Loading (tonne): 35 - 50
label | aeb075fa-a105-510e-8f4d-9c644e078db7 |  | note | • Pipe 2
label | d65f638b-013d-5f8b-bca2-7425946d34d1 |  | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 5ead4e4d-d149-5512-bc89-7267f35ebc90 |  | note | 0.9 ¦¦ 0.7
label | 741b8d44-a797-58cc-9b37-c16d1c885fe6 |  | note | • Pipe 3
label | 56386efa-d112-578d-b22c-ca843ebdbad4 |  | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | d99765ea-666b-5932-9ad4-8151830e252d |  | note | 0.6 ¦¦ 0.5
label | f29aeeaa-fa01-5ca4-84de-4ace7c8cc73f |  | note | • Pipe 4
label | 4e2894f4-a3a6-5ff3-884d-28eae66db95d |  | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | bd2beb70-ca7a-5d1e-803c-cea555a9cdb6 |  | note | 0.5 ¦¦ 0.4
label | c4b6bd3b-c33a-5283-b531-b5a01e4a9e9d |  | note | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
label | 4f704fae-effd-5af4-b8b0-6d600032a41a |  | note | 1.8 ¦¦ 1.2
label | bba3951e-ba71-5264-8b44-75db45b50ec6 |  | note | – – – – – – – – – –
label | d5a6c311-69bd-5861-99a1-43c4ed29cb36 |  | note | Range of Axle or Track Loading (tonne): 50 - 60
label | d040507a-b26d-5101-b7b4-e1c0cb282151 |  | note | • Pipe 2
label | 70c118cd-0598-554b-afb1-5cfcbcb8f2d1 |  | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 085a265a-d5ce-5a0c-9caa-bff8c78b4bcc |  | note | # ¦¦ #
label | dc3c0057-6442-5e52-b75a-5166756c46a8 |  | note | • Pipe 3
label | bc2db98f-e8bc-587c-af82-655878194458 |  | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 8affb9d6-0e0b-59a7-b6aa-8a449908bf49 |  | note | 0.8 ¦¦ 0.8
label | e512c1f2-6091-5da9-a0d9-2a43fb4cd888 |  | note | • Pipe 4
label | 32f3099a-a25b-5865-bee5-d8d249e8e880 |  | note | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 5f8279c0-c4a9-5df2-9807-6c00d2192f80 |  | note | 0.7 ¦¦ 0.7
label | 2ce03691-e6e2-5294-9b9b-bbca8a1c2cbe |  | note | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
label | d2762f93-a3e6-5ae2-9d86-06c7bc1c441d |  | note | 2.1 ¦¦ 1.5
label | a6511a04-a532-5f0f-a350-daff8dbb5485 |  | note | – – – – – – – – – –
label | 8c13dd8e-2a4d-591f-9a21-05085ce720e6 |  | note | # This range of loading not permissible.
label | 1ef8892e-67fe-564a-abe5-547e5cc1219e |  | note | D Nominal Pipe Diameter
label | ea55a0b2-09bc-5eee-ae24-d33701757361 |  | note | D less than 1200 mm not permitted, D more than 3600 mm as directed by the Superintendent.
checkpoint-no-status |  |  | checkpoint | Table 701.151
label | 5fd0fa10-36ea-55fe-8bb1-d9845fe252b8 |  | note | Pipe Type ¦¦ Nominal Pipe Diameter or Width (mm) ¦¦ Horizontal Clearance to Wall of Trench :: Min. (mm) / Max. (mm)
label | 466f1902-2445-50dc-b8b5-4169d642945f |  | note | – – – – – – – – – –
label | 48952c1d-3849-57c0-8772-05a8223fa40d |  | note | Corrugated Metal Culvert ¦¦ All :: 300 / 1,000
label | 113e6d68-b7b6-519b-bc99-e0ff9fea0889 |  | note | Other ¦¦ All :: 300 / 600
checklist-sectioned |  |  | checklist | ITP - Surfacing - Asphalt Placement & Spray Sealing | itp |  |  |  | Yes | ITP - Surfacing - Asphalt Placement & Spray Sealing Rev1 | a2cbab54-7ee9-498d-8552-07aa6d9299b1
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 Submission of Mix Design
label | fec0f063-3c38-572a-9436-4eb420fff53c |  | note | FREQUENCY: Prior to commencing paving
label | a94c406a-e35a-509f-8677-6072e832558b |  | note | ACCEPTANCE CRITERIA: All asphalt mixes proposed for use in the works shall have a mix design registered by the Victorian Department of Transport as 'General', unless otherwise approved by the Victorian Department of Transport.
label | ca92db62-5f91-5772-bb2a-744023e21632 |  | note | ○ The registration for all mixes incorporated into the works shall be current at the time of their use. The contractor shall submit documentation to the Superintendent nominating the asphalt mixes to be supplied no less than 7 days prior to their use.
label | d01617c5-dfd3-5ae9-9a15-7eafca868b0f |  | note | REFERENCE DOCUMENTS: Cl 407.09
label | 88a48501-151b-5817-a21f-7a63a3c1ce27 |  | note | INSPECTION/TEST METHOD: Verify
label | 6f585264-ef04-53bb-bdf2-fb49a88cbc6b |  | note | RECORD OF CONFORMITY: Mix registration & correspondence
label | e038f972-cf1a-5e55-8354-46cf2d4be254 |  | note | HP
label | ab6157c0-7532-5b9c-80ef-0ba27eb23c4b |  | note | RESPONSIBILITY: FH Engineer/ Superintendent / QAV
text | d548d799-94a7-59a0-a4aa-00bb26677a90 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures and controls
label | 077a4357-f8c3-503e-82bd-ec4ab1b33b54 |  | note | FREQUENCY: Prior to commencing any activity
label | 9d4c66ad-3a41-5821-ba96-88891847ff82 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | a0ddbfec-9ab5-5ad6-b9ff-e1f759d4b37f |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 2fff2d42-b153-5490-bc54-e4c59e11263b |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | add9e394-0874-57ed-b0ae-a8f113c8ec43 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | afdc93a2-2855-5bc7-8e79-dbc0194a4348 |  | note | HP*
label | 08c1c396-a886-50dc-aa11-a183f2239b0b |  | note | RESPONSIBILITY: FH Engineer
text | 6f47dcbf-2a6c-5fe9-b14c-135814de7f34 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 1.3 Site Inspection and Base Condition
label | d90917ce-fee9-543a-a2cd-dd195d666dfc |  | note | FREQUENCY: Prior to commencing paving
label | 5cdeb7e8-d7a2-5165-ba25-57fb721aad59 |  | note | ACCEPTANCE CRITERIA: The surface on which asphalt is to be placed shall be essentially dry and free from surface water. Asphalt shall not be placed when the pavement surface is wet, or rain is imminent.
label | 487bc0dc-b82b-51e3-95c1-4efbc6ff0d7d |  | note | REFERENCE DOCUMENTS: Cl 407.17 (a), AS2150 10.1, AS2150 10.3
label | 71ab2997-83e7-5cfc-9797-8daf05a57db3 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 14979ec4-69da-5a0e-9639-5ad8c08cf4e8 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 2f7b26c3-1b98-5dcf-9983-11383a3ca195 |  | note | IP
label | 2822a0f0-d448-50ad-9030-1a0d31278f7a |  | note | RESPONSIBILITY: FH Engineer / Superintendent
text | 960297c5-bca5-578a-b77d-b8f449aae404 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 1.4 Ambient Conditions for Placing
label | 5eb35fe2-7bc8-5ce3-8efe-a9da9de31ba1 |  | note | FREQUENCY: Prior to commencing paving
label | 30c16611-d8de-5042-9dbd-602382fa5c99 |  | note | ACCEPTANCE CRITERIA: Asphalt shall not be placed when majority of the area to be paved has a surface temperature less than that detailed as follows:
label | 8a3d7141-ea2a-5b6f-ae77-87fa9cc10808 |  | note | ○ Base or Intermediate Courses: 5°C for specified binder class of C170 or C320; or 10°C for asphalt mixes with specified binder class of C600 or containing a PMB.
label | 259af6fd-3566-5890-89f8-ec282b51358b |  | note | ○ Wearing Course: 10°C for specified binder class of C170 or C320; or 15°C for asphalt mixes with specified binder class of C600 or containing a PMB.
label | 8606be80-8ad3-56e9-85ec-71ced3cf4492 |  | note | REFERENCE DOCUMENTS: Cl 407.17 (a) Table 407.171
label | 3ddd60c3-a7bb-556b-a7ab-89de8b286ada |  | note | INSPECTION/TEST METHOD: Verify
label | 0e471bf5-25a9-56a2-8f78-80c51fce9b6b |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 7c9e20fd-09e6-511d-94f4-fa01061645c6 |  | note | IP
label | cd31128e-5a43-5d5b-96f8-2404a0a36540 |  | note | RESPONSIBILITY: FH Engineer / QAV
text | 17dc7130-534b-531b-aa82-55c8ac85d127 |  | textbox | DATE:
checkpoint-group |  |  | section | 2 - Material Procurement for Spray Seal
checkpoint-status |  |  | checkpoint | 2.1 Adhesion Agent
label | e4ba9394-fc8e-5810-b4cb-fb10011c026f |  | note | FREQUENCY: Test cert. upon request
label | a2e22eda-f7fd-540f-8ae3-e8b3c3034843 |  | note | ACCEPTANCE CRITERIA: Satisfactory field performance. When adhesion agent is added to the binder, the total volume of adhesion agent ≤1% of the binder.
label | a8ce983e-b495-52b6-bfe9-eff917e70d0e |  | note | REFERENCE DOCUMENTS: Cl 408.09 (a),
label | 23be5bf5-4413-5303-9df0-d084d0f3e899 |  | note | INSPECTION/TEST METHOD: Verify
label | 7f36a84d-a2c6-5ba8-a181-3c16fc020737 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 23573b8c-eed0-5575-8c95-bc03ae213c47 |  | note | IP
label | c62687ad-4e83-5896-a6a7-f0517d200103 |  | note | RESPONSIBILITY: Site Engineer
text | 328c9946-d740-5602-8b9d-5845f8b35e8d |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.2 Aggregate Precoating Materials
label | 674ab155-0c60-5acf-9350-3ba7029285ca |  | note | FREQUENCY: Test cert. upon request
label | 8ebddf9d-fb4a-5134-9bd9-4c869d341d10 |  | note | ACCEPTANCE CRITERIA: Aggregate Precoating Materials shall be distillate, distillate based product, cutback bitumen, emulsion based product or proprietary product.
label | f06bab81-34f8-5fcb-bd0b-5548b90d33f3 |  | note | REFERENCE DOCUMENTS: Cl 408.09 (b)
label | 545372eb-6ea5-5598-8c1f-e2576200e90b |  | note | INSPECTION/TEST METHOD: Verify
label | 4beefd8f-e967-5c87-a45e-35d410e9cef6 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 4848d9df-fd13-52f0-80a0-5a4c1aab8246 |  | note | IP
label | 3b376778-46b9-55a4-9b11-d2e8210b8434 |  | note | RESPONSIBILITY: Site Engineer
text | 6390691c-b3a5-5c7d-9e9b-ca2a6f8d245d |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.3 Bitumen
label | 0e08d89b-fd7e-5203-861e-aff7c6c128f7 |  | note | FREQUENCY: Test cert. upon request
label | 618198e3-bdce-5be5-a8a9-e82582dbdffc |  | note | ACCEPTANCE CRITERIA: Bitumen shall be Class 170 complying with the requirements of AS 2008.
label | 36865afc-1977-548d-8909-a1f6809eb263 |  | note | REFERENCE DOCUMENTS: Cl 408.08 (a), AS 2008
label | e97c4589-bd4a-5df3-8291-9c0a7e02e8c1 |  | note | INSPECTION/TEST METHOD: Verify
label | d03a4e29-d73d-5dcc-a442-f5f3367a4691 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 0d3b3f0b-f842-576a-91e5-e3f505ee7efc |  | note | IP
label | e71cf501-0dd3-57d7-9ab2-db692a19041d |  | note | RESPONSIBILITY: Site Engineer
text | 046af3ae-7215-5185-b2df-32cd7eaf3476 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.4 Bitumen Emulsion
label | f8c8835c-400e-553f-8d00-0b001220fdb0 |  | note | FREQUENCY: Test cert. upon request
label | 4e5727af-7d2a-58be-8bd0-2141850f37b7 |  | note | ACCEPTANCE CRITERIA: Bitumen Emulsion shall comply with the requirements of AS 1160.
label | fddec355-0f87-5666-841d-dcc0627ca3b4 |  | note | REFERENCE DOCUMENTS: Cl 408.08 (b), AS 1160
label | 08dafd1a-2654-57de-9199-44a3890b2cc1 |  | note | INSPECTION/TEST METHOD: Verify
label | b9128a55-e5ae-5a6e-a519-12542fdb60a1 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | a31ccd42-355a-5792-a33f-5a30bd4929f4 |  | note | IP
label | e32fe0bc-7d9e-54a8-aedb-30e8900f05cd |  | note | RESPONSIBILITY: Site Engineer
text | c2e1fe7c-5f1c-5acc-9b30-97ea8fd2bb64 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.5 Cutback Bitumen
label | 23792d8e-deb8-5072-8ac6-e6e2a8a91d03 |  | note | FREQUENCY: Test cert. upon request
label | efe50a31-d092-5b87-81c5-fc9d19cb413a |  | note | ACCEPTANCE CRITERIA: Cutback bitumen shall comply with the requirements of AS 2157.
label | 22c9f111-c593-519f-b3f1-e8ad1fd1fd44 |  | note | REFERENCE DOCUMENTS: Cl 408.08 (c), AS 2157
label | 0c8c595a-e02f-52a7-bea5-c643b76301c0 |  | note | INSPECTION/TEST METHOD: Verify
label | 42beca64-cd60-5cd7-9493-001655273e26 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 9a19ed5a-e96e-5ff9-afb9-7f67bcd71179 |  | note | IP
label | 02ee404a-f2d0-57e6-97b6-799bdafc8222 |  | note | RESPONSIBILITY: Site Engineer
text | c58ffb5c-2104-53b7-bdc4-0cf2725363b0 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.6 Cutter
label | 0a0ee208-c317-5e2a-9b2d-ec24b082f2b9 |  | note | FREQUENCY: Test cert. upon request
label | e3def007-dbcc-586b-89e3-ffa884462b17 |  | note | ACCEPTANCE CRITERIA: Cutters shall comply with the properties in the Table 408.091.
label | afe53e6c-4aec-5a7d-996f-59490ef3a945 |  | note | REFERENCE DOCUMENTS: Cl 408.09 (d) Table 408.091
label | 5ae630cd-f5bd-5f3a-8894-5cdfa7a7102e |  | note | INSPECTION/TEST METHOD: Verify
label | bfcf39d9-46cb-5753-8d44-f600be041332 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | bef02523-9821-5f63-99ad-1c3cee10e30f |  | note | IP
label | becacbf1-85b3-5982-89e8-15641f13422f |  | note | RESPONSIBILITY: Site Engineer
text | e72a5bc7-6f6c-502b-8341-6a96471f03a5 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.7 Polymer Modified Binder (PMB)
label | decf5286-1100-53bc-97a7-20fd0ccf6bb8 |  | note | FREQUENCY: Test cert. upon request
label | f67ea290-43fa-57aa-960a-011771e2a1c7 |  | note | ACCEPTANCE CRITERIA: The class of PMB shall comply with the requirements of Austroads Technical Specification ATS-3110. Alternative or 'ungraded' PMMBs which do not comply with the specified test requirements of ATS-3110 shall not be used without approval by the Superintendent and will be subject to the Contractor providing evidence that the product has delievered satisfactory fiels performance for a period of at least three years.
label | e306adbb-c623-5bf3-8f47-cbe2fa0fc886 |  | note | REFERENCE DOCUMENTS: Cl 408.08 (d), AST-3110
label | 79db46a4-cfc8-50b4-8e43-ab60a1275b84 |  | note | INSPECTION/TEST METHOD: Verify
label | f06a9600-f6de-5693-b92a-8f174eb1c0b1 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | c8e8b7a7-12ab-571a-8577-d10ea0c00aec |  | note | IP
label | 92815260-31d1-572f-884d-ba0037d7a516 |  | note | RESPONSIBILITY: Site Engineer
text | 7f638231-cd4f-5a03-a911-b3d454052838 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.8 Primer
label | ba7167b8-7f54-5956-ad5f-58d6ed099424 |  | note | FREQUENCY: Test cert. upon request
label | 2323262b-d9c9-5b60-963e-d64429f20079 |  | note | ACCEPTANCE CRITERIA: The primer shall be cutback bitumen complying with the requirements of clause 408.08(c) and shall be water resistant, of uniform appearance and capable of providing a strong bond between the bituminous surfacing and the pavement.Bitumen emulsion alternative acceptable upon providing evidence that the emulsion product meets the same functional requirements.
label | fd2efbdd-e659-5daa-a471-a9e150ff5858 |  | note | REFERENCE DOCUMENTS: Cl 408.08 (e)
label | 6370027a-d412-5f5e-bef9-eb6fb4b37439 |  | note | INSPECTION/TEST METHOD: Verify
label | 42818196-1340-5a26-a212-6dc797837306 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 7f2168b2-8d09-5d6f-963a-db96616caeb3 |  | note | IP
label | fece0b03-a5a6-5475-942e-6aa178e0cf21 |  | note | RESPONSIBILITY: Site Engineer
text | d11433bd-c234-592f-ad07-2a5b7def9b67 |  | textbox | DATE:
checkpoint-group |  |  | section | 3 - Aggregate
checkpoint-status |  |  | checkpoint | 3.1 Aggregate Specification
label | e3a2fedd-8da5-5da6-ac52-d837294660a1 |  | note | FREQUENCY: Each lot
label | 7b33edb2-34f1-51f0-8285-f5889df333ec |  | note | ACCEPTANCE CRITERIA: Aggregate shall comply with sections:
label | d0df300f-fc7d-52c0-800f-302cbefacfd9 |  | note | ○ 801 - Source Rock for the Production of Crushed Rock and Aggregates
label | 3a7f1380-3f45-5d77-8ed3-2601c8b23396 |  | note | ○ 831 - Aggregate for Sprayed Bituminous Surfacing
label | 87857653-ebd6-547a-aea1-c0d39714e70f |  | note | REFERENCE DOCUMENTS: Cl 408.11 (a)
label | 76b3e987-455a-5a25-ab39-5662bea89b34 |  | note | INSPECTION/TEST METHOD: Verify
label | 64e99ac1-287b-55fa-8040-c8f3983bf974 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 1f96e5d5-50ba-5a4e-899d-344883d204a4 |  | note | IP
label | ddc0db36-0281-5fc9-8d03-5db3bf58e2fe |  | note | RESPONSIBILITY: Site Engineer
text | 31fc6d2f-bc9f-52f7-8949-00b930f9b6b0 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 3.2 Aggregate Precoating
label | d0db489a-02c9-5507-84de-b92b37b8f533 |  | note | FREQUENCY: Each lot
label | 87278936-4873-5faa-84e8-bcd7c2e6d0f1 |  | note | ACCEPTANCE CRITERIA: Supply plant precoated aggregate or field precoated aggregate.
label | 287a7d3e-4eb2-5af7-9d90-8560c7dc6519 |  | note | ○ Aggregate precoating shall be undertaken using a purpose-built item of plant to apply to the precoating material in a controlled manner that produces a uniform coating.
label | 496c629c-2d33-531a-ab42-da229911bc1a |  | note | REFERENCE DOCUMENTS: Cl 408.11 (b)
label | 9f11c91c-15ad-5a2c-97d4-b98e439ff61c |  | note | INSPECTION/TEST METHOD: Verify
label | f529dd94-96ea-54d6-9730-96748d45c557 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | f2d10456-12f2-51a8-a6c7-f01e26612e2f |  | note | IP
label | b52693ef-98b9-503e-a8ac-bb456ca2af9f |  | note | RESPONSIBILITY: Site Engineer
text | 9f5cb432-663c-5177-b87a-383ac694ebec |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 3.3 Removal of loose aggregate
label | c6092503-1d22-5049-b40a-332208c85565 |  | note | FREQUENCY: Each lot
label | 8d3be493-e430-580c-afe5-d041e461c98c |  | note | ACCEPTANCE CRITERIA: All areas – within 8 hours of sealing as it is mfreeway and AADT is greater than 5000, as per table 408.141, unless otherwise agreed with the Superintendent.
label | f76e2af1-fcd4-595c-957e-777fe922be6d |  | note | ○ For seal of nominal size ≥ 10mm, < 40 loose stones/m2 to remain after removal of loose aggregate. For seal of nominal size ≤ 7mm, < 60 loose stones/m2 to remain after.
label | dbd6e8fb-ab39-5906-b3c8-2806e58a0476 |  | note | REFERENCE DOCUMENTS: Table 408.141
label | c5adef48-448c-54b6-989a-fcc2f1a2725a |  | note | INSPECTION/TEST METHOD: Verify
label | bd022259-2f59-52e2-8ddd-ad6786a4eb3b |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 92f22a68-d3c8-5b71-a9d4-f621f18458c0 |  | note | IP
label | f071bd3e-c95c-5992-b42b-011f15d7564c |  | note | RESPONSIBILITY: Site Engineer
text | a4b74336-1737-5394-8c6b-d606b120b6e5 |  | textbox | DATE:
checkpoint-group |  |  | section | 4 - Asphalt Placement
checkpoint-status |  |  | checkpoint | 4.1 Tack Coat
label | 2277f6f3-6368-59d7-a56c-694db3f8a88c |  | note | FREQUENCY: Prior to commencing paving
label | d7c4f338-0479-5a61-a6b9-5defa0885dd5 |  | note | ACCEPTANCE CRITERIA: Tack coat shall consist of a bituminous based binder. From 1 July 2022 only trackles stack coat will be permitted. The contractor shall submit the details of the trackless tack coat proposed to be used in the works
label | efd3da5b-fc6a-5074-a654-b74f40cf82d5 |  | note | REFERENCE DOCUMENTS: Cl 407.08 (d) AS2150 11
label | 25e7ec49-e1c0-5a1d-b88b-c8185d8b1211 |  | note | INSPECTION/TEST METHOD: Verify
label | ad5aace7-c7f5-55d7-ad2b-bea56bd0c920 |  | note | RECORD OF CONFORMITY: Hold Point Release
label | 295af3f1-3475-526e-83e4-b0d9d506ae90 |  | note | HP
label | dc66285b-7e60-5a80-948e-b3c7d828643b |  | note | RESPONSIBILITY: FH Engineer/ Superintendent
text | 5c7a71df-af43-53b1-8312-c3a4fbd74239 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 Application of Tack Coat
label | dc6506bc-8bdc-5d36-bed7-dd8b3b8b35df |  | note | FREQUENCY: Prior to Asphalt placement
label | 2a71f10c-b531-5f14-a818-fcc16c5844df |  | note | ACCEPTANCE CRITERIA: A tack coat shall be applied to all asphalt, concrete or sprayed seals on which asphalt is to be placed. The tack coat shall achieve an effective bond between the asphalt and the underlying layer.
label | a1f7a217-d773-5170-b130-e7b977ac9676 |  | note | REFERENCE DOCUMENTS: Cl 407.19
label | c04e51c6-1476-5b14-be63-c73866fb3abc |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 16b7f844-6866-591e-9735-63313430a685 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 0e593177-042e-5922-80c3-f7357602c575 |  | note | IP
label | 00c5dfb2-9e2e-5a9e-a303-4490dd04f4be |  | note | RESPONSIBILITY: FH Engineer / QAV
text | c34479df-6cb5-555c-84b1-48ae97223b3b |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 4.3 Commencement of Asphalt Placement
label | e55680d1-38ba-51d9-9e83-e7b384f220fd |  | note | FREQUENCY: Prior to commencing Paving
label | 2b4745e6-6795-5ce6-96ac-5efedf799932 |  | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from the Superintendent
label | 528256a3-1387-5248-aff7-7d553e4dbb6b |  | note | REFERENCE DOCUMENTS: Cl 407.23
label | 8c14fb89-cd95-5e22-a17d-d5806b4ec877 |  | note | INSPECTION/TEST METHOD: Verify
label | d898f4a6-d30f-5b00-b9bc-de014ad34787 |  | note | RECORD OF CONFORMITY: Hold Point Release
label | ef0bde0f-5548-595a-98dc-5bcd2b6f3876 |  | note | HP
label | 151cf548-e9c8-5ebc-bb2a-53ed171c5a19 |  | note | RESPONSIBILITY: FH Engineer / QAV
text | 4989c05f-81b9-5fc0-9647-cf8d1d1c9e57 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 Delivery of Mix
label | 67e3d5ab-ae49-5e18-ac8b-fa349006c9d6 |  | note | FREQUENCY: Each load
label | 7cf93183-8e21-5c70-b248-86f0b4c603e6 |  | note | ACCEPTANCE CRITERIA: Asphalt delivered to site, which is segregated, has been overheated, is too cold, contains separated binder, uncoated particles or which does not comply with the Specification shall be removed from the site.
label | 64103f7d-f21a-5750-b1de-0febf63198c1 |  | note | REFERENCE DOCUMENTS: Cl 407.20 (a)
label | 6aaaaa25-f793-5043-b312-e5d3bbbfc1f1 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | c88abff8-d387-5378-a1f3-0a60a4b9a885 |  | note | RECORD OF CONFORMITY: Delivery Docket /Asphalt Traceability Sheet
label | 7cdd209f-d100-5d75-8c23-a3f92ce6fa31 |  | note | IP
label | e5f897aa-01e5-5d3f-a44d-c4d7f412dcb7 |  | note | RESPONSIBILITY: FH Foreman / FH Engineer
text | 63e24050-67d2-5406-b1ca-526431ed34d3 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 4.5 Layer Thickness and Scale of Level
label | 34b08ba8-b60f-54e5-a41c-f39f6cf794d1 |  | note | FREQUENCY: Regularly during paving
label | 3fd05892-fd2b-5035-b8a7-729afd47bd8a |  | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness and Scale for Level as specified on drawings or specifications
label | c44d46b6-8960-53cf-bb56-129238dec781 |  | note | REFERENCE DOCUMENTS: Cl 407.30 Drawings
label | ba6e3378-6178-591b-9e28-619d401074c7 |  | note | INSPECTION/TEST METHOD: Verify
label | e89131d2-b528-58a9-a981-9a7d60e72dc1 |  | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
label | 26478501-4c84-592c-9234-f56abd02bd66 |  | note | IP
label | 5ac0112b-ecb3-521b-9a11-13a74c0c7bcc |  | note | RESPONSIBILITY: FH Foreman / FH Engineer
text | 97cfb773-d3bb-52bd-9d4c-290b0897999b |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 4.6 Paver Stoppages
label | e66914a5-23dc-5071-8126-1d942c2415c8 |  | note | FREQUENCY: If paver stops
label | 4e0aa3dd-3227-5ad4-9311-f753c79f6351 |  | note | ACCEPTANCE CRITERIA: If the paver is required to stop and asphalt in front of the screed cools to below 120°C , a transverse joint shall be constructed.
label | e4d93715-be72-5b87-beb4-0a3f7e09bf44 |  | note | ○ Hand spreading shall only be used for small areas where it is not practical to use a paver
label | 2fc8c793-ff05-55bc-aebe-7167096fd9bf |  | note | REFERENCE DOCUMENTS: Cl 407.25
label | 24475775-554d-514a-bf9d-f2b20df75d53 |  | note | INSPECTION/TEST METHOD: Verify
label | a646990f-9db4-53b5-b1a8-91e89676c40b |  | note | RECORD OF CONFORMITY: Thermometer
label | 6085e041-221a-54db-ac3e-f49e094ab7cc |  | note | IP
label | bda1de31-126f-575c-9f57-97d8e19dd6f6 |  | note | RESPONSIBILITY: FH Foreman / FH Engineer
text | 9c5ea807-0f90-526d-b88b-d5e5882cee35 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 4.7 Surface Finish of Wearing Course
label | 5660b89c-6591-5091-b659-0a6c75d610b1 |  | note | FREQUENCY: During paving and after final roll
label | d7c4d022-9895-5e8f-8dbf-1e569ae95a46 |  | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | b0f0c33e-4200-5e1b-97fd-d2abfb85a4db |  | note | REFERENCE DOCUMENTS: Cl 407.29 (i)
label | 4d96e63b-a623-5f56-8c33-ab4707bff620 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 62c67cb2-7e53-531b-a068-c4a938823e2d |  | note | RECORD OF CONFORMITY: This ITP signed off
label | c786df9f-2b4d-5ea4-ba93-6e15c15e2e2a |  | note | IP
label | 410a08c7-36ab-5011-8f25-5d5af82ce2b0 |  | note | RESPONSIBILITY: FH Foreman / FH Engineer
text | 58957420-3e69-5915-866a-fc87f889b3a7 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 4.8 Kerb and Channel
label | c9d47d7c-5360-5c70-9450-d113b56b58e8 |  | note | FREQUENCY: During paving and after final roll
label | cd64aca1-a498-5993-b9a3-a8b886f32858 |  | note | ACCEPTANCE CRITERIA: Where asphalt is placed against kerb and channel the surface at the edge of the wearing course shall be either flush with or not more than 5mm above the lip of the channel.
label | 16f5d669-7553-5908-828b-a7d75af3183c |  | note | REFERENCE DOCUMENTS: Cl 407.29 (ii)
label | 8128a339-b788-5ca6-9727-c807dcf13f62 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | a612c522-bd07-52e2-9d07-57bbdee5067a |  | note | RECORD OF CONFORMITY: This ITP signed off
label | c1508688-e05e-5806-a7a1-4e55512aaf8f |  | note | IP
label | dd00ddf9-ed4d-5c5d-999d-1b99bd6f386b |  | note | RESPONSIBILITY: FH Foreman / FH Engineer
text | 16026315-4e75-52e5-95c6-0a30fac41a43 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 4.9 Alignment of layers not placed against concrete edge
label | 6841d0db-c351-56df-9e4e-dafa69b225ee |  | note | FREQUENCY: During paving and at completion of work
label | b5b52ab3-94bf-5445-9663-a9c6d0a60fa3 |  | note | ACCEPTANCE CRITERIA: Where asphalt is not placed against a concrete edging, the edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designated offset from centreline or design line. Within these tolerances, the rate of change of offset of the edge of layer shall not be greater than 25mm in 10 m.
label | 3c82c683-fb51-5c7f-9622-294e4addfcd8 |  | note | REFERENCE DOCUMENTS: Cl 407.29 (iv) Drawings
label | 35685d30-d482-51da-8d04-52e0678a0904 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 03b70a59-071c-5298-a69f-080ed1111228 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | d985e88a-def9-580c-a4bc-269bd8fac1a1 |  | note | IP
label | 411b4914-9c74-584e-aa25-f4ccbf243d5e |  | note | RESPONSIBILITY: FH Foreman / FH Engineer
text | 614d6145-c65e-5a28-8ba8-4837925cbc9f |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 4.10 Width of layers not placed against concrete edge
label | 5b005b85-504b-5628-865f-42c75581e3f4 |  | note | FREQUENCY: During paving and at completion of work
label | 30a36014-2215-5d5a-a7ec-e54611f855f0 |  | note | ACCEPTANCE CRITERIA: Where asphalt placement is not placed against a concrete edging, the width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm. The average width over any 300 m shall not be less than the design or specified width.
label | f674e77e-f595-505e-9393-843f4e286274 |  | note | REFERENCE DOCUMENTS: Cl 407.29 (v)
label | 1b7454a8-7bc9-5d8c-9867-2bad7a911902 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | d0cfd101-392f-597d-9b47-00897c847e87 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | a1ea308e-5754-552f-a31e-d882142d2d25 |  | note | IP
label | e9255063-24f9-5071-8d15-5253d0c20fe0 |  | note | RESPONSIBILITY: FH Foreman / FH Engineer
text | bd282613-b5ca-57da-901e-0f7b2efb9c73 |  | textbox | DATE:
checkpoint-group |  |  | section | 5 - Spray Sealing
checkpoint-status |  |  | checkpoint | 5.1 Rates of Application
label | a5db75e2-08e9-5bb6-8f1b-6d6febd4daf9 |  | note | FREQUENCY: Each lot
label | 24a58556-9c20-5afb-90ec-f5452424d6e4 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | b720d004-c158-5c51-9d93-6dce7ed01fbe |  | note | ○ At least one week prior to the commencement of work, the Contractor shall submit the initial design rates of application for bituminous material, aggregate, and rates for pre-treatment for review by the Superintendent.
label | 70f5ae26-ab66-5598-ad5e-93fd40b0c681 |  | note | REFERENCE DOCUMENTS: Cl 408.13 (a)
label | 4ad4cc07-f7c5-53b0-a9ed-c28af841bf0d |  | note | INSPECTION/TEST METHOD: Verify
label | f472ec20-0159-539d-9a02-a7fa67345e20 |  | note | RECORD OF CONFORMITY: Signed ITP
label | e80db94f-53f3-50f2-bdaf-2fd772afdab6 |  | note | HP
label | 8c410b6d-ed02-5bc6-9928-e924e695dfb9 |  | note | RESPONSIBILITY: Site Engineer / QAV
text | efd31726-e79f-54f8-b7fd-15b1802d9394 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 Surface Pre-treatment
label | 96511205-dba1-5e30-b59e-52c37175bca9 |  | note | FREQUENCY: Each lot
label | a3a90026-4017-56ec-90c1-94f00e4ab268 |  | note | ACCEPTANCE CRITERIA: Surface pre-treatments to correct variable surface texture shall be allowed for and carried out as part of the works to meet the requirements of Surface Texture and Aggregate Loss specified in Tables 408.152 and 408.153.
label | ec43ca11-2581-50ea-a268-ca0faea1f79f |  | note | REFERENCE DOCUMENTS: Cl 408.13 (b)
label | d76a00eb-ff20-5a4c-9b35-740717409929 |  | note | INSPECTION/TEST METHOD: Verify
label | f47654d2-34f3-5388-ae2b-47f56696d388 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 7e344b4e-f645-5967-8cf7-8ce82170b1ba |  | note | IP
label | 7933e6fd-0c92-597b-b55f-e2f0449c0792 |  | note | RESPONSIBILITY: Site Engineer
text | 7cb2f266-8f82-5c6e-ae58-b0d7105c36f2 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 5.3 Calibration of Bitumen Sprayer
label | 94481338-81be-5bc6-8537-c662f33d31f4 |  | note | FREQUENCY: Prior to commencing works
label | e57eec00-13ac-5216-be62-c66d0222e34e |  | note | ACCEPTANCE CRITERIA: All sprayers used for application of bituminous materials shall have a current Certificate of Calibration showing compliance with Austroads Test Methods AGPT-T530, and AGTP-T536 and renewed every 12 months.
label | d6e1b7f3-3433-5db0-9266-19d01e98cb29 |  | note | REFERENCE DOCUMENTS: Cl 408.07
label | 20b8cd90-c1b8-503d-8435-9f0228ddc0c1 |  | note | INSPECTION/TEST METHOD: Verify
label | 86b9f01b-0069-559d-87d1-5ec669608677 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 59909614-350d-569f-8894-00d7c01f6021 |  | note | IP
label | 0258fab8-f3a5-5fdc-aaf5-b47bde143c1f |  | note | RESPONSIBILITY: Site Engineer
text | a8eff580-d380-56a7-88c2-481d3c76f8c8 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 5.4 Commencement of seal works
label | 5cc05c5f-ac1a-5898-99d7-307b0fd8d025 |  | note | FREQUENCY: Prior to commencing works
label | d671c648-b6bc-5a32-9a1e-7cefdb0d5dff |  | note | ACCEPTANCE CRITERIA: Hold Point
label | f3d3d2ca-0e3d-54db-a7e5-1f962ec36f10 |  | note | ○ Work shall not commence until the Contractor & Superintendent have agreed that the road or pavement surface is fit and ready for surfacing no more than 24 hours prior to the works occuring. For Periodic Resurfacing and Maintenance Works this includes patching and other preparatory works, and for the Initial Seals on Construction Projects the requirements of Standard Section 310 shall be satisfied.
label | 0a33fc0c-d77a-59d2-90f0-0087f95cb828 |  | note | REFERENCE DOCUMENTS: Cl 408.04
label | 51d2ebbe-091a-59c4-8296-53c7a374ffaf |  | note | INSPECTION/TEST METHOD: Verify
label | 8e1dc2b6-9f89-5221-ab35-c218d6db157e |  | note | RECORD OF CONFORMITY: Signed ITP
label | 84c6440b-f439-51f5-9d9f-cf43d53c17f5 |  | note | HP
label | ea971ada-7609-5e60-9675-d39daee165aa |  | note | RESPONSIBILITY: Site Engineer / QAV
text | 8402871c-9b0b-52ef-84af-92ff1911d4ac |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 Commencement of seal works
label | 546de32f-12c4-504a-ba50-6f5cbacb0eda |  | note | FREQUENCY: Prior to commencing works
label | 745c3e44-0e6a-5821-95c3-78b46a504c57 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | 48bf2eda-10da-5ef9-824d-ef0bea9faa85 |  | note | ○ Written confirmation of the works that will be undertaken the following day and obtain agreement from the superintendent to any variation in the design rates of appliaction to those provided under clause 408.13(a).
label | c0d74ad4-4944-5745-8c27-77cb1192dad7 |  | note | REFERENCE DOCUMENTS: Cl 408.04
label | 6eac86d9-0d4e-576d-be2e-a2880708705f |  | note | INSPECTION/TEST METHOD: Verify
label | 6ada9c48-418a-5a47-9aae-2c743427bb3f |  | note | RECORD OF CONFORMITY: Signed ITP
label | 43e9354c-dfda-50f6-868f-15eec3258670 |  | note | HP
label | becd8601-71aa-512e-b15d-cbfa74151893 |  | note | RESPONSIBILITY: Site Engineer / QAV
text | 91d8222e-c821-597b-94be-ecf1f0a253ba |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 Records
label | 72bfecdb-b992-5233-9601-1000aac420e8 |  | note | FREQUENCY: Each lot
label | 936ad953-6f0b-51f0-8037-b75842df27cf |  | note | ACCEPTANCE CRITERIA: Job completion report using the proforma included as Attachment A to Section 408, or an equivlant proforma as approved by the Superintendent, completed and submitted within 7 days of completion of sealing each job.
label | 6421dd54-890b-5852-b21b-d2e9647acd21 |  | note | REFERENCE DOCUMENTS: Cl 408.17
label | dcdf56b0-d4c1-538c-84b1-c456fdd70088 |  | note | INSPECTION/TEST METHOD: Verify
label | 80daf20d-6fb1-5746-ab18-6e5aab5b1ff4 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 591d035e-9c33-58e7-b790-bdd23f94632b |  | note | IP
label | 97b6c07f-bd65-51bb-be87-b9df5e2b64d8 |  | note | RESPONSIBILITY: Site Engineer / QAV
text | d14c4408-ee48-5ec3-88db-fd75e3260ead |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 5.7 Binder application rates
label | 2f503879-dc14-566b-ae35-8c171a066d38 |  | note | FREQUENCY: Each lot
label | 9ea5f824-a455-5f07-9cd7-1396278ffbfe |  | note | ACCEPTANCE CRITERIA: The Contractor shall produce evidence to show that the actual rate of application complies with the design rates of application. Variation between the actual rates and the design rates will be assessed in accordance with Table 408.151.
label | f4ff770e-b9d1-5900-9724-e758c622b2ad |  | note | REFERENCE DOCUMENTS: Cl 408.15 (a)
label | 044afcb8-b4b1-520a-a3f2-3c3777e231f2 |  | note | INSPECTION/TEST METHOD: Verify
label | 4eb1dd27-c845-54dc-bb31-a44793567bcc |  | note | RECORD OF CONFORMITY: Signed ITP
label | b1d01722-2c2d-5311-a8ab-53c786f55cea |  | note | IP
label | bdde8155-d09d-5dd6-8de2-47de88d51e9a |  | note | RESPONSIBILITY: Site Engineer
text | 459d727f-abaa-5154-933a-34d7361d4d0f |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 5.8 Surface Texture
label | fed6ae0c-f7e9-5d7a-b608-3ed7b0bc85ba |  | note | FREQUENCY: Each lot
label | 089440b1-1106-5c11-93db-6742c8ef6f12 |  | note | ACCEPTANCE CRITERIA: Acceptance of work for surface texture and surface enrichment shall be based on visual assessment, or tested in accordance with VicRoads Test Method RC 317.01 and assessed in accordance with Table 408.152 if required by the Superintendent
label | 8995ba93-de24-5899-8e6d-4696f93eb2fb |  | note | REFERENCE DOCUMENTS: Cl 408.15 (b)
label | d887db4c-c959-52f1-9b6a-16f5e487ecb2 |  | note | INSPECTION/TEST METHOD: Verify
label | 34aaa221-1506-5eb9-a981-1e368bca2297 |  | note | RECORD OF CONFORMITY: Signed ITP
label | e2a5be15-f2c2-517e-bc9b-946f6e6202b8 |  | note | IP
label | 19391525-1a8b-51b6-8620-9cfdc4fd23b3 |  | note | RESPONSIBILITY: Site Engineer
text | 62f9e64a-0fcf-5ec2-81f5-1687c8c7dfe0 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 5.9 Aggregate retention
label | ec6f3e19-4681-54ab-a616-9e80b76199c1 |  | note | FREQUENCY: Each lot
label | f8f8c350-051d-55e3-b96e-45a51db462db |  | note | ACCEPTANCE CRITERIA: Acceptance of work for aggregate retention shall be based on visual assessment, or tested in accordance with the VicRoads Test Method RC 317.03 and assessed in accordance with Table 408.153 if required by the Superintendent.
label | e372d495-f964-5332-ab7f-f6e1123afa12 |  | note | REFERENCE DOCUMENTS: Cl 408.15 (c)
label | fa088d39-1ea3-5fa6-9e8c-cdf388e33759 |  | note | INSPECTION/TEST METHOD: Verify
label | c6214c3b-1d84-5f19-abe9-dfae452db89a |  | note | RECORD OF CONFORMITY: Signed ITP
label | 3daf5ce4-6202-5d5b-a9ee-2c7c0a2ebb0f |  | note | IP
label | 9ede18a7-84e5-5677-8865-2f8f2d9f1818 |  | note | RESPONSIBILITY: Site Engineer
text | eed30247-6049-5268-b9da-6776d72d7749 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 5.10 Visual Uniformity
label | 080a8d79-4a5c-5d9d-b441-a614e736a8b1 |  | note | FREQUENCY: Each lot
label | 70459bb1-3fa1-5703-89aa-fa459f85fdf6 |  | note | ACCEPTANCE CRITERIA: Provide a surface with uniform colour, texture and consistent appearance
label | bee2cfa2-e826-52c2-bd62-220f516ac20b |  | note | REFERENCE DOCUMENTS: Cl 408.15 (d)
label | 49daa13a-a5f1-5f05-84a5-9a2f52e2d89b |  | note | INSPECTION/TEST METHOD: Verify
label | 57708b57-4870-5ebf-98a3-0f157792ef06 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 5f2b7631-7d64-5d49-8ecb-775502219c07 |  | note | IP
label | ae1b969b-bf90-590c-80a4-8d0b707f1c53 |  | note | RESPONSIBILITY: Site Engineer
text | ecef7329-427f-50d4-8e6c-caa3ead3c108 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 5.11 Maintenance of seals
label | 9d7c39bb-677a-57ab-9561-f354cd597067 |  | note | FREQUENCY: Each lot
label | 193aaad3-3ee4-5a18-9574-4250d6ae2e21 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | 120439fd-55b6-57e2-b821-a2a6d75b1c62 |  | note | ○ The contractor shall be responsible for the monitoring and maintenance of seals from the time of application until the end of the defects liability period. The Contractor shall advise the Superintendent in writing of the proposed treatment to effect the above work before undertaking the work
label | c0f64a9f-8335-5f39-a54e-71055aca2eba |  | note | REFERENCE DOCUMENTS: Cl 408.16
label | 6a00ca24-3f9a-593a-b68c-2f9fb813fe99 |  | note | INSPECTION/TEST METHOD: Verify
label | a6b37e3b-2854-5ddf-adc6-37d8658ab362 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 583ad90d-6517-55f2-a888-0341fc3a89fb |  | note | HP
label | ef5ad065-5a12-5f11-b623-601f3f9a4c3a |  | note | RESPONSIBILITY: FH Engineer / Spray Supervisor / Superintendent
text | 5add9476-db53-5d7b-923b-8db9b2ead0b0 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.12 Maintenance of seals
label | 15340c7d-333d-5842-adfc-ab115ef2c828 |  | note | FREQUENCY: Each lot
label | 8107f910-7dd4-539e-ab9c-cef748474a87 |  | note | ACCEPTANCE CRITERIA: The Contractor shall obatin the agreement of the Superintendent of the proposed treatment before undertaking the work.
label | b83719ff-9080-5a88-9000-bbfa2ca6f900 |  | note | REFERENCE DOCUMENTS: Cl 408.16
label | 1d6d4fd9-f95b-5220-9eba-885a3b4b55e8 |  | note | INSPECTION/TEST METHOD: Verify
label | 8c108d98-3a07-56e3-a599-048ee77ae1cf |  | note | RECORD OF CONFORMITY: Signed ITP
label | e6b232f5-24fc-5ca5-b924-76c98838743d |  | note | HP
label | 09eecd95-897a-5844-b649-0fb0aa3c75f2 |  | note | RESPONSIBILITY: FH Engineer / Spray Supervisor / Superintendent
text | 89626521-5d7c-5fe7-9a83-814987129fb1 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6 - Testing
checkpoint-status |  |  | checkpoint | 6.1 Compaction of Asphalt layers
label | b73478c2-0167-5737-98b9-550948dbad59 |  | note | FREQUENCY: Per Lot
label | dba0b3ad-b3f7-52d0-9375-2ebce663281e |  | note | ACCEPTANCE CRITERIA: For layers <= 50mm, if characteristic density ration is:
label | 50fadcb6-a9fb-5337-9062-fe4892f1ad59 |  | note | • 95.0% or more - Accept Lot
label | 435622b1-ce36-598a-9712-c0caed07af9c |  | note | • 94.9% to 93.0% - Lot may be accepted at reduced rate
label | d7f838bb-251f-59c2-9da9-3fa8ece7bba2 |  | note | ○ For layers >= 50mm, if characteristic density ratio is:
label | 7eba83b6-ce29-5694-8cc6-916e30eb3a49 |  | note | • 96.0% or more - Accept lot
label | a9f9a844-1209-550f-b51e-405388b8c656 |  | note | • 94% to 95.9% Lot may be accepted at reduced rate
label | f8ff64dd-e246-5a4b-920e-563269498c8b |  | note | REFERENCE DOCUMENTS: Cl 407.27 Table 407.271 Cl 173.04
label | 3f2e1d85-84cb-513f-bb3d-cc18c5cc1402 |  | note | INSPECTION/TEST METHOD: Verify
label | 77a7b114-9c9e-580b-9b16-17ef1a7cc4bd |  | note | RECORD OF CONFORMITY: Test Report
label | 9a8a248c-2a80-55a7-9841-ffd17d714da3 |  | note | TP
label | a42ce67b-ec5a-5703-b6c9-7aaab761a135 |  | note | RESPONSIBILITY: FH Engineer/ Lab Technician
text | 20838a7b-4d90-5349-b3c1-1a711a1dffa6 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 6.2 Level Conformance for Asphalt layers
label | bf323ac3-3362-53b8-a26d-9697b09df2eb |  | note | FREQUENCY: Per 4,000m2 at completion of work
label | 7bd50374-3816-5c1b-9ec6-4dd1fef0aff9 |  | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of ±8mm (Scale B)
label | b02e992e-6b71-5abd-8e0d-d575d7d85278 |  | note | REFERENCE DOCUMENTS: Cl 407.29 Table 407.293
label | 931a42a8-18ce-5884-ba86-a1a878385a73 |  | note | INSPECTION/TEST METHOD: Verify
label | 4610e5e7-29ba-56ea-b812-5fa0e0b5c711 |  | note | RECORD OF CONFORMITY: Visual match existing / This ITP signed off
label | f653844b-4b75-586a-9e54-f20a655e1334 |  | note | SCP
label | 6edae322-73f7-5ee5-9cec-464bcc6f92a9 |  | note | RESPONSIBILITY: FH Engineer/ Surveyor
text | c861a040-67b9-5d59-8fb7-ab1effc706c9 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 89f9be43-67d4-5f4c-9c8d-1ea1f08ac3f0 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 5f0c2e7a-7dc4-5be7-8108-580d49b57dca |  | textbox | Print Name:
text | 25f5f7ae-0f0a-5453-8e25-5f39de3d82bb |  | textbox | Position:
text | 5850792d-b5e2-5f85-9e3c-954b0e3d5676 |  | textbox | Date:
holdpoint |  |  | signoff | Add Signature
checkpoint-no-status |  |  | checkpoint | Table 407.171 Minimum Pavement Temperatures Prior to Laying Asphalt
label | 1ebb333d-859d-5819-ac53-175343701199 |  | note | Asphalt Type ¦¦ Intermediate or Base Courses ¦¦ Wearing Course
label | a4f7356b-6fb4-5b4d-89a8-19b2d5972d1e |  | note | – – – – – – – – – –
label | 6c800524-add4-5fb6-a4ea-3840384c6a36 |  | note | All asphalt with a specified binder class of C170 or C320 ¦¦ 5°C ¦¦ 10°C
label | 56011257-c2ed-53c5-9958-0d7c1568b8f1 |  | note | All asphalt with a specified binder class of C600 or containing a PMB ¦¦ 10°C ¦¦ 15°C
checkpoint-no-status |  |  | checkpoint | Table 407.271 Limits for Characteristic Density Ratio (Six Tests)
label | 5cf074b3-a8c0-58ec-9cc9-432d3befea0d |  | note | For layers less than 50 mm thick
label | c2588d75-d584-5c39-aa66-bad78c18d1fc |  | note | Characteristic Value of the Density Ratio (Rc) ¦¦ Assessment
label | 121ffb16-0612-5079-bc02-6eb189615a9f |  | note | – – – – – – – – – –
label | 5d9fa45c-fb98-5574-a642-dc7020a1aace |  | note | 95.0% or more ¦¦ Accept lot subject to no other nonconformances raised for the lot
label | dd990079-963f-5a35-9cd1-eb6c585efc8f |  | note | 94.9% to 93.0% ¦¦ Lot may be accepted at a reduced rate calculated by P = 15 Rc - 1325
label | 53813a14-1ed0-5028-97c6-5280f5b47767 |  | note | 92.9% or less ¦¦ Remove and replace asphalt
label | 77a181af-3307-5cd0-8984-d79f92714689 |  | note | – – – – – – – – – –
label | 660542d6-e819-53e6-b6d5-14abe6923779 |  | note | For layers 50 mm thick or greater
label | 11a2e32b-778e-5580-ab53-b5efa3a450d5 |  | note | Characteristic Value of the Density Ratio (Rc) ¦¦ Assessment
label | a7aafc4e-c0d4-5219-b4dc-9e54669befcd |  | note | – – – – – – – – – –
label | 908f1984-63d4-57c7-9cb9-b342c910131e |  | note | 96.0% or more ¦¦ Accept lot subject to no other nonconformances raised for the lot.
label | 29d4ab00-0073-5d36-8604-41752766ca09 |  | note | 95.9% to 94.0% ¦¦ Lot may be accepted at a reduced rate calculated by P = 15 Rc - 1340
label | ad062eed-8bd1-5f3a-80b9-a28a6e1f22ab |  | note | 93.9% or less ¦¦ Remove and replace asphalt
checkpoint-no-status |  |  | checkpoint | Table 407.292 Minimum Number of Level Measurements per Lot
label | da7e4d72-b6af-5b6f-a833-f5e2c4a531c8 |  | note | Scale of Surface Level Measurement ¦¦ Minimum Number of Measurements Per Lot
label | f5e09f56-0418-5bb4-8de6-f2a08b70a3db |  | note | – – – – – – – – – –
label | b6dda7d8-296a-52ad-9a09-f5830a39ae0b |  | note | Scale A ¦¦ 80
label | 9a51aa75-fb53-5d7e-89dc-302c3bc332ea |  | note | Scale B ¦¦ 40
checkpoint-no-status |  |  | checkpoint | Table 407.293 Mean Surface Level Tolerances for the Sub-base and Pavement Courses
label | 48de1df7-d552-52a9-abf9-beabaa8f028a |  | note | Granular or Cement Treated Subbase: x̅ Range (mm) / Max. S (mm) ¦¦ Asphalt Layers: x̅ Range (mm) / Max. S (mm)
label | 5820e474-dcd7-5aff-9431-f4e413a7031f |  | note | – – – – – – – – – –
label | 24eded61-d98f-5dbe-b7c0-4ae5677145e9 |  | note | Scale of Surface Level Measurement: Scale A
label | 9a84fe47-33fe-5bc6-a8ee-bb199c1b478f |  | note | +4 to -8 / 8 ¦¦ ±5 / 8
label | f46d6919-ae06-517f-8e4d-a77deb2c50e4 |  | note | – – – – – – – – – –
label | 1cd5892e-f7c9-577b-ab7c-c3d3688646fe |  | note | Scale of Surface Level Measurement: Scale B
label | 52ee4204-3f5a-523d-ab8d-f854cd427ff5 |  | note | +6 to -12 / 13 ¦¦ ±8 / 10
label | 6f78e07e-36d1-5b07-af32-5eb3a5e9034c |  | note | – – – – – – – – – –
label | aaa731a2-a53c-5ea5-8a8d-f296a30fb81b |  | note | Notes on Table 407.293
label | e7b6504c-029d-5ac3-a8e2-1d4419d61080 |  | note | x̅ is the mean value of all level readings taken in the lot (a negative value designates a measured departure below the design level and positive value designates a surface level above the design level)
label | 0d67dfee-5e9f-5e14-843a-1a4c33fd2919 |  | note | S is the standard deviation of all level readings taken in the lot.
checkpoint-no-status |  |  | checkpoint | Table 408.141 Maximum Time Limit for Removal of Loose Aggregate
label | 2234ea65-df36-5559-aa6b-3e875cf5673a |  | note | Traffic Volume (AADT) * ¦¦ Maximum Time Limit
label | 5df8fa54-c83d-55b6-9edd-50b3d3337d40 |  | note | – – – – – – – – – –
label | f2161b4b-ab09-5025-9340-55c9b8571e30 |  | note | >5000 and all Freeways ¦¦ Within 8 hours of sealing
label | ba638221-4784-5ce3-98a6-d09d2cedc7fb |  | note | >2000 to 5000 ¦¦ Within 24 hours of sealing
label | 500f0f62-fefa-5d9a-9825-57ba66eb61cf |  | note | >500 to 2000 ¦¦ Within 48 hours of sealing
label | f66fdb17-394e-5997-b7db-d92ec134201d |  | note | <500 ¦¦ Within 5 days of sealing
checkpoint-no-status |  |  | checkpoint | Table 408.152 Surface Texture Requirements
label | 588e999b-7fc2-5f6b-ab93-aee12215de9f |  | note | SINGLE/SINGLE TREATMENTS
label | 7abc28d1-b2f0-5015-8c9b-ff3e45326a58 |  | note | Mean Texture Depth (mm)
label | 103a9d1f-7b81-59db-86d4-ac003807959e |  | note | Size 5 :: Size 7 :: Size 10 :: Size 14 ¦¦ Action Required
label | 0f6dfb16-e058-5021-a3ac-6c6f8c8f157e |  | note | – – – – – – – – – –
label | 6998815d-d72a-5aa3-9f3f-a06f98c4096c |  | note | Treatment: Seals (All Types) (1)
label | 5a3c020c-e89b-53d5-9e14-19a397e9469f |  | note | 1.0 to 1.6 :: 1.3 to 1.8 :: 1.5 to 2.5 :: 2.0 to 4.0 ¦¦ Accept
label | 5bde1f7b-8fa8-577e-b660-a2502373f748 |  | note | 0.8 to 1.0 or 1.6 to 1.8 :: 1.2 to 1.3 or 1.8 to 2.0 :: 1.3 to 1.5 or 2.5 to 3.0 :: 1.7 to 2.0 or 4.0 to 4.5 ¦¦ The Superintendent may require rectification of the works or elect to reduce payment for the lot by $1.00/m^2
label | 310f8445-cde1-5478-b7ab-85add48b4395 |  | note | < 0.8 or > 1.8 :: < 1.2 or > 2.0 :: < 1.3 or > 3.0 :: < 1.7 or > 4.5 ¦¦ Work to be rectified
label | 56c21904-d873-541a-ac77-6e6d7ff27bae |  | note | – – – – – – – – – –
label | 512a33fa-a38b-5874-8f76-43478c62b54c |  | note | Treatment: Initial Seals (2)
label | e6dd59fa-4529-58e0-8afb-e72465056b1c |  | note | N/A :: 1.0 to 2.0 :: 1.2 to 3.0 :: N/A ¦¦ Accept
label | a3eec8e0-fdad-5425-afeb-110638960113 |  | note | N/A :: < 1.0 or > 2.0 :: < 1.2 or > 3.0 :: N/A ¦¦ Work to be rectified
label | 7916af2d-788b-5dcd-99c6-d242f822f841 |  | note | – – – – – – – – – –
label | 1cd5a017-e867-5508-9a7e-ea4841de577c |  | note | Treatment: Surface Enrichment (1)
label | f940ccf3-a3c4-55f0-b52d-e2c943504176 |  | note | N/A :: N/A :: 0.8 :: 0.8 ¦¦ Accept
label | 4345339f-2adb-51cc-9391-8498fb9cc315 |  | note | N/A :: N/A :: < 0.8 :: < 0.8 ¦¦ Work to be rectified
label | dbe5ac0a-f01b-5cb1-99e9-e0f8fc7bd576 |  | note | – – – – – – – – – –
label | 2f2e587c-3267-5ea1-8091-26db6c54b9fa |  | note | DOUBLE/DOUBLE TREATMENTS
label | 3dc7bcef-dc90-5403-9c66-c7ae72af6929 |  | note | Mean Texture Depth (mm)
label | 9aac93d3-7bcf-5605-b739-f1da34fdb0af |  | note | Size 10/5 :: Size 10/7 :: Size 14/5 :: Size 14/7 :: Size 20/7 ¦¦ Action Required
label | 0e2982e2-7c07-52e5-8cde-4d538d52d762 |  | note | – – – – – – – – – –
label | 1b6e6916-7e41-5f4e-8ff2-76c14d4c4d51 |  | note | Treatment: Seals (All Types) (1)
label | 14315b02-d7a5-5708-aaa0-83b45eaefa05 |  | note | 1.3 to 2.1 :: 1.3 to 2.2 :: 1.3 to 2.4 :: 1.3 to 2.4 :: 1.4 to 2.5 ¦¦ Accept
label | db05f0ad-fac8-552f-8f42-7f46757820cf |  | note | 1.2 to 1.3 or 2.0 to 2.3 :: 1.2 to 1.3 or 2.1 to 2.4 :: 1.2 to 1.3 or 2.4 to 2.7 :: 1.2 to 1.3 or 2.4 to 2.7 :: 1.3 to 1.4 or 2.5 to 2.8 ¦¦ The Superintendent may require rectification of the works or elect to reduce payment for the lot by $1.00/m^2
label | a7853d89-52e6-5873-b0ba-0d106dcd11fd |  | note | < 1.1 or > 2.3 :: < 1.1 or > 2.4 :: < 1.2 or > 2.7 :: < 1.2 or > 2.7 :: < 1.3 or > 2.8 ¦¦ Work to be rectified
label | b792b8d3-9a44-5d26-8869-5e1bfe057199 |  | note | – – – – – – – – – –
label | 3e14d991-78eb-56f4-86d4-d9c3be2a0aa6 |  | note | Treatment: Initial Seals (2)
label | 2c8259ed-a623-5e92-a62a-46b009b102c1 |  | note | 1.0 to 2.0 :: 1.0 to 2.0 :: N/A :: N/A :: N/A ¦¦ Accept
label | 3b31b8bc-ec09-54cb-a797-8719a3624ac9 |  | note | < 1.0 or > 2.0 :: < 1.0 or > 2.0 :: N/A :: N/A :: N/A ¦¦ Work to be rectified
label | 05df2092-a00c-50cd-b4f5-5f582c28c19e |  | note | – – – – – – – – – –
label | dabdcbe4-9ffd-5536-aa87-4f2da3c03061 |  | note | Notes:
label | 12ba42cd-cac1-5d19-beac-68b05cef6fc3 |  | note | (1) Surface texture measurements for sprayed seals and surface enrichment may be undertaken at any time during the Defects Liability Period, but final acceptance of works is not affected until the end of the Defects Liability Period.
label | 989dc65a-18dd-56e0-b2d3-6298f7168e72 |  | note | (2) Surface texture measurements for initial seals shall be undertaken between 10 and 15 weeks after placement. If tests are not undertaken in this period and later test results require the works to be rectified, the later test results are to be used for acceptance of the works.
checkpoint-no-status |  |  | checkpoint | Table 408.153 Assessment of Aggregate Retention
label | cdf5e603-3a0b-57b0-9463-cbf3aca9c492 |  | note | Degree of Aggregate Stripping ¦¦ Action Required
label | 352de07c-fc5d-5a3b-aaa2-6845a856a981 |  | note | – – – – – – – – – –
label | 1cab8edc-7f31-5020-be46-fcd06676679c |  | note | 0 to 2 ¦¦ Accept
label | 9bb8f8d5-11ec-5f67-bb2e-0223da4b0ab8 |  | note | 3 to 5 ¦¦ Work to be re-tested within one month prior to the end of the Defects Liability Period. If the Degree of Aggregate Stripping has increased since it was last tested, the work shall be rectified before the end of the Defects Liability Period.
label | c16856e7-11ac-50a5-8fb9-c7e93ecb7687 |  | note | Greater than 5 ¦¦ Work shall be rectified within 5 days.
label | 50210208-7721-5599-a6f9-950e0059e942 |  | note | – – – – – – – – – –
label | 5541b30a-175e-5dfd-94d6-d9dd6ac42266 |  | note | Note: Aggregate retention measures may be undertaken at any time during the Defects Liability Period, but final acceptance of works is not affected until the end of the Defects Liability Period.
checklist-sectioned |  |  | checklist | ITP - Unbound Flexible Pavement Construction | itp |  |  |  | Yes | ITP - Unbound Flexible Pavement Construction Rev0 | bdb50099-780b-471e-9a31-0061e85b9413
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | 8d3aebad-063d-5de1-90c9-675d59887f2f |  | note | FREQUENCY: Prior to commencing any activity
label | 6f3c9f9b-5e19-54b1-ac16-991716f7de9e |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | be689eee-2778-509c-994e-1b3c6622a263 |  | note | – using the correct and complete set of drawings
label | 2f47da77-39fd-5f85-a09d-ac01a84b863d |  | note | – all drawings are the latest revision
label | 9bcbbbaa-4b07-5906-a9d3-d30009aaceb2 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 9ed9f9c3-da98-5bb1-86b7-a65901996a53 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 36fd22a2-d9d0-5cb9-a67d-a338ac06492b |  | note | RECORD OF CONFORMITY: This ITP signed
label | d855ff07-c3bc-53f5-92c6-69893f96e404 |  | note | HP*
label | 531b3268-af0b-515a-8269-8d03ab6631a1 |  | note | RESPONSIBILITY: Site Engineer
text | 0783f79f-6948-54f1-874b-f1b6960b6870 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 1.2 Material Classification
label | e682a616-3957-5939-b441-3c1d030e9496 |  | note | FREQUENCY: Prior to commencing works
label | b24f4a0f-b568-508d-8fe6-dc16611ccee6 |  | note | ACCEPTANCE CRITERIA: Hold Point:
label | 00edaf20-6f7d-5412-9419-8537b5140ede |  | note | ○ All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads RC500.02 and conform to specified requirements applicable to that class of product
label | 4a219f95-5b62-5f44-9ec7-8db2bbd14f2f |  | note | REFERENCE DOCUMENTS: 812.04 VicRoads RC500.02
label | ffa320ee-2f78-5c3e-83ad-3cfc87be0036 |  | note | INSPECTION/TEST METHOD: Document Review
label | 6c25426f-dbd0-510f-a0c9-52c7e8712cc0 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 1de0fe54-638f-534d-85a9-d91716c307ea |  | note | AP
label | 803c475e-d757-5d4d-a663-71dad2cbc6fb |  | note | RESPONSIBILITY: Site Engineer / QAV
text | 2ec1d6cf-76b9-5d1e-a259-c017e1c9c017 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 1.3 Implementation of all measures and controls
label | 6550897a-9971-57c6-b5f0-00c0b786f166 |  | note | FREQUENCY: Prior to commencing works
label | 04c985eb-3cd2-51e1-8eab-95135c0e54ee |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP`
label | a5b53110-e533-5528-a0fd-e4cb25d03564 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 7d719df5-1406-5869-a05e-c32e81682212 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 3d882d92-a13d-56a9-a467-354792858246 |  | note | RECORD OF CONFORMITY: This ITP signed
label | bb69bb63-4a24-5be3-920e-6eb9afe6eb40 |  | note | HP*
label | 5b17fe87-0571-52cd-90c1-3e9e80322a25 |  | note | RESPONSIBILITY: Site Engineer
text | c8a67ecd-ef08-5a50-9f5d-b3c4ac027f4f |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 1.4 Plant and Equipment
label | a8f8b0b1-7a96-587a-8c5f-e1deca50b2ec |  | note | FREQUENCY: Prior to commencing works
label | 3f5debb5-b3ee-5b77-84d3-3a209ba5db28 |  | note | ACCEPTANCE CRITERIA: Plant and equipment used in the Works are appropriate to achieve specification requirements and is inducted
label | 1bb555f1-e545-540f-be85-dd2699979d3a |  | note | REFERENCE DOCUMENTS: N/A
label | bb4886de-2a98-5675-8574-a6cb6d6ef7e4 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | f4e723d9-bc6f-5350-ab82-9e9e66398fa3 |  | note | RECORD OF CONFORMITY: This ITP signed
label | ba4e8295-4baa-5082-a538-7ade931cfb1e |  | note | IP
label | 6aa4b487-ce6e-53df-89d0-7088123f3a96 |  | note | RESPONSIBILITY: Site Engineer
text | 988576b6-3c06-544f-8619-2b0281ad23ef |  | textbox | DATE:
checkpoint-group |  |  | section | 2 - Placement
checkpoint-status |  |  | checkpoint | 2.1 The commencement of construction of base and subbase
label | af41b0d5-c9eb-51df-a857-93bb80dc3dfe |  | note | FREQUENCY: Prior to placing subbase
label | a89f8300-f329-5557-9c2a-d5cf63734526 |  | note | ACCEPTANCE CRITERIA: Underlying ITP signed off
label | 3bd62c97-0e96-5488-8937-b39268f93fa9 |  | note | ○ Identifying and removing soft areas to a minimum of 200mm depth. Underlying layer shall be clean of all foreign matter. The edges of previously placed materials shall be watered. Proof roll underlying layer prior to commencing
label | 2bf513f5-8cef-596c-81c7-4432837b2300 |  | note | REFERENCE DOCUMENTS: Drawings
label | 2269d68b-d4bb-5c92-a6d4-2c78c77c9af8 |  | note | INSPECTION/TEST METHOD: Verify
label | ae201930-39cc-5c47-ae9e-6306a355de10 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 7fc48494-6c82-5743-a701-e1bae5e8868b |  | note | IP
label | ce8a13cc-ff9e-5798-b90c-c9d35b05580d |  | note | RESPONSIBILITY: Site Engineer
text | 9cc6a703-3220-5d01-9976-2edb8e4fabbe |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.2 Delivery Dockets
label | 9defe0b1-ac75-5ed2-b202-8c7c0de71fcd |  | note | FREQUENCY: Each lot
label | 9546fc29-4db6-5aa6-a53f-4dc00ee826e8 |  | note | ACCEPTANCE CRITERIA: Where material is scheduled for measurement by loose volume in delivery vehicles or by mass, a delivery docket for each load shall be issued to the Superintendent at the point of delivery.
label | 65a5e63c-1647-5a0e-afad-a73c6c1f3245 |  | note | REFERENCE DOCUMENTS: –
label | 5483c596-a7db-5568-800b-108bd3c6fbba |  | note | INSPECTION/TEST METHOD: Verify
label | 59433da4-00bf-5ca4-bc8b-98eada973392 |  | note | RECORD OF CONFORMITY: This ITP signed
label | b784ebf7-057c-5499-9bc8-0c2d01ff30fb |  | note | IP
label | 3a445433-f50e-5344-ac3f-2eef7755cb21 |  | note | RESPONSIBILITY: Site Engineer
text | 230125f8-04ba-5c3b-b320-17052a917f6b |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.3 Layer Thickness
label | 0750f23f-0a5e-5b23-8f82-fe02b302c96d |  | note | FREQUENCY: Each layer
label | 5bc87d80-c413-5937-a8f9-40286ad7fc3d |  | note | ACCEPTANCE CRITERIA: Material is to be compacted to the overall thickness shown in the drawings (dependent on pavement type), subbase not less than the specified thickness by more than 15 mm
label | 60ff0523-a9b6-5a21-94b4-96fe76549302 |  | note | REFERENCE DOCUMENTS: Drawings and 304.06(c)
label | 35340d4b-5c3a-5f02-b2d7-7be1941b9238 |  | note | INSPECTION/TEST METHOD: Visual and Measure
label | 16c5fb00-ed52-5ce0-8937-676abe9abdba |  | note | RECORD OF CONFORMITY: This ITP signed
label | 833197d4-78a8-5c37-b975-e890622ef7da |  | note | IP
label | def18d82-ebfb-5aa6-91ca-cdc1852e9430 |  | note | RESPONSIBILITY: Site Engineer
text | 51cc3034-e565-5423-958c-eaab73c5abab |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.4 Conformity with Drawing
label | 694855f4-1d59-5696-9833-194519f18533 |  | note | FREQUENCY: Each lot
label | f3cf8382-0aa6-5a9d-bc7d-92a840cb1c7f |  | note | ACCEPTANCE CRITERIA: Width of each side of the pavement shall not be less than the specified offset width or more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line.
label | d14f48b9-ee8a-5ae0-b1cd-c89182f3351e |  | note | ○ Where pavement is to be constructed to the lip level of kerb and channel, it shall be constructed flush with the lip of the channel or not more than 5 mm above.
label | 97f4da71-afde-5989-9517-00bfc499803d |  | note | ○ Any material that has been compacted and then trimmed from the compacted surface to conform
label | 68fa71b6-69b0-551e-b4e8-bcbde52d8844 |  | note | REFERENCE DOCUMENTS: –
label | 74bbd18d-d534-5a8d-985d-fc0dcee605ef |  | note | INSPECTION/TEST METHOD: Verify
label | 49d45c36-4c65-5289-a0b1-6487ff5cc497 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 2a915c64-c6cb-516c-9c44-2499434b87b7 |  | note | IP
label | 2f3c5854-111e-580b-97f6-6804dfa9ce15 |  | note | RESPONSIBILITY: Site Engineer
text | bd6b6e24-da4c-5aaa-969c-2750d86b338c |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 2.5 Jointing
label | 561b4744-c97e-5612-9574-ec4bc9bb332a |  | note | FREQUENCY: Each lot
label | 3777f2aa-f690-594d-95c3-fb0b69c4091e |  | note | ACCEPTANCE CRITERIA: (a) material shall be spread in such a manner as to minimise the number of joints
label | 80486b03-8cbd-544b-bc1e-836fe1cc6014 |  | note | (b) transverse joints shall be offset from one layer to the next by not less than 2m
label | cbf3318d-fd2a-5d77-a74a-3c86b06ff29e |  | note | (c) longitudinal joints shall be offset from one layer to the next by not less than 150mm.
label | 9a149986-d0c9-5f5e-87fd-d1c03b5159a7 |  | note | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
label | 96f4e698-0faa-5e17-8bd4-213f2c9afa60 |  | note | REFERENCE DOCUMENTS: 304.07
label | d318f95d-28c6-5c17-b715-72b09b8f772f |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | f8b79527-8fd1-5da3-94f4-44ce72733379 |  | note | RECORD OF CONFORMITY: This ITP signed
label | d64c2146-2318-52b7-b4a0-45c7708d36f5 |  | note | IP
label | 49fb1473-d8a8-5771-a062-85895415b42b |  | note | RESPONSIBILITY: Site Engineer
text | b19614d3-ec63-50f3-8951-849c3dfc661f |  | textbox | DATE:
checkpoint-group |  |  | section | 3 - Testing and Conformance
checkpoint-status |  |  | checkpoint | 3.1 Determine Testing Scale & Initial testing frequency
label | 7eac433f-bef6-5079-98f0-3b51fcb5db19 |  | note | FREQUENCY: Prior to Testing
label | e9c417ee-3012-56e3-bbab-a13d71a6ccf9 |  | note | ACCEPTANCE CRITERIA: Where testing is specified in Clause 304.10(c) or (d) and Clause 304.12 requires it to be Scale B, the first lot of each pavement course shall be tested for post-compaction grading and PI.
label | ef41eab2-8564-5a27-a233-bc5fc16904cc |  | note | ○ If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post-compaction testing will be required for that pavement course.
label | 2dd9801a-7b4b-5807-b849-12c564d8f8a2 |  | note | REFERENCE DOCUMENTS: Table 204.161 304.10 (c or d) 304.10 (a) 304.10 (b)(ii) Table 304.101 Table 304.103 304.11 (c) (ii)
label | 61ef6505-1b09-5121-80e0-b92db74df38d |  | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
label | d4549a18-41c9-5197-871f-09b018ab1736 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 6e122f1b-ba60-5f15-be17-d0869031c298 |  | note | AP
label | ab0f7d9e-dd67-592a-80e7-1ab4634121b3 |  | note | RESPONSIBILITY: Site Engineer
text | e2d77b22-9f9c-5e36-aebb-f58376add9d0 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 3.2 Post Compaction Testing
label | 492b71f6-a715-58a8-8084-75eecc720077 |  | note | FREQUENCY: Each Lot 304.10 (a) & (b)
label | 09b036c3-1b16-5aa1-a758-c7f41d89d4de |  | note | ACCEPTANCE CRITERIA: If the first lot does not meet the requirements specified in Clause 304.10(a) and (b), the Contractor shall then seek approval from the Superintendent before work proceeds.
label | 61f44749-2338-58e4-a9af-5e65d2c742fc |  | note | REFERENCE DOCUMENTS: 304.11 (c) (ii)
label | 18e6684d-f24d-5dde-9a02-e0aeae5c5de3 |  | note | INSPECTION/TEST METHOD: PI
label | c13da60f-a488-5138-83bd-d2ea5e53c2c6 |  | note | RECORD OF CONFORMITY: This ITP sIgned
label | a145548d-b5f7-5829-a4ef-1b605f27b3cf |  | note | HP
label | 18693821-af5c-501d-8d78-b6f1712aed3c |  | note | RESPONSIBILITY: Site Engineer
text | 03f1e5e0-d86e-5fe4-bb65-446141372953 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Test Rolling
label | f1ff754f-983f-583b-81d4-1309a3e43610 |  | note | FREQUENCY: Each lot
label | 3fa37dfa-e8cb-52fa-9ea8-3510b52f8ef7 |  | note | ACCEPTANCE CRITERIA: Hold Point:
label | d0a36ff9-cf3f-5571-930c-da28329536b8 |  | note | ○ All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173, prior to acceptance of the layer.
label | c6ca99a1-67df-5cbf-83db-e085a0defccd |  | note | REFERENCE DOCUMENTS: 304.08
label | f6bec923-bb5b-59f3-a79a-517164ebdcbd |  | note | INSPECTION/TEST METHOD: Test Roll
label | e8edb2f3-75e7-5b21-94d9-a5318606cc89 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 4ce4c470-ef22-5d69-ac86-462d6faa2814 |  | note | HP
label | fe00b6ba-4845-5cba-954c-bf9b4c5b4b46 |  | note | RESPONSIBILITY: Site Engineer / QAV
text | d46189e6-a709-519c-966c-3718f6bcd3d9 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Compaction Testing
label | b41d6902-b4e5-5eb9-b952-75c0de7a3140 |  | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
label | dc5b942e-c109-59c5-9e2a-8549d70eaa4a |  | note | ACCEPTANCE CRITERIA: The calculation of density ratio shall be based on tests performed using Modified compactive effort. The work shall be assessed for compliance with Scale B requirements for testing and acceptance of compaction as specified in the table below
label | a8527f9e-1f21-5700-81a8-9b0cbd6f470f |  | note | – – – – – – – – – –
label | ad9833c0-e183-5c3f-a40b-7c01847baeaa |  | note | Characteristic Density Ratio % (six tests)
label | 3d99e54f-2652-5ddb-b844-78def0ea8d60 |  | note | Lower Subbase Layers ¦¦ Upper Subbase Layers ¦¦ Base Layers: Layer directly beneath the Bituminous Surfacing ¦¦ Base Layers: Other Layers
label | 938dfe18-c967-599f-b094-00e2d78688f9 |  | note | – – – – – – – – – –
label | b8f71dba-aa4a-5360-b03e-1194fa59e75e |  | note | ○ Compaction Scale: A
label | 94dd5aa4-bf5f-52f2-acab-c4de02729474 |  | note | Not less than 98.0 ¦¦ Not less than 98.0 ¦¦ Not less than 100.0 ¦¦ Not less than 99.0
label | 328a0ae5-e296-5193-b2bf-10733a65e079 |  | note | ○ Compaction Scale: B
label | 2370d66a-027d-5652-a3b6-ec3397b7913c |  | note | Not less than 97.0 ¦¦ Not less than 97.0 ¦¦ Not less than 98.0 ¦¦ Not less than 98.0
label | b6402dfa-b9b3-5a16-86a7-4c73cc8d75d6 |  | note | – – – – – – – – – –
label | fce5442b-65f4-5765-a83a-441e2a478760 |  | note | REFERENCE DOCUMENTS: 304.08 Table 304.061 304.11 (b) Table 304.111
label | 5c07b090-1cd7-5877-a45f-c284b361a9d4 |  | note | INSPECTION/TEST METHOD: Test point
label | 733e7ab2-b539-56a8-8d0a-b995c60e1a01 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 3dd8b7a7-7e7a-5468-8499-dd0b2f91ad64 |  | note | TP
label | 868db1af-655c-5c41-a88e-1fffba71f390 |  | note | RESPONSIBILITY: Site Engineer
text | c70e952d-3b2b-53fd-a7a8-d02dce3a8ef8 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 3.5 Post Compaction Testing
label | f9d2e15c-33d3-5a01-adcf-56c004adf9db |  | note | FREQUENCY: Refer to table 304.111 for various minimum frequency or testing for Grading and PL
label | 52ab95ee-e176-530c-a1bc-335495bcdd43 |  | note | ACCEPTANCE CRITERIA: If specified in Clause 304.10(c) or Clause 304.10(d), following completion of compaction, material shall be tested for post-compaction grading or Plasticity Index (PI) at the frequency specified in Clause 304.11 for the appropriate Scale of Testing specified in Clause 304.12(a).
label | e632f621-984e-53c3-a8d2-dae59fe14868 |  | note | REFERENCE DOCUMENTS: 304.10 Table 304.101
label | 85a6da43-26b1-5544-8cf8-21e4a2be7c06 |  | note | INSPECTION/TEST METHOD: Test point
label | debd498c-315d-5281-8bec-3289de392586 |  | note | RECORD OF CONFORMITY: This ITP signed
label | cd6338fd-28cf-503e-84b5-c32732e4d1d9 |  | note | TP
label | 7f74638d-50cb-5394-9fd1-3b77a2fc360b |  | note | RESPONSIBILITY: Site Engineer
text | bc2f555c-0d8b-51b3-9190-723117d2a5ec |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 3.6 Shape
label | 41830422-0c96-5dcb-a8ec-793776556dfa |  | note | FREQUENCY: Each lot
label | b7ad7fd4-a7e1-5fa3-a534-9446c7f6e078 |  | note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall have no point deviation > 8mm from 3m straight edge. The subbase shall also not be less than the specified thickness by more than 15mm
label | 016242c1-b1ed-53c5-9456-c51ea2ac88a6 |  | note | REFERENCE DOCUMENTS: 304.06(b, d, i) Drawings Table 304.062
label | 07d0aa87-aad4-5b25-87ba-63609b4d6bc1 |  | note | INSPECTION/TEST METHOD: Survey
label | a4c4ef30-d53a-51d6-b1ac-1afa598663b9 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 005e4e77-3d14-591a-b81b-05a76ee02d59 |  | note | IP
label | b1430579-f66b-5da2-8bbd-8324fbb01630 |  | note | RESPONSIBILITY: Site Engineer
text | 065083a3-ed18-5811-bca9-b689c71c9b67 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 3.7 Completed Surface Level Compliance
label | 40461a33-cc53-5068-b998-d7f09b943bfa |  | note | FREQUENCY: Each lot
label | 474a66eb-bc8e-5cbd-96f5-51d5d5f08b6b |  | note | ACCEPTANCE CRITERIA: Each level measurement shall be taken at random locations over the area of the lot in accordance with the VicRoads Test Method and the number of measurements taken within each lot shall not be less than the number specified in Table 304.061.
label | 549bbf79-a755-5726-b9a9-9240cc8cbdd9 |  | note | ○ The mean and standard deviation of the departures from the design surface level for the pavement courses at their respective levels within each lot shall meet the requirements of Table 304.062.
label | f6bd8299-c200-5da8-8c0b-1b271055853c |  | note | – – – – – – – – – –
label | 026c0075-3ff5-5cfb-b0d2-b09c31c3da1c |  | note | Table 304.062 Surface Level Tolerances for the Pavement Courses
label | a5f82ef3-887c-5292-ad2f-ac274390f1df |  | note | – – – – – – – – – –
label | b9e3822a-7c1f-53ed-be9c-632df0731689 |  | note | Scale of Level Measurement: Scale A
label | 653c9a11-3893-5aa1-a39c-cd8c44836dbe |  | note | Lower Subbase: x̅ Range (mm) ¦¦ Max. S (mm)
label | 1e43efab-726e-5ace-a392-712facfd470c |  | note | +6 to -10 ¦¦ 10
label | 7536b513-694d-521b-92db-d650fcf3619b |  | note | Upper Subbase: x̅ Range (mm) ¦¦ Max. S (mm)
label | ba4b465d-5bed-53bc-82b8-9572d4384e33 |  | note | +4 to -8 ¦¦ 8
label | 501d28b0-113a-5c02-bd0f-36e49f3d992a |  | note | Base: x̅ Range (mm) ¦¦ Max. S (mm)
label | 9f166a76-2822-55d9-8c9c-33b0bee0029d |  | note | ±5 ¦¦ 8
label | 80f5485a-a970-5525-9718-0c10f492254a |  | note | – – – – – – – – – –
label | 2d7b247d-a838-563b-b680-0b0227f548ce |  | note | Scale of Level Measurement: Scale B
label | 0352a575-928e-57a5-a2b9-1396f97a21f7 |  | note | Lower Subbase: x̅ Range (mm) ¦¦ Max. S (mm)
label | bd455349-8d07-5aac-9c6f-2f817f7d2f44 |  | note | +8 to -16 ¦¦ 15
label | e1d769f5-3be7-5d28-8892-b161bba5f75e |  | note | Upper Subbase: x̅ Range (mm) ¦¦ Max. S (mm)
label | 894bdb68-6eef-5597-8407-6baf975ff610 |  | note | +6 to -12 ¦¦ 13
label | 693f249c-f25e-5a45-a88e-44b5dd40faef |  | note | Base: x̅ Range (mm) ¦¦ Max. S (mm)
label | 51a21ea4-d5b5-56cb-93fe-29994366ae3d |  | note | ±8 ¦¦ 10
label | 615aedc6-e3f5-5927-a41a-5cf27551c249 |  | note | – – – – – – – – – –
label | 80e7edad-7d90-530d-aee3-9c5b20977b72 |  | note | Notes:
label | db4e2c66-d117-5bf7-85ea-d2ec18160861 |  | note | 1. x̅ is the mean value of all level readings taken in the lot
label | 0e141545-8cfe-5617-8315-a5e150282352 |  | note | 2. S is the standard deviation of all level readings taken in the lot
label | 8296d963-198b-59cc-81f0-f2d1b5bf3f84 |  | note | 3. A negative value designates a measured departure below the design level and positive value designates a surface level above the design level
label | a004b80b-1573-5860-9d6b-751e4d1a665c |  | note | – – – – – – – – – –
label | 4a93b6ae-2ab2-5c74-a1f6-c79fcd70f986 |  | note | REFERENCE DOCUMENTS: 304.06(b) Drawings Table 304.062
label | 83fdb978-446f-56a9-afe5-e4ff415acf35 |  | note | INSPECTION/TEST METHOD: Survey
label | 2525db75-8413-5c04-b969-54795f7767a0 |  | note | RECORD OF CONFORMITY: This ITP signed
label | b0c40f2c-90ab-5f51-8405-e26d50086b2f |  | note | SCP
label | 6996bce9-19ee-5445-9e80-4be8a7b6006b |  | note | RESPONSIBILITY: Site Engineer
text | 08aba1f2-d862-5316-94ae-aa7a5558a28c |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 759e5c6e-9bba-527c-966e-ebdb75d74f05 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | bc62d1fd-6578-5a61-b54a-c45ce7fbcd35 |  | textbox | Print Name:
text | a86760f0-3c5f-5914-ace5-c802c17bde3c |  | textbox | Position:
text | 1b0c8540-70b1-56b6-85f7-dc37c5730127 |  | textbox | Date:
holdpoint |  |  | signoff | Add Signature
checkpoint-no-status |  |  | checkpoint | Table 204.161 Schedule for Surface Tolerance, Material Properties and Compaction Testing
label | bf40d4ad-bda2-560c-a887-cd968090679d |  | note | Road Name ¦¦ Chainage/Location ¦¦ Scale of Surface Level Measurement (A, B or C) ¦¦ Scale of Material Property Testing (A or B) ¦¦ Scale of Compaction (A, B or C)
label | 98b41ee7-b465-5045-97f9-49dd3acbf4bb |  | note | – – – – – – – – – –
label | d4dfcb35-02b9-5ac5-901a-7ef4122e65d9 |  | note | Bruny Island Main Road ¦¦ Within Limits of Works ¦¦ B ¦¦ B ¦¦ B
checkpoint-no-status |  |  | checkpoint | Table 304.081 Acceptance Limits for Scale A and Scale B Standards of Compaction
label | f78fe94a-7512-58b9-8267-bb914160a40f |  | note | Characteristic Density Ratio % (six tests)
label | c9111b62-ba08-5891-8991-3fb67ec4c726 |  | note | Lower Subbase Layers ¦¦ Upper Subbase Layers ¦¦ Base Layers: Layer directly beneath the Bituminous Surfacing ¦¦ Base Layers: Other Layers
label | 52f643a8-d831-54e1-b861-18ccf50a4fb2 |  | note | – – – – – – – – – –
label | 895864e4-f0fb-5b69-b86f-47a93c7def3c |  | note | Not less than 98.0 ¦¦ Not less than 98.0 ¦¦ Not less than 100.0 ¦¦ Not less than 99.0
label | 1247efd7-d967-5860-a233-4acf5323235a |  | note | Not less than 97.0 ¦¦ Not less than 97.0 ¦¦ Not less than 98.0 ¦¦ Not less than 98.0
checkpoint-no-status |  |  | checkpoint | Table 304.101 Post-Compaction Grading Requirements for Crushed Materials
label | 1b654723-7bde-5239-b313-3c13b0162173 |  | note | Post-Compaction Grading Limits (% Passing by Mass)
label | 73a844a3-34ec-51c4-b1df-d8546f3b3953 |  | note | – – – – – – – – – –
label | eaaa45e9-61ae-5636-a380-84a78957a5f0 |  | note | Class 1 or Class 2 Crushed Rock
label | a421f102-c27f-5c21-9e6c-73e4b52b35e3 |  | note | Crushed Scoria Base
label | 9550c2f5-4208-5d18-a303-840a577b6450 |  | note | Class CC2 Crushed Concrete
label | 44b542ac-fa5a-5315-b60a-53bf5318b127 |  | note | – – – – – – – – – –
label | 00843076-4e27-5272-ab81-f02c396ca12b |  | note | Sieve Size ¦¦ Nominal Size (mm): 20
label | fc60e699-e3f4-5325-89a6-206979322b2d |  | note | – – – – – – – – – –
label | 62f34540-b253-5286-9a0e-a7fad49b73ae |  | note | 53.0 ¦¦ -
label | 6cd7e143-9e07-5470-9073-90a5686376e7 |  | note | 37.5 ¦¦ -
label | bc04053f-51f8-50b7-bc91-1c2e5a307d10 |  | note | 26.5 ¦¦ 100
label | b735a6a9-4d47-5991-ac0b-a71dfa65cbb7 |  | note | 19.0 ¦¦ 95 - 100
label | 595ff79a-83dc-5a1b-b547-f1b48909a546 |  | note | 13.2 ¦¦ 78 - 92
label | f7bada3d-f5f2-5a19-88d8-1adb667477e7 |  | note | 9.5 ¦¦ 63 - 83
label | 286e8e4c-ff64-519e-be68-88a160399f63 |  | note | 4.75 ¦¦ 44 - 64
label | d23bb9f4-be24-54d1-b9cb-886247c66082 |  | note | 2.36 ¦¦ 30 - 49
label | 761d5521-3f4b-5ee5-a4a0-beee4871b47c |  | note | 0.425 ¦¦ 14 - 23
label | 94a2b847-007d-5984-bef5-07a21e6896d0 |  | note | 0.075 ¦¦ 6 - 12
label | 59f5536d-dd17-5888-a74a-df6d79d39a07 |  | note | – – – – – – – – – –
label | 77f6ef7a-3459-5072-a359-31611eed885d |  | note | Class 3 Crushed Rock
label | cea30a0b-a0e3-523c-a229-0cb8ab36b9fc |  | note | Crushed Scoria Upper Subbase
label | 46dac082-b390-5d23-86f6-59790dd8505a |  | note | Crushed Concrete Class CC3
label | f6eefd04-0f51-59b3-83d6-616b914919bb |  | note | – – – – – – – – – –
label | dc21a10c-3372-55e9-9614-afd7e1a154bc |  | note | Sieve Size ¦¦ Nominal Size (mm): 20 ¦¦ Nominal Size (mm): 40
label | 164bc1c0-4886-59a7-bbe3-0bdb421536d7 |  | note | 53.0 ¦¦ - ¦¦ 100
label | 13809be0-9921-53cb-847e-aff4e0cc6c3f |  | note | 37.5 ¦¦ - ¦¦ 95 - 100
label | 253e3c5d-600a-512e-8402-340cce3438fd |  | note | 26.5 ¦¦ 100 ¦¦ 75 - 95
label | b36ec433-16e0-52e5-bf21-bfb29e3b8bd6 |  | note | 19.0 ¦¦ 95 - 100 ¦¦ 64 - 90
label | 66392211-67b8-582f-96f7-7ab5932104fd |  | note | 13.2 ¦¦ 75 - 95 ¦¦ -
label | e0300b07-db14-5a1e-a59a-4dcf4ead9a78 |  | note | 9.5 ¦¦ 60 - 90 ¦¦ 42 - 78
label | b811e7f0-0252-57b0-84be-548ec230c692 |  | note | 4.75 ¦¦ 42 - 76 ¦¦ 27 - 64
label | b96ab11e-d467-53d2-986a-541923f63ad6 |  | note | 2.36 ¦¦ 28 - 61 ¦¦ 20 - 51
label | fe32d247-80b0-5053-8992-03c067a01b0a |  | note | 0.425 ¦¦ 14 - 29 ¦¦ 10 - 24
label | f39c7ffc-1190-5497-ba71-07cf9c682769 |  | note | 0.075 ¦¦ 6 - 14 ¦¦ 6 - 13
checkpoint-no-status |  |  | checkpoint | Table 304.103 Post-Compaction Requirements for Plasticity Index
label | 4d113d38-63b2-5ae4-bc06-c74ffc90ab03 |  | note | Material ¦¦ Plasticity Index: Minimum ¦¦ Plasticity Index: Maximum
label | b0884cd6-6d2f-59ed-bbeb-1e78ee43d2be |  | note | – – – – – – – – – –
label | ed8e99df-1549-53a8-9e47-0d69b0f9cb21 |  | note | Class 1 Crushed Rock ¦¦ 0 ¦¦ 6
label | 04b22f71-972c-572d-8d1e-a04d98273197 |  | note | Class 2 Crushed Rock ¦¦ 0 ¦¦ 6
label | dbf4edf8-2ace-57ec-af00-f9ed66591238 |  | note | Class 3 Crushed Rock ¦¦ 0 ¦¦ 10
checkpoint-no-status |  |  | checkpoint | Table 304.111 Maximum Lot Size and Minimum Frequency of Testing for Compaction, Post-compaction Grading and PI (after passing the minimum number of qualifying lots)
label | 4272931c-00e5-5b62-b93d-aee363e2327a |  | note | Maximum Allowable Lot Size for a Single Layer of Work ¦¦ Minimum Frequency of Testing for Compaction ¦¦ Minimum Frequency of Testing for Scale A Post-compaction Grading ¦¦ Minimum Frequency of Testing for Scale A Post-compaction PI
label | 1a64ae41-401f-5ef7-ab82-69a6dab404ce |  | note | – – – – – – – – – –
label | c859878c-d559-59aa-a4eb-a3e8ab413294 |  | note | Pavement Layer: Upper Base Layer
label | 1ed80f03-aaa3-5070-95a1-1369233152b2 |  | note | The lesser of 4000 m^2 or one day's production ¦¦ One per 2 lots ¦¦ One per 2 lots ¦¦ One pair per 4 lots
label | 92e083a1-e174-5ee2-96ce-8b79dc6868af |  | note | – – – – – – – – – –
label | e2a784a9-0f00-57ea-87e9-113e6aed5e16 |  | note | Pavement Layer: Lower Base Layer
label | 4f7ec515-50dc-5f7f-8ec8-d0eaa259c991 |  | note | The lesser of 4000 m^2 or one day's production ¦¦ One per 2 lots ¦¦ One per 2 lots ¦¦ One pair per 8 lots
label | fab2b742-24e8-54c9-babc-f9435af90458 |  | note | – – – – – – – – – –
label | 01e9fd6a-9639-5bf8-b0d7-d2fec300ea2c |  | note | Pavement Layer: Upper Subbase
label | 4d94dab8-ffae-5b2c-8c1d-590dec73fd1d |  | note | The lesser of 4000 m^2 or one day's production ¦¦ One per 2 lots ¦¦ One per 4 lots ¦¦ One pair per 8 lots
label | e63534a5-1b80-5339-8573-3ecf855b67bb |  | note | – – – – – – – – – –
label | 6ce6363c-9622-58dd-8a43-14acfacb7e4c |  | note | Pavement Layer: Lower Subbase
label | 59965caf-189f-5d67-8bf3-10d8e8b93dfc |  | note | The lesser of 4000 m^2 or one day's production ¦¦ One per 2 lots ¦¦ – ¦¦ –
checkpoint-no-status |  |  | checkpoint | Table 310.032 Testing Schedule for Pavement Dryback and Embedment
label | 66600c34-aa8d-594b-b650-f2f19d068d95 |  | note | Road ¦¦ Location/Chainage ¦¦ Testing Scale
label | e7839bd3-a9b1-55c6-97f3-3e885351ae6c |  | note | – – – – – – – – – –
label | 47d00bbe-a914-5275-9a53-7c9d9377ed41 |  | note | Bruny Island Main Road ¦¦ Within the limits of works ¦¦ B
checklist-sectioned |  |  | checklist | ITP - Linemarking & RRPM & Road Furniture and Signage | itp |  |  |  | Yes | ITP - Linemarking & RRPM & Road Furniture and Signage Rev0 | fd6eabfd-74ad-4454-8b4c-e4bd2a0af041
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | ab492cb0-b6d0-51de-803c-11c9532d6700 |  | note | FREQUENCY: Prior to commencing any activity
label | 42f37e4d-03d1-510d-b586-886f061796fd |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 1cd36932-f387-5c37-bf37-5a94415fcb70 |  | note | – using the correct and complete set of drawings
label | ab0f15fb-6a66-5c15-9a00-97e82dde147a |  | note | – all drawings are the latest revision
label | 23609ad3-c42d-5319-898e-8467dabecd5c |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 9f5b1a42-acd5-5866-9acd-86144d98a393 |  | note | INSPECTION/TEST METHOD: Document review
label | d305ffc7-49d9-5447-af83-68e6d024d3cf |  | note | RECORD OF CONFORMITY: This ITP signed off
label | e1ff2ef2-a2ad-5bef-8814-e7c293ca5efc |  | note | HP*
label | 26c28481-bbb3-5100-9386-14ed79b0cf6d |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
text | 06cec7e4-1c71-5250-a7ea-f13c0d751dfb |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures and controls
label | d8a469f4-add9-5586-8948-e349c4e3048d |  | note | FREQUENCY: Prior to commencing any activity
label | 35b33f42-fedf-58c7-9f20-42fcd3e493cc |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | 34d4252c-8ba9-5f78-847d-bfab91d0849e |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 1b51a57c-a429-5a5d-9743-0a2c9b81f466 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | bad9cdf4-4696-5bf9-93d5-bca773706d29 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 0ccead72-2b98-5ee2-ac3d-ab89e536e496 |  | note | HP*
label | a61394e8-5292-51f9-a70e-5b086b94a3e5 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
text | 35019def-0e64-5520-abcb-f8c2f646d580 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 1.3 Signage Conformance
label | a6b18721-1b62-595b-8c6b-aaead6e46482 |  | note | FREQUENCY: Before commencement of activity
label | a873ba1d-efff-560f-9c96-88059490af36 |  | note | ACCEPTANCE CRITERIA: Ensure sign size and image correspond with contract drawings Road Signage Installation
label | f58ed995-dfe5-51e1-bfac-e8e949a61bd4 |  | note | REFERENCE DOCUMENTS: Drawings 2101-2116
label | 5c376c57-1c40-5fa7-951b-680b00f3390b |  | note | INSPECTION/TEST METHOD: Verify
label | ebb5dd25-9420-5747-ab4e-194a122ff35b |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 35ecec4b-4270-55f0-aa4f-c258a37d4ec3 |  | note | IP
label | a2a5f07f-334e-510f-83f8-3d7c8fb0401e |  | note | RESPONSIBILITY: Site Engineer
text | 6a508ef4-29ad-5be6-9099-7c6ebb95fc0f |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 1.4 Service Identification
label | 56233f7c-96fc-58ff-8149-0f27be59f869 |  | note | FREQUENCY: Prior to start
label | 0d48755c-f31e-5312-944b-c0692a6c2626 |  | note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation of posts (Road Sign Preparation)
label | 06dfafda-a6b3-5e9e-8c5c-6cef44233fcf |  | note | REFERENCE DOCUMENTS: DBYD
label | c8be7faf-a057-5e42-a3db-f89a69e646a7 |  | note | INSPECTION/TEST METHOD: Verify
label | 7e0140f1-4e14-5aa6-b52a-a8fe9fec7f00 |  | note | RECORD OF CONFORMITY: Ground penetration permit, This ITP signed off
label | 7ea66fcd-1166-5899-a829-1022c3aa9f37 |  | note | IP
label | 0a03053d-a671-5d12-98ff-c24c77c78b43 |  | note | RESPONSIBILITY: Site Engineer
text | f274446c-4c5f-590e-a3d4-b5ecfb309453 |  | textbox | DATE:
checkpoint-group |  |  | section | 2 - Linemarking Works
checkpoint-status |  |  | checkpoint | 2.1 Set out of line markings; dimensions and spacings
label | a44ee983-c6f0-51b1-b7ba-c23992634406 |  | note | FREQUENCY: Prior to commencing line marking works
label | dd8100cf-8f46-51a6-823d-01e826a5378c |  | note | ACCEPTANCE CRITERIA: Holding Point:
label | 1f6905e1-130b-50e0-b7fa-36afe601405f |  | note | ○ Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless an exemption has been granted in writing by the Superintendent.
label | a9a6f724-b40f-5577-901b-9e088d9fbd75 |  | note | (a) New pavement markings shall be positioned in accordance with the following requirements:
label | 2b729077-90e0-5048-aba4-e57da042c49a |  | note | (i) set out by the Contractor in conformance with the appropriate standard required by Clause 721.A03
label | 20a94d7b-3c17-50cd-82c1-731df1b27822 |  | note | (ii) applied within the tolerances listed in Table 721.A101.
label | d44f25ec-2db8-5bc3-bce4-0436b95f18a9 |  | note | (b) Temporary Reflective Markers Temporary reflective markers for new works shall be placed at the following minimum spacings on all longitudinal lane lines, except that on any curve less than 500 m in radius the spacing shall not be more than 12 metre centres:
label | 2a7ecad1-fc5a-5232-96e3-73be017f9f2f |  | note | ○ AADT ≥5,000 and National Highway 12 metre centres
label | aa66f7b6-3989-5778-b16e-09f9bd4d86b6 |  | note | ○ AADT ≥1,000 and <5,000 24 metre centres
label | d50f7b94-1fbe-5909-ad73-f5322967ce65 |  | note | ○ AADT <1,000 48 metre centres
label | b529169f-3275-5a64-b389-bc7e5ebb6e1f |  | note | REFERENCE DOCUMENTS: Cl.721.B05
label | c05ccbfe-5745-5112-b3a2-e56cbe5215ab |  | note | INSPECTION/TEST METHOD: Document review & Site inspection
label | a4b7f81e-8c84-59e3-88ed-1a470d10645d |  | note | RECORD OF CONFORMITY: Consent to proceed by Superintendent OR written exemption granted, This ITP signed
label | 77cf769b-1a20-5ceb-af8d-48f492a39176 |  | note | HP
label | 964c215f-9fc0-5c4c-8e01-017a9d02cbed |  | note | RESPONSIBILITY: Site Engineer / QAV
text | e24b08fc-5287-5c68-9fa4-d6dbc76145b6 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Verification of line marking material
label | 3637a2b6-37a2-5178-b89b-62eb8ed1de20 |  | note | FREQUENCY: Prior to commencing line marking works
label | 847b2d63-ac9d-5516-b96e-6dac5aa1a613 |  | note | ACCEPTANCE CRITERIA: Line marking material is to comply with minimum requirements as specified in Spec Tables 721.D021 and 721.E021
label | 86c7877b-140a-53cd-a6db-3836d346d47d |  | note | REFERENCE DOCUMENTS: Cl.721.D02, Cl.721.E02
label | 0cbcd07f-3a7e-59d7-b264-68d4ac579e21 |  | note | INSPECTION/TEST METHOD: Document review
label | f924f13a-e3c5-5041-b61f-7daed069e2ae |  | note | RECORD OF CONFORMITY: Material compliance, This ITP signed
label | ea56aefa-3264-58d8-ae52-3c48d4465278 |  | note | IP
label | ed64d6f8-637a-55a7-b078-6e6e3a394765 |  | note | RESPONSIBILITY: Site Engineer
text | f4d720ca-d2a1-5302-9779-6320a761e5d9 |  | textbox | DATE:
checkpoint-group |  |  | section | 3 - RRPMs
checkpoint-status |  |  | checkpoint | 3.1 Materials
label | 27fd536e-b0a3-5833-af6e-a561ef914fc7 |  | note | FREQUENCY: Each lot
label | f4639b49-4f17-59c9-a82d-04b83b5664eb |  | note | ACCEPTANCE CRITERIA: Markers shall comply with the relevant requirements of AS 1906, Part 3.
label | 79268f85-e9ae-5b0b-8c78-48647a0936fb |  | note | ○ Epoxy adhesive shall be Standard Set or Rapid Set adhesive complying with the relevant requirements of AS 3554
label | dc4346bd-1468-5735-98da-9faea48ca70e |  | note | REFERENCE DOCUMENTS: Cl 710.03
label | 3c84d46a-ddf4-5f3d-94e7-cca8c1ae2c00 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | f54901d2-a46f-5fc1-95e9-f9c9d15b7730 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 2cde64c6-719b-50f1-9a02-7bf3ac738279 |  | note | IP
label | a2735607-035c-5b9a-990b-b610059fcc8d |  | note | RESPONSIBILITY: Site Engineer
text | bfa7f8bb-8861-5a6b-9635-91990e6cf378 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 3.2 Preparing Adhesive
label | 39e06130-7055-553f-814a-cfb3e04342f2 |  | note | FREQUENCY: Each lot
label | 7c6ca83b-f46a-50a6-9d03-e6c645ff3b95 |  | note | ACCEPTANCE CRITERIA: Adhesive components shall be batched so that the mixed adhesive contains not less than 45% nor more than 55% by volume of either component. Before starting work each day, or when changing to a different batch of adhesive, a hand mixed colour standard shall be prepared for reference during the day.
label | beb4f418-cd5a-504a-9f09-639933127b28 |  | note | ○ When hand-mixing is used not more than 500 g of each component shall be mixed at any time.
label | 7f6a7f73-05ea-536a-b858-afc72845e04b |  | note | ○ The components shall be mixed on a flat surface and the mixed adhesive shall be used within 10 minutes of the time the two components are brought together.
label | c0f1b46c-3921-582f-818a-47b8a4c55d17 |  | note | ○ Hot melt bitumen adhesive shall not be used on days of total fire ban without the written approval of the Tasmanian Fire Service
label | 224b2ec4-5662-52ad-87bb-46278cc45546 |  | note | REFERENCE DOCUMENTS: Cl 710.04, Cl 710.05
label | 77ad8f05-a6dc-5225-8f3a-664b37606dd6 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | a3f3605e-1f28-579f-9275-07d0d580bded |  | note | RECORD OF CONFORMITY: This ITP signed off
label | f5bf5a3a-71ec-57fb-937e-90c75deefaa7 |  | note | IP
label | 5d3db83a-0491-5c9b-b360-759d0a191a2b |  | note | RESPONSIBILITY: Site Engineer
text | 048a3413-5f59-583d-a7aa-765f3ff41fa2 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 3.3 Pavement preparation
label | 4c1606b1-aee3-5930-9561-d26af87ddf00 |  | note | FREQUENCY: Each lot
label | 248ac9b9-0865-507f-95a2-a6ca0a9822be |  | note | ACCEPTANCE CRITERIA: The Contractor shall sweep or air blast each marker site as necessary to remove loose material before placing markers. Markers shall only be placed at locations where the pavement is free from dirt, oil, grease, paint, or any other material
label | ad3ebfd1-a110-58eb-a609-bc36cb700488 |  | note | REFERENCE DOCUMENTS: Cl 710.06
label | c407c23c-4fd4-58c7-9704-53a59ca612b1 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 0904614b-d33e-51c1-a640-034d2a023d96 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | dc1b8a44-86e5-58bd-a941-f6621e8a8a68 |  | note | IP
label | 0e9b0aac-dc99-552a-81c9-e51c648205c9 |  | note | RESPONSIBILITY: Site Engineer
text | 7f9d745b-5c64-5656-a6e5-0529ba291b5f |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 3.4 Placing markers
label | 1ef39740-2cd8-5a4d-b897-317ccdc527f6 |  | note | FREQUENCY: Each lot
label | 8c40ecc4-b92f-517b-82c0-08a8ed28978b |  | note | ACCEPTANCE CRITERIA: Markers shall not be placed in any of the following circumstances:
label | 88edc233-523e-5fab-a9f8-b604a538f60a |  | note | • when the pavement is wet;
label | 85a0d30a-5be6-533e-9530-e257c97c92b4 |  | note | • when the relative humidity is greater than 80%;
label | 7d50b393-10a3-5fd3-940b-21410fedc815 |  | note | • when the ambient temperature or the temperature of the road surface is less than 15deg for standard set adhesive or 0deg for rapid set or hot melt adhesive.
label | a29cf6ed-b0ac-50da-b658-619862861cb9 |  | note | ○ Where a marker is not positioned correctly within 10 seconds for hot melt bitumen adhesive, 2 minutes for rapid set machine mix adhesive, 4 minutes for standard set machine mix, or 10 minutes for standard set hand mix from the time mixing commences, it shall be discarded and a new marker placed.
label | a39bb411-4a4a-5221-a52b-42fea7844710 |  | note | REFERENCE DOCUMENTS: Cl 710.07
label | 76f1c417-bad4-5024-b8d4-9051585b4651 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 2aa08f5d-1c1b-5d42-b2c0-7a655a7515fc |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 81b31484-5261-5cb7-9ce2-4bcf7ef56caf |  | note | IP
label | e4d38391-11e8-5ea9-932b-8515ad656e99 |  | note | RESPONSIBILITY: Site Engineer
text | c5abeace-8d7f-590a-9b0a-37dae1ee9dfc |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 3.5 Tolerances
label | 83c6c08a-1795-545c-a68c-ab1234c01425 |  | note | FREQUENCY: Each lot
label | 628990b4-5fca-5580-b9b1-d1945cb9862b |  | note | ACCEPTANCE CRITERIA: (a) Markers in Line with Broken Line Segments
label | 8464c265-eae3-56ed-b018-c1fcb5312596 |  | note | ○ Transverse position within 25 mm of the centreline of the segments.
label | f22dcbf3-01ac-5d36-9e5c-a991d18eec44 |  | note | ○ Longitudinal position within 0.5 m of the specified position.
label | 7f0b7e0d-2a28-51ff-873d-e5eadb6cc4aa |  | note | (b) Markers in a Longitudinal Group
label | b01d9003-08a7-5a70-bafb-7186d81274b6 |  | note | ○ Transverse position of the centre of each marker within 25 mm of the specified position and within 10 mm of a line joining the centres of the end markers of the group.
label | 865b3b6a-c498-59e2-93c4-ef2ba0f27ca7 |  | note | (c) Markers Adjacent to Unbroken Line
label | 95a48a7c-bef0-5a6f-b17b-e94a40295316 |  | note | ○ Clearance to edge of line within 5 mm of that specified.
label | 19d70e5e-af87-513d-9342-0e64f3e06e6f |  | note | ○ Longitudinal mismatch between markers in transverse pairs at barrier line not more than 25 mm.
label | d9d09845-f07f-5986-ba5b-c2603bb1a76b |  | note | (d) Orientation of Reflective Markers
label | fb0d9dee-5875-5a04-9045-23b5720762ec |  | note | ○ Lower edge of the reflective face at 85deg to 95deg to the centreline of the roadway or any adjacent line.
label | cce73643-444d-54f5-ad37-ce842733bedb |  | note | REFERENCE DOCUMENTS: Cl 710.02
label | 1523389d-a200-5bf3-a6be-8db304a8bf6e |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 656d27ca-9d05-57e3-a98f-5b209a1a23b9 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | b60136fe-c16e-543e-b16e-e482e7e9ce9d |  | note | IP
label | 01aa5222-4d82-5e2e-8e3f-0a2cb0f5100d |  | note | RESPONSIBILITY: Site Engineer
text | 86d9158c-ca40-53d9-8390-6974d67c7d23 |  | textbox | DATE:
checkpoint-group |  |  | section | 4 - Testing
checkpoint-status |  |  | checkpoint | 4.1 Line Marking Tolerances
label | 69a7d7a5-def8-5eeb-8b04-27eb266578a1 |  | note | FREQUENCY: After completion of works
label | b41d6aa3-68c7-5ea0-b55d-b6ddab6b15b7 |  | note | ACCEPTANCE CRITERIA: Line marking shall comply with the tolerances shown in Table 721.A101.
label | b5862cf9-f243-553b-9b60-305ca749e710 |  | note | REFERENCE DOCUMENTS: Table 721.A131, Project Spec. Table 721.A101
label | 4b832add-c6ba-580c-a2c4-60ab41d0ac8e |  | note | INSPECTION/TEST METHOD: Document review & Site inspection
label | 6c090c01-cc96-5285-acd2-bf0cd35e5868 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 1215966b-b30e-52ee-bba3-1351b4d56e4a |  | note | IP
label | 8c21c822-7ccf-5289-a58c-22ab7d6fc07c |  | note | RESPONSIBILITY: Site Engineer
text | fa9b9799-c3ab-563e-9511-87c2d04aea5f |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 4.2 Removal of Non-compliant marking
label | 52dae808-dd99-5967-a4b9-eff75d567f81 |  | note | FREQUENCY: After completion of works
label | 687f1ef9-a056-5839-9401-f829ae5cebe5 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | 8c361c5c-da6d-5924-a155-d79205ff1dfa |  | note | ○ Where the removal of unsuitable pavement marking is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence
label | 6d4bb5c2-02ac-56b9-9999-4fc218a0cb2e |  | note | REFERENCE DOCUMENTS: Project Spec. Cl.721.A12
label | ec57ae6f-f907-5d21-a96c-3edb32719b4a |  | note | INSPECTION/TEST METHOD: Document review
label | c0480372-c72b-5a95-a833-1e50a21b74cc |  | note | RECORD OF CONFORMITY: Approval from Superintendent, This ITP signed
label | 45562490-dfb8-503d-bc5a-1fe8a93f683d |  | note | HP
label | 90886ec0-f8bf-590d-bd9c-73dec4617065 |  | note | RESPONSIBILITY: Site Engineer / Superintendent
text | 86bf93ac-ca83-5a23-87f0-1fd4afc385f5 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5 - Signage
checkpoint-status |  |  | checkpoint | 5.1 Setting Out
label | 346dfc00-3e5f-56d3-9352-8bb9a38c9a6e |  | note | FREQUENCY: Prior to start
label | 58a3ee2d-5d98-5e09-b157-6f5c230a7fd1 |  | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
label | fba73353-608d-549e-a8e3-d480322d7aac |  | note | REFERENCE DOCUMENTS: Drawings 2101 to 2116
label | 7f8adbeb-b606-5b2c-a1ed-47098a26f6e1 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | e190a216-7f37-5bcd-9043-0d2075ae6a18 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | b6b1c519-e03e-5675-b7ff-b4e034f94a30 |  | note | IP
label | 39398345-8916-5530-bd31-a9a9d0742664 |  | note | RESPONSIBILITY: Site Engineer
text | b026a4e0-fc04-5f3c-af26-c98b7c30ecb1 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 5.2 Conformity with drawings
label | 394cbd1b-9f36-5605-ba6c-416706150d24 |  | note | FREQUENCY: Four weeks prior to installation
label | 7b12e735-381e-5a10-ae95-7a7f4e40d52a |  | note | ACCEPTANCE CRITERIA: Witness Point
label | 252bd21c-136a-5ccd-9e69-0272b1250c49 |  | note | ○ If the Contractor proposes to use an alternative method of installation, the Contractor shall submit full details to the Superintendent for approval not later than four weeks before the commencement of sign installation
label | 19622536-0fd8-5c3e-bda0-4bc707de1421 |  | note | REFERENCE DOCUMENTS: Cl 714.04
label | 9ea484eb-f3cb-5cfc-ab48-49a20619b89a |  | note | INSPECTION/TEST METHOD: Verify
label | 8c1b9dbd-240a-55fa-8d39-b4e35e6812e5 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 5984e666-be3d-5687-953e-05029e0e7ad6 |  | note | WP
label | d292fc3e-d1fc-571b-baf5-54c5494b2b69 |  | note | RESPONSIBILITY: Site Engineer / QAV
text | 1ca882da-6376-5296-8517-77458aa72e85 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 5.3 Post & Foundations
label | 879a078d-e99e-592b-9798-9633486df077 |  | note | FREQUENCY: Prior to Start
label | 0d3e5f9e-87d3-5256-9dc7-4877b79d6fe2 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | 462f642a-d08b-52d0-9d25-ddff8b8d55b7 |  | note | ○ The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
label | 0c1246af-b52c-55f3-adc0-ed747ff7bdca |  | note | REFERENCE DOCUMENTS: Cl 714.06
label | 1c086a84-b94a-58b9-aa15-7a6a8ee91934 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | b352e04a-575f-5837-9992-a1c3964d97c7 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 240e3fd6-5bed-5486-8eb9-dfa8d30fa968 |  | note | HP
label | 6aec7555-fa3c-5de5-9e4b-59878f81a743 |  | note | RESPONSIBILITY: Site Engineer / QAV
text | 49ebe54f-94a0-5ae8-9dcc-4b7a8ae67634 |  | textbox | DATE:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Signage Install
label | 94966fd3-5367-5f9a-abc3-d454b244552a |  | note | FREQUENCY: Each Sign
label | a1ce4edd-a172-584e-a387-3680aa5b6ee4 |  | note | ACCEPTANCE CRITERIA: Sign to be installed as per most current project and DSG standard drawings, local council documentation, and to the correct height and position.
label | eb9d8acf-1dff-5379-9c57-5e217fe3bc12 |  | note | ○ Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
label | 43969804-3fbe-51d5-b20b-886945bbec80 |  | note | REFERENCE DOCUMENTS: DSG standard drawings. Cl 714.07
label | fd2194d7-3d42-50d9-988b-2276086799d8 |  | note | INSPECTION/TEST METHOD: Verify
label | ca1d3ee2-264d-5c40-8af9-5f32bf4fd876 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 1d66f347-2150-5cb2-8558-aeaeb609de56 |  | note | IP
label | 09320a9f-fec6-5691-90de-f3cadbf77ef0 |  | note | RESPONSIBILITY: Site Engineer
text | 4df554a1-f14f-58d9-b463-19cce0a74527 |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | 5.5 Tolerances
label | 1b727555-0b95-5091-a202-0123f93539a8 |  | note | FREQUENCY: Each Sign
label | db6bca97-2c1d-543d-8e8e-2f22d42fa4dd |  | note | ACCEPTANCE CRITERIA: Posts vertical with maximum deviation of 1 in 100
label | eaac4741-df0b-5ea5-bf14-de09b03ad7b4 |  | note | ○ Post tops 50mm +-10mm below top edge of sign
label | b4718ea3-8aa3-5e6a-862e-dd76032b5d83 |  | note | ○ Signs mounted level with maximum deviation of 1 in 100
label | 6cafa19c-01c5-59a4-a04d-51a10e6ffc8d |  | note | ○ +-40mm of the height specified in the Sign and Post schedule
label | 98187b1e-6a9e-5cde-9df8-cbf77875d8cc |  | note | ○ +-100mm of the pegged sign location or specified location
label | 1dc967b5-36ea-5798-912c-da2e812c6f9d |  | note | REFERENCE DOCUMENTS: Cl 714.05, Cl 714.07
label | f264d8f1-e680-5c82-a0fc-0fdf422cc3dd |  | note | INSPECTION/TEST METHOD: Measure
label | 020d7b24-081f-561a-8809-bf3cb179a116 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 340d0902-a318-592f-9f4d-5d276a708b60 |  | note | IP
label | 9ae4637f-1c66-5e41-a600-3450d67341e1 |  | note | RESPONSIBILITY: Site Engineer
text | 9c820287-8554-51d3-bd6e-d179d1eeccbf |  | textbox | DATE:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 427a58e1-987e-5f9e-bf51-8ad28ad316fd |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 7ef6f8bb-f8ca-5cb9-9fea-9dc674172439 |  | textbox | Print Name:
text | 95214040-21ca-5900-aa59-a834bf60e81f |  | textbox | Position:
text | 3f1dc2a0-49f9-541e-b995-04b96d1a61c0 |  | textbox | Date:
holdpoint |  |  | signoff | Add Signature
checkpoint-no-status |  |  | checkpoint | Table 721.A101 Tolerances on Pavement Markings
label | adc62ff8-e13e-565f-a7e7-cf6ff6062728 |  | note | Markings ¦¦ Tolerance
label | ad592cf1-553d-5bc5-aef4-54f7a7c2fa09 |  | note | – – – – – – – – – –
label | ab9bc128-ff03-5093-b541-230b5629562c |  | note | (A) Pavement Markings (1)
label | 9d4a287c-7002-5bf4-b401-28963a474b52 |  | note | Distance between the centreline of the marking and the centreline of the set out mark ¦¦ < 30 mm
label | 5aa1ba26-2df3-56c9-8f77-0f481fe50d2b |  | note | Distance between the centreline of the completed marking and the centreline of the previous marking ¦¦ < 15 mm
label | 9e2a23a6-e0ed-58e0-a356-7cba731754f4 |  | note | Width of completed painted markings ¦¦ ± 10 mm of the specified dimensions
label | 8a341d29-c004-5730-b0d8-36c109125380 |  | note | Width of completed markings for long life materials ¦¦ 0 mm to +10 mm
label | c27d80f4-a7a8-5ca4-ae56-3a5b4ede8baa |  | note | Length of completed stripes and blocks ¦¦ 0% to +10% of the specified length
label | 899497b0-dc1d-55c0-92d8-51d3157c80c0 |  | note | Gap between dobule lines ¦¦ -10 mm to +0 mm of the required 100 mm gap (2)
label | d47043e7-f4ca-5fd2-8197-cf1538f7ab71 |  | note | – – – – – – – – – –
label | cb8c9f65-7565-5745-bc6a-8708f131ecf2 |  | note | (B) Raised pavement markers
label | 619eafb2-d33a-5ba8-b3ec-975c766b98b6 |  | note | (i) Markers in line with broken segments
label | 74d1c2c6-f39f-5275-b07a-f2b9bee3574c |  | note | Transverse position ¦¦ ±25 mm of the centreline of segments
label | 7b727822-ef99-56e3-88bd-d462693c3fa9 |  | note | Longitudinal position ¦¦ ±0.5 mm of the specified position
label | f9164e39-f8a6-5599-8ba1-a8e529a6010f |  | note | (ii) Markers in a longitudinal group
label | fb325cf5-490e-5adb-ae46-9b746bf16d08 |  | note | Transverse position ¦¦ ±25 mm of specified position and ±10 mm of a line joining the centres of the end markers
label | bd308832-3d99-50bb-b56d-9daa121a6084 |  | note | Longitudinal position ¦¦ ±0.5 mm
label | 27872e71-a452-50d0-a245-de26143f1509 |  | note | Spacing of markers within the group ¦¦ ±50 mm of specified spacing
label | 1e540eda-1e39-56f8-85dc-853539dbeedf |  | note | (iii) Markers adjacent to an unbroken line
label | 09dd5911-6470-518a-a4e1-ba5991c98f36 |  | note | Clearance to edge line ¦¦ ±5 mm of the specified dimensions
label | 54154e0b-3950-5dce-8a37-3e09efcf9be6 |  | note | Longitudinal mismatch between markers in transverse pairs ¦¦ <25 mm
label | f2190d79-abc6-54c7-b306-49d1f96765a8 |  | note | (iv) Orientation of reflective markers ¦¦ Lower edge of the reflective face at 85° to 95° to centreline of roadway or adjacent line
label | 9803b9c3-b3be-5880-be6d-3a450dfcaefd |  | note | – – – – – – – – – –
label | d7a61302-e9e8-5bf2-b7d5-ac873a5778a3 |  | note | (C) Thermoplastic profiled lines
label | b4b500b6-0425-5569-ab7e-3cdaba1a5b6c |  | note | (i) Tolerances on dimension
label | 1d628f94-0831-59b0-98b2-2cb1471eb11d |  | note | Line width ¦¦ +20 mm, -5 mm
label | a3869bcd-0965-5a4f-be12-825f603e3b86 |  | note | Line height ¦¦ +2 mm, -0 mm
label | a14057a9-cf66-5d8f-bb21-8e74319c5240 |  | note | Extrusion breadth ¦¦ +10 mm, -0 mm
label | 64648ce5-734e-5614-b3c0-9401829358c2 |  | note | Extrustion spacing ¦¦ ±15 mm
label | 73399784-8a2e-58d5-9aed-e7ee1dead6bd |  | note | Extrustion shape ¦¦ ±25 mm at any point from rectangular shape
label | 3b69110e-3ef4-5bdd-862d-25dbb8db36f5 |  | note | (ii) Tolerances on position
label | cd0b9a2b-f329-51b7-b350-f3e73e4d80a0 |  | note | Distance between the centreline of the marking and the centreline of the setout ¦¦ <30 mm
label | b003c483-b2d6-5bc9-a9c1-d192fd970004 |  | note | Length of the completed lines ¦¦ -0% to +5% of the specified length
label | 8b15ef5c-6133-567c-910d-d52b8aec055a |  | note | Longitudinal position of individual extrusions ¦¦ ±50 mm of any previously applied profiled lining
label | f8fc1933-fb44-55eb-9b3d-c6193e51e2e1 |  | note | – – – – – – – – – –
label | 8a2412c9-4737-5160-8a29-9cdaef537e12 |  | note | (1) Apparent line of the markings is a smooth, continuous alignment when viewed in the direction of the line.
label | b357ca30-d9b7-51dd-b13c-9dff28990ca2 |  | note | (2) Maintenance of pavement markings: If the gap between the existing lines is 90 mm or less the gap shall not be reduced by the maintenance application.
checkpoint-no-status |  |  | checkpoint | Table 721.A131 Acceptance of Retroreflectivity
label | 58fbbbe7-9eb9-57c7-bd08-775da45e24bb |  | note | Testing Period (1) ¦¦ Initial Measurement: 3 - 5 weeks ¦¦ Additional Measurement: 5 - 6 months
label | 7675f940-7c02-5e3c-8ad4-f81bfc0b9efd |  | note | Minimum level of retroreflectivity on sprayed seal surfaces ¦¦ Initial Measurement: 350 mcd/lux/m^2 ¦¦ Additional Measurement: 220 mcd/lux/m^2
label | c9fdde5c-2d3b-5e97-8437-f3cd05767ed5 |  | note | Minimum level of retroreflectivity on asphalt and all other surfaces ¦¦ Initial Measurement: 350 mcd/lux/m^2 ¦¦ Additional Measurement: 250 mcd/lux/m^2
label | 3358af33-5d1b-53c2-8d90-4c3aafa58026 |  | note | – – – – – – – – – –
label | a2a8264a-dfb4-53eb-8b26-795a57b0e763 |  | note | (1) Measured after application of the second/final coat of material.
checkpoint-no-status |  |  | checkpoint | Table 721.D021 Minimum Requirements - Paint and Glass Beads
label | 1cd5328a-5018-5307-a295-ae2352048ecc |  | note | Paint (1) ¦¦ Glass Beads (2)
label | 3763ffcb-2165-555e-b4b5-53cac42b5b6f |  | note | – – – – – – – – – –
label | 6cb17166-e875-54f2-aeb4-c6a49750d0f9 |  | note | Linemarking
label | 4f326048-b4be-5a15-ba38-b36b28d96e57 |  | note | • New Markings (initial application only)
label | 10f5d101-29d0-579a-aed2-6e76c9642e31 |  | note | 0.38 mm dft on sprayed seals ¦¦ Type D-HR (3)
label | c8d6c927-aa7b-5b85-843b-91f96b313edf |  | note | 0.35 mm dft on asphalt and all other surfaces ¦¦ Type D-HR (3)
label | 71d68405-7891-5ae9-b193-19089bf69ee3 |  | note | • Re-marking (including second application on new markings
label | 4c931174-2335-59ad-aed6-a774fcf6cfdb |  | note | 0.38 mm dft on sprayed seals ¦¦ Type D-HR (3)
label | 9e66e9b7-1904-5405-8567-50ac1379c141 |  | note | 0.35 mm dft on asphalt and all other surfaces ¦¦ Type D-HR (3)
label | b0a47a9b-cc0c-5a57-8da7-fdac3395f693 |  | note | – – – – – – – – – –
label | 264969cf-bb51-5b08-98c2-9e9b0189f560 |  | note | Roadmarking
label | 5618c868-0ded-56e0-9676-a30e2600f5f5 |  | note | • All marking
label | af018137-b7e7-5e45-81e5-52525f861e2c |  | note | 0.35 mm dft on sprayed seals ¦¦ Type B-HR
label | 9eb9287c-57b4-5b73-a5fe-a592a9065713 |  | note | 0.30 mm dft on asphalt and all other surfaces ¦¦ Type B-HR
label | 970978dc-d096-5e32-aa66-d86f9d3557fc |  | note | – – – – – – – – – –
label | 54e8298b-23eb-59e2-951a-d79e54cda77f |  | note | (1) The minimum dry paint film thickness (dft) specified above shall be the end product thickness measured on a 200 mm x 100 mm sheet metal test plate without beads. Consideration shall be given to the texture of the road surface and the method of application used to achieve the requirements of this section.
label | ffb2f9a5-dea9-5106-9ce9-826c5b1ca113 |  | note | (2) A minimum of 400 g/m^2 shall be retained in the painted marking for all glass beads.
label | 7f2b87de-325d-57fb-8556-dd7a2a290f07 |  | note | (3) An alternative glass bead application rate shall be 300 g/m^2 of D-HR with a separate drop of 200 g/m^2 of B-HR provided that 75% minimum of the D-HR beads is retained at the 5 demonstrated by photographs at each test site.
checkpoint-no-status |  |  | checkpoint | Table 721.E021 Minimum Requirements - Long Life and Glass Beads
label | 70bdcc7e-79d4-577b-8e31-65803d8244c1 |  | note | Material ¦¦ Applied Minimum Thickness, Glass Bead and Other Requirements
label | fbd38464-d02c-56e6-b7e6-0fe3479f31b9 |  | note | – – – – – – – – – –
label | e130c8f7-5a79-5d4b-a67b-d3e4124b8416 |  | note | Thermoplastic
label | cc990f50-6c41-54d7-a473-78b863775257 |  | note | Sprayed markings ¦¦ 2.0 mm minimum thickness on logitudinal lines contaiing internmix beads and with a minimum of 400 g/m^2 of Type D-HR or Type B-HR(3) drop-on glass beads retained on the marking surface
label | d2fa96d4-8831-5bf6-bdc9-7c38dcf71b50 |  | note | Extruded line markings (1) ¦¦ 2.0 mm minimum thickness on longitudinal lines containing internmix beads and a minimum of 400 g/m^2 of the Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
label | cd6362f9-6456-5e1a-83da-a6069f790e51 |  | note | Extruded road markings (1) ¦¦ 3.0 mm minimum thickness on intersections containing internmix beads and a minimum of 400 g/m^2 of Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
label | 7858be6a-3924-5e26-adf4-6fce2ec552a7 |  | note | Preformed markings ¦¦ 2.3 mm with a minimum skidding resistance value of 45 BPN (British Pendulum Number) and retroreflective properties agreed with the Superintendent
label | 75d1b6ff-7c96-5288-a4dc-a5ccdea6eb83 |  | note | Profiled lines (1) ¦¦ 8.0 mm minimum thickness with a minimum of 400 g/m^2 of Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
label | de1b2cbf-eb3a-5fe1-8364-42c62583551b |  | note | – – – – – – – – – –
label | ecb568fa-7e73-5e7c-814e-8a2df77413c5 |  | note | Cold-applied Plastic
label | d9a6999b-166a-5833-93fb-a4b2a3350f39 |  | note | Sprayed line markings (2) ¦¦ 1.0 mm minimum thickness for longitudinal line markings only with a minimum of 400 g/m^2 of Type D-HR or Type B-HR glass beads retained in and on the marking surface
label | 3e340c23-3837-54b1-84ce-687e9716783b |  | note | Sprayed road markings (2) ¦¦ 2.0 mm minimum thickness for all road markings containing intermix beads and a minimum of 400 g/m^2 of Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
label | 26f07c15-313f-5f67-8811-fe37bed0319b |  | note | Trowelled, screeded, or extruded markings (1) ¦¦ 2.0 mm minimum thickness of markings containing intermix beads and a minimum of 400 g/m^2 of Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
label | a300815d-617a-52a9-b745-f2f76b375949 |  | note | – – – – – – – – – –
label | 577901a7-68ea-5f79-b675-72bc48b55876 |  | note | Pliant Polymer Tape
label | ec36da5a-a572-5440-a253-69961c18cf09 |  | note | As approved by the Superintendent
label | f6cf92d5-95d1-5a13-a9cc-7b8df07c9e23 |  | note | – – – – – – – – – –
label | 08e30395-1646-51ff-a670-5d1bf10ece99 |  | note | (1) The minimum thickness specified shall be the height above the upper road surface level or above the existing marking as appropriate.
label | ef21bb62-5c48-5c5a-a9fd-21294d5a0653 |  | note | (2) The minimum thickness specified shall be the height of the material between the glass beads on a metal test plate. All other thicknesses shall be as measured on a metal test plate including glass beads.
label | fc4db6e0-0847-5900-8ce9-b128d1258295 |  | note | (3) Pristine drop-on Type B glass beads (Type B-HR), as per Clause 721.A05.