## res_1630-P200-SYM-QAC-ITP-0021.
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CC0394 - ITP-012 - Asphalt | itp |  |  |  | Yes | CC0394 - ITP-012 - Asphalt REV0 | 1d018ecb-d150-4f4c-8e86-d9d2629449a8
section | Lot Conformance.
checkpoint-status | Lot Conformance
select | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes, No
text | NCR Raised Date:
button | NCR closed? | Yes, No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | AUTHORITY HOLDPOINT
section | 1.0
checkpoint-status | 1.1 - Determine Lot Size
label | Ref docs - IFC Drawings
label | Acceptance criteria - Maximum Lot Size = 4000m2
button | Acceptance | Yes,No,N/A
label | • See Work Lot Map
label | Resp - SE
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | Work Lot Map
checkpoint-status | 1.2 - Survey Set-out
label | Ref docs - IFC Drawings
label | Acceptance criteria - Prior to the commencement of works, the contractor shall engage a suitably qualified surveyor to set out the works and clearly mark its limits.
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp - SE
checkpoint-status | 1.3 - Approved Material Type
label | Ref docs - IFC Drawings
label | Acceptance criteria - Asphalt types specified within IFC Drawings.
label | Acceptance
boolean | 40mm wearing course size 10mm Type H (C320) Asphalt 7mm Cationic rapid setting (CSR) emulsified primerseal (C170); or primer AMCO
label | Key - H
label | Resp - SE
checkpoint-group | 2.0
checkpoint-status | 2.1 - Storage of Asphalt
label | Acceptance criteria - Asphalt mix has not been stored in a hot bin for more than 18 hours prior to use.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp - SE
checkpoint-status | 2.2 - Conditions for Placing
label | Acceptance criteria - Surface on which asphalt is to be placed is dry, free from surface water & has a surface temperature >10⁰C
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp - SE
checkpoint-status | 2.3 - Commencement of Placing
label | Ref docs - IFC Drawings
label | Acceptance criteria - Crushed rock surface to be primed prior to placement of asphalt.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp - SE
checkpoint-status | 2.4 - Spreading
label | Ref docs - IFC Drawings
label | Acceptance criteria - All asphalt shall be spread with an asphalt paver except for small areas where use of a paver is not practicable.
label | • All asphalt shall be spread to form a uniformly smooth asphalt mat without segregation, tearing or gouging.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp - SE
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | As-Built Attached
checkpoint-status | 2.5 - Joints & Junctions
label | Acceptance criteria - If the paver is required to stop & asphalt in front of the screed cools to below 120⁰C, a transverse joint shall be constructed.
label | • Longitudinal joints in the wearing course shall be parallel to the traffic lanes.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp - SE
checkpoint-status | 2.6 - Surface Finish
label | Ref docs - IFC Drawings
label | Acceptance criteria - The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches & roller marks.
label | • Where asphalt is placed against kerb, the surface at the edge of the wearing course shall be either flush with or not more than 5mm above the lip of the channel.
label | • No point on the finished surface of the wearing course shall lie more than 4mm below a 3m straight edge laid either parallel to the centreline.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp - SE
checkpoint-group | 3.0
checkpoint-status | 3.1 - Compaction Testing
label | Ref docs - IFC Drawings
label | Acceptance criteria - Testing to be undertaken in accordance with XXX
button | Acceptance | Yes,No,N/A
label | Key - H
label | Resp - SE
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | Testing Attached
checkpoint-status | 3.2 - As-Builts
label | Ref docs - IFC Drawings
label | Acceptance criteria - Measurements have been taken randomly throughout the lot & are within tolerance.
label | Scale B:
label | • Measurements: 40
label | • Mean: ±8mm
label | • SD: 10mm
button | Acceptance | Yes,No,N/A
label | Key - H
label | Resp - SE
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | Survey Attached
checkpoint-status | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint-status | Lot Conformance
select | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes, No
text | NCR Raised Date:
button | NCR closed? | Yes, No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP