## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-0059 - HOT MIX ASPHALT PLACEMENT | itp |  |  |  | Yes | ITP-0059 - HOT MIX ASPHALT PLACEMENT | 0ef28e36-0015-447b-9ce3-74211e475cc5
checkpoint-group |  |  | section | NA HOLD POINTS
checkpoint-status |  |  | checkpoint | 1.6 ASPHALT MIX DESIGN
text | 2b8a9f63-f8a5-5d8d-8ed4-5af6fb85b833 |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 1.8 BITUMINOUS MATERIALS
text | fc9afdf4-1976-5843-a1bf-8432779050dc |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 2.1 RAP MAMNAGEMENT
text | 237c0e66-caca-5682-88fb-8c1af3b3aa42 |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 2.6 APPROVAL FOR COMMENCEMENT OF PLACING
text | e37c4234-ade8-51ab-af2c-0b9180a94b4b |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 2.9 AMBIENT CONDITIONS FOR PLACING
text | 79e00bac-7a92-5911-9ea7-e3c0c5bf0816 |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 2.10 COMMENCEMENT OF PLACEMENT
text | 1fdbc9cb-d9f8-5657-a6b8-21740217aa92 |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 2.13 TRAFFICKING PAVEMENT AFTER PLACEMENT
text | 707d5bee-9500-5c97-b82b-122cad1d5780 |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 2.17 SURFACE RECTIFICATION (IF REQUIRED)
text | f94d31a3-dbf1-527e-8cdb-30fc918e4ebe |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 3.3 NCR CLOSE OUT (IF APPLICABLE)
text | 06c451d0-c28c-5cc3-ad13-313df32feb26 |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-group |  |  | section | ATTACHMENTS
checkpoint-status |  |  | checkpoint | LOT MAP
checkpoint-status |  |  | checkpoint | GEOTECHNICAL REPORT - COMPACTION
checkpoint-status |  |  | checkpoint | GEOTECHNICAL REPORT - MATERIAL PROPERTIES
checkpoint-status |  |  | checkpoint | PHOTOS
checklist-sectioned |  |  | checklist | ITP-0042 - CONDUITS (TRENCHING & INSTALL) | itp |  |  |  | Yes | ITP-0042 - CONDUITS (TRENCHING & INSTALL) | 9597842a-4227-4420-866d-8138b8d19646
checkpoint-group |  |  | section | NA HOLD POINTS
checkpoint-status |  |  | checkpoint | 2.5 EXCAVATION AND BORING
text | f1113df2-6f0b-560b-ad17-4f13e801c623 |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 3.1 CERTIFICATION OF INSTALLATION
text | 14ab26fb-7fb1-599a-8c29-f9165a66bde4 |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-group |  |  | section | ATTACHMENTS
checkpoint-status |  |  | checkpoint | LOT MAP
checkpoint-status |  |  | checkpoint | GEOTECHNICAL REPORT - COMPACTION
checkpoint-status |  |  | checkpoint | DELIVERY DOCKETS
checkpoint-status |  |  | checkpoint | AS-BUILT SURVEY REPORT
checklist-sectioned |  |  | checklist | ITP-0024 - STORMWATER DRAINAGE PITS AND PIPES | itp |  |  |  | Yes | ITP-0024 - STORMWATER DRAINAGE PITS AND PIPES | ad863f98-28d3-44d9-9514-482d98cddcdf
checkpoint-group |  |  | section | NA HOLD POINTS
checkpoint-status |  |  | checkpoint | 1.4 Trench Shields
text | 74ce4a71-8114-5452-85ac-c07858a0b762 |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 1.5 Material Conformance Mortar
text | 36c3bc25-4214-573c-b903-257b131eff2e |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 1.9 Acceptance of precast reinforced Concrete Pipes & Pits
text | 0bd81177-84eb-5379-a865-c5f9503b5874 |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 1.10 Supply Precast Covers, Grates, Box Culverts, Lids and Pits
text | b3d3843c-c9b5-5c17-9e29-8d58510f0047 |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 2.1 Set Out
text | 66f13415-6aee-5019-9df0-83e0958fc40d |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 2.11 Precast Fibre Reinforced Concrete Drainage Pit (if applicable)
text | fd1f8762-31c8-51e2-816a-ad4aeb6d731c |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 2.13 Step Iron Fitting
text | 884d5e94-69c3-5cdd-8a35-383319c4823e |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 2.17 Backfill with Cement Stabilised Sand
text | 176c3889-c296-5d2f-b418-786ee21b3272 |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 2.22 Inspection of Drainage Lines
text | b4d7313d-8ae9-5f24-95cf-37fb63e76dce |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 2.23 Repairs to Damaged Pipes
text | 732534ec-3d6e-5791-a2ea-d37d89efbfcc |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 3.5 NCR Close out (if applicable)
text | e442203f-766d-5cf0-9c82-de9d043551e3 |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-group |  |  | section | ATTACHMENTS
checkpoint-status |  |  | checkpoint | LOT MAP
checkpoint-status |  |  | checkpoint | MATERIAL DELIVERY DOCKETS
checkpoint-status |  |  | checkpoint | PHOTOS
checkpoint-status |  |  | checkpoint | GEOTECHNICAL REPORT - COMPACTION
checkpoint-status |  |  | checkpoint | GEOTECHNICAL REPORT - MATERIAL PROPERTIES
checkpoint-status |  |  | checkpoint | SURVEY CONFORMANCE REPORT
checklist-sectioned |  |  | checklist | ITP-0029 - UNBOUND FLEXIBLE PAVEMENTS | itp |  |  |  | Yes | ITP-0029 - UNBOUND FLEXIBLE PAVEMENTS | c861ea2a-759d-438e-963d-6977f3cb0b8b
checkpoint-group |  |  | section | NA HOLD POINTS
checkpoint-status |  |  | checkpoint | 2.4 Material of Nominal Size Greater than 40mm (if required)
text | 5c5dccaf-27aa-561c-bf9a-1f9afa49c98a |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 2.6 Testing – Stability (Proof Roll)
text | 9c068026-5e16-5732-9975-e3453e91b623 |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-group |  |  | section | ATTACHMENTS
checkpoint-status |  |  | checkpoint | LOT MAP
checkpoint-status |  |  | checkpoint | GEOTECHNICAL REPORT - COMPACTION
checkpoint-status |  |  | checkpoint | GEOTECHNICAL REPORT - MATERIAL PROPERTIES
checkpoint-status |  |  | checkpoint | AS-BUILT SURVEY REPORT
checklist-sectioned |  |  | checklist | ITP-0027 - TYPE A FILL PLACEMENT | itp |  |  |  | Yes | ITP-0027 - TYPE A FILL PLACEMENT | ecfae3b6-e386-4449-beba-ecd425934bec
checkpoint-group |  |  | section | NA HOLD POINTS
checkpoint-status |  |  | checkpoint | 2.1 PRE-CONDITION
text | 1bef9374-02d1-5e5e-a8e2-7e9f8b38d822 |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 2.4 FILL AT STRUCTURES
text | 3ddb76fe-9f04-51f1-80ef-ad52af29330b |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 2.5 TEST ROLL
text | df8239aa-649e-5db8-a890-350f1b6386da |  | textbox | Holdpoint number
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-group |  |  | section | ATTACHMENTS
checkpoint-status |  |  | checkpoint | LOT MAP
checkpoint-status |  |  | checkpoint | GEOTECHNICAL REPORT - COMPACTION
checkpoint-status |  |  | checkpoint | GEOTECHNICAL REPORT - MATERIAL PROPERTIES
checkpoint-status |  |  | checkpoint | OTHER