## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-0016 - KERB INSTALLATION | itp |  |  |  |  | ITP-0016 - KERB INSTALLATION
section | NA HOLD POINTS
checkpoint | 1.5 Survey Set Out
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 3.5 NCR Close out (if applicable)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
section | ATTACHMENTS
checkpoint | LOT MAP
checkpoint | DELIVERY DOCKETS
checkpoint | PHOTOS
checkpoint | AS-BUILT REPORT
checkpoint | OTHER
checklist | ITP-0022 - SPRAY SEAL | itp |  |  |  |  | ITP-0022 - SPRAY SEAL
section | NA HOLD POINTS
checkpoint | 1.7 Rate of Application
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.8 Forward Aggregate Spreading
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.1 Commencement of Placing
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.8 Sweeping of surface prior to application of a seal treatment
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 3.2 Maintenance Seal
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 3.6 NCR Close out (if applicable)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
section | ATTACHMENTS
checkpoint | LOT MAP
checkpoint | JOB COMPLETION REPORT
checkpoint | OTHER
checklist | ITP-0025 - STRUCTURAL CONCRETE | itp |  |  |  |  | ITP-0025 - STRUCTURAL CONCRETE
section | NA HOLD POINTS
checkpoint | 1.4 CONCRETE MATERIAL COMPLIANCE
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.5 STEEL MATERIAL COMPLIANCE
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.6 TEMPORARY WORKS - FALSEWORK/FRAMEWORK DESIGN
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.7 WELDING PROCEDURE - CARBON & STAINLESS-STEEL REINFORCEMENT
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.8 CURING PROCEDURE
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.9 POURS IN HOT OR COLD WEATHER CONDITIONS (IF APPLICABLE)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.10 ON-SITE RE-BENDING PROCEDURE (IF APPLICABLE)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.11 SUB-CONTRACTOR'S QUALITY DOCUMENTATION
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.2 EXCAVATION & BLINDING PLACEMENT
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.5 CERTIFICATION OF AS-CONSTRUCTED FALSEWORK AND FORMWORK
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.7 PRE-POUR INSPECTION
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.10 CONSTRUCTION JOINTS ENHANCEMENT (WATERSTOPS)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.12 POST POUR
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.13 CRACKS/PATCH AND DEFECTS (IF APPLICABLE)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.15 BACKFILL AGAINST CONCRETE
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.16 EARLY LOADING AND TRAFFICKING OF BRIDGE DECKS, DECK OVERLAYS AND APPROACH SLABS
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.17 CONSTRUCTION OF DECK WIDENING, LONGITUDINAL, STITCH POURS, IN-FILL STRIPTS AND STAGED CONSTRUCTION OF DECK OVERLAYS UNDER LIVE TRAFFIC (IF APPLICABLE)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.18 DRILLING HOLE IN CONCRETE MEMBER AND PLACEMENT OF EMBEDDED ITEMS
textbox | Holdpoint number
holdpoint | Authority Holdpoint
section | ATTACHMENTS
checkpoint | LOT MAP
checkpoint | GEOTECHNICAL REPORT - COMPACTION
checkpoint | GEOTECHNICAL REPORT - MATERIAL PROPERTIES
checkpoint | PHOTOS
checklist | ITP-0034 - BORED PILES | itp |  |  |  |  | ITP-0034 - BORED PILES
section | NA HOLD POINTS
checkpoint | 1.5 REVIEW OF CONCRETE MIX DESIGN
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.6 REINFORCEMENT CAGE MATERIAL COMPLIANCE
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.8 PILE TESTER APPROVAL
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.9 SUBCONTRACTOR QUALITY DOCUMENTATION AND TOOLBOX (QUALITY PROCEDURE FOR CONSTRUCTION OF PILE, SHOP FABRIFICATON ITP AND CHECKLIST)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.10 RE-BENDING ON SITE (IF APPLICABLE)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.12 WELDING OF SPLICES IN CARBON STEEL (IF REQUIRED)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.13 WELDING OF STAINLESS-STEEL REINFOREMENT (IF APPLICABLE)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.1 REINFORCEMENT CAGES INSPECTION PRIOR TO PLACEMENT IN BORED PIER
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.3 INSPECTION OF PILE EXCAVATION
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.7 PRE-POUR CHECKS
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.16 TRAFFIC SIGNAL HARDWARE
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 3.7 NCR CLOSE OUT (IF APPLICABLE)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
section | ATTACHMENTS
checkpoint | LOT MAP
checkpoint | GEOTECHNICAL REPORT - COMPACTION
checkpoint | GEOTECHNICAL REPORT - MATERIAL PROPERTIES
checkpoint | PHOTOS
checklist | ITP-0040 - CEMENT TREATED CRUSHED ROCK | itp |  |  |  |  | ITP-0040 - CEMENT TREATED CRUSHED ROCK
section | NA HOLD POINTS
checkpoint | 1.4 MATERIAL REGISTRATION
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.5 USE OF ALTERNATIVE BINDER
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.3 PROOF ROLLING (IF REQUIRED)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.6 CURING AND PROTECTION OF COMPACTED LAYERS
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 3.2 FINAL INSPECTION SITE WALK
textbox | Holdpoint number
holdpoint | Authority Holdpoint
section | ATTACHMENTS
checkpoint | LOT MAP
checkpoint | GEOTECHNICAL REPORT - COMPACTION
checkpoint | GEOTECHNICAL REPORT - MATERIAL PROPERTIES
checkpoint | DELIVERY DOCKETS
checklist | ITP-0068 - STREET LIGHTING INSTALLATION | itp |  |  |  |  | ITP-0068 - STREET LIGHTING INSTALLATION
section | NA HOLD POINTS
checkpoint | 2.5 DISTRIBUTION CABINET LABELLING
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.6 POLE LABELLING
textbox | Holdpoint number
holdpoint | Authority Holdpoint
section | ATTACHMENTS
checkpoint | LOT MAP
checkpoint | GEOTECHNICAL REPORT - COMPACTION
checkpoint | GEOTECHNICAL REPORT - MATERIAL PROPERTIES
checkpoint | PHOTOS
checklist | ITP-0072 - LINEMARKING | itp |  |  |  |  | ITP-0072 - LINEMARKING
section | NA HOLD POINTS
checkpoint | 1.3 Removal of Existing Pavement markings (If Required)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.4 Setout - Line Marking, road marking and RRPMs
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 3.2 NCR Close out (if applicable)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
section | ATTACHMENTS
checkpoint | LOT MAP
checkpoint | JOB COMPLETION REPORT
checkpoint | RETOR-REFLECTIVITY REPORT
checkpoint | OTHER
checklist | ITP-0074 - CONCRETE FOOTPATH | itp |  |  |  |  | ITP-0074 - CONCRETE FOOTPATH
section | NA HOLD POINTS
checkpoint | 2.1 Setting Out
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.14 Concrete Repairs
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 3.2 Final Inspection Side Walk
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 3.4 NCR Close out
textbox | Holdpoint number
holdpoint | Authority Holdpoint
section | ATTACHMENTS
checkpoint | LOT MAP
checkpoint | GEOTECHNICAL REPORT - COMPACTION
checkpoint | DELIVERY DOCKETS
checkpoint | PHOTOS
checkpoint | OTHER
checklist | ITP-0075 - STATIC SIGN | itp |  |  |  |  | ITP-0075 - STATIC SIGN
section | NA HOLD POINTS
checkpoint | 2.2 Signpost Positioning and installation
textbox | Holdpoint number
holdpoint | Authority Holdpoint
section | ATTACHMENTS
checkpoint | LOT MAP
checkpoint | COMPLIANCE CERTIFICATE
checkpoint | CONCRETE TEST REPORTS
checkpoint | OTHER
checklist | ITP-0094 - SUBSOIL INSTALLATION | itp |  |  |  |  | ITP-0094 - SUBSOIL INSTALLATION
section | NA HOLD POINTS
checkpoint | 2.1 Method of Compaction
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 3.02 Inspection of Base Trench
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 3.07 Flushing
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 3.10 Inspection of Subsurface Drainage Lines
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 4.2 NCR Close out (if applicable)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
section | ATTACHMENTS
checkpoint | LOT MAP
checkpoint | GEOTECHNICAL REPORT - COMPACTION
checkpoint | DELIVERY DOCKETS
checkpoint | PHOTOS
checkpoint | CCTV REPORT
checkpoint | AS BUILT REPORT
checkpoint | OTHER
checklist | ITP-0099 - TRAFFIC SIGNAL INSTALLATION | itp |  |  |  |  | ITP-0099 - TRAFFIC SIGNAL INSTALLATION
section | NA HOLD POINTS
checkpoint | 1.5 SUB-CONTRACTOR(S) PREQUALIFICATION + QUALITY DOCUMENTS + INSPECTION PLANS + CONCRETE PLACEMENT AND CURING PROCEDURE
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.7 CONCRETE MIX DESIGN ACCEPTANCE
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.1 PRE-INSTALLATION MEETING
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.2 EXCAVATION, BORING,TRENCHING AND BEDDING
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.5 INSPECTION OF BEDDING AND CONDUITS INSTALLATION
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.6 PITS
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.8 NON-STANDARD FOUNDATIONS (IF REQUIRED)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.9 INSPECTION OF CONDUIT, PIT AND FOUNDATION
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.10 BACKFILLING
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.14 SUPPLY AND PLACEMENT OF CONCRETE IN FOUNDATIONS
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.16 TRAFFIC SIGNAL HARDWARE
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.18 CABLING SCHEME FOR LARGE SIGNAL INSTALLATION (WHERE APPLICABLE)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.20 TESTING OF ELECTRICAL WORKS
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 3.1 COMPLETION OF SITE WORKS
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 3.7 NCR CLOSE OUT (IF APPLICABLE)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
section | ATTACHMENTS
checkpoint | LOT MAP
checkpoint | GEOTECHNICAL REPORT - COMPACTION
checkpoint | GEOTECHNICAL REPORT - MATERIAL PROPERTIES
checkpoint | PHOTOS