## Resources
Warnings | Type | Id | Name | Values | Prompting Name | Resource Id
| checklist |  | Punch Windows |  | Punch Windows | 0b69beba-6ef1-4623-ba49-598cff1bfb68
| checkpoint |  | Precast concrete surface no damage
| checkpoint |  | Precast concrete face free from oil, grease, dirt etc
| checkpoint |  | Gap 10mm +/-4 between structure and frame
| checkpoint |  | Frame endstops and corners properly sealed
| checkpoint |  | Appropriate PEF rod installed continuously
| checkpoint |  | Sikalastic 152 applied on the opening all round
| checkpoint |  | Sikaseal Tape F applied as per specification all round
| checkpoint |  | Fixing HUS4-HR6x70mm @ 350 ctrs. Min 55 embedment
| checkpoint |  | Fixing oversealed
| checkpoint |  | HDPE packers installed the right way
| checkpoint |  | Continues sealant on backing rod properly tooled
| checkpoint |  | Wip holes cleared and unobstructed
| checkpoint |  | Wedge and gasket properly mounted
| checkpoint |  | Glass and frame free of scratches
| checkpoint |  | Angle closer size correct and offset 6mm from frame
| checkpoint |  | Window protection installed
| signoff |  | Request Signoff
| checklist |  | Roof Skylight |  | Roof Skylight | 0caee07f-1e24-4b92-8e66-1ce8935c1409
| checkpoint |  | Waterproofing QA done before start
| checkpoint |  | Slop of the nib to create 7 degree to glass skylight
| checkpoint |  | Powder coated aluminium flashing installed at the edge of the nib
| checkpoint |  | Under-flashing/Framing sealed to the roof membrane with Soudal Gorilla sealant on backing rod. Min 6mm gap
| checkpoint |  | Under-flashing/Framing powder coated with Duratek eternity range: Gun metallic kinetic matt
| checkpoint |  | Cover flashing fixed with 2x6mm EPDM compressed washers to form 6mm gap at fixing.
| checkpoint |  | Fixing as per specification
| checkpoint |  | Glass type in accordance to the specification
| checkpoint |  | Glass clean, and free from scratch, chips or any damage
| signoff |  | Request Signoff
| checklist |  | QA - Precast Walls |  | Precast for Area: | 173d5682-9e59-4b52-9e9c-d7294fcecf3c
| section |  | Pre installation
| checkpoint |  | Precast elements inspected, correct and damage free before placement
| checkpoint |  | All pre installation work completed
| tickbox | 6279d689-eeea-5047-8125-f68bf6632e06 | Site set-out completed
| signoff |  | Request Signoff
| section |  | Installation
| checkpoint |  | Alignment and levels of the panel checked/correct
| checkpoint |  | Panel propping checked
| checkpoint |  | Drypacking / grouting complete
| checkpoint |  | Any additional photos, comments and observations
| checkpoint |  | Panel installation completed within tolerance in respective area
| tickbox | e2594693-2ab9-5714-b7ae-0051cc7b56ec | Trades QA received, reviewed, attached and approved
| signoff |  | Request Signoff
| checklist |  | Seismic Gap IBS Series |  | Seismic Gap IBS Series | 1754d090-ed25-421f-8460-0a67646b2164
| checkpoint |  | Joint is clean, uniform gap 100mm, dry and undamaged
| checkpoint |  | Silicon adhesive is applied both sides
| checkpoint |  | Correct type of precompressed sealant used. (IBS 100) check depth and width
| checkpoint |  | Precompressed sealant run through without gap and enough offset to avoid clashes to DM Series framing
| checkpoint |  | Joint cut square/mitered, no gap and applied with silicon adhesive
| checkpoint |  | Sealant applied continuously and tooled properly
| signoff |  | Request Signoff
| checklist |  | Add - Consultant Inspection Checklist (V3) |  | Consultant Inspection - | 1a39894f-1959-48ce-a38c-c424149ab37d
| checkpoint |  | Consultant inspection completed, attached and any relevant observations closed out
| textbox | 7b7a025d-81fa-4409-9ef9-3281b2d64523 | Date of Inspection
| textbox | dd36bd0b-3ee0-4704-912f-3f8f961a2cb6 | Type of Inspection
| textbox | da74bdd5-b086-41a1-94ef-12814f41c3f5 | Area inspection relates to
| tickbox | e495e118-490c-453e-af9d-13b99904e2dc | Consultant Inspection attached
| button | 0f8e78cc-ac2e-4458-b897-ef644c2cb994 | All Relevant Observation Closeout evidence attached here if applicable (Pass once completed) | PASS, N/A
| note | 1f26a12b-97a7-4354-afab-298bf48ac079 | "PASS" once corrective closeout evidence has been attached
| note | 5b90254d-0b5f-40ab-b626-60f2f7e09379 | If there are no corrective action requirements select "N/A"
| textbox | 3d06351b-6af4-431a-909b-5a78ef041b49 | Corrective Actions (listed here if required)
| signoff |  | Request Signoff
| checklist |  | Add - Council Inspection Checklist (V3) |  | Council Inspection - | 1a732614-648c-4004-b460-d06c77a7584c
| checkpoint |  | Council inspection completed, attached and any relevant observations closed out
| note | 3444c651-e5e2-4a4d-87f9-f06b48de741d | PASS once all information is attached including Observations/Failed comments with evidence of closeout
| textbox | dc83a024-74b8-4254-9ddd-e5098acc1bd8 | Date of Inspection:
| textbox | 9078e12c-052d-4e8e-aaa0-bf0ee4a8e674 | Type of Inspection:
| textbox | 52f91732-bf1d-45c6-bd07-b9da5bc92d07 | Area inspection relates to
| dropdown | b4da29de-ea63-439e-a19e-c0f75d938880 | Inspection Outcome | Pass, Fail, Partial Pass,Completed, N/A
| tickbox | e163160e-48f6-4a1e-925a-fc9517380516 | Council Inspection attached
| textbox | 202aee45-e7db-4a11-a3cd-d58c1ed02669 | Failed Comment(s) & Required Action
| note | 3c7bfeb2-48cc-4c75-8c53-db434c64e996 | Select N/A if there are no Observations/Failures requiring closeout
| button | 5fc35eaa-61ff-4a6a-85df-bfb72c73a67d | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed) | Pass, N/A
| signoff |  | Request Signoff
| checklist |  | Lift Glass |  | Lift Glass | 1e829b73-eb91-4199-bce2-34223e2e98b5
| checkpoint |  | Steel structure painted and handed over prior to start of work
| checkpoint |  | Spider fixing type as per specified (metroglass)
| checkpoint |  | Spider fixing installed as per drawing
| checkpoint |  | Spider fixing in good condition without damage to all parts
| checkpoint |  | 18mm single structural glass installed as per drawing layout (metroglass)
| checkpoint |  | Glass is 50mm offset to steel structure and 15 glass gap at the bottom of L0 and 10mm elsewere
| checkpoint |  | Glass logo visible
| checkpoint |  | Clear sealant on gap
| checkpoint |  | Spider centre at 120-130 edge distance to glass edge
| checkpoint |  | Conduit penetration in the correct location
| checkpoint |  | Glass free from scratch, chips or any damages
| checkpoint |  | Glass protection installed
| signoff |  | Request Signoff
| checklist |  | QA - Piling |  | QA - Piling | 2201e1f7-b7e9-495c-a440-8088b52fa508
| section |  | Prepour
| checkpoint |  | Pile diameter
| textbox | d07b8dab-206d-5921-a3f5-275207599823 | Pile diameter
| checkpoint |  | Engineer Inspection reinforcing
| checkpoint |  | Geotech inspection
| checkpoint |  | Council inspection
| checkpoint |  | CLL QA received
| checkpoint |  | Any Issues with Pile
| textbox | 409b3ddd-32e8-5b53-8e15-a74f47a38569 | Any issues/ collapse?
| textbox | 459d666f-42f1-53e3-8e02-1476a2c064bb | Weather conditions
| section |  | Post pour
| checkpoint |  | Concrete poured to the correct height
| textbox | a0456b24-1b48-4914-8ca0-12b6176fc593 | Date of Concrete Pour:
| checkpoint |  | Sand filled to clay height
| checkpoint |  | Cage centre of the hole
| checkpoint |  | No bars damaged
| checkpoint |  | Concrete cleaned from reinforcing
| checklist |  | Add Council BC Minor Variation Checklist (V3) |  | Council BC Minor Variation - | 23f538fc-821b-426d-a468-f44765e0cd22
| checkpoint |  | Minor variation status (PASS once approved & all information is attached including observations, correspondence & close out evidence)
| note | 39cfa62b-530c-435d-8c31-5ab24ebcb3d6 | PASS above checkpoint when variation is approved
| note | c5a175be-3b1a-445a-9336-4c5e4810c3ff | If minor variation is a FAIL - document why below and follow appropriate corrective actions
| textbox | a88179f2-77b1-4269-9f04-8c5059bb8975 | Date of application
| textbox | 2ddfe846-481f-4a8a-b0ae-2b214a1997f4 | Reason for application
| textbox | f01f557d-4086-43f4-a7ee-16bb2a52089f | Date of approval / acceptance
| textbox | ae299b30-acf7-438f-ac12-da27eef39fab | How was the minor variation approved? e.g. email from council, site meeting etc
| tickbox | a1fe9857-6309-49c9-8fe5-e06aaf747a30 | Council approval of minor variation attached
| note | f778aad6-b641-49d0-9b65-ea18fd7f65d3 | Ensure this minor variation and respective changes are communicated to any relevant parties
| checklist |  | QA - Setout / Surveying Checklist (V1) |  | Setout / Surveying - | 26b40be6-8dda-40b3-a96e-ac0979d6173f
| checkpoint |  | Any RL's setout are correct, labelled and photographed
| checkpoint |  | Any grid setout are correct, labelled and photographed
| checkpoint |  | Any other relevant setout/ survey documentation attached
| checkpoint |  | Survey work completed, checked and accurate
| checklist |  | Doors |  | Doors | 306a22ab-18f8-4157-a4d3-e27abfaa0b4f
| checkpoint |  | Door frames plumb and straight
| checkpoint |  | Door size and opening as per drawing
| checkpoint |  | Hinges, latches, knob, and other mechanical fixture in good condition
| checkpoint |  | Motors/door closer working properly
| checkpoint |  | If fire door, sealant applied as per speficied
| checkpoint |  | Sealant along frames correct size and thickness
| checkpoint |  | Correct sealant on PEF rod
| checkpoint |  | Door protection installed
| signoff |  | Request Signoff
| checklist |  | QA - Structural Steel |  | Structural Steel for Area: | 3bb5e337-d000-4817-8aec-c4ff0e18ab05
| section |  | Pre installation
| checkpoint |  | Structural steel items checked
| tickbox | bca0ce93-507b-5f41-9ea4-9fb262643b58 | Type/Size Checked
| tickbox | 6603a5d4-47c2-5281-8dce-ecc448006cde | Finishing checked (ie. Painted, Galvanised, etc)
| checkpoint |  | Cast in/anchor bolts and plates installed
| checkpoint |  | All pre installation work completed
| signoff |  | Request Signoff
| section |  | Installation
| checkpoint |  | Alignment and levels checked/correct
| checkpoint |  | All dry packing completed
| checkpoint |  | Any additional photos, comments and observations
| checkpoint |  | Structural steel work completed within tolerance in respective area
| tickbox | 4c22c5cb-4c52-5160-acda-257757d2c746 | Trades QA received, reviewed, attached and approved
| signoff |  | Request Signoff
| checklist |  | QA - Piling Completion_Handover Checks |  | QA - Piling Completion/Handover Checks | 3bea8de2-aadb-475b-8d06-10e6fbb6e6b7
| checkpoint |  | Trades QA completed, received & reviewed
| checkpoint |  | General progress photos recorded
| checkpoint |  | All piles completed (locations and heights checked and correct within tolerance)
| signoff |  | Request signoff
| checklist |  | QA - Site Establishment Checklist (V1) |  | Site Establishment | 3beb5133-9a2a-430e-abcf-485d3c5c2143
| checkpoint |  | Existing site conditions captured (pass once relevant information documented)
| checkpoint |  | Attach relevant site establishment photos/ documents
| checkpoint |  | Appropriate site fencing installed
| checkpoint |  | Site establishment completed
| signoff |  | Raise Remedial / Request Signoff
| checklist |  | Steel Frame Balustrade with Mesh Infill |  | Steel Frame Balustrade with Mesh Infill | 41eadf9b-6238-4629-9c55-9e325f5a528a
| checkpoint |  | Balustrade using 50x25x3mm HD galv powder coated steel
| checkpoint |  | Balustrade spacing as per specification
| checkpoint |  | SS mesh as per specified
| checkpoint |  | Height correct
| checkpoint |  | Fixing done in accordance to drawing
| checkpoint |  | Balustrade straight and plumb
| signoff |  | Request Signoff
| checklist |  | QA - Drainage |  | QA - Drainage | 46189d8f-c80a-41d4-be65-03143914c93c
| checkpoint |  | Council inspection records
| checkpoint |  | General Photos
| checkpoint |  | Bassett CONQA link/attached
| checklist |  | Curtain Wall System |  | Curtain Wall System | 4848b33c-9566-46db-8f3b-f11cf2e83c95
| section |  | Pre-installation. Waterproofing membrane
| checkpoint |  | Surface clean and free from dust, oil, grease, sealant etc..
| checkpoint |  | Sikalastic 152 applied before and after Sika Tape F. Continuous and 100mm up to the wall
| checkpoint |  | Sikaseal Tape F applied as per specification
| checkpoint |  | Dress at steel fin done in correct sequence
| checkpoint |  | Reveal shield applied with 150mm overlapping
| checkpoint |  | Liquiflash continuously applied and as per drawing
| dropdown | 3cf476a5-4d96-560e-be48-05d3c4792c26 | All checked and ready to proceed to next stage | Pass, Fail, Partial Pass, N/A
| section |  | Hanging Brackets
| checkpoint |  | Brackets type (aluminium/steel) used as per drawing. L0-L1 Aluminium. L2 Steel
| checkpoint |  | Bracket thickness and dimension as per drawing
| checkpoint |  | Bracket finish as per specified (powdercoated/intumicent painted/galvanized painted, etc...)
| checkpoint |  | Washer size and type as per specification.
| checkpoint |  | Bolt fixing used as per specification. Size,embedment depth, edge distance checked
| dropdown | 8f4a609f-e8b0-588a-97b9-ab31bfdd120c | All checked and ready to proceed to next stage | Pass, Fail, Partial Pass, N/A
| section |  | Seismic frame installation
| checkpoint |  | Sill frame undamaged, straight and plumb
| checkpoint |  | Sill frame screw fixing using Hilti HUS4 HR10x115, 75mm each side of mullion. Oversealed
| checkpoint |  | Drainage slot 8x50mm size, 100mm from both ends and each side of mullion
| checkpoint |  | End stops 100mm ht, fully sealed to structure
| checkpoint |  | Jamb undamaged, straight and plumb
| checkpoint |  | Jamb screw using M6x30 SS to steel, HUS HRS M6x70 to conc, 12G screw to timber with 450mm C/C max
| checkpoint |  | Corner reinforcement as per detail
| checkpoint |  | 20mm GAP between jamb frame and head channel
| checkpoint |  | Screws oversealed
| checkpoint |  | Head channel undamaged, straight and plumb
| checkpoint |  | Head channel fixed with M12 SS screws at 350 mm C/C min
| checkpoint |  | Screws oversealed
| checkpoint |  | Sikagard 52 is applied as per specification
| dropdown | 8347358b-9aa3-5c5a-99db-2dc865b18aa1 | All checked and ready to proceed to next stage | Pass, Fail, Partial Pass, N/A
| section |  | Sealant works
| checkpoint |  | Sika primer 3N/aktivator 205 is applied before sealant
| checkpoint |  | PEF rod correct size and in good location
| checkpoint |  | Gap 10mm +/-4
| checkpoint |  | Continuous AT Façade applied all round air seal properly tooled
| dropdown | 328ef0cd-4fe6-542f-98c2-728a64ecf220 | QA done ready for panel install | Pass, Fail, Partial Pass, N/A
| section |  | Curtain wall panel install
| checkpoint |  | Panel frame free from dents, dings and scratches
| checkpoint |  | Glass undamaged and free from scratches
| checkpoint |  | Gaskets and wedge in good condition
| checkpoint |  | Wip holes unblocked
| checkpoint |  | Gaps consistent to the drawings
| checkpoint |  | Panels aligned and plumb
| checkpoint |  | Angle closer installed as per drawing
| signoff |  | Request Signoff
| checklist |  | Office Roof |  | Office Roof | 49c10cd9-f6e4-4cde-bc18-fd784518e370
| section |  | Underlays
| checkpoint |  | Covertek 403 separation layer to purlin structure and cavity battens
| checkpoint |  | 20mm H3.2 castellated cavity battens installed before plywood
| checkpoint |  | Nog support timber framing at C purlin level at 600x600 spacing
| checkpoint |  | 17mm thick H3.2 waterborne CCA treated plywood fixed with 10x50 countersunk screw head
| checkpoint |  | Plywood used is non LOSP (light organic solvent preservative) or copper nitrate treated
| checkpoint |  | Screw 150mm c/c at edge and 200mm c/c at body of sheets
| checkpoint |  | Internal corners with 25mm fillet, external corners with 5mm radius.
| checkpoint |  | Timber plinth SG8 H3.2 100x50 timber layout as per drawing
| checkpoint |  | Timber plinth screw head countersunk Hex 14G M10x150 tek fixed at 600mm c/c
| checkpoint |  | Timber plinth with 45 degree timber fillet at corners
| checkpoint |  | 90mm Ht Timber diverter installed
| checkpoint |  | Conduit penetration to roof, location checked as per drawing
| checkpoint |  | Enough fall to drain
| checkpoint |  | Gutter and sump area done as per drawing
| checkpoint |  | No sharp object and all nail head flush to the plywood face
| dropdown | d76fc444-2170-527d-857c-7519a16a9b22 | All checked and ready to proceed to next stage | Pass, Fail, Partial Pass, N/A
| section |  | Roof Membrane
| checkpoint |  | All surface is clean, dry, free from sharp edges, oil, grease or other materials that my affect adhesion
| checkpoint |  | Worker is approved applicator to do the job
| checkpoint |  | Nuralite Nuraply 3PM double layer torch on system installed continuously
| checkpoint |  | No visible cracks, holes, damages into the membrane
| checkpoint |  | Joint overlapping fully welded
| checkpoint |  | Nuraglaze sealer is applied to portion of roof as shown in the architectural drawing
| checkpoint |  | Sheets fully adhered to plywood
| checkpoint |  | Double thickness application at all internal and external corner
| checkpoint |  | Conduit penetration done with ring clamp
| checkpoint |  | All penetration done properly
| signoff |  | Request Signoff
| checklist |  | Nuraply Waterproofing Membrane at Terrace to Warehouse Roof |  | Nuraply Waterproofing Membrane at Terrace to Warehouse Roof | 4b20bfcd-999a-4318-a8ce-000ced158916
| section |  | Nuraply Waterproofing Membrane at Terrace to Warehouse Roof
| checkpoint |  | All surface is clean, dry, free from sharp edges, oil, grease or other materials that my affect adhesion
| checkpoint |  | Worker is approved applicator to do the job
| checkpoint |  | Nuralite Nuraply 3PM double layer torch on system installed continuously
| checkpoint |  | No visible cracks, holes, damages into the membrane
| checkpoint |  | Joint overlapping fully welded
| checkpoint |  | Nuraglaze sealer is applied to portion of roof as shown in the architectural drawing
| checkpoint |  | Sheets fully adhered to plywood
| checkpoint |  | Double thickness application at all internal and external corner
| checkpoint |  | Pipe penetration done with ring clamp
| section |  | At Seismic Joint
| checkpoint |  | 5mm powder coated aluminium scupper rebated to ply at seismic gap fix to 1 end only
| checkpoint |  | Nuradeck bandage flashing with 50mm overlap to 3PM at scupper
| checkpoint |  | Membrane dressed over seismic end cap at 70mm min
| signoff |  | Request Signoff
| checklist |  | QA - Concrete Pour (Slabs) |  | Concrete Pour for Area: | 518abdd0-5b55-4662-8c42-477156e7097e
| section |  | Concrete - Pre Pour
| checkpoint |  | Set-out correct
| checkpoint |  | Any/All cast in items checked / correct (location and size)
| checkpoint |  | Penetrations correctly formed/located, checked and accurate
| checkpoint |  | Reinforcing checked and correct
| button | 4dc878d9-304e-536a-bfc9-1152c453f1dd | Size and type correct to specification | Yes, N/A
| tickbox | 2394572d-10c5-51c8-b44e-11842d036890 | Reinforcing spacing and location correct
| tickbox | 63b623d2-cd36-5864-a2c1-065815ca50ee | Specified covers checked/correct
| tickbox | a5a3e83a-6e14-5766-94b5-a46868affe87 | Splice laps checked/correct
| tickbox | 3de42f6b-b5cc-51fa-81c1-eec7aa1c962d | Any starter bars are installed correctly (location, size and spacing )
| tickbox | 243d6ce0-2160-5538-9532-742903b48e59 | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
| checkpoint |  | Waterproofing (checked and correct)
| checkpoint |  | Bottom of concrete pour is clean and free of debris/roughened
| checkpoint |  | Engineer informed of pour checks completed (see consultant folder and ensure observations are closed out)
| signoff |  | Request Signoff
| section |  | Concrete - Pour /Post Pour
| checkpoint |  | General photos/comments/observations
| tickbox | f5024dcb-51b2-5ff4-841c-413ac416afa6 | All concrete dockets photographed/attached here
| tickbox | 5eb53f38-6e22-5ca8-8b5e-c7a803fa8336 | Trades QA received & attached as applicable
| checklist |  | Site Wide QA - Drainage |  | Drainage for Area: | 566e9290-d8c7-46d9-9094-4aa576ab84d4
| section |  | Manhole
| checkpoint |  | Diameter confirmed
| checkpoint |  | IL confirmed
| checkpoint |  | Base haunched
| checkpoint |  | Lid plastered
| checkpoint |  | Ladder condition acceptable
| section |  | Drainage line
| checkpoint |  | Upstream RL confirmed
| checkpoint |  | Downstream RL confirm
| checkpoint |  | Fall acceptable
| checkpoint |  | Pipe diameter correct
| checkpoint |  | Pipe material correct
| checkpoint |  | Connections complete
| checkpoint |  | Fines placed
| checklist |  | Terrace Glass Balustrade |  | Terrace Glass Balustrade | 5b181474-7c17-43ed-baf7-08c6c18ebf4f
| checkpoint |  | Concrete nib straight with no damage
| checkpoint |  | Hilti HIT-HY200 + HIT V-R M10 Grade 316 SS anchor fixing @ 200 c/c and 160 embedment
| checkpoint |  | 1st Anchor placed at 120mm from edge of the concrete
| checkpoint |  | Continuous solid aluminium packer installed before between con structure and glass bottom support
| checkpoint |  | 2mm Powdercoated capping to concrete nib done as per drawing
| checkpoint |  | Base powder coating dulux eternity metro silver pearl kinetic
| checkpoint |  | Glass using 21.52mm safety sentry glass by Metroglass
| checkpoint |  | Glass ht 1100-1150mm to the top of the nib
| checkpoint |  | Glass is straigth and plumb
| checkpoint |  | Glass protection installed
| signoff |  | Request Signoff
| checklist |  | QA - Detailed Excavation Checklist (V1) |  | Detailed Excavation - | 72d99bbb-d347-4848-b021-e2e2df5071ee
| checkpoint |  | General Photos / Comments / Observations during excavation
| checkpoint |  | Excavation checked, correct and approved
| tickbox | 44b11573-9a80-47ed-8f5f-4b2516b78465 | Location accurate
| tickbox | 7cbd784f-6f9c-482a-bee7-6cd5f508d0eb | Depth correct (allow for site concrete if required)
| tickbox | 240f12b5-8297-4a76-b009-d33f90b28600 | Width correct (allow for boxing if required)
| checkpoint |  | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
| checkpoint |  | Excess Material Cleaned up and removed as required
| checkpoint |  | Detailed excavation completed, reviewed and approved
| note | b01560f3-933e-4ec0-bcf6-3ac688f2e87e | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
| tickbox | 91a8366b-e0fb-4816-8003-4c352c94db3f | Trades QA received & attached as applicable
| checklist |  | Terrace Canopy |  | Terrace Canopy | 7736b53f-b9db-4604-a09c-512c83ece6b1
| section |  | Stainless Steel Gutter at L1 Canopy
| checkpoint |  | Steel structure is painted and handed over before start work
| checkpoint |  | SS gutter weld continues and without hole, dent or crack
| checkpoint |  | SS gutter and sump fall about 1:100
| checkpoint |  | SS bracket at 600 C/C. Fixed to cladding with neoprene compressed washer with 12mm gap to cladding
| checkpoint |  | Diverter flashing over terrace column installed as per drawing
| section |  | Glazed Roof
| checkpoint |  | Spider fixing installed per shop drawing and without damage
| checkpoint |  | Glass using 21.52 toughened laminated safety glass with 115 clearance at structure
| checkpoint |  | Glass with anti-reflective frit as per drawing
| checkpoint |  | Glass overhung about 200mm from the spider fixing
| checkpoint |  | Glass edge as per drawing
| checkpoint |  | Joint sealant done with the correct type and properly tooled
| checkpoint |  | Drip angle installed at the the lower edge
| section |  | Aluminium Battened Soffit
| checkpoint |  | 50x50 aluminium box powder coated with Dulux Eternity Metro Silver Pearl Kinetic
| checkpoint |  | Spacing as per drawing
| checkpoint |  | Alignment as per drawing
| checkpoint |  | Batten adequately fixed and no damage
| signoff |  | Request Signoff
| checklist |  | Cast In Items |  | Cast In Items | 7951885b-c342-419b-8630-6d9e4bbee089
| checkpoint |  | Drawings are marked for construction, are the latest revision and are entered on drawing register
| checkpoint |  | All cast in items installed to correct positions
| note | cc41aebf-a028-5557-b7a8-e10d6475795b | Ends sealed for in slab conduits
| note | 0031cb8c-460b-5653-9c68-4696e00d803f | Is the correct size
| note | 24940fc0-bf35-5042-9161-1ea565abc37d | Is securely fixed
| note | 211723e9-792b-57c2-a813-8462104687d3 | Saddled and tied in position
| checkpoint |  | Concrete pour has been observed to ensure cast in items have not been damaged
| checkpoint |  | Final as installed drawings have been drafted
| checklist |  | Panel Sealant |  | Panel Sealant | 7b0969cd-2ac3-4cf7-a6a6-90e99faeff01
| checkpoint |  | Cut and remove existing sealant
| checkpoint |  | Clean all sealant residue and dirt/dust
| checkpoint |  | Insert correct size backing (tight fit) rod to correct depth
| checkpoint |  | Surface clean and dry - ready for application
| checkpoint |  | Correct depth achieved prior to sealant
| checkpoint |  | Apply specified sealant primer
| checkpoint |  | Correct Sealant Applied as per manufacturers instructions
| checkpoint |  | Sealant properly tooled
| checkpoint |  | No visible voids, flaws or defect.
| checkpoint |  | Double seal required from exterior - refer architect's detail
| checkpoint |  | Double seal installed as per architect's direction (clearly mark double sealed area on elevation)
| checkpoint |  | Ensure that drain slots are created the lowest point of panel 10mm dia
| checklist |  | QA - Service Location / Isolation Checklist (V1) |  | Service Location / Isolation | 7d2495e3-2d67-4d04-aa21-159c2e127030
| checkpoint |  | Power located
| signoff |  | Raise remedial / request trades QA / signoff
| checkpoint |  | Water Supply located
| signoff |  | Raise remedial / request trades QA / signoff
| checkpoint |  | Sewer located
| signoff |  | Raise remedial / request trades QA / signoff
| checkpoint |  | Stormwater located
| signoff |  | Raise remedial / request trades QA / signoff
| checkpoint |  | Telecommunication/Fibre located
| signoff |  | Raise remedial / request trades QA / signoff
| checkpoint |  | Any other relevant services located/ isolated
| signoff |  | Raise remedial / request trades QA / signoff
| checkpoint |  | All Services located/ isolated (Pass once all services are located/isolated)
| signoff |  | Raise remedial / Request signoff
| checklist |  | Add Council BC Amendment Checklist (V3) |  | Council BC Amendment - | 82360c94-120f-4dd9-8ae7-cffc53ba63f7
| checkpoint |  | Building consent amendment status (Pass once approved & all information is attached including observations, correspondence & close out evidence)
| note | d98f29dd-33e5-491e-a711-395516a2b7d0 | PASS above checkpoint when amendment is approved
| note | 13ec50bf-c00e-4072-b748-5e7184045207 | If amendment is a FAIL - document why below and follow appropriate corrective actions
| textbox | 3ac5e947-9f3e-472d-80b5-cc37078c23f1 | Date of application
| textbox | 6aed6b13-06af-402c-b599-1b9386a6b3a4 | Reason for application
| textbox | f7aadbe4-bd83-484c-92f2-1420b81e75c8 | Date of approval / acceptance
| textbox | d5b1824d-d66e-41a8-953e-7d5759affa90 | How was the amendment approved? e.g. email from council, site meeting etc
| tickbox | b919d047-81f4-483a-a98b-7655bddda5e9 | Council approval of amendment attached
| textbox | 828274cd-74c3-4f32-baeb-614afdf4064d | Update building consent number (including amendment)
| tickbox | 3800231c-74fa-4e51-a23b-0fdbb73d0f16 | Latest building consent including amendment has been attached in the "Latest Building Consent" folder to superseed the previous consent
| note | c93744fa-e3ba-44dc-903a-441321ca4ec9 | Ensure this amendment and respective changes are communicated to any relevant parties
| checklist |  | Add Council BC Upload Checklist (V3) |  | Building Consent - | 84eb61bc-bf6e-4f9b-b1a8-f5c8c6ab87bd
| checkpoint |  | Latest building consent attached (superseded and attached as required)
| note | a9de507b-5933-4720-b76c-375bcb740674 | If a new building consent is issued as a result of an amendment upload here
| checklist |  | Curtain Wall Timber Framing |  | Curtain Wall Timber Framing | 89d15098-ce2c-4b55-a8e5-26872b7274f2
| checkpoint |  | Set out from gridline correct
| checkpoint |  | Dimension of wall opening correct
| checkpoint |  | DPM installed where required
| checkpoint |  | Timber frames type as per specification
| checkpoint |  | Frame square and plumb
| dropdown | f412ae3c-a205-51ca-8fd4-990163c48013 | Council inspection done. Preline | Pass, Fail, Partial Pass, Completed, N/A
| checkpoint |  | Board type (RAB) as per drawing
| checkpoint |  | Fixing used as per specification
| checkpoint |  | Fixing spacing and edge distance correct
| checkpoint |  | Board no damage and in good condition
| dropdown | 780342de-9ddb-509e-a5e8-3895624b67cc | Council inspection done. Postline | Pass, Fail, Partial Pass, Completed, N/A
| signoff |  | Request Signoff
| checklist |  | QA - Backfill Checklist (V1) |  | Backfill - | 8c2ce3d1-5608-4958-b64f-f1bf64637f84
| checkpoint |  | Backfill methodology and material confirmed
| checkpoint |  | Any formwork/ debris removed from area
| checkpoint |  | Any waterproofing/ drainage / service requirements completed and inspected
| checkpoint |  | Approval given to commence backfill - attach any other relevant inspections and observations closeout
| checkpoint |  | General photos and observations during backfill
| checkpoint |  | Backfill completed correctly and heights checked/ correct - desired compaction achieved
| note | 17bdc79c-e784-452a-99a4-fb83371c3f0c | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
| tickbox | 06086830-9801-49e2-a664-44ca3869ec91 | Trades QA received & attached as applicable
| checklist |  | Nuraply Waterproofing Membrane at Green Roof |  | Nuraply Waterproofing Membrane at Green Roof | 9188e00f-4709-47e1-af42-ff93fda119f5
| checkpoint |  | All surface is clean, dry, free from sharp edges, oil, grease or other materials that my affect adhesion
| checkpoint |  | Nuralite bitumen LM fillet at internal corners
| checkpoint |  | 5mm fillet radius at external corners
| checkpoint |  | Worker is approved applicator to do the job
| checkpoint |  | Nuralite Nuraflux primer installed continuously to cover whole area
| checkpoint |  | Nuraply 3PB-SA installed continuously without any damage
| checkpoint |  | Nuraply 3PB membrane installed continuously without any damage installed in accordance to specification
| checkpoint |  | Nuralite aluminium tape to separate sealant and membrane
| checkpoint |  | Nuraply base sheet reinforcing strip on primer installed at precast joint
| checkpoint |  | Termination bar mechanically fixed as per manufacturers manual
| checkpoint |  | No visible cracks, holes, damages into the membrane
| checkpoint |  | Joint overlapping fully welded
| checkpoint |  | Double thickness application at all internal and external corner
| checkpoint |  | Pipe penetration done with ring clamp
| checkpoint |  | All penetration done properly
| signoff |  | Request Signoff
| checklist |  | Villaboard Soffit Lining |  | Villaboard Soffit Lining | 9746d6d6-570f-4002-aae8-1516b77aa700
| checkpoint |  | Correct timber framing installed with 600 c/c stud spacing and max 1200 frame
| checkpoint |  | Correct type of fixing used and not overdriving
| checkpoint |  | Correct spacing for fixings. 70mm at corners, 200mm C/C at edge, 300mm C/C at internal studs, 12mm edge distance
| checkpoint |  | Sheets rebated at joints with 1-2mm gap each joint
| checkpoint |  | Minimum 6mm gap to soffit edge structure
| checkpoint |  | Inseal tape along the edge
| checkpoint |  | All site cut and recessed must to sealed as specified
| checkpoint |  | Perforated paper tape applied at joint rebate as necessary during plaster
| checkpoint |  | Control joints if specified, has been done as per specification
| checkpoint |  | Edge of the soffit straight
| checkpoint |  | Paint done properly with correct colour as specified
| signoff |  | Request Signoff
| checklist |  | Nuwall Soffit Lining |  | Nuwall Soffit Lining | 994dd3b9-5a2a-4f61-9313-7ec18bdcf5b6
| checkpoint |  | Timber framing using 90x45 SG8 with 600 C/C spacing
| dropdown | 3ddaba91-86aa-507c-b0da-30666b62f0e1 | Council inspection done. Preline | Pass, Fail, Partial Pass, Completed, N/A
| checkpoint |  | RAB exposed cut edge to be primed
| checkpoint |  | 2-4mm gap in between joints
| checkpoint |  | Nail with 12mm edge distance and 200mm c/c minimum spacing
| checkpoint |  | Nail flush with board surface
| checkpoint |  | RAB Joints and corner sealed with 75mm wide tape
| checkpoint |  | RAB free of dust, oil, grease, etc
| dropdown | 5a8d3f2c-156c-54db-a994-11fef4a26ff8 | Council inspection done. Postline | Pass, Fail, Partial Pass, Completed, N/A
| checkpoint |  | Flashings needed installed before batten if required
| checkpoint |  | 20mm H3.2 castellated cavity batten at 600 c/c spacing. Castellation againts RAB
| checkpoint |  | Castellated cavity batten fixed to timber frame with 40x12mm SS flat head nail 800 c/c
| checkpoint |  | Nuwall type and colour as specified. Mono 200 with Dulux eternity metro silver pearl kinetic
| checkpoint |  | Orientation as per drawing
| checkpoint |  | 10g SS fixing screw with 30mm min embedment to timber structure
| checkpoint |  | Isolator strip to underside of all castellated soffit battens by Nuwall
| checkpoint |  | End Cap installed at all edges p.c. to match soffit
| checkpoint |  | Soffit Lining free from scratches, dents and damages.
| signoff |  | Request Signoff
| checklist |  | Warehouse Roof |  | Warehouse Roof | 9c833457-32b0-47bd-94dc-32e9e3e5c9c4
| section |  | Metal Roofing
| checkpoint |  | Metal roof type and colour as per specification. ST963 Gull Grey both sides
| checkpoint |  | Galvanized fixing screw neoprene washer with epdm seals rip fixed
| checkpoint |  | Metal roof free from scratches, dents and holes
| checkpoint |  | Fixings not over or underdriven to roof sheet and with enough embedment to structure
| checkpoint |  | Thermakraft Thermabar 397 FRR roofing underlay installed without damange
| checkpoint |  | Thermakraft Ausmesh mesh installed as per specification fixed at 600 c/c
| checkpoint |  | Sika expansion tape 600 installed at the top of precast
| checkpoint |  | Colorsteel eaves flashing installed as per drawing fixed at 600
| checkpoint |  | Vermin flashing insalled hard up the the gap
| checkpoint |  | Apron flashing as per detail and sufficient amount of fixing. Screws oversealed and birdproof. 200mm width
| checkpoint |  | Apron flashing minimum upstand 110mm. Continues sealed and with compressible foam seal
| checkpoint |  | Secondary apron flashing with continuous compressible foam and seal
| checkpoint |  | Secondary apron flashing fixing at 600mm c/c oversealed
| section |  | Roof penetration
| checkpoint |  | Conduit penetration to roof with Dektite EPDM boot in diamond layout
| checkpoint |  | Dektite screwed and sealed properly as per manufactorers detail
| section |  | Gutter and downpipe
| checkpoint |  | Gutter straight and with enough slop towards downpipe
| checkpoint |  | Gutter secure, undamaged and free from any debris
| checkpoint |  | Downpipe location as per drawing
| checkpoint |  | Downpipe free from dents, leaks and damages
| checkpoint |  | Downpipe plumb with clips and fixing spacing as per specification
| signoff |  | Request Signoff
| checklist |  | Sika 740W Spray on Paint |  | Sika 740W Spray on Paint | a25c556a-8b93-4009-b643-5eba1b43f100
| checkpoint |  | Surface free of dust, oil, efflorescence and paint coatings
| checkpoint |  | Damage of concrete if any, have been patched
| dropdown | f64073cd-1c33-59cf-8447-dbb854de7119 | Consultant/Client Inspection | Pass, Fail, Partial Pass, N/A
| checkpoint |  | Surface is dry and no damp patches
| checkpoint |  | Windows and curtain wall installed and well protected especially along the sealant area
| checkpoint |  | 2-3 coats applied wet-wet bottom-up without letting the product run into the surface
| checkpoint |  | Area is protected from rain for at least 6 hours
| signoff |  | Request Signoff
| checklist |  | Aluminium Battened Soffit |  | Aluminium Battened Soffit | a2b28bd5-6102-4dfc-a1e1-b0e194ba1c87
| checkpoint |  | 50x50 aluminium box powder coated with Dulux Eternity Metro Silver Pearl Kinetic
| checkpoint |  | Spacing as per drawing
| checkpoint |  | Alignment as per drawing
| checkpoint |  | Batten adequately fixed and no damage
| signoff |  | Request Signoff
| checklist |  | QA - Concrete Pour FOUNDATION Checklist (V1) |  | Concrete Pour - | a473598c-3f59-4454-8d35-97034f975163
| section |  | Concrete - Pre Pour
| checkpoint |  | Area Accessible & Approval to start
| checkpoint |  | Formwork - Correct Dimensions & Heights
| checkpoint |  | Formwork cleaned, oiled and braced sufficiently
| checkpoint |  | Any/All cast in items checked / correct (location and size)
| checkpoint |  | Penetrations correctly formed/located, checked and accurate
| checkpoint |  | Reinforcing checked and correct
| button | e4c2dec8-ae7c-4dfe-b825-d3428fd0612a | Size and type correct to specification | Yes, N/A
| tickbox | 704b0cf7-319f-4fde-a9a9-69b6f130fe04 | Reinforcing spacing and location correct
| tickbox | 3d3193fa-0ccd-43bf-8af1-048f37f7b9ee | Specified covers checked/correct
| tickbox | 53f05949-f284-473a-8971-88ccad352568 | Splice laps checked/correct
| tickbox | 0e615d2a-4bb1-44b9-b269-437eb0872ec1 | Any starter bars are installed correctly (location, size and spacing )
| tickbox | 2ebffacc-3a83-418c-8b81-4b139d0cea0a | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
| checkpoint |  | Waterproofing (checked and correct)
| checkpoint |  | Bottom of concrete pour is clean and free of debris/roughened
| checkpoint |  | Engineer informed of pour checks completed (see consultant folder and ensure observations are closed out)
| signoff |  | Request Signoff
| section |  | Concrete - Pour /Post Pour
| checkpoint |  | Concrete checked on arrival & correct (slump, MPa etc)
| tickbox | b6373989-333f-475a-ac74-24e2d76a699b | All concrete dockets photographed/attached here
| checkpoint |  | General photos/comments/observations during placement
| checkpoint |  | Concrete surface finish to specifications
| checkpoint |  | Concrete Pour completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
| note | d8280fe4-960c-4214-82de-2808b94d159a | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
| tickbox | ce508a38-d6ff-4593-a9dd-a47094abe648 | Trades QA received & attached as applicable
| checklist |  | Flashing QA |  | Flashing QA | ac4dcb4c-b155-4f37-a89d-af43a9efc8f6
| checkpoint |  | Flashing material and color as specified
| dropdown | 3934dd4f-c4ae-527f-9574-102dff354d4b | Flashing Type | Sill flashing, Jamp flashing, Head flashing, Cap flashing, Soffit flashing, Other type
| checkpoint |  | Flashing height, depth, width as per drawing
| checkpoint |  | Flashing fixed with appropriate fixing type and cetre-centre spacing
| checkpoint |  | Flashing joints done with enough overlapping/soaker legth and as per drawing
| checkpoint |  | Flashing cavity or space between structure/frame as per drawing
| checkpoint |  | Screw oversealed if necessary
| checkpoint |  | Enough fall
| checkpoint |  | Staight and plumb
| checkpoint |  | Upstand height as per drawing
| checkpoint |  | Flashing tape applied as necessary
| checkpoint |  | No scartches, dents and any damages
| checkpoint |  | Flashing protection installed
| signoff |  | Request Signoff
| checklist |  | Add CCC Code Compliance Certificate Checklist (V3) |  | Code Compliance Certificate - BC0 - | b01340bf-8996-47c7-813d-163150838ebe
| section |  | Code Compliance Certificate Lodgement
| checkpoint |  | Code Compliance Certificate lodgement form completed/received and attached
| note | e1d54ab8-482b-427f-b519-9161821ddbcd | Attach confirmation of CCC lodgement and PASS above checkpoint when CCC has been applied for
| checkpoint-no-value |  | Code Compliance Certificate RFI's
Not allowed as a child of checklist-sectioned. | folder-normal |  | Code Compliance Certificate RFI's
| section |  | Code Compliance Certificate Approval
| checkpoint |  | Final Code Compliance Certificate (approved & attached)
| section |  | Code Compliance Certificate Approval
| checkpoint |  | Final Code Compliance Certificate (approved & attached)
| note | 339edcee-2b88-4e6d-abc0-6eb47f59ca1d | Attach approved Code Compliance Certificate and PASS above checkpoint when CCC has been approved
| checklist |  | Terrace Tiled Flooring |  | Terrace Tiled Flooring | b9f96958-926d-435d-81f9-1c495e5d4ae7
| section |  | Nuraply waterproofing membrane
| checkpoint |  | All surface is clean, dry, free from sharp edges, oil, grease or other materials that my affect adhesion
| checkpoint |  | Surface screed slop to drain as per drawing
| checkpoint |  | Worker is approved applicator to do the job
| checkpoint |  | Nuralite Nuraply 3PM double layer torch on system installed continuously
| checkpoint |  | No visible cracks, holes, damages into the membrane
| checkpoint |  | Joint overlapping fully welded
| checkpoint |  | Sheets fully adhered to surface
| checkpoint |  | Double thickness application at all internal and external corner
| checkpoint |  | Pipe penetration done with ring clamp
| checkpoint |  | Termination bar mechanically fixed as per manufacturers manual
| section |  | Tiled Flooring
| checkpoint |  | Nurajack start T installed as per manufacturers manual
| checkpoint |  | Nurajck levellers installed as per manufacturers manual
| checkpoint |  | Nurapoxy tg applied at raised concrete when necessary
| checkpoint |  | Outdure Qwickbuild aluminium support frame system installed on top of nurajack
| checkpoint |  | Selected R11 non-slip 302x604x20 think porcelain tile installed, level and without damage
| signoff |  | Request Signoff
| checklist |  | Add Drawings & Programme Checklist (V1) |  | Drawings & Programme | ba496c6a-d1a4-45ed-8dba-ed2acabf5615
| checkpoint |  | Relevant Drawings Uploaded
| checkpoint |  | Construction Programme Uploaded
| checklist |  | Flat Slab Placement |  | Flat Slab Placement | bbe48d53-d902-48a8-a399-a67483dc6821
| checkpoint |  | Check RL of landing place
| checkpoint |  | Mark out flat slab layout on site
| checkpoint |  | Install bearing strip
| checkpoint |  | Set heights for midspan
| checkpoint |  | Check dimensions of the panel - on delivery
| button | 62ab6a79-7faf-5d01-af19-9cc327cb7b18 | If applicable cut flat slab | Yes,No
| checkpoint |  | Place flat slab
| checkpoint |  | Photos and observations
| checklist |  | Add CCC RFI Checklist (V3) |  | RFI - | c58de946-dbb5-4dfb-9b71-454762b91047
| section |  | RFI Status
| checkpoint |  | RFI Status - Pass once approved by Council
| note | c3c60ca2-29d0-4391-a572-3d5f30a041b1 | Use the "RFI Management of Individual Items" folder to manage and close out the individual RFI items
| note | 6be915f4-b900-42f5-8690-eb77aaa4cab3 | Final "PASS" once all RFI items have been responded to/actioned and approved
| textbox | 9c2c1506-cf20-4bdf-973e-807e089ebba7 | Date RFI was received from Auckland Council
| tickbox | 2164cf0e-1749-4ccd-ae2a-7fe3311404e6 | RFI Attached
| textbox | 7b4124fa-1949-44ae-87c5-c39734267641 | Date Main Contractor/Builder sent response to RFI
| textbox | f6d690e7-d406-4c0b-b07b-2a29d56227b9 | Date of response/approval from Council
Not allowed as a child of checklist-sectioned. | folder-normal |  | RFI Management of Individual Items
| checklist |  | Add CCC RFI Individual Item Checklist (V3) |  | Individual RFI - | c6210e0b-acd9-4949-911f-970573160ebc
| checkpoint |  | RFI Item Status - pass once answered/actioned
| textbox | 3e4ddc18-d0a7-4ad1-a02f-d6ad4683ba1b | Description of RFI Item
| textbox | 7c142801-2bc7-4643-9829-8403d6028ee0 | Action Required
| note | 51ac393b-9522-4cf5-bf29-8c4f224ebdfe | Relevant documentation / close out evidence attached
| checklist |  | QA - Waterproofing Checklist (V1) |  | Waterproofing Checklist - | c888aabb-7390-4a7a-ae87-215944b99d7f
| checkpoint |  | Preparation / Substrate acceptable
| checkpoint |  | Correct product delivered and checked - approval given to install
| checkpoint |  | General photos/comments during install
| checkpoint |  | Any inspections / observations documented, reviewed and closed out
| checkpoint |  | Waterproofing install completed, reviewed and approved to meet required specifications
| note | 954cb805-cfd4-46ea-94f8-c2f061ec1b97 | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
| tickbox | 8d7ba9b9-a9e1-4d4b-bbb6-364cdc1d324a | Trades QA received & attached as applicable
| checklist |  | Insitu Concrete Inspection |  | Insitu Concrete for area: | cfde5b5b-cee7-4589-b1fc-824f5a87a9f5
| section |  | Formwork
| checkpoint |  | Installed as per formwork design
| checkpoint |  | Dimensions correct
| checkpoint |  | Position and orientation correct
| checkpoint |  | Forms vertical, plumb and true
| checkpoint |  | Forms coated with release agent
| checkpoint |  | Forms clean and clear of debris
| checkpoint |  | Joints sealed
| checkpoint |  | Pour level marks
| section |  | Reinforcement
| checkpoint |  | Starters bars included if required
| checkpoint |  | Refer to Brilliance Steel QA
| checkpoint |  | All Cast in elements checked and correct
| checkpoint |  | Penetrations checked and correct
| section |  | Construction Joints
| checkpoint |  | Correct location
| checkpoint |  | Adequately prepped
| checkpoint |  | Joint board installed
| section |  | Concrete Orderd
| checkpoint-no-value |  | Details
| textbox | 7127c40a-69b5-5c10-bd86-34f1389db71b | Mix Type
| textbox | 5e7fb3c2-b9db-5d94-a7e0-08a917ada65c | Volume
| section |  | Post Pour
| checkpoint |  | General photos/comments/observations
| checklist |  | Curtain Wall Steel Post |  | Curtain Wall Steel Post | d076f3d8-4f45-4ff5-bfb0-0e4595cb0b6e
| checkpoint |  | Post location correct
| checkpoint |  | Post welding to cast in plate done properly
| checkpoint |  | Steel fin straight and not bent
| checkpoint |  | Bolts and nuts used as per detail
| checkpoint |  | Minimum 20mm gap at top and joint of the fin
| dropdown | 4a8dd184-308e-58db-9ff3-e2ba1c9d07e2 | Intumescent paint applied | Completed, Not completed, N/A
| checkpoint |  | Paint colour as per specification
| checkpoint |  | Paint undamaged
| tickbox | 420fe702-c83e-59b5-8653-a4998d1e48c7 | Protection around post is installed
| signoff |  | Request Signoff
| checklist |  | Seismic Gap DM Series with Vapour Barrier |  | Seismic Gap DM Series with Vapour Barrier | d7329d22-c474-49d6-bcc0-3bdc85856fc5
| checkpoint |  | Concrete haunching done on the floor slab with slop to outside slab
| checkpoint |  | Vapour barrier fixed from top to bottom without damage
| checkpoint |  | DMS framing fixed to concrete wall straight and plumb and in good condition
| checkpoint |  | Conc-conc joint +/- 150mm
| checkpoint |  | Frame-frame gap +/- 127mm centred to the concrete gap fix with screw at 450mm c/c, 150mm start and end
| checkpoint |  | Center plate/ cover plate surface finish as per specification (PC Dulux Gunmetal Kinetic Matt)
| checkpoint |  | Center plate/ cover plate resting firmly against the gasket of the framing
| checkpoint |  | Center plate screw tight and secured to centering bar: Cover against the concrete structure
| signoff |  | Request Signoff
| checklist |  | Staircase Glass Balustrade |  | Staircase Glass Balustrade | d76fe13c-069e-40d7-85f8-5e673a2ded0c
| checkpoint |  | 125x100x75 10tk Bottom plate rebated into precast concrete
| checkpoint |  | 50x25mm metal post balustade plumb and straight
| checkpoint |  | 50mm metal handrail installed at 900mm ht
| checkpoint |  | Spider fixing secured and no damage
| checkpoint |  | 10mm balustrade glass installed as per layout and with 1100mm ht
| checkpoint |  | Handrail and glass gap at 50mm
| checkpoint |  | Glass free from scratch, chips or any damages
| checkpoint |  | Glass protection installed
| signoff |  | Request Signoff
| checklist |  | James Hardie Easylap Cladding at L1 Terrace Canopy Area |  | James Hardie Easylap Cladding at L1 Terrace Canopy Area | e4d95f95-25b9-455a-9f60-78f5901fdf0e
| checkpoint |  | Timber framing using 90x45 SG8 with 600 C/C spacing
| checkpoint |  | Wall Therman Insulation R2.9 140mm Greenstuff thermal blanket fitted into wall
| checkpoint |  | Council inspection done. Preline
| checkpoint |  | RAB exposed cut edge to be primed
| checkpoint |  | 2-4mm gap in between joints
| checkpoint |  | Nail with 12mm edge distance and 200mm c/c minimum spacing
| checkpoint |  | Nail flush with board surface
| checkpoint |  | RAB free of dust, oil, grease, etc
| checkpoint |  | Steel plate dressed properly with aluminium saddle flashing with continuous sealant to plate
| checkpoint |  | Council inspection done. Postline
| checkpoint |  | Revealshield done as per specification
| checkpoint |  | Curtain wall head flashing installed in good condition
| checkpoint |  | JH PVC vent strip installed at the bottom with 600mm c/c max
| checkpoint |  | Cavity batten fixed at 600 c/c apart with 250mm c/c nail fixing to the structure
| checkpoint |  | Easylap edges is sealed
| checkpoint |  | 11 FC sealant is applied at the cavity batten before the Easylap panel is installed
| checkpoint |  | Panel is fixed with SS fixing at 150mm C/C flush to the face
| checkpoint |  | Painted as per specification
| checklist |  | Facia Plate |  | Facia Plate | f45702c5-7856-48d8-88c0-4e21e33cb80d
| checkpoint |  | Waterproofing QA done bafore start work
| checkpoint |  | Plate using 6mm 5052 aluminium powder coated plate with countersunk fixing
| checkpoint |  | Powdercoated Dulux eternity metro silver pearl kinetic
| checkpoint |  | Max edge distance 100mm of fixing
| checkpoint |  | 10mm gap at joints with 150mm joint at seismic gap
| checkpoint |  | Fixing 2x 10g countersunk s/s screws with 75mm embedment at 600mm c/c spacing
| checkpoint |  | Plate spaced of structure with 2 50x50x6 SS washer with 6mm EPDM washer maintaining 12mm min clear gap
| checkpoint |  | Normal length 2.4m per sheet
| checkpoint |  | Facia overall depth covers all of facia structure
| checkpoint |  | Facia align to each other
| checkpoint |  | No scratches, dents or damages
| signoff |  | Request Signoff
| checklist |  | QA - Underslab Services Install Checklist (V1) |  | Underslab Services - | fdf6d07a-ee49-48ff-aeb7-c869d5ecbc53
| checkpoint |  | ELECTRICAL services/ conduits installed, fixed in correct location, backfilled and correct as per design
| checkpoint |  | HYDRAULIC services installed, fixed in correct location, backfilled and correct as per design
| checkpoint |  | GAS services installed, fixed in correct location, backfilled and correct as per design
| checkpoint |  | MECHANICAL services installed, fixed in correct location, backfilled and correct as per design
| checkpoint |  | DATA/COMMS services installed, fixed in correct location, backfilled and correct as per design
| checkpoint |  | Any other services installed, fixed in correct location, backfilled and correct as per design
| checkpoint |  | Underslab Services completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
| note | 7a46d5a6-661d-43a6-9bc4-0d745305036d | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
| tickbox | 778fcbab-dab2-4a0c-9f65-3e7539e33f4e | Trades QA received & attached as applicable