## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Facade - Detailed Progress
| Scope |  |  | Atlas | Facade
Rows
|  | Precast Panel Sealant QA (Office and Warehouse) | grouping | Precast Panel Sealant QA (Office and Warehouse)
|  | Panel Sealant for AH8-AH 55 |  | Atlas | Building | Envelope | Facade | Precast Panel Sealant QA (Office and Warehouse) | Panel Sealant for AH8-AH 55
|  | Grid B&8 Panel grouting |  | Atlas | Building | Envelope | Facade | Precast Panel Sealant QA (Office and Warehouse) | Grid B&8 Panel grouting
|  | 27-02-2024 Panel Sealant on grid 4 & B |  | Atlas | Building | Envelope | Facade | Precast Panel Sealant QA (Office and Warehouse) | 27-02-2024 Panel Sealant on grid 4 & B
|  | Grid 2-3 Panel Sealant |  | Atlas | Building | Envelope | Facade | Precast Panel Sealant QA (Office and Warehouse) | Grid 2-3 Panel Sealant
|  | 04-04-2024 AH133 & 134 Panel Sealant |  | Atlas | Building | Envelope | Facade | Precast Panel Sealant QA (Office and Warehouse) | 04-04-2024 AH133 & 134 Panel Sealant
|  | L2 Panel AH 229 & AH 230Sealant |  | Atlas | Building | Envelope | Facade | Precast Panel Sealant QA (Office and Warehouse) | L2 Panel AH 229 & AH 230Sealant
|  | 15-05-2024 Panel Sealant on grid A & E |  | Atlas | Building | Envelope | Facade | Precast Panel Sealant QA (Office and Warehouse) | 15-05-2024 Panel Sealant on grid A & E
|  | Precast Panel Sealant QA (Office and Warehouse) - Facade Grid 3-4 / Ground-Mez Floor | dynamic | Precast Panel Sealant QA (Office and Warehouse) | Facade Grid 3-4 / Ground-Mez Floor
|  | Curtain Wall QA (Office) - Level 1-Level 2 | dynamic | Atlas | Building | Envelope | Facade | Curtain Wall QA (Office) | Level 1-Level 2
|  | Curtain Wall QA (Office) - Level 0 | dynamic | Atlas | Building | Envelope | Facade | Curtain Wall QA (Office) | Level 0
|  | Punch Windows and Doors (Office and Warehouse) - Office Area | dynamic | Atlas | Building | Envelope | Facade | Punch Windows and Doors (Office and Warehouse) | Office Area
|  | Punch Windows and Doors (Office and Warehouse) - Warehouse | dynamic | Atlas | Building | Envelope | Facade | Punch Windows and Doors (Office and Warehouse) | Warehouse
|  | Seismic Gap | dynamic | Atlas | Building | Envelope | Facade | Seismic Gap
|  | Various Flashing | dynamic | Atlas | Building | Envelope | Facade | Various Flashing
|  | Concrete Sealer | dynamic | Atlas | Building | Envelope | Facade | Concrete Sealer
Columns
|  | Panel Sealant - Cut & remove existing sealant |  | Cut and remove existing sealant
|  | Panel Sealant - Clean all sealant residue & dirt/dust |  | Clean all sealant residue and dirt/dust
|  | Panel Sealant - Insert correct size backing (tight fit) rod to correct depth |  | Insert correct size backing (tight fit) rod to correct depth
|  | Panel Sealant - Surface clean & dry - ready for application |  | Surface clean and dry - ready for application
|  | Panel Sealant - Correct depth achieved prior to sealant |  | Correct depth achieved prior to sealant
|  | Panel Sealant - Apply specified sealant primer |  | Apply specified sealant primer
|  | Panel Sealant - Correct Sealant Applied as per manufacturers instructions |  | Correct Sealant Applied as per manufacturers instructions
|  | Panel Sealant - Sealant properly tooled |  | Sealant properly tooled
|  | Panel Sealant - No visible voids, flaws or defect |  | No visible voids, flaws or defect.
|  | Panel Sealant - Double seal required from exterior - refer architect's detail |  | Double seal required from exterior - refer architect's detail
|  | Panel Sealant - Double seal installed as per architect's direction |  | Double seal installed as per architect's direction (clearly mark double sealed area on elevation)
|  | Panel Sealant - Ensure drain slots are created the lowest point of panel 10mm dia |  | Ensure that drain slots are created the lowest point of panel 10mm dia
|  | Curtain Wall Steel Post - Post location correct |  | Post location correct
|  | Curtain Wall Steel Post - Post welding to cast in plate done properly |  | Post welding to cast in plate done properly
|  | Curtain Wall Steel Post - Steel fin straight & not bent |  | Steel fin straight and not bent
|  | Curtain Wall Steel Post - Bolts & nuts used as per detail |  | Bolts and nuts used as per detail
|  | Curtain Wall Steel Post - Minimum 20mm gap at top & joint of fin |  | Minimum 20mm gap at top and joint of the fin
|  | Curtain Wall Steel Post - Intumescent paint applied | Intumescent paint applied | Minimum 20mm gap at top and joint of the fin
|  | Curtain Wall Steel Post - Paint colour as per spec. |  | Paint colour as per specification
|  | Curtain Wall Steel Post - Paint undamaged |  | Paint undamaged
|  | Curtain Wall Steel Post - Protection around post installed | Protection around post is installed | Paint undamaged
|  | Curtain Wall Timber Framing - Set out from gridline correct |  | Set out from gridline correct
|  | Curtain Wall Timber Framing - Dimension of wall opening correct |  | Dimension of wall opening correct
|  | Curtain Wall Timber Framing - DPM installed where required |  | DPM installed where required
|  | Curtain Wall Timber Framing - Timber frames type as per spec. |  | Timber frames type as per specification
|  | Curtain Wall Timber Framing - Frame square & plumb |  | Frame square and plumb
|  | Curtain Wall Timber Framing - Council inspection done. Preline | Council inspection done. Preline | Frame square and plumb
|  | Curtain Wall Timber Framing - Board type (RAB) |  | Board type (RAB) as per drawing
|  | Curtain Wall Timber Framing - Fixing used as per spec. |  | Fixing used as per specification
|  | Curtain Wall Timber Framing - Fixing spacing & edge distance correct |  | Fixing spacing and edge distance correct
|  | Curtain Wall Timber Framing - Board no damage & in good condition |  | Board no damage and in good condition
|  | Curtain Wall Timber Framing - Council inspection done. Postline | Council inspection done. Postline | Board no damage and in good condition
|  | Curtain Wall System - Surface clean & free from dust/oil/grease/sealant |  | Surface clean and free from dust, oil, grease, sealant etc.. | Pre-installation. Waterproofing membrane
|  | Curtain Wall System - Sikalastic 152 applied before & after Sika Tape F |  | Sikalastic 152 applied before and after Sika Tape F. Continuous and 100mm up to the wall | Pre-installation. Waterproofing membrane
|  | Curtain Wall System - Sikaseal Tape F applied as per spec. |  | Sikaseal Tape F applied as per specification | Pre-installation. Waterproofing membrane
|  | Curtain Wall System - Dress at steel fin done in correct sequence |  | Dress at steel fin done in correct sequence | Pre-installation. Waterproofing membrane
|  | Curtain Wall System - Reveal shield applied with 150mm overlapping |  | Reveal shield applied with 150mm overlapping | Pre-installation. Waterproofing membrane
|  | Curtain Wall System - Liquiflash continuously applied & |  | Liquiflash continuously applied and as per drawing | Pre-installation. Waterproofing membrane
|  | Curtain Wall System - All checked & ready to proceed to next stage | All checked and ready to proceed to next stage | Liquiflash continuously applied and as per drawing | Pre-installation. Waterproofing membrane
|  | Curtain Wall System - Brackets type (aluminium/steel) used |  | Brackets type (aluminium/steel) used as per drawing. L0-L1 Aluminium. L2 Steel | Hanging Brackets
|  | Curtain Wall System - Bracket thickness & dimension |  | Bracket thickness and dimension as per drawing | Hanging Brackets
|  | Curtain Wall System - Bracket finish as per specified |  | Bracket finish as per specified (powdercoated/intumicent painted/galvanized painted, etc...) | Hanging Brackets
|  | Curtain Wall System - Washer size & type as per spec. |  | Washer size and type as per specification. | Hanging Brackets
|  | Curtain Wall System - Bolt fixing used as per spec. |  | Bolt fixing used as per specification. Size,embedment depth, edge distance checked | Hanging Brackets
|  | Curtain Wall System - All checked & ready to proceed to next stage | All checked and ready to proceed to next stage | Bolt fixing used as per specification. Size,embedment depth, edge distance checked | Hanging Brackets
|  | Curtain Wall System - Sill frame undamaged, straight & plumb |  | Sill frame undamaged, straight and plumb | Seismic frame installation
|  | Curtain Wall System - Sill frame screw fixing using Hilti HUS4 HR10x115 |  | Sill frame screw fixing using Hilti HUS4 HR10x115, 75mm each side of mullion. Oversealed | Seismic frame installation
|  | Curtain Wall System - Drainage slot 8x50mm size, 100mm from both ends |  | Drainage slot 8x50mm size, 100mm from both ends and each side of mullion | Seismic frame installation
|  | Curtain Wall System - End stops 100mm ht, fully sealed to structure |  | End stops 100mm ht, fully sealed to structure | Seismic frame installation
|  | Curtain Wall System - Jamb undamaged, straight & plumb |  | Jamb undamaged, straight and plumb | Seismic frame installation
|  | Curtain Wall System - Jamb screw using M6x30 SS/HUS HRS M6x70/12G screw to timber |  | Jamb screw using M6x30 SS to steel, HUS HRS M6x70 to conc, 12G screw to timber with 450mm C/C max | Seismic frame installation
|  | Curtain Wall System - Corner reinforcement as per detail |  | Corner reinforcement as per detail | Seismic frame installation
|  | Curtain Wall System - 20mm GAP between jamb frame & head channel |  | 20mm GAP between jamb frame and head channel | Seismic frame installation
|  | Curtain Wall System - Screws oversealed |  | Screws oversealed | Seismic frame installation
|  | Curtain Wall System - Head channel undamaged, straight & plumb |  | Head channel undamaged, straight and plumb | Seismic frame installation
|  | Curtain Wall System - Head channel fixed with M12 SS screws at 350 mm C/C min |  | Head channel fixed with M12 SS screws at 350 mm C/C min | Seismic frame installation
|  | Curtain Wall System - Screws oversealed |  | Screws oversealed | Seismic frame installation
|  | Curtain Wall System - Sikagard 52 is applied as per spec. |  | Sikagard 52 is applied as per specification | Seismic frame installation
|  | Curtain Wall System - All checked & ready to proceed to next stage | All checked and ready to proceed to next stage | Sikagard 52 is applied as per specification | Seismic frame installation
|  | Curtain Wall System - Sika primer 3N/aktivator 205 is applied before sealant |  | Sika primer 3N/aktivator 205 is applied before sealant | Sealant works
|  | Curtain Wall System - PEF rod correct size & in good location |  | PEF rod correct size and in good location | Sealant works
|  | Curtain Wall System - Gap 10mm +/-4 |  | Gap 10mm +/-4 | Sealant works
|  | Curtain Wall System - Continuous AT Façade applied all round air seal properly tooled |  | Continuous AT Façade applied all round air seal properly tooled | Sealant works
|  | Curtain Wall System - QA done ready for panel install | QA done ready for panel install | Continuous AT Façade applied all round air seal properly tooled | Sealant works
|  | Curtain Wall System - Panel frame free from dents, dings & scratches |  | Panel frame free from dents, dings and scratches | Curtain wall panel install
|  | Curtain Wall System - Glass undamaged & free from scratches |  | Glass undamaged and free from scratches | Curtain wall panel install
|  | Curtain Wall System - Gaskets & wedge in good condition |  | Gaskets and wedge in good condition | Curtain wall panel install
|  | Curtain Wall System - Wip holes unblocked |  | Wip holes unblocked | Curtain wall panel install
|  | Curtain Wall System - Gaps consistent to drawings |  | Gaps consistent to the drawings | Curtain wall panel install
|  | Curtain Wall System - Panels aligned & plumb |  | Panels aligned and plumb | Curtain wall panel install
|  | Curtain Wall System - Angle closer installed |  | Angle closer installed as per drawing | Curtain wall panel install
|  | Flashing QA - Flashing material & color as specified |  | Flashing material and color as specified
|  | Flashing QA - Flashing Type | Flashing Type | Flashing material and color as specified
|  | Flashing QA - Flashing height, depth, width |  | Flashing height, depth, width as per drawing
|  | Flashing QA - Flashing fixed with appropriate fixing type & cetre-centre spacing |  | Flashing fixed with appropriate fixing type and cetre-centre spacing
|  | Flashing QA - Flashing joints done with enough overlapping/soaker length |  | Flashing joints done with enough overlapping/soaker legth and as per drawing
|  | Flashing QA - Flashing cavity or space between structure/frame |  | Flashing cavity or space between structure/frame as per drawing
|  | Flashing QA - Screw oversealed if necessary |  | Screw oversealed if necessary
|  | Flashing QA - Enough fall |  | Enough fall
|  | Flashing QA - Staight & plumb |  | Staight and plumb
|  | Flashing QA - Upstand height |  | Upstand height as per drawing
|  | Flashing QA - Flashing tape applied as necessary |  | Flashing tape applied as necessary
|  | Flashing QA - No scartches, dents & any damages |  | No scartches, dents and any damages
|  | Flashing QA - Flashing protection installed |  | Flashing protection installed
|  | Doors - Door frames plumb & straight |  | Door frames plumb and straight
|  | Doors - Door size & opening |  | Door size and opening as per drawing
|  | Doors - Hinges, latches, knob, & other mechanical fixture in good condition |  | Hinges, latches, knob, and other mechanical fixture in good condition
|  | Doors - Motors/door closer working properly |  | Motors/door closer working properly
|  | Doors - If fire door, sealant applied as per spec. |  | If fire door, sealant applied as per speficied
|  | Doors - Sealant along frames correct size & thickness |  | Sealant along frames correct size and thickness
|  | Doors - Correct sealant on PEF rod |  | Correct sealant on PEF rod
|  | Doors - Door protection installed |  | Door protection installed
|  | Punch Windows - Precast concrete surface no damage |  | Precast concrete surface no damage
|  | Punch Windows - Precast concrete face free from oil/grease/dirt |  | Precast concrete face free from oil, grease, dirt etc
|  | Punch Windows - Gap 10mm +/-4 between structure & frame |  | Gap 10mm +/-4 between structure and frame
|  | Punch Windows - Frame endstops & corners properly sealed |  | Frame endstops and corners properly sealed
|  | Punch Windows - Appropriate PEF rod installed continuously |  | Appropriate PEF rod installed continuously
|  | Punch Windows - Sikalastic 152 applied on the opening all round |  | Sikalastic 152 applied on the opening all round
|  | Punch Windows - Sikaseal Tape F applied as per specification all round |  | Sikaseal Tape F applied as per specification all round
|  | Punch Windows - Fixing HUS4-HR6x70mm @ 350 ctrs. Min 55 embedment |  | Fixing HUS4-HR6x70mm @ 350 ctrs. Min 55 embedment
|  | Punch Windows - Fixing oversealed |  | Fixing oversealed
|  | Punch Windows - HDPE packers installed the right way |  | HDPE packers installed the right way
|  | Punch Windows - Continues sealant on backing rod properly tooled |  | Continues sealant on backing rod properly tooled
|  | Punch Windows - Wip holes cleared & unobstructed |  | Wip holes cleared and unobstructed
|  | Punch Windows - Wedge & gasket properly mounted |  | Wedge and gasket properly mounted
|  | Punch Windows - Glass & frame free of scratches |  | Glass and frame free of scratches
|  | Punch Windows - Angle closer size correct & offset 6mm from frame |  | Angle closer size correct and offset 6mm from frame
|  | Punch Windows - Window protection installed |  | Window protection installed
|  | Seismic Gap DM - Concrete haunching done on floor slab with slop to outside slab |  | Concrete haunching done on the floor slab with slop to outside slab
|  | Seismic Gap DM - Vapour barrier fixed from top to bottom without damage |  | Vapour barrier fixed from top to bottom without damage
|  | Seismic Gap DM - DMS framing fixed to concrete wall straight & plumb |  | DMS framing fixed to concrete wall straight and plumb and in good condition
|  | Seismic Gap DM - Conc-conc joint +/- 150mm |  | Conc-conc joint +/- 150mm
|  | Seismic Gap DM - Frame-frame gap +/- 127mm centred to concrete gap |  | Frame-frame gap +/- 127mm centred to the concrete gap fix with screw at 450mm c/c, 150mm start and end
|  | Seismic Gap DM - Center plate/cover plate surface finish as per spec. |  | Center plate/ cover plate surface finish as per specification (PC Dulux Gunmetal Kinetic Matt)
|  | Seismic Gap DM - Center plate/cover plate resting firmly against gasket of framing |  | Center plate/ cover plate resting firmly against the gasket of the framing
|  | Seismic Gap DM - Center plate screw tight & secured to centering bar |  | Center plate screw tight and secured to centering bar: Cover against the concrete structure
|  | Seismic Gap IBS - Joint is clean, uniform gap 100mm, dry & undamaged |  | Joint is clean, uniform gap 100mm, dry and undamaged
|  | Seismic Gap IBS - Silicon adhesive is applied both sides |  | Silicon adhesive is applied both sides
|  | Seismic Gap IBS - Correct type of precompressed sealant used. (IBS 100) |  | Correct type of precompressed sealant used. (IBS 100) check depth and width
|  | Seismic Gap IBS - Precompressed sealant run through without gap & enough offset |  | Precompressed sealant run through without gap and enough offset to avoid clashes to DM Series framing
|  | Seismic Gap IBS - Joint cut square/mitered, no gap & applied with silicon adhesive |  | Joint cut square/mitered, no gap and applied with silicon adhesive
|  | Seismic Gap IBS - Sealant applied continuously & tooled properly |  | Sealant applied continuously and tooled properly
|  | Sika 740W Spray on Paint - Surface free of dust, oil, efflorescence & paint coatings |  | Surface free of dust, oil, efflorescence and paint coatings
|  | Sika 740W Spray on Paint - Damage of concrete if any, have been patched |  | Damage of concrete if any, have been patched
|  | Sika 740W Spray on Paint - Consultant/Client Inspection | Consultant/Client Inspection | Damage of concrete if any, have been patched
|  | Sika 740W Spray on Paint - Surface is dry & no damp patches |  | Surface is dry and no damp patches
|  | Sika 740W Spray on Paint - Windows & curtain wall installed & well protected |  | Windows and curtain wall installed and well protected especially along the sealant area
|  | Sika 740W Spray on Paint - 2-3 coats applied wet-wet bottom-up |  | 2-3 coats applied wet-wet bottom-up without letting the product run into the surface
|  | Sika 740W Spray on Paint - Area protected from rain for at least 6 hours |  | Area is protected from rain for at least 6 hours
Roof - Detailed Progress
| Scope |  |  | Atlas | Roof
Rows
|  | Office | grouping | Office
|  | Office Nuraply Roof |  | Atlas | Building | Envelope | Roof | Office Nuraply Roof
|  | Office Grid 8 Cap Flashing |  | Atlas | Building | Envelope | Roof | Office Grid 8 Cap Flashing
|  | Office Roof Skylight |  | Atlas | Building | Envelope | Roof | Office Roof Skylight
|  | Warehouse Metal Roof |  | Atlas | Building | Envelope | Roof | Warehouse Metal Roof
|  | Terrace to Warehouse Nuraply Roof | dynamic | Atlas | Building | Envelope | Roof | Terrace to Warehouse Nuraply Roof
|  | Facia Plate | dynamic | Atlas | Building | Envelope | Roof | Facia Plate
|  | Nuwall Soffit Lining | grouping | Nuwall Soffit Lining
|  | Grid B Soffit (Office) |  | Atlas | Building | Envelope | Roof | Nuwall Soffit Lining | Grid B Soffit (Office)
|  | Grid H Soffit (Office) |  | Atlas | Building | Envelope | Roof | Nuwall Soffit Lining | Grid H Soffit (Office)
|  | Grid J Soffit (Office) |  | Atlas | Building | Envelope | Roof | Nuwall Soffit Lining | Grid J Soffit (Office)
|  | Grid I Soffit (Office) |  | Atlas | Building | Envelope | Roof | Nuwall Soffit Lining | Grid I Soffit (Office)
|  | Grid 5 Soffit (Office) |  | Atlas | Building | Envelope | Roof | Nuwall Soffit Lining | Grid 5 Soffit (Office)
|  | Nuwall Soffit Lining - Terrace to Warehouse Soffit | dynamic | Atlas | Building | Envelope | Roof | Nuwall Soffit Lining | Terrace to Warehouse Soffit
|  | Canopy | dynamic | Atlas | Building | Envelope | Roof | Canopy
Columns
|  | Covertek 403 separation layer to purlin structure & cavity battens |  | Covertek 403 separation layer to purlin structure and cavity battens
|  | 20mm H3.2 castellated cavity battens installed before plywood |  | 20mm H3.2 castellated cavity battens installed before plywood
|  | Nog support timber framing at C purlin level at 600x600 spacing |  | Nog support timber framing at C purlin level at 600x600 spacing
|  | 17mm thick H3.2 waterborne CCA treated plywood fixed with 10x50 countersunk screw head |  | 17mm thick H3.2 waterborne CCA treated plywood fixed with 10x50 countersunk screw head
|  | Plywood used is non LOSP (light organic solvent preservative) or copper nitrate treated |  | Plywood used is non LOSP (light organic solvent preservative) or copper nitrate treated
|  | Screw 150mm c/c at edge & 200mm c/c at body of sheets |  | Screw 150mm c/c at edge and 200mm c/c at body of sheets
|  | Internal corners with 25mm fillet, external corners with 5mm radius |  | Internal corners with 25mm fillet, external corners with 5mm radius.
|  | Timber plinth SG8 H3.2 100x50 timber layout |  | Timber plinth SG8 H3.2 100x50 timber layout as per drawing
|  | Timber plinth screw head countersunk Hex 14G M10x150 tek fixed at 600mm c/c |  | Timber plinth screw head countersunk Hex 14G M10x150 tek fixed at 600mm c/c
|  | Timber plinth with 45 degree timber fillet at corners |  | Timber plinth with 45 degree timber fillet at corners
|  | 90mm Ht Timber diverter installed |  | 90mm Ht Timber diverter installed
|  | Conduit penetration to roof, location checked |  | Conduit penetration to roof, location checked as per drawing
|  | Enough fall to drain |  | Enough fall to drain
|  | Gutter & sump area done |  | Gutter and sump area done as per drawing
|  | No sharp object & all nail head flush to the plywood face |  | No sharp object and all nail head flush to the plywood face
|  | All checked & ready to proceed to next stage | All checked and ready to proceed to next stage | No sharp object and all nail head flush to the plywood face
|  | All surface is clean/dry/free from sharp edges/oil/grease |  | All surface is clean, dry, free from sharp edges, oil, grease or other materials that my affect adhesion
|  | Worker is approved applicator to do the job |  | Worker is approved applicator to do the job
|  | Nuralite Nuraply 3PM double layer torch on system installed continuously |  | Nuralite Nuraply 3PM double layer torch on system installed continuously
|  | No visible cracks/holes/damages into membrane |  | No visible cracks, holes, damages into the membrane
|  | Joint overlapping fully welded |  | Joint overlapping fully welded
|  | Nuraglaze sealer is applied to portion of roof as shown in architectural drawing |  | Nuraglaze sealer is applied to portion of roof as shown in the architectural drawing
|  | Sheets fully adhered to plywood |  | Sheets fully adhered to plywood
|  | Double thickness application at all internal & external corner |  | Double thickness application at all internal and external corner
|  | Conduit penetration done with ring clamp |  | Conduit penetration done with ring clamp
|  | All penetration done properly |  | All penetration done properly
|  | Flashing material & color as specified |  | Flashing material and color as specified
|  | Flashing Type | Flashing Type | Flashing material and color as specified
|  | Flashing height/depth/width |  | Flashing height, depth, width as per drawing
|  | Flashing fixed with appropriate fixing type & cetre-centre spacing |  | Flashing fixed with appropriate fixing type and cetre-centre spacing
|  | Flashing joints done with enough overlapping/soaker length |  | Flashing joints done with enough overlapping/soaker legth and as per drawing
|  | Flashing cavity or space between structure/frame |  | Flashing cavity or space between structure/frame as per drawing
|  | Screw oversealed |  | Screw oversealed if necessary
|  | Enough fall |  | Enough fall
|  | Staight & plumb |  | Staight and plumb
|  | Upstand height |  | Upstand height as per drawing
|  | Flashing tape applied |  | Flashing tape applied as necessary
|  | No scartches, dents & any damages |  | No scartches, dents and any damages
|  | Flashing protection installed |  | Flashing protection installed
|  | Waterproofing QA done before start |  | Waterproofing QA done before start
|  | Slop of the nib to create 7 degree to glass skylight |  | Slop of the nib to create 7 degree to glass skylight
|  | Powder coated aluminium flashing installed at edge of nib |  | Powder coated aluminium flashing installed at the edge of the nib
|  | Under-flashing/Framing sealed to roof membrane with Soudal Gorilla sealant on backing rod |  | Under-flashing/Framing sealed to the roof membrane with Soudal Gorilla sealant on backing rod. Min 6mm gap
|  | Under-flashing/Framing powder coated with Duratek eternity range: Gun metallic kinetic matt |  | Under-flashing/Framing powder coated with Duratek eternity range: Gun metallic kinetic matt
|  | Cover flashing fixed with 2x6mm EPDM compressed washers to form 6mm gap at fixing |  | Cover flashing fixed with 2x6mm EPDM compressed washers to form 6mm gap at fixing.
|  | Fixing as per spec. |  | Fixing as per specification
|  | Glass type in accordance to the spec. |  | Glass type in accordance to the specification
|  | Glass clean & free from scratch/chips/damage |  | Glass clean, and free from scratch, chips or any damage
|  | Pipe penetration done with ring clamp |  | Pipe penetration done with ring clamp
|  | 5mm powder coated aluminium scupper rebated to ply at seismic gap fix to 1 end only |  | 5mm powder coated aluminium scupper rebated to ply at seismic gap fix to 1 end only
|  | Nuradeck bandage flashing with 50mm overlap to 3PM at scupper |  | Nuradeck bandage flashing with 50mm overlap to 3PM at scupper
|  | Membrane dressed over seismic end cap at 70mm min |  | Membrane dressed over seismic end cap at 70mm min
|  | Waterproofing QA done bafore start work |  | Waterproofing QA done bafore start work
|  | Plate using 6mm 5052 aluminium powder coated plate with countersunk fixing |  | Plate using 6mm 5052 aluminium powder coated plate with countersunk fixing
|  | Powdercoated Dulux eternity metro silver pearl kinetic |  | Powdercoated Dulux eternity metro silver pearl kinetic
|  | Max edge distance 100mm of fixing |  | Max edge distance 100mm of fixing
|  | 10mm gap at joints with 150mm joint at seismic gap |  | 10mm gap at joints with 150mm joint at seismic gap
|  | Fixing 2x 10g countersunk s/s screws with 75mm embedment at 600mm c/c spacing |  | Fixing 2x 10g countersunk s/s screws with 75mm embedment at 600mm c/c spacing
|  | Plate spaced of structure with 2 50x50x6 SS washer with 6mm EPDM washer maintaining 12mm min clear gap |  | Plate spaced of structure with 2 50x50x6 SS washer with 6mm EPDM washer maintaining 12mm min clear gap
|  | Normal length 2.4m per sheet |  | Normal length 2.4m per sheet
|  | Facia overall depth covers all of facia structure |  | Facia overall depth covers all of facia structure
|  | Facia align to each other |  | Facia align to each other
|  | No scratches, dents or damages |  | No scratches, dents or damages
|  | Timber framing using 90x45 SG8 with 600 C/C spacing |  | Timber framing using 90x45 SG8 with 600 C/C spacing
|  | Council inspection done. Preline | Council inspection done. Preline | Timber framing using 90x45 SG8 with 600 C/C spacing
|  | RAB exposed cut edge to be primed |  | RAB exposed cut edge to be primed
|  | 2-4mm gap in between joints |  | 2-4mm gap in between joints
|  | Nail with 12mm edge distance & 200mm c/c minimum spacing |  | Nail with 12mm edge distance and 200mm c/c minimum spacing
|  | Nail flush with board surface |  | Nail flush with board surface
|  | RAB Joints & corner sealed with 75mm wide tape |  | RAB Joints and corner sealed with 75mm wide tape
|  | RAB free of dust/oil/grease |  | RAB free of dust, oil, grease, etc
|  | Council inspection done. Postline | Council inspection done. Postline | RAB free of dust, oil, grease, etc
|  | Flashings needed installed before batten |  | Flashings needed installed before batten if required
|  | 20mm H3.2 castellated cavity batten at 600 c/c spacing. Castellation againts RAB |  | 20mm H3.2 castellated cavity batten at 600 c/c spacing. Castellation againts RAB
|  | Castellated cavity batten fixed to timber frame with 40x12mm SS flat head nail 800 c/c |  | Castellated cavity batten fixed to timber frame with 40x12mm SS flat head nail 800 c/c
|  | Nuwall type & colour as specified. Mono 200 with Dulux eternity metro silver pearl kinetic |  | Nuwall type and colour as specified. Mono 200 with Dulux eternity metro silver pearl kinetic
|  | Orientation |  | Orientation as per drawing
|  | 10g SS fixing screw with 30mm min embedment to timber structure |  | 10g SS fixing screw with 30mm min embedment to timber structure
|  | Isolator strip to underside of all castellated soffit battens by Nuwall |  | Isolator strip to underside of all castellated soffit battens by Nuwall
|  | End Cap installed at all edges p.c. to match soffit |  | End Cap installed at all edges p.c. to match soffit
|  | Soffit Lining free from scratches/dents/damages |  | Soffit Lining free from scratches, dents and damages.
|  | Steel structure is painted & handed over before start work |  | Steel structure is painted and handed over before start work
|  | SS gutter weld continues & without hole/dent/crack |  | SS gutter weld continues and without hole, dent or crack
|  | SS gutter & sump fall about 1:100 |  | SS gutter and sump fall about 1:100
|  | SS bracket at 600 C/C. Fixed to cladding with neoprene compressed washer with 12mm gap to cladding |  | SS bracket at 600 C/C. Fixed to cladding with neoprene compressed washer with 12mm gap to cladding
|  | Diverter flashing over terrace column installed |  | Diverter flashing over terrace column installed as per drawing
|  | Spider fixing installed per shop drawing & without damage |  | Spider fixing installed per shop drawing and without damage
|  | Glass using 21.52 toughened laminated safety glass with 115 clearance at structure |  | Glass using 21.52 toughened laminated safety glass with 115 clearance at structure
|  | Glass with anti-reflective frit |  | Glass with anti-reflective frit as per drawing
|  | Glass overhung about 200mm from spider fixing |  | Glass overhung about 200mm from the spider fixing
|  | Glass edge |  | Glass edge as per drawing
|  | Joint sealant done with correct type & properly tooled |  | Joint sealant done with the correct type and properly tooled
|  | Drip angle installed at lower edge |  | Drip angle installed at the the lower edge
|  | 50x50 aluminium box powder coated with Dulux Eternity Metro Silver Pearl Kinetic |  | 50x50 aluminium box powder coated with Dulux Eternity Metro Silver Pearl Kinetic
|  | Spacing |  | Spacing as per drawing
|  | Alignment |  | Alignment as per drawing
|  | Batten adequately fixed & no damage |  | Batten adequately fixed and no damage
Terrace - Detailed Progress
| Scope |  |  | Atlas | Terrace
Rows
|  | Green Roof Waterproofing | dynamic | Atlas | Building | Envelope | Terrace | Green Roof Waterproofing
|  | Terrace Easylap Cladding | dynamic | Atlas | Building | Envelope | Terrace | Terrace Easylap Cladding
|  | Terrace Tiled Flooring | dynamic | Atlas | Building | Envelope | Terrace | Terrace Tiled Flooring
|  | Terrace Glass Balustrade | dynamic | Atlas | Building | Envelope | Terrace | Terrace Glass Balustrade
Columns
|  | All surface is clean/dry/free from sharp edges/oil/grease |  | All surface is clean, dry, free from sharp edges, oil, grease or other materials that my affect adhesion
|  | Nuralite bitumen LM fillet at internal corners |  | Nuralite bitumen LM fillet at internal corners
|  | 5mm fillet radius at external corners |  | 5mm fillet radius at external corners
|  | Worker approved applicator to do job |  | Worker is approved applicator to do the job
|  | Nuralite Nuraflux primer installed continuously to cover whole area |  | Nuralite Nuraflux primer installed continuously to cover whole area
|  | Nuraply 3PB-SA installed continuously without damage |  | Nuraply 3PB-SA installed continuously without any damage
|  | Nuraply 3PB membrane installed continuously without damage |  | Nuraply 3PB membrane installed continuously without any damage installed in accordance to specification
|  | Nuralite aluminium tape to separate sealant & membrane |  | Nuralite aluminium tape to separate sealant and membrane
|  | Nuraply base sheet reinforcing strip on primer installed at precast joint |  | Nuraply base sheet reinforcing strip on primer installed at precast joint
|  | Termination bar mechanically fixed as per manual |  | Termination bar mechanically fixed as per manufacturers manual
|  | No visible cracks/holes/damages into membrane |  | No visible cracks, holes, damages into the membrane
|  | Joint overlapping fully welded |  | Joint overlapping fully welded
|  | Double thickness application at all internal & external corner |  | Double thickness application at all internal and external corner
|  | Pipe penetration done with ring clamp |  | Pipe penetration done with ring clamp
|  | All penetration done properly |  | All penetration done properly
|  | Timber framing using 90x45 SG8 with 600 C/C spacing |  | Timber framing using 90x45 SG8 with 600 C/C spacing
|  | Wall Therman Insulation R2.9 140mm Greenstuff thermal blanket fitted into wall |  | Wall Therman Insulation R2.9 140mm Greenstuff thermal blanket fitted into wall
|  | Council inspection done. Preline |  | Council inspection done. Preline
|  | RAB exposed cut edge to be primed |  | RAB exposed cut edge to be primed
|  | 2-4mm gap in between joints |  | 2-4mm gap in between joints
|  | Nail with 12mm edge distance & 200mm c/c minimum spacing |  | Nail with 12mm edge distance and 200mm c/c minimum spacing
|  | Nail flush with board surface |  | Nail flush with board surface
|  | RAB free of dust/oil/grease |  | RAB free of dust, oil, grease, etc
|  | Steel plate dressed properly with aluminium saddle flashing with continuous sealant to plate |  | Steel plate dressed properly with aluminium saddle flashing with continuous sealant to plate
|  | Council inspection done. Postline |  | Council inspection done. Postline
|  | Revealshield done as per spec. |  | Revealshield done as per specification
|  | Curtain wall head flashing installed in good condition |  | Curtain wall head flashing installed in good condition
|  | JH PVC vent strip installed at bottom with 600mm c/c max |  | JH PVC vent strip installed at the bottom with 600mm c/c max
|  | Cavity batten fixed at 600 c/c apart with 250mm c/c nail fixing to structure |  | Cavity batten fixed at 600 c/c apart with 250mm c/c nail fixing to the structure
|  | Easylap edges is sealed |  | Easylap edges is sealed
|  | 11 FC sealant applied at cavity batten before Easylap panel installed |  | 11 FC sealant is applied at the cavity batten before the Easylap panel is installed
|  | Panel is fixed with SS fixing at 150mm C/C flush to face |  | Panel is fixed with SS fixing at 150mm C/C flush to the face
|  | Painted as per spec. |  | Painted as per specification
|  | Surface screed slop to drain as per drawing |  | Surface screed slop to drain as per drawing
|  | Nuralite Nuraply 3PM double layer torch on system installed continuously |  | Nuralite Nuraply 3PM double layer torch on system installed continuously
|  | Sheets fully adhered to surface |  | Sheets fully adhered to surface
|  | Nurajack start T installed as per manual |  | Nurajack start T installed as per manufacturers manual
|  | Nurajck levellers installed as per manual |  | Nurajck levellers installed as per manufacturers manual
|  | Nurapoxy tg applied at raised concrete when necessary |  | Nurapoxy tg applied at raised concrete when necessary
|  | Outdure Qwickbuild aluminium support frame system installed on top of nurajack |  | Outdure Qwickbuild aluminium support frame system installed on top of nurajack
|  | Selected R11 non-slip 302x604x20 think porcelain tile installed, level & without damage |  | Selected R11 non-slip 302x604x20 think porcelain tile installed, level and without damage
|  | Concrete nib straight with no damage |  | Concrete nib straight with no damage
|  | Hilti HIT-HY200 + HIT V-R M10 Grade 316 SS anchor fixing @ 200 c/c & 160 embedment |  | Hilti HIT-HY200 + HIT V-R M10 Grade 316 SS anchor fixing @ 200 c/c and 160 embedment
|  | 1st Anchor placed at 120mm from edge of concrete |  | 1st Anchor placed at 120mm from edge of the concrete
|  | Continuous solid aluminium packer installed before between con structure & glass bottom support |  | Continuous solid aluminium packer installed before between con structure and glass bottom support
|  | 2mm Powdercoated capping to concrete nib done |  | 2mm Powdercoated capping to concrete nib done as per drawing
|  | Base powder coating dulux eternity metro silver pearl kinetic |  | Base powder coating dulux eternity metro silver pearl kinetic
|  | Glass using 21.52mm safety sentry glass by Metroglass |  | Glass using 21.52mm safety sentry glass by Metroglass
|  | Glass ht 1100-1150mm to top of nib |  | Glass ht 1100-1150mm to the top of the nib
|  | Glass is straight & plumb |  | Glass is straight and plumb
|  | Glass protection installed |  | Glass protection installed
|  | 125x100x75 10tk Bottom plate rebated into precast concrete |  | 125x100x75 10tk Bottom plate rebated into precast concrete
|  | 50x25mm metal post balustade plumb & straight |  | 50x25mm metal post balustade plumb and straight
|  | 50mm metal handrail installed at 900mm ht |  | 50mm metal handrail installed at 900mm ht
|  | Spider fixing secured & no damage |  | Spider fixing secured and no damage
|  | 10mm balustrade glass installed as per layout & with 1100mm ht |  | 10mm balustrade glass installed as per layout and with 1100mm ht
|  | Handrail & glass gap at 50mm |  | Handrail and glass gap at 50mm
|  | Glass free from scratch/chips/damages |  | Glass free from scratch, chips or any damages