## Resources
Type | Id | Name | Values | Prompting Name | Resource Id
checklist |  | ITP - STRUCTURAL REHAB INSPECTION TESTING PLAN Rev 1 | itp | ITP - STRUCTURAL REHAB INSPECTION TESTING PLAN | 64b9fb2f-3676-48de-be09-f1da5daacd78
section |  | Subgrade
checkpoint |  | 1.01 - Field
note | 83dd20eb-d88d-5cca-9a26-1a35b7431106 | Material Test Method Requirement - Scala Penetrometer Cohesive soils only
note | d7fec1b2-f63c-5e24-9998-ea9d6ae9de08 | Reference Documents - RITS Table 3-20
note | e5b0912b-5edc-5154-88df-2fa571823835 | Material Acceptance Criteria (Method) - NZS 4402.6.5.2:1988
note | e380152b-ceac-52ee-ae96-d321f79e7ade | Material Test Frequency - 1m inside of edge of seal, on alternating lanes, at 10m spacing (no greater than 20m between tests)
note | abf12906-d37d-509d-a431-21cce82c1c23 | ○ Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater
note | 68729cd6-be26-5338-88ef-5a04f650121c | Target Criteria - Confirm design assumptions - Scalar reaches minimum 7 blows/300mm
note | c86ddecf-f3b4-59de-8f8f-351c88d00dfd | Action Point Records Required - Test Record
note | d7640c3d-951b-57cd-9b88-61d72038490a | Responsibility - QA / SE / PE
checkpoint |  | 1.02 - Field
note | 1e7ab05a-46d4-5e56-b438-b269b7bd0459 | Material Test Method Requirement - Clegg Hammer Aggregate fill only where subgrade undercut or trench backfilled
note | ad2aaad3-fbbb-564f-91fd-de2629bd00ee | Reference Documents - RITS Table 3-21
note | ea6e231b-43a3-5a38-b5cf-4be7d15b2bd1 | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
note | a4bbaed3-50c5-584a-a5d2-ee34e01189b7 | Material Test Frequency - In centre of undercut or trench Minimum of 1 test per undercut location
note | bb70b9eb-38c3-56df-a4ee-6bf5ce5976d1 | Target Criteria - CIV ≥ 15 or CBR of 20
note | 437eaf52-9bda-5f41-a800-1ebd36ddeb0a | Action Point Records Required - Test Record
note | e89d3361-c686-5036-8991-900d78d9f0d3 | Responsibility - QA / SE / PE
checkpoint |  | 1.03 - Field
note | fb7bf29d-3d8f-5073-b0ac-181540de1c68 | Material Test Method Requirement - Surface Level, Shape, and crossfall
note | 9a72360e-2450-5c09-b14b-bf2ee2c19f66 | Reference Documents - RITS Table 3.24
note | a346496c-67ec-5614-9c7f-d370a061e9e7 | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
note | f8ffc8e8-f876-5da1-86c8-d565f14c9f44 | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
note | a8548cc7-00f5-56d5-a3c9-1f8025d4dedd | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
note | 72a0244b-d623-5155-a787-914fd3e43318 | Target Criteria - +0mm/-30m from design or nominated level
note | db47f28f-5779-575a-a33b-bae4b67b3521 | ○ No more than 15mm deviation from a 3m straight edge
note | 4a3524e2-3cb9-522c-a11c-32c5f8785e45 | Action Point Records Required - Survey record
note | 610a7e85-942a-52c4-8bcc-2834b66f993c | Responsibility - QA / SE / PE
checkpoint |  | 1.04 - Field
note | 6444c82e-1657-557b-88ab-66a6e1d6ffc1 | Material Test Method Requirement - Tenser Triaxial Geogrid and Geofabric (cloth) installation
note | 7978ee5c-6ee8-56ab-83f0-caf5a7d963a1 | Reference Documents - Tensar construction sequence CS_TriAx/30.04.08
note | fd9f1c38-95da-5f6d-98d2-12c75f68d1ce | Material Acceptance Criteria (Method) - Manufacturer installation instructions
note | d3e620fd-5d77-52c0-b69d-7bb2cdcee57f | Material Test Frequency - 100% of Surface
note | f01ad8fe-8dc1-5c8d-8deb-26de06319f86 | Target Criteria - Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints.
note | 31ceeba8-10d4-5e46-8f7d-41dafd03f9b0 | ○ Geogrid and Geofabric shall be neatly installed without creases or folds.
note | b78c8054-5e6b-5d39-a602-389f4f282c92 | Action Point Records Required - Site Record
note | e925d51a-78b1-5df3-98ab-90f1955232cd | Responsibility - QA / SE / PE
checkpoint |  | 1.05 - PQE
note | 408513dd-2693-5790-a61d-dcf6509e556b | Material Test Method Requirement - Is the layer closed out?
note | f7336156-6d4a-5792-9e3b-129e604eac8f | Reference Documents - See PQE
note | 0944a583-edc0-5cd6-abe1-9f1a84420820 | Material Acceptance Criteria (Method) - See PQE
note | b0a9b218-b9d7-5b6f-be3c-be7f8488b99c | Material Test Frequency - 100% of Surface Prior to placement of material
note | 9124b237-6f47-503f-9eb1-dafba5559857 | Target Criteria - PQE Approval
note | 52049364-bb1c-55a3-b523-149984b67a51 | ○ All testing record & reviewed as compliant.
note | f87bf984-58a5-5184-8106-a241a59d6a82 | Available Documents:
note | b92cb638-5127-5d06-8646-7a99c00176a8 | ○ Test records
note | db124d70-023c-5a2f-9ce7-6cc815bee769 | ○ Survey records
note | 868007fc-6be4-5abb-a731-be1eaf06e4c4 | ○ Hold Point Records
note | a3d3c43b-578f-520e-ad2f-2936889bb82a | Action Point Records Required - Hold Point
note | 4b208ca8-f3ba-5c31-aeab-3a1872cf2a1d | Responsibility - SE / PE / PM / PQE
signoff |  | AUTHORITY HOLDPOINT
section |  | Subbase
checkpoint |  | 2.01 - PQE
note | f39b84ed-d56f-5475-a326-5e23ebc854d3 | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
note | e702bd3c-a3a3-5a0b-a4dd-3e245aade11c | Reference Documents - Insert Material Testing link
note | 78b0dfa0-085d-5569-935d-1aa8969be135 | Material Acceptance Criteria (Method) - See PQE
note | 8dddd834-3b81-5445-a90c-148e96e09b56 | Material Test Frequency - Prior to construction commencing
note | 17942e98-3028-5ecd-a4d0-38a609180a16 | Target Criteria - Material meets project requirements
note | 0f735402-85b2-52c5-8280-d16bc2334a09 | Action Point Records Required - Hold Point
note | be997440-b8ce-5977-a737-94efe7da529e | Responsibility - SE / PE / PM / PQE
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 2.02 - Field
note | fe437cb5-0b5a-5a37-b7b7-9a267eb20d2c | Material Test Method Requirement - Plateau Density Test
note | 3d9bff9f-9010-54d7-bec0-624af08eb4a2 | Reference Documents - TNZ B/02: 2005
note | 3449acb9-02c4-5a7f-a146-53f9e00fef23 | Material Acceptance Criteria (Method) - TNZ B/02: 2005
note | ce739100-9655-57a8-b730-d2b7f4531e90 | Material Test Frequency - Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing Target to be approved by Engineer
note | d6d44070-a443-5b0b-8aa6-e317b881501f | Target Criteria - N/A
note | 95e47d95-37c4-5dc8-ba72-7616f35dcb7f | Action Point Records Required - Hold Point, Test Record
note | e47a4c89-8ab4-5479-9b07-bb03869cc768 | Responsibility - SE / PE / PM / PQE
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 2.03 - Field
note | c4bba904-07bd-59a3-ac20-85c0d8278e40 | Material Test Method Requirement - Clegg Hammer
note | 6da8dbcd-ed8e-5dde-b491-73be485d9ff4 | Reference Documents - RITS Table 3-21
note | ba3182e0-5157-5673-8706-cc632b9c02dd | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
note | 7a1dfb6c-0e29-5423-a00d-08160a86abad | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
note | 858ba4ec-090d-57da-be04-b66dd6e43476 | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
note | 0a49bce7-8f56-535d-850e-a5f7de783c1e | Target Criteria - CIV ≥ 25
note | 5c4ef9b8-36dd-5150-826b-e204b9b9ea0d | Action Point Records Required - Test Record
note | 530775b3-4e90-500c-9542-787bccfea5e5 | Responsibility - QA / SE / PE
checkpoint |  | 2.04 - Field
note | 8ac03dbd-dd94-553b-923d-b85bf8c241e8 | Material Test Method Requirement - Compaction NDM Back Scatter
note | bec9dc1a-98ae-5530-a3c2-354391ae8015 | Reference Documents - RITS Table 3-22
note | 1cd50b59-3351-56bc-8459-ac8528cce809 | Material Acceptance Criteria (Method) - RITS 3.8.3.4, 4407:2015 test 4.3
note | 208c94ab-7af2-55f9-8534-f6b900d5cf7e | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
note | a5f04211-0bf8-5093-be97-9bcb5fab281d | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
note | ec4c4467-690d-51d7-9d46-425badbd717d | Target Criteria - Mean ≥ 95 % MDD
note | 52e62f4d-d4bb-53ec-86d5-1a0e278e077f | ○ Minimum ≥ 92% MDD
note | ad0ed00f-e8cf-5f6b-93a0-133b395c4b2d | Action Point Records Required - Test Record
note | de6b53b2-6d82-5f8a-8f02-219a0a289723 | Responsibility - QA / SE / PE
checkpoint |  | 2.05 - Field
note | 43ef66f2-04c7-5e07-8d51-aa30dff9ee04 | Material Test Method Requirement - Surface Level, Shape, and crossfall
note | 42629ad7-f119-55b8-baef-4bb2dcf9a383 | Reference Documents - RITS Table 3.24
note | 69ac5100-6b33-5127-90a9-436723342f43 | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
note | eb3c0327-f1d9-5a04-b7be-aeef70c041d9 | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
note | fc87979f-ca9b-54fe-9463-8c5e76009e2d | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
note | 0a6bb718-2046-54c7-98c1-04114e2e2a33 | Target Criteria - +5mm/-25m from design or nominated level
note | 2dcf72a5-da0c-5e00-b9fb-065d32019736 | ○ No more than 15mm deviation from a 3m straight edge
note | 596d7d2b-a181-58f1-9868-4e6692fdd5a3 | Action Point Records Required - Survey record
note | 7d8c89f6-f8ee-5ef8-a8a9-c6cd0c614b86 | Responsibility - QA / SE / PE
checkpoint |  | 2.06 - PQE
note | 6ff6404e-794d-5cb9-9894-6b15acf7a1f2 | Material Test Method Requirement - Is the layer closed out?
note | e6ed3098-2650-590e-aa69-3bb91f5b40f3 | Reference Documents - See PQE
note | cd0f387c-77c0-5652-8b38-c9bb4f84ce31 | Material Acceptance Criteria (Method) - See PQE
note | d91a534f-f662-5ce7-998c-13b769171479 | Material Test Frequency - 100% of Surface Prior to placement of material
note | a0aaad04-9ed2-5676-b639-67ec2e24d7f0 | Target Criteria - PQE Approval
note | a123d0cb-291c-5f8a-a417-1df986637bcb | ○ All testing record & reviewed as compliant.
note | fdf8007a-2095-5391-bb96-0d7095d96357 | Available Documents:
note | 488f7cb5-e622-5db2-b3f2-07c60d3df7df | ○ Test records
note | 6141ee7e-9b0d-517c-ad6c-36fd1a1f271d | ○ Survey records
note | 0f3ddd01-c70e-5945-8bc3-e30c9c1cf5d0 | ○ Hold Point Records
note | 7f82ec50-4ba2-5483-acbf-5b5b7853aa1d | Action Point Records Required - Hold Point
note | 44fe665e-5f8e-5478-bd79-b6e95d087157 | Responsibility - SE / PE / PM / PQE
signoff |  | AUTHORITY HOLDPOINT
section |  | Membrane or First Coat Seal
checkpoint |  | 3.01 - PQE.
note | 829f6a4b-86db-5a27-af40-eea65ee117f1 | Material Test Method Requirement - Seal Design
note | 9ed8ad2d-8ee5-5283-9cbe-8fc77093f601 | Reference Documents - INSERT SEAL DESIGN
note | 8bf8800c-4299-5b62-9921-b64c8e89f21c | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
note | 8b23908d-5926-5796-b7a5-067fb00ffd70 | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
note | 649eef1e-f6fb-5b93-941f-3df1ae9a650f | Target Criteria - Meets project requirements
note | cab5c74d-58b8-5b67-945d-21cb24635e00 | Action Point Records Required - Hold Point
note | 64dd4c67-0377-5bf2-8217-131d9efc4d45 | Responsibility - SE / PE / PM / PQE / ER
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 3.02 - PQE
note | 95447a1b-8147-5520-ab33-6b3ad5b6c951 | Material Test Method Requirement - Bitumen Sprayer
note | e46bba72-c4df-58ab-9c85-0331eb693e01 | Reference Documents - TNZ P3
note | 65395671-aae0-51c2-8ad1-57fcd12fd05b | Material Acceptance Criteria (Method) - Certification provided
note | bdee1325-51f0-5635-ba61-b57c548443c8 | Material Test Frequency - Prior to starting
note | e82a07a3-3014-59e2-9e02-d3fb335dddf2 | Target Criteria - Current E/2 Certificate
note | 1e6169a5-214b-5d80-8ec3-8816b028995f | Action Point Records Required - Certificate Sheet
note | e511e1b3-f838-5317-909a-d074c70c0e3a | Responsibility - SE / PE / PM / PQE / Era
checkpoint |  | 3.03 - PQE
note | a5242764-6ea7-5917-aa17-778da73cdbba | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
note | 5fcdb352-3b2a-5d9d-838e-3b5f90cae371 | Reference Documents - Insert Material Testing
note | 0727c617-b7c8-5651-a363-e5369c254735 | Material Acceptance Criteria (Method) - See PQE
note | 7f50c619-1db5-55e4-945f-2122688cf992 | Material Test Frequency - Prior to construction commencing
note | b0a47dd6-2ef9-5ee6-abef-71a870ca7e4e | Target Criteria - Material meets project requirements
note | 13b67c3f-ed21-5fce-a783-597a7422572e | Action Point Records Required - Hold Point
note | 5525912a-a183-5ec3-95f8-807089426e43 | Responsibility - SE / PE / PM / PQE
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 3.04 - Field
note | db05c041-a4f7-54bf-ad01-ae50dd18936c | Material Test Method Requirement - Preseal Inspection
note | 9a25afdb-5e62-5f1d-aff0-5dc32fd9f138 | Reference Documents - TNZ B/02: 2005
note | 40cffd30-bedb-5264-8c73-722f11b701ea | Material Acceptance Criteria (Method) - TNZ B/02: 2005
note | 4f228b03-6f49-504b-ade2-115a971df52f | Material Test Frequency - 100% of Surface Prior to sealing of surface
note | 4c828742-0603-5646-a944-b9b69ea4b2aa | Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed.
note | 5b170bed-0e45-5808-97bb-eabcf5c5c8ba | Action Point Records Required - Test Record
note | c2846382-0350-5b53-8c74-da278ff34af4 | Responsibility - FM /QA / SE / PE
checkpoint |  | 3.05 - Field
note | 6816269e-f098-5d16-a80d-a8150c56c473 | Material Test Method Requirement - Degree of Saturaton
note | c42d3424-ff07-5d3f-90d8-68e505ba1c09 | Reference Documents - TNZ B/02: 2005
note | 64501425-62ca-58aa-9048-18f2a6fbfe4b | Material Acceptance Criteria (Method) - TNZ B/02: 2005
note | eb1a163e-0f72-5c39-a13b-5282cd91f33b | Material Test Frequency - 1 set of 5 per 1000m² - then 1 per 200m²
note | a526c021-ea2f-5100-9100-5c46dd88a474 | Target Criteria - < 80 % Completed Max 48hrs before sealing
note | d5985ecc-6e4b-5e2f-bb3b-ad04cb4ad937 | Action Point Records Required - Test Record
note | 8a91fec9-503f-5996-95c2-23ff192baab0 | Responsibility - QA / SE / PE
checkpoint |  | 3.06 - Field
note | 0f770f35-41de-581c-bb24-1b492b4286ff | Material Test Method Requirement - GO/NO GO Survey
note | 8776e696-d184-567c-9552-15320a949307 | Reference Documents - Downers processes
note | ea542827-4ff5-555b-ae1c-78b7ec2851c8 | Material Acceptance Criteria (Method) - Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app
note | bd290bb4-ce40-5406-abda-95283939a036 | Material Test Frequency - Prior to sealing on each site
note | 1e5352f1-db09-56e4-beb9-3cf948f09ad5 | Target Criteria - Pass on GO/NO GO ,Marginal & discussion with contract Manager or Written approval from Rehab manager
note | e3cf381e-642d-53d0-a9f8-2fbc2cbd8ab8 | Action Point Records Required - Survey record
note | 17b85a33-a940-542a-84e2-4208971c822e | Responsibility - QA / SE / PE
checkpoint |  | 3.07 - Field
note | 1c06b392-9215-5f99-abcb-916696b6fef7 | Material Test Method Requirement - Road temp
note | 79e84a91-b784-5c97-bc36-72133bc9765d | Reference Documents - TNZ P3:1995.18
note | 4c04e2b0-0e85-5386-b81d-713c4c8ca855 | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
note | 027bc837-2e19-5c08-8518-0ed31588a5d6 | Material Test Frequency - Once per day of sealing prior to sealing commencing
note | eda8a95e-0855-50f0-92b8-9ea17bbf95b0 | Target Criteria - Air temp >10°C
note | e3cf7935-bf2e-5ae0-8aba-9525d02b8c58 | Action Point Records Required - Spray sheet
note | 9ae2d44c-3f90-5e3f-89db-0fd80aa0b1b7 | Responsibility - QA / SE / PE
checkpoint |  | 3.08 - Field
note | 11a6b816-5487-592a-9d9b-0baea9622b31 | Material Test Method Requirement - Application Rate
note | 7c0fdbfe-2fd8-52e7-9f51-24de45b5519d | Reference Documents - TNZ P/3 : 1995.18
note | 440598d8-88d3-5716-a5f2-d57a5414f1c6 | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
note | 565b240f-5598-5055-8bfe-1ff2b19adfcd | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
note | 1ff48aa3-7c33-52e0-84c9-89b6559c0b6f | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
note | e75ddb50-2a70-5764-9bfa-baa6ac4ba899 | Action Point Records Required - Spray Sheet
note | 33474055-c7b4-51d6-8701-ffef804d7c12 | Responsibility - QA / SE / PE
checkpoint |  | 3.09 - Field
note | 249422b6-5cd3-5e32-938b-98ba0d543ef0 | Material Test Method Requirement - Chip spread rate
note | 298f15e2-166f-532b-844d-0688bf709a1f | Reference Documents - TNZ P3: 1995.21
note | a717ae2f-5262-5bf5-92d6-2bb46c28131c | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3), Chipsealing in New Zealand (pg 435)
note | d28a4e6d-6875-55cf-8308-51baa7182f4e | Material Test Frequency - Total amount of chip used to be calculated at end of days sealing
note | 23149d55-6246-510b-96a6-102221922550 | Target Criteria - Visual checks meets seal design requirements
note | b1ae87d4-45ca-571a-8ebb-5e793dce4bd4 | Action Point Records Required - Witness Point/Spray sheet
note | 8e3cb14f-4d34-5ac5-a4d7-e4ef11559226 | Responsibility - QA / SE / PE
checkpoint |  | 3.10 - Field
note | 4655f788-ed72-5638-9f77-e90e93beb65e | Material Test Method Requirement - Rolling Checks
note | cb0672d2-c3fc-54e7-9986-f05a7cbf06c1 | Reference Documents - TNZ P3: 1995.22
note | 32dc68b1-523c-5dce-859f-8504c490998f | Material Acceptance Criteria (Method) - Sealing Record
note | c76d2fd3-98d1-5eba-a074-30017d37ebba | Material Test Frequency - for each sealing site per day
note | 926ac038-6b3e-5b5c-b834-bcbe44f2792d | Target Criteria - As per rolling requirements defined in TNZ P3: 1995.22.
note | 103bdd56-de3d-5648-9d61-639fd3d535cd | Action Point Records Required - Witness Point/Spray sheet
note | 4f4caccc-c454-5f1b-b6e6-6f063351cd11 | Responsibility - QA / SE / PE
checkpoint |  | 3.11 - Field
note | ef7525a4-0afb-5db2-a3dc-4941cdb85a0a | Material Test Method Requirement - Post Seal Inspection
note | d39e484a-05e4-5afd-92be-6ca2bf78a622 | Reference Documents - TNZ P3: 1995
note | aac293e9-f2a5-5e97-9bb5-cdaeea9322d0 | Material Acceptance Criteria (Method) - Engineers Inspection
note | 67202766-d85d-5b63-a457-3bbde14a9872 | Material Test Frequency - After sealing
note | 12054c9f-c12c-5bd1-b91b-11a31e462749 | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
note | 61b0f736-2bdc-55d6-b197-5d87fd465e59 | Action Point Records Required - Witness Point
note | 5ad7eeb3-fd0c-50c6-84d6-bb0b0ca1ffed | Responsibility - QA / SE / PE
section |  | DG and AC Mixes NZTA M10:2020, SMA Mixes NZTA M27:2020, PA Mixes TNZ P/11
checkpoint |  | 4.01 - PQE
note | 03ab5605-7885-554e-a201-e6d618c40a28 | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
note | b617fda2-60d2-5061-8e58-0ba4a4f5327e | Reference Documents - Insert Asphalt Design & Material Records NZTA SP-M-032 Asphalt Surfacing Treatment selection Guidelines
note | a5eab962-4425-54cd-93ee-5cbf4a66d1c2 | Material Acceptance Criteria (Method) - Approved Treatment Design
note | 295f55cd-7474-564d-bf6f-f98e4da5e3c1 | Material Test Frequency - Prior to paving works commencing
note | d87a73da-759b-5418-a927-9089f4c08ace | Target Criteria - Treatment Design validation
note | 5e2e04b3-3abc-5297-a5c3-a53af64495fe | Action Point Records Required - Hold Point
note | c2b11687-7b32-5c61-8e0b-2d1a3a9618c5 | Responsibility - SE / PE / PM / PQE
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 4.02 - Lab
note | db23a61d-2cd5-5a85-99bb-22580314fa24 | Material Test Method Requirement - In-situ mat density calibration cores
note | f5899597-053c-580d-a588-24fc320ab027 | Reference Documents - NZTA M10:2020 9.9.1, NZTA M27:2020 9.9.1
note | 4ec42ec8-3ad4-5df4-b102-4e14484b2973 | Material Acceptance Criteria (Method) - ASTM D5361
note | a9625ac0-4146-5a3d-a801-3e5250fd578d | Material Test Frequency - One test per 900 t of asphalt plant production
note | 26a770ae-db1a-53b9-b70d-eac3359aa69d | Target Criteria - Characteristic value - mix design air void +3% -2%
note | 63bfa68b-e5c5-58e9-8f0c-8050b3fb8454 | Action Point Records Required - Hold Point
note | 3d3ce661-0272-5422-86ad-44c9da122e7e | Responsibility - SE / PE / PM / PQE
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 4.03 - Lab
note | 87b9a9d5-348b-5de8-986b-0656d2569407 | Material Test Method Requirement - Grading (Particle Size Distribution)
note | 9df70da6-06ce-50db-bc0f-748b4bde2095 | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
note | 204fc621-f770-5fc6-9435-d918e3bcd6bb | Material Acceptance Criteria (Method) - NZS 4407:2015 test 3.8
note | a2140b49-2157-5faa-923f-690d38c46664 | Material Test Frequency - One test per 900 t of asphalt plant production
note | 9c2ec068-edfb-5229-8ffd-b44227c12431 | Target Criteria - Tolerance from nominated JMF grading as per
note | 62204bf0-886d-542d-909c-dfea9890bb0d | ○ NZTA M10 Table 5.3
note | e1e9d656-7e1b-5429-84e5-9652a70f4b8b | ○ NZTA M27 Table 5.3
note | 6eff57b3-71d8-5fb4-9e9a-06af5d36cb5c | ○ TNZ P/11 Table 7.1
note | 591587bc-6572-55d7-a872-22cfb2a6d890 | Action Point Records Required - Test record
note | c337748a-7293-526e-b681-cbf53673c81d | Responsibility - SE / PE / PM / PQE
checkpoint |  | 4.04 - Lab
note | b0aec730-5203-5723-918e-8b643d1c7e8b | Material Test Method Requirement - Binder content
note | 8765b322-50ee-5146-9418-c1184db1c76f | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
note | 39e0d41c-78f5-5ad9-8089-4a27a9229593 | Material Acceptance Criteria (Method) - ASTM D2172
note | 9280f8ce-d8c4-5665-9eaf-ef6c7a462c44 | Material Test Frequency - One test per 900 t of asphalt plant production
note | c02a3560-da84-5e57-8c93-ffb8dbe48598 | Target Criteria - Tolerance on JMF
note | 07381507-3617-5c8f-8811-c61db14c5635 | ○ Individual ±0.5 (All)
note | 6dc63d23-9c08-5f95-b77e-ea0136f9330f | ○ Rolling Average of 3 ±0.3% (DG, AC, SMA)
note | cd7d297f-ee2b-5799-99e3-01488fe61b7c | ○ Rolling Average of 3 ±0.4% (PA)
note | 931d136e-e743-58c9-b518-594a9227fc64 | Action Point Records Required - Test record
note | c2a57365-48a4-5fb2-bec2-0aac63ef1b12 | Responsibility - SE / PE / PM / PQE
checkpoint |  | 4.05 - Lab
note | 7188c1f2-0cf9-554b-ae02-772b8b4d98d5 | Material Test Method Requirement - Air Voids
note | 326b7412-27b8-558b-9918-fe9b5f710ac1 | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
note | 6fe197c2-74d5-5f08-a971-3ccbcb9e6faf | Material Acceptance Criteria (Method) - ASTM D3203-22
note | 35f8d412-e184-5d15-90da-a22197199620 | Material Test Frequency - One test per 900 t of asphalt plant production
note | b5b9c78d-ef46-5293-9924-83f0293b8785 | Target Criteria - As specified for each mix type
note | f74061a8-cfe2-5d26-a066-face8f9cc51a | Action Point Records Required - Test record
note | 366c71ac-d0c6-5b53-87d1-384b965cb91f | Responsibility - SE / PE / PM / PQE
checkpoint |  | 4.06 - Lab
note | 6a0582ec-3f3f-57c8-92e5-529e84bb1650 | Material Test Method Requirement - Maximum Theoretical Specific Gravity
note | decbf91b-bf49-5061-ba65-a89aecbfa08e | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
note | 1a2d1159-2be1-50cd-9ec0-cb45d6710f66 | Material Acceptance Criteria (Method) - ASTM D2041
note | 48147a46-ab8c-513e-bb00-7a6b324cae32 | Material Test Frequency - One test per 900 t of asphalt plant production
note | 694ec183-8c9d-5377-81bb-6919fc54d39c | Target Criteria - Report Value
note | cdbd5e73-ddda-52e3-87f4-1d65ebc51666 | Action Point Records Required - Test record
note | 419a830c-da46-55b8-9c46-c224fc0b873a | Responsibility - SE / PE / PM / PQE
checkpoint |  | 4.07 - Field
note | 88bee2ec-f686-54cb-8a21-a710eaea4f4d | Material Test Method Requirement - Load Locate
note | e83eba02-76ae-525e-8a42-4fe8593bb43b | Reference Documents - Downer Procedures
note | a7e5c555-c3e3-5656-97ab-e5211354f01a | Material Acceptance Criteria (Method) - Each load can be indentified to a location. Record includes:
note | c2b61529-84fe-5dd1-9489-f757f3fbbd52 | – Truck ID/Rego/Driver
note | 3d12f4f6-6c51-500b-9e90-2b088e75b8e1 | – Depart Plant Time
note | f3a4200f-35a4-5681-843a-169e0c04c2ea | – Arrive Site Time
note | fa30dfe7-fe8b-5376-a222-ab03afb05b92 | – AC Temp on Arrival
note | 3889a381-b014-5791-b01d-a3654851c667 | – Ground Temp on Arrival
note | f35f0789-dd6f-5b7f-aaba-c803240f27d9 | – Tonnage
note | 6ff753f6-f608-5fef-981d-e7b58e895527 | – Run Width
note | e264a5a6-9e3e-51ee-8841-b4cef5c660d7 | – Estimated Run Length
note | 76ef0a28-cf11-5c30-952b-3cc4a25996d3 | – Calculated Area
note | 86e1ecfd-0888-5a58-8502-c15e5a9b62d6 | – Calculated Average Depth
note | 957999f9-3a71-5c95-9845-12ea76885e71 | Material Test Frequency - Every Load
note | a1471619-d002-5875-b006-275c904c152f | Target Criteria - All data is collected
note | 43c7f9b4-f67a-5128-b3a1-071fdfca0200 | Action Point Records Required - QA Sheet
note | 205820a2-fcfb-52cd-a7f2-e154e377c5e6 | Responsibility - QA / SE / PE
checkpoint |  | 4.08 - Field
note | e8c1e572-1a70-5a7e-9436-0fe9fe0ef28d | Material Test Method Requirement - NDM Density Testing On-Site Mat and Joint
note | 9e12e809-737c-5b16-abde-69391e490242 | Reference Documents - NZTA M10:2020 9.9.1 and 9.9.2, NZTA M27:2020 9.9.1 and 9.9.2
note | f537e9b1-a296-5a99-b389-b69f67601a59 | Material Acceptance Criteria (Method) - ASTM D2950, ASTM D5361
note | a75f5fac-3e0f-561a-96ad-731ae697b75b | Material Test Frequency - 1 test per 300m² per layer (Min 8 / Construction lot)
note | 6ac0d290-5410-5171-b58b-fe7f24d5a874 | ○ 1 test per 100m per layer length (min 3 / Construction lot)
note | 13840120-5fbf-54e2-9ec1-b3262cc2fb46 | Target Criteria - Mat: Mean air voids JMF +3,-2
note | c10ad175-511d-5405-ba93-c7fb2826e663 | ○ Join: Mean air voids JMF +5,-2
note | 9dbd1423-58b6-5e74-bfeb-6eba536ee02b | Action Point Records Required - Test record
note | ee87f9cb-9d28-5739-a3a9-74ab564d6f49 | Responsibility - QA / SE / PE
checkpoint |  | 4.09 - Field
note | 4b79e4ff-d168-5290-a19f-a264ef9c3ea3 | Material Test Method Requirement - Surface Level- Stringline checks for validation
note | 21f96f03-d5b4-5727-92ab-a473ffe927e1 | Reference Documents - NZTA M10:2020 10.2, NZTA M27: 2020 10.2 Downer Procedures
note | 494c2550-74a3-5fcd-99c1-070a451f219b | Material Acceptance Criteria (Method) - NZTA M/10
note | b9ba6700-f771-576e-a527-d1b03f1f2af5 | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
note | ed803c8b-e6b2-5876-9a53-0fea451e1fd5 | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
note | 9852a97f-de06-5a8f-9630-1fe235326d55 | Target Criteria - +15mm/-5mm from design or nominated level
note | 5596f386-d448-525c-80bc-6c9b3e75bd23 | ○ No more than 8mm deviaton from a 3m straight edge
note | d417b127-4357-51bb-856b-9dbaa11b94b5 | Action Point Records Required - Survey record
note | 35e5a2b6-9096-5983-966a-30cf63cbdf13 | Responsibility - QA / SE / PE
checkpoint |  | 4.10 - Field
note | cafb8d5f-a482-5f82-bf97-dd530aeff262 | Material Test Method Requirement - Post Surfacing Inspection
note | 181f69eb-413d-5164-bf56-126f9a93d99e | Reference Documents - CCA Procedures
note | b3f7922c-5628-5ece-8b2d-80b6dfdb9b6d | Material Acceptance Criteria (Method) - Contract Specifications
note | 6b440ce3-7e2d-575d-8ce8-cef9907b6ad9 | Material Test Frequency - 100% of site After surfacing (within 5 days)
note | 06b1c1cd-72de-513a-86df-bfad1b259621 | Target Criteria - Line marking has been reinstated
note | 575702c4-97df-5b3e-bbb6-405d5b5d1607 | ○ All excess material has been removed from site
note | d7b9f9f6-2d4c-5511-991b-f4e1f580e09f | ○ All CPs are clear from filter fabric and any excess material removed from on top service covers
note | 05fa6542-c271-58ff-acdc-126e992cc261 | Action Point Records Required - Hold Point
note | 92106a43-6019-5f14-ac9a-668b98c858df | Responsibility - QA / SE / PE
signoff |  | AUTHORITY HOLDPOINT
section |  | Post Construction
checkpoint |  | 5.01 - PQE
note | 200b8d7f-eb52-555e-81a6-14a8ef9c2ecd | Material Test Method Requirement - Asbuilt and RAMM Data
note | f72a5a35-5a9d-5fa3-ac08-785c2b3e34dd | Reference Documents - RAMM Update sheet
note | 997e9c06-cb09-5010-8a31-762138fe1cdf | Material Acceptance Criteria (Method) - Asset Management Information Plan
note | 103e55de-c1be-56b9-b5c6-e26003c8fe64 | Material Test Frequency - After works complete
note | 568fd26e-add3-5183-abc8-4a569e24df97 | Target Criteria - RAMM sheet 100% complete and accurate .
note | ad4ccd32-1e54-5272-816c-573b6b01e7de | Action Point Records Required - RAMM Asset Update sheet
note | 80e4faf6-3e0e-5e5b-9ed1-4802167fa8c4 | Responsibility - site engineer / Project Engineer/PQE
checkpoint |  | 5.02 - Lab
note | cf2bd284-6073-5252-b705-00215da3e177 | Material Test Method Requirement - High speed Rutting - Road Roughness
note | 86568a45-4e7c-55aa-a3ab-d6c3536961d4 | Reference Documents - CCA DOC
note | 8ff5ad7a-f279-571f-9157-60693a2714b1 | Material Acceptance Criteria (Method) - Laser Profilometer Survey
note | dd2c5e16-d01e-5d20-87c5-e837b0c2ddae | Material Test Frequency - After first coat sealing and prior to final surfacing with either EMOGPA, OGPA, SMA, or second coat sealing; After 12 months of trafficking; End of defects liability
note | 22c10ade-f858-5b6f-874f-bc9a2866cbe0 | ○ All lanes at 20m intervals in each wheel path and staggered by 10m between wheel paths
note | 5595abbd-9639-57c2-8ab0-86d03629d0f6 | Target Criteria - High Speed Rutting: > 5mm Report to Designer
note | c175a12d-8a11-57fd-a3b9-2d52c5a47819 | Action Point Records Required - Test Record
note | b1c3ecc6-3fc1-5cd3-8dbc-83f33c2eaa6b | Responsibility - site engineer / Project Engineer/PQE
checklist |  | ITP - GRANULAR REHAB INSPECTION TESTING PLAN Rev 1 | itp | ITP - GRANULAR REHAB INSPECTION TESTING PLAN | b74486b2-4f30-44da-be0d-73437d9c3ba8
section |  | Subgrade
checkpoint |  | 1.01 - Field
note | 217c5661-52f7-552b-a7ab-a5a90f6909ef | Material Test Method Requirement - Scala Penetrometer Cohesive soils only
note | 3a65fdda-d08c-50f0-af6b-8a8e1d6dd4c0 | Reference Documents - RITS Table 3-20
note | 133e5ec1-a90b-5583-b99d-ddd18d80a640 | Material Acceptance Criteria (Method) - NZS 4402.6.5.2:1988
note | 7802ce43-eda7-5df5-a9ae-7ddfda0dfaf6 | Material Test Frequency - 1m inside of edge of seal, on alternating lanes, at 10m spacing (no greater than 20m between tests)
note | 46cc95f5-2963-5366-a384-28e51fa23d03 | ○ Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater
note | 2fdbc726-0ca9-51fc-a66d-28d8647cc7dd | Target Criteria - Confirm design assumptions - Scalar reaches minimum 2 blows/100mm
note | bff3ab40-b400-594e-886c-d7655d64c207 | Action Point Records Required - Test Record
note | 9fd66279-5859-519f-9073-dd2a21c24c2e | Responsibility - QA / SE / PE
checkpoint |  | 1.02 - Field
note | 4da70fcc-7525-53db-9778-98dd519de912 | Material Test Method Requirement - Clegg Hammer Aggregate fill only where subgrade undercut or trench backfilled
note | fa1197f3-3226-58c7-9810-84d0197c4154 | Reference Documents - RITS Table 3-21
note | d8f05b8b-cbeb-559d-a0e6-809fc70de94c | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
note | f9fba30a-986a-5511-b004-c3c484204bb8 | Material Test Frequency - In centre of undercut or trench, Minimum of 1 test per undercut location
note | 99177218-9f58-5063-946f-15058d750d23 | Target Criteria - CIV ≥ 15 or CBR of 20
note | 22ab9787-a494-5022-8aeb-ef5d8454c99b | Action Point Records Required - Test Record
note | a1280a49-e622-5738-a646-f92f08eea303 | Responsibility - QA / SE / PE
checkpoint |  | 1.03 - Field
note | 8076f805-8775-5018-9627-10381b293b95 | Material Test Method Requirement - Surface Level, Shape, and crossfall
note | 59a028f6-cd8c-5b79-b701-63d760caa071 | Reference Documents - RITS Table 3.24
note | 225e2ba0-e5be-5752-9b11-20c6d8b5fffd | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
note | 5ba26114-b3de-5845-891e-f6e3b4fdf545 | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
note | ba4d9ade-1f23-5319-9ce1-a8d58737781a | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
note | 7f22a1e6-6d6a-56b5-afc3-cd3e03d032da | Target Criteria - +0mm/-30m from design or nominated level
note | bc5bf8b8-25c6-5e47-b943-d374e460e63c | ○ No more than 15mm deviation from a 3m straight edge
note | d0e8e422-eebc-5e6f-a5c2-5aa632ee39c0 | Action Point Records Required - Survey record
note | 44e73bf1-4759-5d82-a8d4-9125f088699e | Responsibility - QA / SE / PE
checkpoint |  | 1.04 - Field
note | 4ba8327e-d6e3-53b9-8c07-e8569bddc636 | Material Test Method Requirement - Tenser Triaxial Geogrid and Geofabric (cloth) installation
note | 776e8d66-53a2-5ac0-b785-348fa908a026 | Reference Documents - Tensar construction sequence CS_TriAx/30.04.08
note | b1977f3b-775f-556a-9d1b-e9fb4ad0bb50 | Material Acceptance Criteria (Method) - Manufracture installation instructions
note | 192439ae-aff8-5d75-ad84-858077eae986 | Material Test Frequency - 100% of Surface
note | 74c5ab3f-aadd-533c-9791-25e1766c191a | Target Criteria - Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints.
note | ef61f35b-cc25-577e-a84f-6bb115d14cd5 | ○ Geogrid and Geofabric shall be neatly installed without creases or folds.
note | 04eac2e0-38de-51b3-a298-e33d318cc6b1 | Action Point Records Required - Site Record
note | 12eddcc3-4f6e-555a-a5c8-055a7872039f | Responsibility - QA / SE / PE
checkpoint |  | 1.05 - PQE
note | dfc1f7f7-7272-5839-8256-b2a6e2cfc245 | Material Test Method Requirement - Is the layer closed out?
note | af97ccbe-8dad-5e19-9367-e8665e611ae3 | Reference Documents - See PQE
note | 475b2664-5e89-5a50-b7fa-b98e005952ef | Material Acceptance Criteria (Method) - See PQE
note | 4027b42e-d650-5003-9c3a-07d71202b3cc | Material Test Frequency - 100% of Surface Prior to placement of material
note | 02afbcf8-9035-5f8c-a837-ea8aed4da809 | Target Criteria - PQE Approval
note | f6d999d3-4262-599d-a764-5e78f437cf91 | ○ All testing record & reviewed as compliant.
note | 6ef92a32-9ce2-5289-b63f-7e1a7296c25b | Available Documents:
note | 0b1df901-e115-5587-86da-88da8de2d880 | ○ Test records
note | 2fc702d2-3fe4-5804-bfae-27c4d1628b13 | ○ Survey records
note | 177b54cf-79e5-51b3-9516-3e109b5b4ad9 | ○ Hold Point Records
note | bc7746a1-2c80-5328-9056-a9b6e020444a | Action Point Records Required - Hold Point
note | 6ecb63a7-4788-5326-8b6d-67c0739d3a90 | Responsibility - SE / PE / PM / PQE
signoff |  | AUTHORITY HOLDPOINT
section |  | Subbase
checkpoint |  | 2.01 - PQE
note | 4e17b1ac-0e6c-5612-b1a2-c859db4c2c95 | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
note | a1d01ca8-c4df-5e1d-9be7-59e5207a058f | Reference Documents - Insert Material Testing link
note | 43a93335-8969-5841-b990-616de0075df6 | Material Acceptance Criteria (Method) - See PQE
note | 8b55a06a-85db-5e89-a02f-bb5d54077ed2 | Material Test Frequency - Prior to construction commencing
note | 49e30b3c-2d72-581f-a5fd-2e9651a12bda | Target Criteria - Material meets project requirements
note | 9d8cd007-1f60-5f88-a075-83fc8c6173c7 | Action Point Records Required - Hold Point
note | 3b7138fc-4818-5554-91d6-178db1867a85 | Responsibility - SE / PE / PM / PQE
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 2.02 - Field
note | 17612ea0-406c-5ca2-988a-f21a01188a08 | Material Test Method Requirement - Plateau Density Test
note | f5d4e46c-bac7-5c1a-bac6-b1231894b293 | Reference Documents - TNZ B/02: 2005
note | ec154a61-db3a-59a6-b7ec-35e2fb367ef5 | Material Acceptance Criteria (Method) - TNZ B/02: 2005
note | 3d9cf93a-d25e-50f3-90d5-99f746d59b7b | Material Test Frequency - Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing
note | 53980568-45dd-5dce-8101-32374a313787 | ○ Target to be approved by Engineer
note | de7a4797-91b2-5828-986c-a00ad3240a5d | Target Criteria - N/A
note | 54641c7b-c6b0-5588-81ab-2f4f8413dd81 | Action Point Records Required - Hold Point, Test Record
note | 55ac252f-cf45-5103-b919-dc907a2b1526 | Responsibility - SE / PE / PM / PQE
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 2.03 - Field
note | 2f62eb67-6927-5981-85da-9fe62505948e | Material Test Method Requirement - Clegg Hammer
note | dafe8cf0-4f8e-5408-bc00-1e843ad44045 | Reference Documents - RITS Table 3-21
note | a57c0813-5009-5942-87c9-9f4fb2e61bce | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
note | 0a8904c6-432a-598f-8e39-ff96fdcbd0d0 | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
note | af16604e-49b8-54fc-ba4a-0e60b374ce28 | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
note | 50e45a78-d000-5e33-aa0e-6dbeeb7bfe2e | Target Criteria - CIV ≥ 25
note | aec72f6b-d942-524e-9307-c7bb75b97c7b | Action Point Records Required - Test Record
note | 507c570b-c473-55cf-a6c4-180b1415fb15 | Responsibility - QA / SE / PE
checkpoint |  | 2.04 - Field
note | 55cd34b5-e8e0-5c76-ac21-099599e61940 | Material Test Method Requirement - Compaction NDM Back Scatter
note | 24b1889e-1a8b-591e-97c2-fef5dab1dec2 | Reference Documents - RITS Table 3-22
note | 5739aecb-0001-5010-b6ec-4aada27b1540 | Material Acceptance Criteria (Method) - RITS 3.8.3.4, 4407:2015 test 4.3
note | 2416baa1-627d-5eda-b0a7-dede97b2abc3 | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
note | 77d54de2-a490-5510-9b3b-ccf7310aeea9 | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
note | fad2497c-62e2-58d2-a7ef-8c8467d478d4 | Target Criteria - Mean ≥ 95 % MDD
note | 4b87e9b4-7cdc-58fc-aad9-a3603b29fc5b | ○ Minimum ≥ 92% MDD
note | b94ba9ce-ca36-59f0-a291-63486a70fce3 | Action Point Records Required - Test Record
note | db71aa11-d97b-56f5-8dfa-d08c35810b21 | Responsibility - QA / SE / PE
checkpoint |  | 2.05 - Field
note | 2461d8a1-2853-5b8c-8025-0ef0e9a41931 | Material Test Method Requirement - Surface Level, Shape, and crossfall
note | f9d1bc7c-be01-50a3-8a0f-3b09a4ab3cf3 | Reference Documents - RITS Table 3.24
note | 256104bc-683c-5056-a2a5-4a161c812f7f | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
note | e8c5af2d-7e98-565c-b021-ab2d023e0380 | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
note | 6a483674-1b54-575f-b57f-71fc44a7537b | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
note | 7c720fb2-ad5d-5502-a862-f1e351d49f62 | Target Criteria - +5mm/-25m from design or nominated level
note | 9cd91d47-5290-51ed-8be1-251389ebc3c8 | ○ No more than 15mm deviation from a 3m straight edge
note | ff69ed24-a19e-54cc-85fa-10f1cd61794d | Action Point Records Required - Survey record
note | 727b94e9-cbdc-543e-9e04-aa4d4db88200 | Responsibility - QA / SE / PE
checkpoint |  | 2.06 - PQE
note | 51aba292-d103-54b2-b5f3-987f90cbb452 | Material Test Method Requirement - Is the layer closed out ?
note | 867ecb5b-1b55-52d5-9468-7f792c168f2e | Reference Documents - See PQE
note | 62da9652-cc87-532d-bcba-156aba5ca1c9 | Material Acceptance Criteria (Method) - See PQE
note | 8a4e3b41-5cd6-5d46-877c-8f3b46a91ba4 | Material Test Frequency - 100% of Surface Prior to placement of material
note | c0ac5202-6a89-5bb6-ac2f-e27199f3644a | Target Criteria - PQE Approval
note | bd913970-ce2c-56c5-bc4f-6901d92e0c39 | ○ All testing record & reviewed as compliant.
note | 418155dd-cfb2-5b43-93ef-29d1c2292807 | Available Documents:
note | 7300ffca-a510-5db4-bec1-fdb715909978 | ○ Test records
note | e1d84957-ca31-528b-9ef8-dc7d0c47304d | ○ Survey records
note | 3165f9ff-0825-53a0-a093-cc5ad70113c5 | ○ Hold Point Records
note | 55c09936-04d6-596b-bc65-577081b612e2 | Action Point Records Required - Hold Point
note | cc9a8145-6597-5b88-8df7-17c52704c2f2 | Responsibility - SE / PE / PM / PQE
signoff |  | AUTHORITY HOLDPOINT
section |  | Basecourse
checkpoint |  | 3.01 - PQE
note | d89b9fd0-390c-5a4f-9ebd-af6416da7b32 | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
note | 11591ee0-5257-5bb9-9d3d-09e420021ce4 | Reference Documents - See PQE
note | 0e160e31-dce9-5bb3-acfd-c8cdd11dfdb7 | Material Acceptance Criteria (Method) - See PQE
note | 473a5e87-8f04-556a-9443-418988173346 | Material Test Frequency - Prior to construction commencing
note | 753f9814-1f41-51a8-9cfe-82c958ffc466 | Target Criteria - Material meets project requirements
note | e18366fd-8422-5c52-a973-01ed37acbba6 | Action Point Records Required - Hold Point
note | 5ac12076-488d-5ea4-b876-0e08c923ff77 | Responsibility - SE / PE / PM / PQE
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 3.02 - Field
note | 5dd3f8d4-04d8-58c6-90b7-307d35dd5fa7 | Material Test Method Requirement - Cement application Mat test
note | f1d05917-8a28-5b24-897c-316826012acb | Reference Documents - TNZ B/5:2008
note | 5db59e49-c1b3-58d8-93fd-753a58179c7f | Material Acceptance Criteria (Method) - TNZ B/5:2008
note | 9c5d86fe-2806-58c7-9786-c294ab3fc986 | Material Test Frequency - 1 test per 400m² (minimum 1 per run)
note | e34469de-a6dc-5ae2-9708-c4db8acd1112 | Target Criteria - ±0.50kg/m² of specified rate
note | 44944e70-a036-5651-9729-7bed04d17dee | Action Point Records Required - Stabilisation QA sheet
note | ce82c926-dc5d-52c7-ac4a-62a12ef6d108 | Responsibility - QA / SE / PE
checkpoint |  | 3.03 - Field
note | c60e5753-965f-5306-899a-ad6023cd49eb | Material Test Method Requirement - Stabilisation Depth
note | 21b07c92-448f-5d58-a871-4f1b38af4b23 | Reference Documents - TNZ B/5:2008
note | 34483f54-d26c-5e01-9d23-f409db9b4d88 | Material Acceptance Criteria (Method) - TNZ B/5:2008
note | 860c0023-58f7-5184-b7ef-d17b5f898d6c | Material Test Frequency - 2 test per 400m² (minimum 1 per run)
note | 08c336c3-6572-5a19-8008-f97594ad2b9f | Target Criteria - Visual check to confirm that cement has been mixed to the correct depth, and as near as possible to full depth without mixing into the previous layer
note | f31a62f0-dac9-5a5c-b634-4de1ba1d77a4 | Action Point Records Required - Stabilisation QA sheet
note | 2aaa9f8a-8007-5530-85dc-d1aa7b4613fd | Responsibility - QA / SE / PE
checkpoint |  | 3.04 - Field
note | e9d0b731-92ae-560c-9a3f-516254aa59a4 | Material Test Method Requirement - Plateau Density Test
note | dd87ffc1-b24c-5e5d-9d7e-b14196d72b64 | Reference Documents - TNZ B/02: 2005
note | 6cd7dd11-43de-5417-b234-241a1b174b7d | Material Acceptance Criteria (Method) - TNZ B/02: 2005
note | 65bc1887-c7e5-5d26-8d9a-dfb55a0c1ff6 | Material Test Frequency - 1 test per site
note | 0a476c8c-6f92-598d-8509-9baec6159e4f | Target Criteria - N/A
note | fa2dc0b2-dea4-5478-a6c7-eb7fb1d4d5c4 | Action Point Records Required - Test Record
note | 039e5309-b7fd-5152-9383-ba590f1ffe2f | Responsibility - SE / PE / PM / PQE
checkpoint |  | 3.05 - Field
note | c0e6d9e2-86b0-59c7-ae60-e1ca150c5f4a | Material Test Method Requirement - Clegg Hammer
note | c1af60b6-fb74-5f88-b6cc-c7e5b63f18ba | Reference Documents - RITS Table 3-21
note | 5aa0d380-71e7-5445-a835-40ceeeb27cd7 | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
note | 87ac84c8-8380-5f45-881f-1faa6e947822 | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
note | 1fcc8f37-32d9-5fde-b41a-f3c101ad2528 | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
note | f3b71b40-5464-547b-abbf-49d9c7cc99ee | Target Criteria - CIV ≥ 40
note | 33f5ad8d-22d0-50d9-a290-3b7ca6efdd39 | Action Point Records Required - Test Record
note | 23657f1e-dd33-512d-bd86-f5f498fec3a8 | Responsibility - QA / SE / PE
checkpoint |  | 3.06 - Lab
note | b286bf9d-4a5f-5ea1-aa67-56dc816a2e66 | Material Test Method Requirement - Compaction NDM Back Scatter
note | 8ab6dc35-0705-5963-9be8-4d3031f2b7a8 | Reference Documents - RITS Table 3-22
note | 4fabbf8c-0259-5d78-b54c-3836b34b2c8a | Material Acceptance Criteria (Method) - RITS 3.8.3.4, 4407:2015 test 4.3
note | 4e260b44-d17e-56b6-91ee-c6f780f53d34 | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
note | 1d305402-96a2-587b-8cee-d7b5ba17adcc | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
note | 08502657-3607-5633-a3bf-6cbaa26f59c5 | Target Criteria - Mean ≥ 98 % MDD
note | 285bb911-afa3-54a7-8dd7-900bb45dab76 | ○ Minimum ≥ 95% MDD
note | 993e302a-6e44-5ce7-880d-a2429ebbc4f6 | Action Point Records Required - Test Record
note | f38ced75-9069-566b-baa2-2b446c3fd186 | Responsibility - QA / SE / PE
checkpoint |  | 3.07 - Lab
note | 0b4f2dbc-ebc9-50cc-a818-57c057f0c779 | Material Test Method Requirement - Benkelmen Beam Deflection Testing
note | 9e1136cf-ebec-59e4-9fcc-eb185f28bd16 | Reference Documents - RITS Table 3-23
note | e29ab170-055b-5b27-ab1e-5a84f3f44556 | Material Acceptance Criteria (Method) - RITS 3.8.3.5, ASTM D5874-16
note | 23f12a18-9134-5b34-8ec7-8d1dfcd049af | Material Test Frequency - 1m inside of edge of seal, on alternating lanes, at 10m spacing (no greater than 20m between tests)
note | 85bb246c-c73d-5453-a34d-51e1792ef34c | ○ Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater
note | 8360afee-f16c-5e91-81f5-ab7d4479c1eb | Target Criteria - Max deflection allowed: 1.83mm
note | d2bfde77-f9b7-5a77-abc7-bfca8a7245de | ○ From design report - due to non-RITs compliant Subgrade CBR
note | bf080c70-0a74-588b-8026-bc7a52e94d1e | Action Point Records Required - Test Record
note | c881c64f-8672-5269-854a-b91892516da2 | Responsibility - QA / SE / PE
checkpoint |  | 3.08 - Field
note | fbc4b6a1-2917-530e-b17f-ee6da4ff873e | Material Test Method Requirement - Surface Level, Shape, and crossfall
note | 2a8ceb4d-386a-5b65-8a05-012a9d25ba27 | Reference Documents - RITS Table 3.24
note | e58e894f-5e40-58e0-98ac-4506e9c66f27 | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
note | 6fafd489-d9d9-51e0-b23a-2ba8d7596d0d | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
note | 1b8a4d8d-b30e-543c-8437-dd57675a2138 | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
note | 143ff4a3-6ff7-5e72-8032-ee038a11ca14 | Target Criteria - +10mm/-0mm from design or nominated level
note | 9a1e64df-c4c0-51d4-94f2-99e3468fcd58 | ○ No more than 12mm deviation from a 3m straight edge
note | dcaccffa-ce94-57c8-94b8-abfb32138237 | Action Point Records Required - Survey record
note | 786943df-1e2d-5040-9e6e-2e60d14b4d7a | Responsibility - QA / SE / PE
checkpoint |  | 3.09 - Field
note | d7cb7000-8fc5-522f-88d3-4e89c6cd3fef | Material Test Method Requirement - Visual Inspection of Basecourse Surface
note | 3fdbaa6f-5376-5874-b9e1-3338717a6b94 | Reference Documents - TNZ B/02: 2005 7.8
note | c723dd8e-4f67-5133-a078-d9f0202e5ef5 | Material Acceptance Criteria (Method) - TNZ B/02: 2005 7.8
note | 8bbc1d23-a12d-55eb-830c-5ac4a653b09e | Material Test Frequency - 100% of Surface Prior to sealing of surface
note | 18c01434-e1e2-5c51-8ac3-196d987b407e | Target Criteria - Engineers Approval (The larger aggregate is held in place by with a matrix of smaller aggregates, the smaller aggregate is held firmly in place by fine material, and the matrix does not displace under normal trafficking or sweeping No evidence of rutting in surface)
note | 44084d4b-0cee-5a5d-84ce-7cb6df73b5ba | Action Point Records Required - Hold Point
note | 99de7704-b5ea-5aff-899f-7c1d521fcb27 | Responsibility - SE / PE / PM / PQE / ER
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 3.10 - PQE
note | a5649b61-eb6c-5deb-a88c-22453df7b9ef | Material Test Method Requirement - Is the layer closed out ?
note | 75a2432e-419e-5f6c-ab32-5da24dcff6ea | Reference Documents - See PQE
note | 52e8b236-579b-5be8-866d-aa90a0671e49 | Material Acceptance Criteria (Method) - See PQE
note | da34bcfd-9d55-51c1-8883-e1e2d04ac1cb | Material Test Frequency - 100% of Surface Prior to sealing of surface
note | 598cef2d-cf75-58c4-9103-d268905865a7 | Target Criteria - Engineers Approval
note | 4812bbfa-f9d6-5377-a8be-bc6a3fa44f4e | ○ All testing record & reviewed as comliant.
note | ac8e2aa8-5af0-5505-ab41-11ead8e2e9e5 | Available Documents:
note | 7b2ef9f7-55f2-50cc-ac01-a38151082f83 | ○ Test records
note | 5b4f9d0c-5945-598b-bf1d-6e9dacf74e04 | ○ Survey records
note | 75eecdc4-1920-5d93-a2a4-e64bf986b29a | ○ Hold Point Records
note | 36ee847e-9da0-5014-b92d-2f42bb967c6e | Action Point Records Required - Hold Point
note | ccecc880-dbea-5b9d-8524-92e138a545b0 | Responsibility - SE / PE / PM / PQE / ER
signoff |  | AUTHORITY HOLDPOINT
section |  | Membrane or First Coat Seal
checkpoint |  | 4.01 - PQE
note | 41ce1379-6134-5e8d-aac9-e5ecace1c190 | Material Test Method Requirement - Seal Design
note | 70ef40bd-e452-5103-b7e5-cc3f8b6cac6d | Reference Documents - INSERT SEAL DESIGN
note | f1e10dc2-d103-59d8-91d6-9174361d0366 | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
note | 94a02d35-418a-5739-8769-23050648fb49 | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
note | 12d56daf-82ca-57f8-8906-ff6e248d7a3e | Target Criteria - Meets project requirements
note | 6a4118fa-cbac-52b5-b8c0-2c31e7c0a711 | Action Point Records Required - Hold Point
note | 1fa47671-537a-5309-83bd-3e378bb583bb | Responsibility - SE / PE / PM / PQE / ER
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 4.02 - PQE
note | be365c2e-5fc7-5108-b195-7e4407502aa2 | Material Test Method Requirement - Bitumen Sprayer
note | 3a4df9eb-52b5-5050-a816-40453de118eb | Reference Documents - TNZ P3
note | 3ea963ec-43b9-59c9-aecc-b2f2a1492fb6 | Material Acceptance Criteria (Method) - Certification provided
note | a90d80ef-bd47-548b-a089-94341a9fc6c7 | Material Test Frequency - Prior to starting
note | 176c992e-f692-55ba-b233-b446df7b4704 | Target Criteria - Current E/2 Certificate
note | 6f5a5165-ac24-5302-88a1-fea9a01560ba | Action Point Records Required - Certificate Sheet
note | afd8424c-8ccf-5def-bb1e-a9ee14af8810 | Responsibility - SE / PE / PM / PQE / ER
checkpoint |  | 4.03 - PQE
note | 8875da92-7d31-5d67-aea1-7d6ad0ec427e | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
note | cd73aec3-88e2-5b30-bd70-0059cdbc503d | Reference Documents - Insert Material Testing
note | 6101360e-4f2c-5e33-96de-48906f65d10a | Material Acceptance Criteria (Method) - See PQE
note | 1994c5fe-ee3d-57f2-b99b-9afe29e11cc8 | Material Test Frequency - Prior to construction commencing
note | d2f9d746-bcf6-53f0-89f6-b044699d8e35 | Target Criteria - Material meets project requirements
note | 2c5ffbd1-38aa-538d-bc92-3fd73c4ac65e | Action Point Records Required - Hold Point
note | 98d1f77e-c544-5868-a3a9-15b9a3da7679 | Responsibility - SE / PE / PM / PQE
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 4.04 - Field
note | 9337bdc2-855d-5fb4-b9e9-904ad65b091a | Material Test Method Requirement - Preseal Inspection
note | 392617a4-7b02-546b-8632-c6585bfa609f | Reference Documents - TNZ B/02: 2005
note | bf8a7d3f-059b-59dd-a468-c064eefc5950 | Material Acceptance Criteria (Method) - TNZ B/02: 2005
note | c7b20a21-eb7f-586f-b2c8-d306fefbada4 | Material Test Frequency - 100% of Surface Prior to sealing of surface
note | a16589c9-a040-5ab6-af40-d19436cbe45f | Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed.
note | 982ca5a1-1785-5acb-8006-22959e8d36c3 | Action Point Records Required - Test Record
note | 909321db-6de9-55d5-9c06-ee741acfb48d | Responsibility - FM /QA / SE / PE
checkpoint |  | 4.05 - Field
note | 43395f88-cc7b-5268-ab63-0dd844797380 | Material Test Method Requirement - Degree of Saturaton
note | 0b5cf5ec-8bc1-5f5e-8ba2-e4ebc277ae6c | Reference Documents - TNZ B/02: 2005
note | e47e1254-ebbb-53fb-bf15-de2521b56ee9 | Material Acceptance Criteria (Method) - TNZ B/02: 2005
note | eec30acc-984d-57b5-90a8-b1993647bed3 | Material Test Frequency - 1 set of 5 per 1000m² - then 1 per 200m²
note | 4eeb90e8-b2cf-5171-9983-eb3990a95a04 | Target Criteria - < 80 % Completed Max 48hrs before sealing
note | 294f2947-cdfc-5351-9e50-85e77eb58d71 | Action Point Records Required - Test Record
note | aeffbe2a-a7e6-5005-858e-7f7c2fcc1f93 | Responsibility - QA / SE / PE
checkpoint |  | 4.06 - Field
note | f0055c25-3c12-5969-8e0f-e88baba3bd10 | Material Test Method Requirement - GO/NO GO Survey
note | 487f1283-7984-5c48-b3e6-c05d8ed22938 | Reference Documents - Downers processes
note | b941304e-f89c-5ef5-8099-3282b5480953 | Material Acceptance Criteria (Method) - Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app
note | 76180cf3-3f8d-529f-bff0-50b82c03c2fa | Material Test Frequency - Prior to sealing on each site
note | 54fbb06e-8f7f-5275-9120-7ff77ce564cd | Target Criteria - Pass on GO/NO GO, Marginal & discussion with contract Manager or Written approval from Rehab manager
note | d9aa6425-cf7c-5cb5-85d0-a79a159ef17c | Action Point Records Required - Survey record
note | 46514b4a-1fdb-503a-9b80-2c3f9d212c92 | Responsibility - QA / SE / PE
checkpoint |  | 4.07 - Field
note | 7a135c46-629b-5820-a2ff-a3245a7b4202 | Material Test Method Requirement - Road temp
note | 3ac80d12-ae6b-5f2c-93b1-7c5800b61b6e | Reference Documents - TNZ P3:1995.18
note | 8fc698ec-76e7-5355-836d-2ed059f11158 | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
note | 2469b369-fbcf-5eb7-a020-fe489f5c350c | Material Test Frequency - Once per day of sealing prior to sealing commencing
note | 8fd3a21d-8554-5da7-acbd-4bc352dc9b02 | Target Criteria - Air temp >10°C
note | cc7d61dd-f81e-5642-bf3d-bbef158a4c64 | Action Point Records Required - Spray sheet
note | 157fc9aa-492e-5ea4-8075-34d63e83a809 | Responsibility - QA / SE / PE
checkpoint |  | 4.08 - Field
note | bdaa1955-9d8c-5bb8-9e7e-d1e8b7c77351 | Material Test Method Requirement - Application Rate
note | aa725496-7e7b-5e4b-be9a-a7bf865fcba1 | Reference Documents - TNZ P/3 : 1995.18
note | 09448168-a52d-5079-ad59-ef395aa53814 | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
note | f73cd632-85d9-57ef-8946-b1cd668a2d42 | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
note | 9881e53f-9dea-54b2-a2db-62655264074a | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
note | d167f5a6-cb56-5dbe-b762-92d78de90b65 | Action Point Records Required - Spray Sheet
note | d8759027-e115-5aae-9847-5e6ab5f51aaf | Responsibility - QA / SE / PE
checkpoint |  | 4.09 - Field
note | 56978a08-56c2-5c9f-9bef-5bc646d8b076 | Material Test Method Requirement - Chip spread rate
note | 02a5ab45-3923-5f4e-ba45-11c750b14a09 | Reference Documents - TNZ P3: 1995.21
note | ab0fbfa3-e25d-5bec-9c6f-9c1bec7754a0 | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3), Chipsealing in New Zealand (pg 435)
note | 442a4db2-e2be-5b12-9010-25efdca8b1f2 | Material Test Frequency - Total amount of chip used to be calculated at end of days sealing
note | be57aef9-a295-5e09-900f-1cd1a203a8f8 | Target Criteria - Visual checks meets seal design requirements
note | cb0ae1da-6619-5e41-971e-d7275a77e27a | Action Point Records Required - Witness Point/Spray sheet
note | 1e69589f-2d8d-5754-9a2c-f7f92a1dcf7b | Responsibility - QA / SE / PE
checkpoint |  | 4.10 - Field
note | d391db62-d282-527e-81fa-a2e03055fb75 | Material Test Method Requirement - Rolling Checks
note | 8bc85263-68f0-5c8c-af1b-dcdfaef87fd9 | Reference Documents - TNZ P3: 1995.22
note | 4b15e85e-1174-52dc-a966-e15f60b63e11 | Material Acceptance Criteria (Method) - Sealing Record
note | bfaed682-a215-5af1-aa5f-68f24aafd871 | Material Test Frequency - for each sealing site per day
note | 00c39a84-270f-5159-ac47-dc857e7cf715 | Target Criteria - As per rolling requirements defined in TNZ P3: 1995.22.
note | fdc8b082-4046-5513-9278-660c66573a3c | Action Point Records Required - Witness Point/Spray sheet
note | 170e2039-f457-5c9e-8fc8-abea08dd7481 | Responsibility - QA / SE / PE
checkpoint |  | 4.11 - Field
note | 5412f4b2-5e6f-5d6a-b338-8607f98b5824 | Material Test Method Requirement - Post Seal Inspection
note | 72ce7dbf-8387-5a94-a649-8a173305fc82 | Reference Documents - TNZ P3: 1995
note | 37d54f49-d378-5cad-a714-1c3bf78b3410 | Material Acceptance Criteria (Method) - Engineers Inspection
note | 4d75cd0f-2093-574e-8a5c-a3aea63381d6 | Material Test Frequency - After sealing
note | 9c103069-96c9-514a-8147-82fb279af508 | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
note | 7bc3005e-ec81-513b-84b3-76715deef1d9 | ○ Line marking has been reinstated
note | 3540f5f6-f945-53bb-9653-aa9dc731826b | ○ All excess chip has been removed from site
note | d356802f-2926-57df-8bab-735a336e1eb5 | ○ All CPs are clear from filter fabric and excess chip and any excess material removed from on top service covers.
note | 06f4260d-1527-5607-9a94-4abf9636934c | Action Point Records Required - Hold Point
note | 6a513f12-6b0f-52be-a9c0-427897495ba5 | Responsibility - QA / SE / PE
signoff |  | AUTHORITY HOLDPOINT
section |  | Post Construction
checkpoint |  | 5.01 - PQE
note | d0f35973-bf8f-52a1-a824-9d37004c6267 | Material Test Method Requirement - Asbuilt and RAMM Data
note | 1090b273-c9f5-5d0f-9537-6042b57cac06 | Reference Documents - RAMM Update sheet
note | bc9bc198-ae79-5f9e-a679-a200de1ef063 | Material Acceptance Criteria (Method) - Asset Management Information Plan
note | f79655bf-f5a4-5bfd-a4b5-2dbd8d339ded | Material Test Frequency - After works complete
note | 9829020b-afbc-52e1-b469-61122eb669dc | Target Criteria - RAMM sheet 100% complete and accurate .
note | 56c7e62e-8a19-5778-b4f7-1c87146b3402 | Action Point Records Required - RAMM Asset Update sheet
note | 24532aa0-0c2f-5110-ba9a-323b7027ef2f | Responsibility - site engineer / Project Engineer/PQE
checkpoint |  | 5.02 - Lab
note | 39960cf4-5076-52fc-be10-b1b0978d9f36 | Material Test Method Requirement - High speed Rutting - Road Roughness
note | 7f72cada-6816-5ff5-aa49-4ef1b56a8828 | Reference Documents - CCA DOC
note | 3d53d405-edb6-5445-b2b4-612a9ac36f42 | Material Acceptance Criteria (Method) - Laser Profilometer Survey
note | 53bca1be-65bf-59ed-8845-bc36b8a6eaa5 | Material Test Frequency - After first coat sealing and prior to final surfacing with either EMOGPA, OGPA, SMA, or second coat sealing; After 12 months of trafficking; End of defects liability
note | 741c5def-2719-5cb4-9a2e-da25948d5b44 | ○ All lanes at 20m intervals in each wheel path and staggered by 10m between wheel paths
note | 5b3c3025-4dd0-556d-85e1-703875d056ae | Target Criteria - High Speed Rutting: > 5mm Report to Designer
note | 52a6f1ad-442a-5719-b127-c8d20469361b | Action Point Records Required - Test Record
note | be4bfb58-7cec-55ef-8234-ab35003709ea | Responsibility - site engineer / Project Engineer/PQE
checklist |  | ITP - ASPHALT SURFACE RENEWAL INSPECTION TESTING PLAN Rev 1 | itp | ITP - ASPHALT SURFACE RENEWAL INSPECTION TESTING PLAN | cbab5044-b574-4f15-a7a0-29971a18fe72
section |  | Milling
checkpoint |  | 1.01 - Field
note | 5eb17e16-6356-5f43-a14b-79dafd28ecce | Material Test Method Requirement - Surface Level, Shape, and crossfall
note | c13a3f16-f236-58a5-9e71-384ca82b6f43 | Reference Documents - RITS Table 3.24, NZTA M10:2020 10.1
note | 8505615c-e2b6-5615-a277-ab2a2d93647a | Material Acceptance Criteria (Method) - String line or GPS rover
note | 565479aa-f30d-55fc-8215-bc93083f6cd4 | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency, Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
note | 1ff1e347-0ad1-52fb-848b-56966e927462 | Target Criteria - +10mm/-0mm from design or nominated level, No more than 8mm deviation from a 3m straight edge
note | 0817965a-86a6-510c-a2aa-ade0a05c30b6 | Action Point Records Required - Survey record
note | 48d7e28f-e00f-54e1-a643-3466125c790e | Responsibility - QA / SE / PE
checkpoint |  | 1.02 - Field
note | 825f2aa7-8b1d-594c-8cfc-9105e6682714 | Material Test Method Requirement - Surface Inspection
note | 2d3b74d9-e5d2-51f4-9f67-9846278eacee | Reference Documents - NZTA M10:2020 9.2
note | b85949d8-b3f0-581c-829c-6b2612e1800b | Material Acceptance Criteria (Method) - Visual Inspection
note | a80fda84-103a-522e-90ab-034c797e1ae5 | Material Test Frequency - 100% of Surface Prior to paving
note | 290466be-8ed3-5a53-9bd8-0cec0f1a6d46 | Target Criteria - The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping.
note | be6a2bae-d61e-5245-af2e-68e5c2160e5c | Action Point Records Required - Hold Point
note | 033b0fd7-9876-59d0-96a0-aae5c6ff57d6 | Responsibility - QA / SE / PE
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 1.03 - Field
note | f4a515d3-e0fe-57d4-a902-6273f72ec948 | Material Test Method Requirement - Does the surface pre-treatment meet project requirments?
note | 7ad8e5a7-63ec-52d8-9de2-587e7a52acd0 | Reference Documents - NZTA M27:2020 9.3, NZTA M10:2020 9.2, NZTA SP-M-032
note | aafc4526-210c-5ad6-a4e2-8b080feea4b3 | Material Acceptance Criteria (Method) - Design requirements
note | 55871c60-190f-5b93-afaf-6f78e9955dd7 | ○ Visual confirmation after milling
note | 4883d1f5-ee39-565a-a1c9-73238813f513 | ○ NZTA SP-M-032: Step 4 Bond and Seal
note | 954f4976-9018-5842-b879-d7e30c05660e | Material Test Frequency - 100% of Surface Prior to paving
note | ba05650e-be1d-57ae-83f3-51f52e9e99d1 | Target Criteria - Is the suggested surface pre-treatment still suitable after inspectiing the milled surface?
note | ce557bf1-ec02-5566-95d6-f748068db3ed | Action Point Records Required - Hold Point
note | 9fc7821b-20bc-5288-accb-eb7b01f6a694 | Responsibility - SE / PE / PM / PQE / ER
signoff |  | AUTHORITY HOLDPOINT
section |  | Surface pre-treatment, Membrane or Chipseal
checkpoint |  | 2.01 - PQE.
note | 998fdbf9-fce2-5d08-b114-5ccac6c51042 | Material Test Method Requirement - Seal Design
note | 8312b036-1596-5ac2-9964-2d5d2072dfae | Reference Documents - NZTA M27:2020 9.3, NZTA M10:2020 9.2, NZTA SP-M-032
note | cc1d4dfd-b6ff-5dcf-a8b4-7a32f8cbf5d0 | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
note | 44021ff5-774b-5733-8c1b-018423f3ccb2 | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
note | 054acfa0-8424-5514-8ab0-259dba396d79 | Target Criteria - Meets project requirements
note | af7d89fb-d591-5cc9-9b59-9585262cd72d | Action Point Records Required - Hold Point
note | d69b33c9-8e51-5c25-b7af-18a5760fa58b | Responsibility - SE / PE / PM / PQE / ER
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 2.02 - PQE
note | d325cb04-ca58-54dc-be48-0fdca4672891 | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
note | 0db1327d-7452-56e9-bb00-f17628d75a32 | Reference Documents - Insert Material Testing
note | a0a03dc2-e10a-5a8e-8086-e5f1f7fff21e | Material Acceptance Criteria (Method) - See PQE
note | c087094f-3910-52e7-85a3-5024614e7570 | Material Test Frequency - Prior to construction commencing
note | 07256a70-4ef2-5b22-9613-f18fec6c86dc | Target Criteria - Material meets project requirements
note | e8a551f7-c010-590d-a8f0-9565d715ca4a | Action Point Records Required - Hold Point
note | ae0c1b28-39ef-56f3-9147-dc5fa7392f2d | Responsibility - SE / PE / PM / PQE
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 2.03 - Field
note | 757820b9-3d88-5b32-a20d-c8fd336cb8b2 | Material Test Method Requirement - Preseal Inspection
note | 41c308e9-9484-5247-97d7-af7ca39b4ec9 | Reference Documents - TNZ B/02: 2005
note | 9865a0d0-3511-5961-95b8-78f581a4bc1b | Material Acceptance Criteria (Method) - TNZ B/02: 2005
note | 3ca3f856-e536-51c4-899b-ef17b085e792 | Material Test Frequency - 100% of Surface Prior to sealing of surface
note | 48768ea7-324c-5a1b-a01c-d032e5752ccd | Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed.
note | 47b355be-345f-5626-a57c-6e366a2e627b | Action Point Records Required - Test Record
note | 8bf132b7-97ce-57c8-abb0-a59844d153f2 | Responsibility - FM /QA / SE / PE
checkpoint |  | 2.04 - Field
note | a0cc64cd-e86d-5bb8-bf93-fc84a06ff3b0 | Material Test Method Requirement - Road temp
note | 69cc7b3b-1ecd-5a9d-82c5-b2576e7b304c | Reference Documents - TNZ P3:1995.18
note | 2ee4b2b0-b7a7-525f-8348-b10f4dd469a6 | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
note | d360f6d5-75ca-5eee-bc16-9b3799b18353 | Material Test Frequency - Once per day of sealing prior to sealing commencing
note | fa50cbb0-73f2-5190-8c54-2132adf67db4 | Target Criteria - Air temp >10°C
note | 350c0314-6d10-5a85-9c21-3e7e32332451 | Action Point Records Required - Spray sheet
note | 30fbd2ab-e5fa-5c8e-b024-54f3c788488b | Responsibility - QA / SE / PE
checkpoint |  | 2.05 - Field
note | eccbd2d3-0e23-52e3-a196-d03c461d7907 | Material Test Method Requirement - Application Rate
note | bdb09615-275b-50c3-b7e9-d631cd305f05 | Reference Documents - TNZ P/3 : 1995.18
note | 1b7a5e9e-6bcf-5200-9fab-623076154b24 | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
note | 13b0fa3a-c5d2-5050-a5e2-1124731c8862 | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
note | 82aacfe7-40dc-58a6-9e6a-02e5ea497c1a | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
note | df13b87e-4824-5525-a50c-7cba2670c97f | Action Point Records Required - Spray Sheet
note | 09fbfd8f-62b1-52be-b743-c6d24b6a3e4b | Responsibility - QA / SE / PE
checkpoint |  | 2.06 - Field
note | 9eead763-bb81-5f95-b6ad-a480dfb6a110 | Material Test Method Requirement - Chip spread rate
note | 27902cfa-4d06-5a21-9f65-b2172ff9d6f3 | Reference Documents - TNZ P3: 1995.21
note | 3dc2237c-1baf-5d01-882e-c94d117aef25 | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3), Chipsealing in New Zealand (pg 435)
note | 1e028cf2-2009-5568-8d81-29e213ff364d | Material Test Frequency - Total amount of chip used to be calculated at end of days sealing
note | b0306c23-aa20-5e80-a84f-ef9022a6437e | Target Criteria - Visual checks meets seal design requirements
note | eed007a3-1d5e-5202-830b-1d40917abe5c | Action Point Records Required - Witness Point/Spray sheet
note | 4712ffa8-d8c3-5236-8c5c-523531b60dee | Responsibility - QA / SE / PE
checkpoint |  | 2.07 - Field
note | 03a05a92-e34f-5732-ae9b-254ad18a2534 | Material Test Method Requirement - Post Seal Inspection
note | 6186982e-05ce-5dcc-956c-b41e3fc1a68c | Reference Documents - TNZ P3: 1995
note | 18a4d7a0-549e-56a6-a566-a5f4280334be | Material Acceptance Criteria (Method) - Engineers Inspection
note | ee65d32c-3083-5c4a-9c4f-7789d1bbc79d | Material Test Frequency - After sealing
note | 0b60c547-0fb3-5652-8d7c-e6c0487a6755 | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
note | a24de70f-78d5-5c6f-9a5e-5df9ae8b1c37 | Action Point Records Required - Witness Point
note | 79ed917e-6995-5a3f-9ab9-ac0a4f23058f | Responsibility - QA / SE / PE
section |  | DG and AC Mixes NZTA M10:2020, SMA Mixes NZTA M27:2020, PA Mixes TNZ P/11
checkpoint |  | 3.01 - PQE
note | c5bf000c-72cc-549e-a295-c0bb6fed2742 | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
note | 94373dd6-8b53-53c4-b8bf-e894d9ac4040 | Reference Documents - Insert Asphalt Design & Material Records NZTA SP-M-032 Asphalt Surfacing Treatment selection Guidelines
note | 09259de6-da47-5a54-aaae-2f1d807fc8a4 | Material Acceptance Criteria (Method) - Approved Treatment Design
note | bf79692b-2d1e-50a1-bfbc-4785fb8e0c21 | Material Test Frequency - Prior to paving works commencing
note | f6a42ef4-82da-54ee-b53d-114115a2c91b | Target Criteria - Treatment Design validation
note | 8443c5ec-274f-5306-9bde-e850b693f7ee | Action Point Records Required - Hold Point
note | 10e40936-ff7f-5436-92d2-c9344680ac7e | Responsibility - SE / PE / PM / PQE
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 3.02 - Lab
note | a4f5c5c7-fe92-5d5c-8bfc-24bd130b8e91 | Material Test Method Requirement - In-situ mat density calibration cores
note | 20cdc890-ad47-589e-8993-762c0975bc12 | Reference Documents - NZTA M10:2020 9.9.1, NZTA M27:2020 9.9.1
note | cf13b34a-d441-5a00-b41a-80681f1ac24b | Material Acceptance Criteria (Method) - ASTM D5361
note | d199c698-0a10-573a-98ea-cbec21dcd63c | Material Test Frequency - One test per 900 t of asphalt plant production
note | 603a3046-0179-5fbd-9dcb-905a515c2a6a | Target Criteria - Characteristic value - mix design air void +3% -2%
note | fdaa83ec-3a30-55c3-a2e8-dab1258143e9 | Action Point Records Required - Hold Point
note | 3c60383a-0832-5e02-8be1-25f86040042e | Responsibility - SE / PE / PM / PQE
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 3.03 - Lab
note | d7b1d990-2a9a-5e0d-bff6-617ac4db1d3e | Material Test Method Requirement - Grading (Particle Size Distribution)
note | 1b41b44c-5fd2-5398-86b6-4a631f1451ca | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
note | 3fa5c590-7bab-57eb-9479-71c250af685c | Material Acceptance Criteria (Method) - NZS 4407:2015 test 3.8
note | 1a942bcd-39b9-510a-9a00-649889cbef4a | Material Test Frequency - One test per 900 t of asphalt plant production
note | 852cb67a-ced8-5e34-97db-1d7c61df1e17 | Target Criteria - Tolerance from nominated JMF grading as per NZTA M10 Table 5.3, NZTA M27 Table 5.3, TNZ P/11 Table 7.1
note | 391bec09-6a0c-5495-81e1-0539c4a745ad | Action Point Records Required - Test record
note | 67e0547a-f474-557d-9f9e-8dd38da2012f | Responsibility - SE / PE / PM / PQE
checkpoint |  | 3.04 - Lab
note | 235b163c-96a4-50e0-8097-024f1221451f | Material Test Method Requirement - Binder content
note | c07a6e3a-15d0-5656-8424-6ce0fe5a29d6 | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
note | b67f44d2-609d-5392-9cc8-605663ee99c2 | Material Acceptance Criteria (Method) - ASTM D2172
note | bf4506f1-1d72-5d35-9e03-e7c99bb32465 | Material Test Frequency - One test per 900 t of asphalt plant production
note | 0f25dc4d-d643-5fa2-8ab4-0ae020a5766e | Target Criteria - Tolerance on JMF
note | 5d3e29c0-c7e9-5917-8f5b-9c5297e7a2bf | ○ Individual ±0.5 (All)
note | 813a7025-5add-54f4-809c-6f1c609ea07c | ○ Rolling Average of 3 ±0.3% (DG, AC, SMA)
note | 828bdd78-db57-56aa-8c1b-85bb340e4f3e | ○ Rolling Average of 3 ±0.4% (PA)
note | 4fecd764-9f81-5b18-a291-14e11284b12b | Action Point Records Required - Test record
note | 521db5ed-a18e-5876-8431-7b0ffe1deed0 | Responsibility - SE / PE / PM / PQE
checkpoint |  | 3.05 - Lab
note | 7540e9d7-0b41-52d0-b6f3-f36d6f0111ec | Material Test Method Requirement - Air Voids
note | 199f555a-f534-5f87-ae5f-849288b4e26e | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
note | 2431c7c0-817d-5d91-b2e3-233c29c28c40 | Material Acceptance Criteria (Method) - ASTM D3203-22
note | 8f22e512-dda0-5207-bfe0-e3300c8d8861 | Material Test Frequency - One test per 900 t of asphalt plant production
note | c232bc42-ba42-5ae8-bc72-9d619cbb015c | Target Criteria - As specified for each mix type
note | 3e5e9f2f-ea48-5311-a93d-3426cfd20bed | Action Point Records Required - Test record
note | e66e2f87-b3ea-5222-9718-260aeee7840a | Responsibility - SE / PE / PM / PQE
checkpoint |  | 3.06 - Lab
note | 8978a9ce-eb37-520b-8fb6-bd91f6a2d213 | Material Test Method Requirement - Maximum Theoratical Specific Gravity
note | 247620ba-62af-59b6-9993-c655adfc10d5 | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
note | 42168385-52ce-5395-a66b-17b18cb69922 | Material Acceptance Criteria (Method) - ASTM D2041
note | 29042750-93e5-57a8-94a0-e6201e3a1846 | Material Test Frequency - One test per 900 t of asphalt plant production
note | c1c24439-b8c0-5ed8-abd0-9f99140a8162 | Target Criteria - Report Value
note | e134cf91-4fb3-59d9-bc8d-2721c851ad1d | Action Point Records Required - Test record
note | 9904b3cd-a831-5eef-9a28-4e41afdf56f9 | Responsibility - SE / PE / PM / PQE
checkpoint |  | 3.07 - Field
note | 3d632441-e774-565f-8e99-b91521f602e0 | Material Test Method Requirement - Load Locate
note | efce3b20-2754-5918-8e77-a7134a33f5c3 | Reference Documents - Downer Procedures
note | d270ffa0-072d-59ba-a123-de067c8802d8 | Material Acceptance Criteria (Method) - Each load can be indentified to a location. Record includes:
note | 19a97b9d-6795-5a7b-b833-58d14319c3ed | – Truck ID/Rego/Driver
note | 7c104b5c-e3a2-53f1-bfeb-a74522777659 | – Depart Plant Time
note | 972fed59-6f11-5f4b-9864-470bbc2d1d70 | – Arrive Site Time
note | 280f3d6d-3fb0-5163-9d86-1ac7053bdb7c | – AC Temp on Arrival
note | c8d3d334-77e3-5339-b03a-165a5964a3c0 | – Ground Temp on Arrival
note | 55b57fbf-cf18-594f-a79b-dfc70871a98a | – Tonnage
note | b7cc4af8-88a8-551f-a268-01d315b9fe6b | – Run Width
note | 50843712-e0fa-5f5d-9c57-67fdfbad54b4 | – Estimated Run Length
note | 9132ee5c-05ee-553c-98f7-c3286d54767e | – Calculated Area
note | caa88c2c-9738-585a-9540-f3cd1e992b33 | – Calculated Average Depth
note | 145b4590-2f1d-56dd-be02-7726d6a3d378 | Material Test Frequency - Every Load
note | 7dc53dfe-4e50-580e-a1e2-07b242e3e855 | Target Criteria - All data is collected
note | 0bc1de29-0574-5520-bd88-8eac1be6a39f | Action Point Records Required - QA Sheet
note | 6aaa0c5b-c8ab-5049-b8d8-9c5412d807e9 | Responsibility - QA / SE / PE
checkpoint |  | 3.08 - Field
note | 73b67a13-6897-5e4f-9354-4b8919dfaf33 | Material Test Method Requirement - NDM Density Testing On-Site Mat and Joint
note | 5350e8f8-c232-598d-bcab-4ba9aa37e093 | Reference Documents - NZTA M10:2020 9.9.1 and 9.9.2, NZTA M27:2020 9.9.1 and 9.9.2
note | a5102807-94ae-5f26-834b-4242b85c9c09 | Material Acceptance Criteria (Method) - ASTM D2950, ASTM D5361
note | b7643fe2-7171-5038-88ee-d7e2fd290518 | Material Test Frequency - 1 test per 300m² per layer (Min 8 / Construction lot), 1 test per 100m per layer length (min 3 / Construction lot)
note | 0db149ce-bab7-53e0-81a7-45be97560448 | ○ Target Criteria - Mat: Mean air voids JMF +3,-2
note | ea70ede9-a3cc-5409-be2e-7d2b8369dddb | Join: Mean air voids JMF +5,-2
note | a638b9b8-9ea7-5bd2-8d28-482b0f890ac8 | Action Point Records Required - Test record
note | 3fa17434-d9b0-5b22-b4b9-99dcf4895778 | Responsibility - QA / SE / PE
checkpoint |  | 3.09 - Field
note | e45f342c-fce6-5272-bf0c-3fefd882c89b | Material Test Method Requirement - Surface Level- Stringline checks for validation
note | 5775823b-cadd-5d86-b99d-25ab9b9a6baa | Reference Documents - NZTA M10:2020 10.2, NZTA M27: 2020 10.2, Downer Procedures
note | 4c23532f-f5f8-5a15-852c-e14abe288133 | Material Acceptance Criteria (Method) - NZTA M/10
note | 1aa115e3-5b4c-50d9-b372-78fdbf788b46 | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
note | 9891bcb7-aa87-59c8-88b0-8e64391b611b | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
note | ea35fe0d-2c4e-58a4-8847-20273823f4bb | Target Criteria - +10mm/-0mm from design or nominated level
note | b10d5889-22e8-5ace-a0d1-8761d905d6a1 | ○ No more than 8mm deviation from a 3m straight edge
note | d12fc970-46a6-5344-a20f-486c60895f5c | Action Point Records Required - Survey record
note | b21cc13c-c95d-5a23-b0bd-838d5d61b4e4 | Responsibility - QA / SE / PE
checkpoint |  | 3.10 - Field
note | 3a2d1bc5-45af-5509-be5f-431be3347a0a | Material Test Method Requirement - Post Surfacing Inspection
note | 61f6680f-f2dd-5631-b6c7-27a69d217a93 | Reference Documents - CCA Procedures
note | 2e85d106-682b-58ca-83b2-a5b9158694d1 | Material Acceptance Criteria (Method) - Contract Specifications
note | c191eff2-39de-5f63-962a-cd072584a249 | Material Test Frequency - 100% of site After surfacing (within 5 days)
note | 418a9a28-6a95-5d81-a077-6cf605a205df | Target Criteria - Line marking has been reinstated
note | 8c70c758-60a4-52a4-a05a-105a82f9a578 | ○ All excess material has been removed from site
note | 020b12a0-b4b9-50f0-8ace-38bab4243533 | ○ All CPs are clear from filter fabric and any excess material removed from on top service covers
note | 12630793-c98e-5130-92c2-389c76e765b0 | Action Point Records Required - Hold Point
note | 04227ab6-f853-50bf-a5e5-b1286562ac02 | Responsibility - QA / SE / PE
signoff |  | AUTHORITY HOLDPOINT
section |  | Post Construction
checkpoint |  | 4.01 - PQE
note | dbee78e7-37d2-5401-9079-2c3a174d1e65 | Material Test Method Requirement - Asbuilt and RAMM Data
note | 68f015fd-de63-5a10-82e7-dda66196b970 | Reference Documents - RAMM Update sheet
note | c62c202a-8855-5c38-aca0-a9776f4d7f00 | Material Acceptance Criteria (Method) - Asset Management Information Plan
note | 8e870826-f534-5a50-8eba-3af45fe71da4 | Material Test Frequency - After works complete
note | a70ebe0a-86dd-5e24-8e1b-c5913a72aeb4 | Target Criteria - RAMM sheet 100% complete and accurate .
note | 4f5dfa48-6376-5cdf-95ed-52895c5190a8 | Action Point Records Required - RAMM Asset Update sheet
note | 57cc7457-7534-5450-822c-c17067a69e75 | Responsibility - SE / PE / PM / PQE
checkpoint |  | 4.02 - Lab
note | 6d316050-91d7-553a-988f-d3074229b5dd | Material Test Method Requirement - High speed Rutting - Road Roughness
note | fe7d43c0-422f-5ca0-ba92-5dc3cffbf77e | Reference Documents - CCA DOC
note | 8a8d83ce-7ff9-5cbc-bfe1-90ad4bfbd2b0 | Material Acceptance Criteria (Method) - Laser Profilometer Survey
note | c83a0ecf-e220-5ae0-8ab6-6bfd52b36466 | Material Test Frequency - After first coat sealing and prior to final surfacing with either EMOGPA, OGPA, SMA, or second coat sealing; After 12 months of trafficking; End of defects liability
note | bd97dff3-0417-5ab8-97a0-a0cb6c0e5cb9 | ○ All lanes at 20m intervals in each wheel path and staggered by 10m between wheel paths
note | 7dc9694c-449d-588f-b106-a5a3cea2bfeb | Target Criteria - High Speed Rutting: > 5mm Report to Designer
note | 4225a644-afc1-58ae-9d96-513ff18ba079 | Action Point Records Required - Test Record
note | e624145b-bbb9-5733-ae03-e4b79a86ee81 | Responsibility - SE / PE / PM / PQE
checklist |  | ITP - CHIPSEAL RENEWAL INSPECTION TESTING PLAN Rev 1 | itp | ITP - CHIPSEAL RENEWAL INSPECTION TESTING PLAN | edab29c4-40a0-4f1d-ba6c-91106dfa89a4
section |  | Preliminaries
checkpoint |  | 1.01 - PQE
note | 2a8efb71-c07e-5558-9f60-8bedf0e4e67d | Material Test Method Requirement - Has all preseal repairs been completed?
note | db36277c-66e8-560c-ae4c-46fc40d1fd6c | Reference Documents - Insert Layer Acceptance ITP No
note | 5d634e2c-0ac7-5e5d-bc38-cdac560ffa1b | Material Acceptance Criteria (Method) - Workpack closeout record
note | 6dfa3419-4c55-5cf2-805c-92e9a65724eb | Material Test Frequency - Prior to sealing commencing
note | 386b0241-2ff4-562c-9497-74f33ff6ead7 | Target Criteria - All underlying layers meets project requirements
note | 26b26df6-80c9-5cd8-9ea8-0a56172e3f99 | Action Point Records Required - Hold Point
note | 4791d770-510f-557f-990b-95098293dae7 | Responsibility - SE / CE / PM / PQE
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 1.02 - PQE
note | 6381a9b7-263c-56b2-8df5-f15a51cdcc75 | Material Test Method Requirement - Bitumen Sprayer
note | e57ac68e-b0cc-540d-a1ac-e454c75cf25c | Reference Documents - TNZ P3
note | 2b921693-4be5-5dc8-910b-4a0fed4a4c20 | Material Acceptance Criteria (Method) - Certification provided
note | f87b7fbb-b838-5fb1-9b89-390d746b7ef4 | Material Test Frequency - Prior to starting
note | 593cdcc9-318e-565d-84ef-d784f8c74199 | Target Criteria - Current E/2 Certificate
note | ee71efea-9091-5f75-849e-d5ba482eaa6a | Action Point Records Required - Certificate Sheet
note | 5804a00f-7df1-57ff-a86e-214c9b960ceb | Responsibility - SE / CE / PM / PQE
section |  | Chip Seal Application
checkpoint |  | 2.01 - PQE.
note | 6a6f238e-323a-570b-ab43-248242d70c0c | Material Test Method Requirement - Seal Design
note | 706d4f37-0dc5-592e-81bf-c3e19cab58c8 | Reference Documents - INSERT SEAL DESIGN
note | 7cd69426-a0c4-5dfd-910a-edfc0c188d04 | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
note | ed77fd80-290b-59de-9317-2859d2b923d2 | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
note | d7287ebe-8a44-5b63-b9b6-de6a416445d1 | Target Criteria - Meets project requirements
note | c062c19f-0aec-533a-bf7b-f44098153af5 | Action Point Records Required - Hold Point
note | ef5009a9-44ae-560e-a963-ec334635fb14 | Responsibility - PQE / CE / PM
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 2.02 - Field
note | bb9d8ae4-8964-54e1-aadd-dddc70a9f093 | Material Test Method Requirement - GO/NO GO Survey
note | 281ed66e-a750-5811-b15c-f6c8d302ea33 | Reference Documents - Downer survay sealing Go/NO GO , road science Zeus app & Downer Iris app.
note | 492c3a4a-c3c7-5a5b-b73b-6d30cec36735 | Material Acceptance Criteria (Method) - Downers Procedures
note | fcd04599-5bec-5678-81e5-eeaae74a43f6 | Material Test Frequency - prior to sealing on each site
note | cf42247e-e94e-553f-8d12-379c545c1c8c | Target Criteria - Pass on GO/NO GO , Marginal &discussion with contract manager or approval from Rehab manager
note | a1aba39f-a2b1-5f65-842d-dd332949cbd4 | Action Point Records Required - Hold Point
note | e271a0f6-4cbc-59ad-a897-221f0d0a55ce | Responsibility - PQE / CE / PM
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 2.03 - PQE
note | b367becb-c924-5be8-a275-cea65ce5a29c | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
note | 1c3a8faa-4e13-53ca-8e53-a90ef413ed04 | Reference Documents - Insert Material Testing
note | 3d658994-6bec-5cf9-b3ec-769940a2d7a2 | Material Acceptance Criteria (Method) - See PQE
note | c3b227b6-aaf6-5065-b5d8-a4fa24416431 | Material Test Frequency - Prior to construction commencing
note | 6f34686e-653d-5970-bbd7-49ac7f12c4f1 | Target Criteria - Material meets project requirements
note | d5dbb0d5-431a-5b33-ba34-9e6fce2d811f | Action Point Records Required - Hold Point
note | c6b62254-00bc-5c6f-8fea-3ca7e95a7c07 | Responsibility - PQE / CE / PM
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 2.04 - Field
note | 9ff5638e-d672-53ca-a553-e9a0848d3bd7 | Material Test Method Requirement - Pre-seal Inspection
note | 51c14599-b6b4-5b24-806d-1d442669cf5c | Reference Documents - TNZ P3:1995.7
note | 3495d175-e53a-5079-8690-8d7f697cfe23 | Material Acceptance Criteria (Method) - Downers Procedures
note | d3915da8-a274-5eb0-9c51-44eb0072a82d | Material Test Frequency - 100% of Surface Prior to sealing
note | 72b129e5-b24e-5216-8ed5-ebd2b911e889 | Target Criteria - The surface shall then be swept clean of loose aggregate, dust, dirt and other deleterious matter.
note | 9e5fbfc4-bbe6-56a3-be7e-f1f45a64fda8 | ○ Street Furniture and Start and End poitns have been taped and/or masked for overspray
note | f0a4720a-26cd-5a64-abc7-3432fbf38440 | ○ Line marking tags are in place.
note | b5eecb47-fe9b-51d8-92de-3c071774de01 | Action Point Records Required - Hold Point
note | e39980f9-57c3-5c0a-b7cb-cec194a5e1c8 | Responsibility - PQE / CE / PM
signoff |  | AUTHORITY HOLDPOINT
checkpoint |  | 2.05 - Field
note | 46860edd-de23-5bee-8c15-3752ee258ace | Material Test Method Requirement - Road temp
note | 001b8b3d-742f-53f0-b821-1d2e2b861f1f | Reference Documents - TNZ P3:1995.18
note | 9d8668f5-ebb2-53de-aa14-3c11d7314fc4 | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
note | 9efc10ea-b80d-5714-801f-ff0db13621bd | Material Test Frequency - Once per day of sealing prior to sealing commencing
note | cdcab9c4-dc7f-5303-b18b-6d3aa70aa3b5 | Target Criteria - Air temp >10°C
note | c912cfca-d91a-5ad0-89f3-fa96ee7ad913 | Action Point Records Required - Spray Sheet
note | eab79de5-3d23-5ec1-8124-8305ab1be4cb | Responsibility - SE / CE / PM
checkpoint |  | 2.06 - Field
note | f01a08c0-cde0-597c-b541-b1a51aa753fa | Material Test Method Requirement - Application Rate
note | 4790a93f-2c02-5e84-b72f-5eeed0e03fe5 | Reference Documents - TNZ P3 : 1995.18
note | b8562673-11a7-5b5f-b380-641606ac78d9 | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
note | d88d7bae-ff94-5021-b214-26519ed2c2cc | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
note | 6b8ec101-5326-52b5-95e3-828abaecb1ef | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
note | f52fa8c5-c3b8-5362-b693-9c8cb269c8d2 | Action Point Records Required - Spray Sheet
note | e9d30898-75da-5a93-becb-d8b56891778e | Responsibility - SE / CE / PM
checkpoint |  | 2.07 - Field
note | 3aafe76a-32e5-5a99-9a5f-1c263238f809 | Material Test Method Requirement - Chip spread rate
note | 5001eded-e342-5f9e-b42c-e1aa549ddc7f | Reference Documents - TNZ P3: 1995.21
note | 00098d81-0f14-5298-87e2-fc328a40ff02 | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3), Chipsealing in New Zealand (pg 435)
note | 1ed35fff-8d36-54b6-a818-5e3c3d61c94f | Material Test Frequency - Total amount of chip used to be calculated at end of days sealing
note | a5910637-a7df-5667-81f6-2d2990bd323d | Target Criteria - Visual checks meets seal design requirements
note | 6d04ef63-bdc8-58fd-8c18-07b7acda6ab0 | Action Point Records Required - Witness Point/Spray sheet
note | 63f6ba5f-4a5c-5a32-a4b3-dbb2aa604d28 | Responsibility - SE / CE / PM
checkpoint |  | 2.08 - Field
note | 666f1e8b-3a73-502e-b867-ff0ee62a79eb | Material Test Method Requirement - Rolling Checks
note | 88ae3b1b-1585-5bc5-988d-ef811f683a3d | Reference Documents - TNZ P3: 1995.22
note | a0eed3ca-c1f1-599f-987c-b002abeb6782 | Material Acceptance Criteria (Method) - Sealing Record
note | d42cac64-7c6e-50bc-8d52-db54c90c2ff6 | Material Test Frequency - for each sealing site per day
note | 1e22f789-3066-544e-a6a2-c5cc6a640e1d | Target Criteria - As per rolling requirements defined in TNZ P3: 1995.22.
note | 6eba2edd-0a3d-52b7-b1d2-d919e64e67bd | Action Point Records Required - Witness Point/Spray sheet
note | b494cfd0-e326-5a35-adc8-4ce57d7759e2 | Responsibility - SE / CE / PM
checkpoint |  | 2.09 - Field
note | 605c49a4-a115-52c5-ac68-75ebe8023c57 | Material Test Method Requirement - Post-seal Inspection
note | ddc3154f-225c-5189-b9f1-fce1eb50bcc0 | Reference Documents - TNZ P3: 1995
note | 5bdde5fc-d4e8-59b5-a599-7b8eb83412ca | Material Acceptance Criteria (Method) - Engineers Inspection
note | 2ed639d7-ef4f-5f80-8917-40b7d28add72 | Material Test Frequency - 100% of Site After sealing (within 5 days)
note | c0e21395-f41e-56da-b126-5eb860329f81 | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
note | a2f34c7f-8177-5c34-a812-fb13d8d93820 | ○ Line marking has been reinstated
note | a4747e55-62d8-5d7d-a74f-bb8b41b80b0c | ○ All excess chip has been removed from site
note | ca3c39b7-006f-54fb-b6a5-93d40cf41983 | ○ All CPs are clear from filter fabric and excess chip and any excess material removed from on top service covers.
note | d537749b-40e4-5f69-87a4-01198dced3b0 | Action Point Records Required - Hold Point
note | a25c5ab8-4ce6-511a-881e-24cec60112eb | Responsibility - SE / CE / PM / ER
signoff |  | AUTHORITY HOLDPOINT
section |  | Post Completion
checkpoint |  | 3.01 - Field
note | 7c1a2b60-fec7-55d7-8b9b-cfc09137e21c | Material Test Method Requirement - Asbuilt and RAMM Data
note | a88c8179-c342-5eaf-a645-be12fcc9050c | Reference Documents - RAMM update sheet
note | 33a55897-f0f2-5231-bfff-adc869a613ff | Material Acceptance Criteria (Method) - See Asset Management Information Plan
note | c48cc83f-5bef-5357-8b24-3cfeb86f96d6 | Material Test Frequency - After works complete
note | d360882f-7d5c-5288-ba9c-d1eeafd8bf62 | Target Criteria - RAMM sheet 100% complete and accurate.
note | 09e11103-942d-5ddb-9838-9169073bb738 | Action Point Records Required - RAMM Asset Update Sheet
note | 1e4bb71e-45f9-5499-b395-aa24f6f7c3a8 | Responsibility - PQE / CE / PM / ER