## Resources
Type | Id | Name | Values | Prompting Name | Postfix
checklist | 0ab4163e-c8c8-4724-ae7a-3f607e5c8538 | Pre-Pour Checklist |  | Pre-Pour Checklist
section | 71237582-3a25-4efc-8a32-b3e4e4d36436 | Product Detail
checkpoint | 4333faa5-c2a2-419e-b910-9350aa6a1d47 | Details
textbox | 8a2d6b97-6ca0-5d19-bbff-fc6eff68f50f | Product ID
textbox | 331e08a7-1ebb-5b3a-bbf4-d1c1f87e9b1b | Weight
textbox | 8e306097-3237-52a3-949c-0782ec8d2a0c | Manufacture Date
section | fc130f05-5623-438c-aae7-b05e04e23ce1 | Formwork
checkpoint | ad723b66-2003-4581-b4a4-95f9cd3457d5 | Check Length
textbox | d3cc0c48-0c7c-57db-a6d0-e69b140da55f | length
checkpoint | 588a3452-2c6e-437e-9a88-49dbad4e098b | Check Width
textbox | 3089d711-3eb3-56ff-9554-b1287e8801b9 | width
checkpoint | efb4ca93-c165-4251-bd74-c36d6000e9c3 | Check Thickness
textbox | 5d56b875-298a-5d6e-818b-6c6aa8661d71 | thickness
checkpoint | 1a8e3915-dbf1-48fb-82e5-c8d0d49852e8 | Check Diagnonal
checkpoint | 95d6ab43-6cb8-44f9-af04-887e532327ab | Sideform Trueness
checkpoint | 22eac8c4-07bb-4ab2-8c85-2e94cb3f4e6b | Magnets / Forms Secure
checkpoint | d8fd7fe8-67ea-4e84-871c-160a57149e99 | Splayed forms checked
checkpoint | 28411e45-3a65-420c-94bf-02bbbb34c3ec | Penotration dimensions checked
checkpoint | 671ffb8e-ef41-462a-b5f7-4ec8108b4aed | Curves / Radius Checked
checkpoint | 06f25685-01b5-4ffa-b481-723f52956de0 | Rebates size and location checked
checkpoint | 0022bb24-8aeb-4928-ae2a-c759970cc4b6 | Weather steps dimensions checked
checkpoint | bef1971e-b5d5-4e14-af31-c61d2b3621ce | Weather steps orientation checked
checkpoint | 6a523abb-30a6-4b5d-a8b0-01b49db68536 | Form release applied correctly
section | 1248e0e6-d9b5-4479-82bb-6a7ef3c0926b | Reinforcement
checkpoint | 95bb7804-b0dc-48cb-8af1-fefc91cd0415 | Reinforcement mat as per shop drawings
checkpoint | 476cb84e-4390-4a16-a028-973838ed199d | Reo Mat Orientation
checkpoint | 3439715a-5404-428c-a8ea-ea65a8870375 | Perimeter Bars Size Correct
checkpoint | 8c81e8bb-35f9-4e9d-bd81-7613742ac6e6 | Perimeter Bars No. Off Correct
checkpoint | f5d8745a-fa84-46ac-b9cf-edcddf6f53ea | Additional Bars Correct
checkpoint | 769de4c1-5735-402e-8732-66192e1cd3f7 | Reo Changes Noted
checkpoint | b6105f34-ad96-48b7-a1b8-af82b0909f36 | Reo Changes Passed By PM
checkpoint | 856d15f2-7d26-4294-a7c8-fa8cc9a54939 | COGS / Laps As Per SD
checkpoint | 8b733acb-29f4-4731-966f-acdb5e6e4023 | Any Splice 40 x Dia Min
checkpoint | 91b6b6c1-b10a-4806-8223-0aeb78f685af | Rebar Photos
section | 7e5b60d9-f482-43e4-8ece-eb4530d5b764 | Fixings / Cast Ins
checkpoint | 236e9e03-ac02-4ac8-a0cf-01401dd7bdcb | Details
textbox | 96a13377-bedf-5fe6-90dc-8d2c8aea8e6e | Strand Size
textbox | dede8aac-cf41-5415-8862-a78d961745f6 | Coil Id
textbox | 8cea9afa-90c6-55cb-b1bf-44122074d8d8 | Strand Photo
checkpoint | b0c05e99-c315-4145-8bbf-4f1a59fa46e4 | Ferrule Location Checked
checkpoint | 4f73175e-9175-4fcb-aa81-01925dbf77d2 | Ferrule Cross Bars Inserted
checkpoint | 3cc4c539-99e2-45e6-839d-0e5a49f1ce27 | Lifting Inserts as Per Lift Design
checkpoint | ae5ab204-d3f1-4f4d-8c3d-f7dfbc7f03c9 | Lifter Type correct
dropdown | c0c92514-9c1c-5012-9e12-8c505e78fae3 | Lifter Type | Leviat Edj Pro Mini 8.5T, Leviat Edj Pro Max 15T, Foot Anchor 1.3T, Foot Anchor 2.5T, Foot Anchor 5T, Foot Anchor 10T, Foot Anchor 20T
checkpoint | 3de314b4-0da6-4c49-8609-95a7a829499e | Lifting V Bars Inserted
checkpoint | 9303ec02-47c9-435f-b00e-1af94800eee0 | Cast Plates Per Design
checkpoint | 0a60a0d3-f465-466e-aeb8-d1249ffea401 | Cast Plate Location Checked
checkpoint | bcb76f99-5850-404b-9eec-8a64bca26a32 | Additional Cast Plate Bars Inserted
checkpoint | 2a3280f1-b8b9-4b44-8230-996227a5c996 | Starter Bars Correct Per SD
checkpoint | d56a1698-6525-41d5-8160-9ed714d760d9 | Pertruding Bars Orientation
checkpoint | b1d5daa5-a6b7-4ff9-91a6-6171c6b7757b | Grout Tube Size Checked
checkpoint | 60365f19-772f-407c-95af-65cd615cac47 | Grout Tube Exit Orientation Checked
checkpoint | 8cef0c00-0e0d-4914-b8bf-6e4c024aa74b | Grout Tube Photo
checkpoint | e45e9c7f-f306-4853-bffb-1879f39e1fba | Lifting Insert Photo
checkpoint | c4f4bad6-c511-4387-9322-15a4064151c1 | Cast In Plate Photo
checkpoint | bcaf0b6f-a0d1-4450-ba81-ae2853b2bf0c | Penetration Photo
section | 6775c555-3249-4f9a-95b3-cd2c5364f5d0 | Final Checks
checkpoint | b27dacd7-98ee-4e0e-a24e-95ba0b9634be | All SD Dimensions Shown
checkpoint | c0abe395-9906-4d98-931a-4590237e87b7 | Photo of For "Construction" Shop Drawing
checkpoint | f4d394f4-28b7-4848-a504-c73e867b339a | Panel ID Tag Placed
checkpoint | 32bde135-0fa8-43cd-80b3-9053211d8da7 | Product Cleared For Pouring
checkpoint | fc888160-e042-45b9-a600-c9d4b80190c3 | Inspector sign off attached below
checklist | 6c034146-61bd-49aa-be43-a449c45ac8d1 | Transport Checklist |  | Transport Checklist
checkpoint-no-value | 0faa0a2d-7ed7-47d8-b93f-eaa7551c2f20 | Details
textbox | 73c3f390-c154-553e-ac39-a8a1229394e4 | Shipment Number
textbox | 54bbc1f1-1cd6-5cda-b427-1f247c723efe | Shipment Date
textbox | 38f18811-2c33-5205-8533-9a024af52c37 | Install Date
textbox | 23bc02dc-f9ca-5a94-a61f-e3b7ba6162b7 | Time Requested Onsite
textbox | f7e917bc-62f5-59a9-a9a4-dd59c2015394 | Carrier
textbox | 579ed872-b384-5769-bca8-513ce31dfb6a | Delivery Driver Name
textbox | 0192f996-df66-58f0-b2a4-d8b6f501753c | Delivery Drivers Phone Number
textbox | 7b3efae9-9d46-5d54-a028-dd8ab32ab823 | Trailer Rego
checkpoint | 2436cde7-5040-431c-9f5e-6cbaa5f8e95e | Correct Products on Transport
checkpoint | cb4dbc40-ec2f-4435-b62d-ff4c073b7f99 | Safety Restraints
checkpoint | bc3048ab-1fbc-4584-9c5b-c5f66119d1df | Rego Photo
checkpoint | fba8dec4-29cb-4647-a38a-b21705c7c829 | Drivers Side Photo
checkpoint | b587c7a4-3cb9-491f-8e8f-4ef13d599074 | Passenger Side Photo
checkpoint | 0864fd77-74f3-470f-bce8-958d60068759 | Transport Safe To Leave Yard
checkpoint | efae3246-1196-4373-b3b6-584edb113c12 | Inspector sign off attached below
textbox | d1d025ed-08c7-57c0-9e12-64e8e96f73aa | Item Status
checklist | 1c30f522-a026-486d-a84f-b10a03ef2f02 | Defects Checklist |  | Defects Checklist
checkpoint | 527b4f3f-f3ec-449a-aac6-5b28bd73b1e8 | Details and photos below
checklist | 593559b4-d0cf-454f-916d-b2ca07efd47e | Concrete Delivery Checklist |  | Concrete Delivery Checklist
checkpoint-no-value | 592cb40a-40a3-495c-8cb3-7968eae2adbd | Details
textbox | 00d4fff8-8702-525a-bb16-2af29796b77c | Concrete Docket Number
textbox | 72d49f09-ca01-5ae9-8bf0-eef57f2d7a62 | Pour Date
textbox | 7906b908-03c3-5dc0-a0b2-b6cdc6cb0e5e | Time Batched
textbox | 50d87fea-5db7-5e9b-a18d-91e930eb101d | Load M3
checkpoint | f969e7af-20ef-4487-963d-c470a2d67dfb | Picture of Concrete Docket
checkpoint | 3799c218-8671-41b2-ac33-8b7c3a0fd8fd | Load size match order sheet
checkpoint | 28400e61-b2ab-48eb-8ac4-1f8a446c2c3a | Mix type match the order sheet
checkpoint | 47a6ad5d-dae3-4128-b7b8-7965ecbb7ad0 | Mix color match the order sheet
checkpoint | b9259093-0262-4fae-ba49-be674e4ba849 | MPa match the order sheet
textbox | ef16278c-b461-5ff1-abb1-0718380cc9fc | Concrete Strength |  |  | MPa
checkpoint | 06c16106-c31c-42a1-9d01-49f1d28796d7 | Spread / slump within range
textbox | c178acd7-a162-5912-aa03-600f2714cf75 | Spread / Slump in mm |  |  | mm
checkpoint | 2c14a410-ef01-4ef6-8ca3-963c09661c04 | Water Added (N/A if no)
textbox | 174650dd-de95-51b4-8ab7-e5b179cf6138 | Quantity of water added
checkpoint | 033ab66e-528f-48f9-b427-2be90e1cd10f | Concrete test taken (N/A if no)
checkpoint | 76cb840b-5fea-44e1-93a7-8f38b56287b3 | Picture of spread check before dispatch
checkpoint | 644e4a08-4619-4900-8321-8dcea55cdb2f | Inspector sign off attached below
checklist | 54a90f31-efa0-45ac-b1e7-5729454f76f5 | Onsite Install Checklist |  | Onsite Install Checklist
checkpoint | 9ec3c215-a904-453d-8499-bbefc9c1d2ce | All Electrical Equipment is tested and tagged.
tickbox | 4ac7017e-3510-5a79-ad06-658e533a74a9 | Small Hammer Drill
tickbox | 34ea1e43-951d-5074-83aa-40a52df2b8df | 20mm Bit
tickbox | c8948549-b895-533d-87a7-273a759bc793 | Mash Hammer
tickbox | 527bd99f-a372-547d-9a4c-60ec2881199d | Rattle Gun
tickbox | 8c37fac3-66de-5882-8a6c-cd77f24f67be | 30mm bit
tickbox | 02450704-feaf-5d1c-b9a6-803662cfca37 | 32mm bit
tickbox | b996b4ed-b172-55ed-beb7-7ca0ad18fc81 | Batteries & Charger
tickbox | fff9dfb8-e3b8-5adf-b428-e220e11bda23 | Extension Leads
tickbox | 89075447-0f12-5136-a686-7ee570c1945d | RCD Box
tickbox | 6e7f0c75-39b4-5e26-8042-f764947d3968 | Generator
tickbox | f36cfee5-9de5-5ed7-972c-a1b3ce9cdf52 | Level 2000mm
tickbox | 5454b43b-3eb4-50c1-8fe2-d76f31d047f3 | Berker Bar
tickbox | 866444d6-40c1-5113-a749-d0b2dad880a5 | 20mm Prop Bolts
tickbox | cd4e927a-60e1-536f-a49a-d11c1fe28a3f | PBI Bolts
tickbox | b2d679a1-1a55-5235-8151-73b336e0656b | Packers (20mm, 10mm, 5mm, 3mm, 2mm)
tickbox | 305f8d79-2243-53bc-ab22-976123d5b37f | Dowels
tickbox | bf4d16cb-3346-591c-b3f9-1037490f7070 | Stitch Plates
tickbox | f337cc8c-141b-5280-b30c-eb2e99a8bcf6 | Ladder/s
tickbox | a88fe6ff-7bd3-503d-b96c-e94ef218cde1 | Brace Locks & Brace Pins
tickbox | 943b3a87-76da-517c-a5b3-fb1edd0b3747 | Lifting Clutches
tickbox | f4d020a7-c4d9-5839-b48e-36542ea89db6 | Guide Rope
tickbox | 7c1c0a86-9fe8-5a80-aeb8-8ddb08dd3a66 | Release Rope
tickbox | 279bd3a7-0f23-51c3-9c54-d0be1e3e9b04 | Shovel
tickbox | d32ecb34-f7c9-594e-83b8-3bf00bc0d556 | Broom
tickbox | e5a00ee3-2760-5b2a-ab04-f117925fd1e1 | Fuel
checkpoint | 8a250c7e-5704-4bae-b39b-36e49f34f4d8 | Are any hazards impacting safe panel installation?
checkpoint | 7a6716a7-b097-447e-adf1-4efbf42ce7c4 | The Shipment of Precast panels match the Install Sequence
checkpoint | 6811f69e-be84-46a2-a215-b241e62ac4d2 | Panel numbers and location match as per the marking plan?
checkpoint | 8c396d5b-2f97-4a74-87e1-48a4741ff701 | Dowel pin set out and packer locations are as per drawings?
checkpoint | 5f6b719f-e3f9-4800-b0c4-1899d7c3f12a | Dowel Bars are correctly aligned, and the size and length are correct?
checkpoint | 27db8a0b-e505-4b62-ba86-e5e289e51066 | Is correct-size foam doughnuts used?
checkpoint | 63a80ed4-fdaf-460b-9597-a76048256610 | Are Panel R/L heights are correct?
checkpoint | f1fa6e9a-608b-4263-9f74-322aeb1f35c8 | The panels are Straight and free from any bows.
checkpoint | b54649e7-d62f-4e7a-abbd-98f8b1ad8956 | Ferrules, cast plates, rebates, and checkout are correct and as per drawings.
checkpoint | 710f31d6-704c-48f3-8d1b-1f3852bffa32 | Panel Props are secure and brace locking pins are all locked?
note | e9b392a7-bac0-593e-aba7-b6d712ea1ac4 | Take a photo of Props installed with pins and lock.
checkpoint | 8a98f717-6d49-4643-b92a-90b8bfa5c52d | Are Props erected between 45 - 60 degrees angle?
note | 28e25069-beca-56a8-a4f6-4e99f0f7c371 | Bracing in any alternative locations?
checkpoint | 95036c6b-3800-47a9-9778-c3b14ea53319 | Site Welding of Stichplates, Corner plates, and any other.
checklist | 54bedb5b-298f-4b25-8593-da54ab1495ed | Grouting/Patching Checklist |  | Grouting/Patching Checklist
checkpoint | d07b817e-0d00-4f96-8057-b87bab3e1107 | Have the required gear for works
tickbox | ccda7f4a-e865-5d06-9b87-c98bbd998614 | General Grout
tickbox | f08c97cd-dee4-5d16-81bf-c70fc6313acd | Light Weight
tickbox | 744bbd6b-1887-596e-a8c8-dddf8af10f6a | Fairing Coat
tickbox | f010a600-b73e-5a55-819b-c194d1098596 | Bucket
tickbox | 75041bfc-15e2-522e-b0b4-ea67779f7db9 | Mixer
tickbox | c47af38c-8413-5831-818b-ef4e77a6f4b2 | Water
tickbox | 6616cad8-6072-527b-a015-148d9729a446 | Scraper
tickbox | 1da08cb4-09e6-5976-b87f-f14e037fade0 | Trowel
tickbox | 8aa8326d-136b-533e-91b4-531ea05e2aa2 | Extension Leads
tickbox | 59ec39ef-64ed-5944-9bc0-5782e099136e | Ladder/s
tickbox | 6b5f32ca-05a0-5b62-9995-241e15fe3a23 | Sander
tickbox | 8779c597-76e7-5907-84ae-de48f4211fe1 | Sanding Discs
tickbox | 672a0da9-0e69-5118-9986-98064bd951ae | Batteries & Charger
tickbox | 4fa521c8-93e3-54ce-b725-db0c0a38920a | Generator
tickbox | 36ff2621-5369-5a65-b8fe-417e394c493d | Grinder
tickbox | e3df2163-7a5a-5d7e-82d1-7b99ee5228f9 | Caulk
tickbox | 7a3c0cef-ff3f-5ee4-8bc7-0dfa8f494c88 | Caulking Guns
tickbox | db271ed1-90f4-5a06-b749-8cd6bc50c1eb | Diamond Cutting Disc
tickbox | 1cab87fa-5703-565a-b688-76f201957a31 | Diamond Cup Disc
tickbox | adbf014b-4b6b-536d-8985-12c3f82c7782 | Broom
tickbox | f959c506-4e50-5137-b8e5-c81f8e4b1dc2 | Fuel
checkpoint | c77fa268-f44d-428b-9575-f17fb9fe56ba | Does the grout match the client's architectural drawings?
checkpoint | a4b5c614-c527-4ae6-9047-3c0589e52a44 | 20mm Panel base for each panel is filled?
note | 15fef299-21aa-5a06-bd3f-681ac99c0cd2 | Filled Panel base photo
checkpoint | a105e8f5-e1a9-426d-8ad5-4c397205c790 | Grout Tubes location checked and cleaned.
checkpoint | 484a2566-abe8-4eda-99d5-938a448bc481 | Grout Tubes for each panel are filled?
note | 0f845626-6ac9-5d89-a121-00ed868231c4 | Filled Panel Grout tube photo
checkpoint | c9bd6a2b-5db2-4eec-856b-a8675775fb5b | Cast Plates for each panel are filled?
note | 8715808c-db81-5700-b6ea-a6c5bc97be2e | Filled Panel Castplate photo
checkpoint | 30be046f-511b-46a3-9a8a-705d77c29bd1 | Lifters and ferrules for each panel filled?
note | 1e01d5c0-e046-51c0-97b6-e05da78804a6 | Filled Panel lifters and ferrules photo
checklist | fd451922-3d32-4bdd-8ccf-2885925a0436 | Pre-Pour Checklist Strand |  | Pre-Pour Checklist Strand
section | 3b4c79d6-a607-4331-b4be-fd7bc444b2e7 | Product Detail
checkpoint | 57c29981-cbcc-473a-8dfa-f73880f835a1 | Details
textbox | 7233ee70-ab58-5cbb-b2c6-c0fbe21720d5 | Product ID
textbox | 00431790-c665-59a3-8cb9-315b438d38bf | Weight
textbox | 1b04ade1-e485-551e-8f0f-da7cb090dcdc | Manufacture Date
section | d864ac16-f363-4f78-98aa-9acdd772aef8 | Formwork
checkpoint | 6da9b84d-61dc-4b4b-92c1-d3734743f0ee | Check Length
textbox | dd84890b-3959-51ee-ae5d-dc0a1b676a39 | length
checkpoint | 9abc2ea3-b8cd-4533-b99e-d4640b033bfd | Check Width
textbox | 50e0b2c0-6701-53ba-9122-7bda59d59e52 | width
checkpoint | 786405f2-55d4-47e3-ac70-1350f0ab87c6 | Check Thickness
textbox | 97ece5af-4211-505f-8bb8-e3a010263e54 | thickness
checkpoint | c091e3b8-c064-4db3-a4d2-e2c81f5e4f07 | Check Diagnonal
checkpoint | d8886378-6d11-49cb-91af-64e46f085a76 | Sideform Trueness
checkpoint | 55f91b35-757a-4a2f-b9c1-17005a27daee | Magnets / Forms Secure
checkpoint | 6470a893-ee96-4ddc-8787-b79162978e75 | Splayed forms checked
checkpoint | b195679c-a956-4b7f-ba2d-68b5d8d41040 | Penotration dimensions checked
checkpoint | 866f1f0a-2076-42c2-ac02-13f22f43959b | Curves / Radius Checked
checkpoint | f435282e-8a0b-4fd4-8713-f63ff861ffa9 | Rebates size and location checked
checkpoint | f47dcb5c-ae35-4ab2-9055-0543e8a6a388 | Weather steps dimensions checked
checkpoint | b43f05de-eea8-43de-93f0-1f742753e195 | Weather steps orientation checked
checkpoint | 2215c343-4161-488a-b478-8c58c78634db | Form release applied correctly
section | 0fad1d38-b744-4b4e-b072-da2574f70a4c | Reinforcement
checkpoint | e73ec773-a5ac-4e13-848c-192be0f61d5e | Reinforcement mat as per shop drawings
checkpoint | 12f3ea7c-6a09-4742-b0fb-a0e4825d93a6 | Reo Mat Orientation
checkpoint | de70b218-06a0-45aa-ac81-3533c3c74d4b | Perimeter Bars Size Correct
checkpoint | f2505313-f76e-48e1-9570-819cebb9ef0d | Perimeter Bars No. Off Correct
checkpoint | 5673881c-138d-431f-888f-5e4f062a1689 | Additional Bars Correct
checkpoint | 02ab1c29-3a7b-46b0-9814-64600a745521 | Reo Changes Noted
checkpoint | 75b69920-f37d-49d6-acae-07add1224d27 | Reo Changes Passed By PM
checkpoint | 4fc04166-f8d5-4f2a-bb47-045cbf113947 | COGS / Laps As Per SD
checkpoint | c0667ad6-3e05-42a8-9374-281afc317d6f | Any Splice 40 x Dia Min
checkpoint | 74202838-93cd-414c-890c-85c220e409b5 | Rebar Photos
section | 5f54e234-6665-4602-bb93-151a81d6281e | Fixings / Cast Ins
checkpoint | b0ab1932-b633-4810-88e3-dff9fbd19940 | Details
textbox | ce8a454b-0af1-5572-89cd-fed6424b70b4 | Strand Size
textbox | 83c74cdb-7d87-599b-935c-8240f788f3e9 | Coil Id
textbox | 99487dd4-5f97-5570-b057-c611c7f24d10 | Strand Photo
checkpoint | 6988efb1-4bc3-4ecc-8b89-8461b8c502ab | Ferrule Location Checked
checkpoint | adf465d7-29a8-4292-9279-ab32b5461589 | Ferrule Cross Bars Inserted
checkpoint | f7f1eada-a7ed-4e5f-afbb-fa6b6e72ff4c | Lifting Inserts as Per Lift Design
checkpoint | 0d5c03ed-5b69-48cd-b258-514523e59679 | Lifter Type correct
dropdown | aad0581e-3cbd-54d2-871f-24f963ceac49 | Lifter Type | Leviat Edj Pro Mini 8.5T, Leviat Edj Pro Max 15T, Foot Anchor 1.3T, Foot Anchor 2.5T, Foot Anchor 5T, Foot Anchor 10T, Foot Anchor 20T
checkpoint | d6b5d77e-36d2-4250-8f7e-05f7699b36bd | Lifting V Bars Inserted
checkpoint | 719f68db-d6e1-499e-ac67-9ecadda5d10c | Cast Plates Per Design
checkpoint | b8df0af0-57c5-4532-adbd-0ab64db073c8 | Cast Plate Location Checked
checkpoint | 3869a242-451c-4229-bee2-b163fac05989 | Additional Cast Plate Bars Inserted
checkpoint | 6fcd6a4a-3ec1-4347-a039-517db51a5f70 | Starter Bars Correct Per SD
checkpoint | 17f0f6c1-c3c3-4772-bae3-bffa348cf5c2 | Pertruding Bars Orientation
checkpoint | f9ac8fc8-698c-455c-8053-679835c62e1b | Grout Tube Size Checked
checkpoint | 8c38edf5-a648-4c43-9667-de11406e3e18 | Grout Tube Exit Orientation Checked
checkpoint | 3f0a76b2-c13c-4f7c-aaf4-174d1d09b759 | Grout Tube Photo
checkpoint | 3a2d9fe1-1e9f-4802-91ad-72b00054d3e8 | Lifting Insert Photo
checkpoint | e1b50328-5f4c-4a03-9dc5-8768e9a2041c | Cast In Plate Photo
checkpoint | f15e079d-23cf-42f4-b657-29257ecdee38 | Penetration Photo
section | 49682576-074a-4bff-acdd-774fec400acc | Final Checks
checkpoint | 430639d0-17cb-4254-a56a-53752225f1d1 | All SD Dimensions Shown
checkpoint | 3ad6f01c-832d-4060-b1f3-7c13e1cee1c2 | Photo of For "Construction" Shop Drawing
checkpoint | feeb23db-3e1a-4c67-9a3a-03e7d5b7e0c6 | Panel ID Tag Placed
checkpoint | 7e09dfc1-e350-4b96-beaa-ae5a40fcac08 | Product Cleared For Pouring
checkpoint | ebdcbe3b-aaab-4f0e-8d91-e7e46868c5dc | Inspector sign off attached below
checklist | 69d9751a-978c-48d8-b90d-8ab305ecdf20 | Pre-Install Checklist (Set-out) |  | Pre-Install Checklist (Set-out)
checkpoint | 08a987fe-705a-4127-bacc-48163d8832d0 | All Electrical Equipment is tested and tagged.
checkpoint | 58ca14d4-d1bc-4b34-96ae-20f803fab821 | Have the required gear for installation
tickbox | 474305e9-509b-5c61-a586-bada8ae2c69a | Laser level
tickbox | 37518730-3052-5f2b-85df-fdb30e40f5f6 | Tripod
tickbox | b9cb4d83-86c9-514f-9c12-e6e3e6b5c95c | Staff
tickbox | 4e021244-e2ce-5070-b047-66f462f33f70 | 30 mtr Tape
tickbox | b883938d-fea5-598f-b139-251a3bfde569 | 10 mtr Tape
tickbox | 52effd98-5024-57a8-9d31-8fb9a3d0abd5 | 300 mm Combination Square
tickbox | 53bbd56c-5f46-5719-b25a-4483f8455fb1 | 600mm Set Square
tickbox | ed23a68b-0b9d-5512-8a53-f91cb10876d8 | Level 2000mm
tickbox | da9d4fe9-f697-5877-b5f0-7c06e93cc1f7 | Level 500mm
tickbox | 4542e1d8-2629-565e-b932-eb2bc8625d37 | Pencils
tickbox | 1921dcbb-0b00-5976-b185-f31be3a38020 | Grinder
tickbox | be82982c-235f-5ebd-a06e-614d6fd563c8 | Batteries & Charger
tickbox | 27dc19c7-d761-55c1-beb1-943b9c8accee | Concrete Cutting Disk
tickbox | 59b61e90-ffe3-517a-b3cd-0bcbfb245284 | Large Hammer Drill
tickbox | fe3b945b-4683-589f-bd2a-8ac47556c3a7 | 32mm bit
tickbox | 4cc2fc27-6e98-577d-a8bf-532ac264f758 | Core Drill
tickbox | 9d1a3ab7-3b5e-5bfb-8219-031502c4978d | 50mm Core bit
tickbox | f0304790-e358-5321-996e-9d7c49910fb4 | 28mm Core nit
tickbox | d1d0c32a-b088-5fab-aab1-22586e819d5f | Extension Leads
tickbox | 51e4b019-8501-5a24-bed8-cd3dcff54b77 | RCD Box
tickbox | 955b6fcb-a2df-5c70-9e3b-800e2ef9f746 | Generator
tickbox | e8983efa-3bc2-5ac5-bb80-c05e1611c32b | Hose and Fittings
tickbox | 667aed42-8035-565f-917f-108ea61d63f1 | Shovel
tickbox | fdfca348-4f5c-5267-aec1-e3b252cbba16 | Marking Paint
tickbox | 2d41a192-62cd-50f2-9d41-47dd73e658fd | Broom
tickbox | 0debcef9-1959-5bf6-a547-54a54a29a69a | Fuel
checklist | e90f1869-561d-401c-b451-543bfb3da2be | Pre-Pour Checklist 1 |  | Pre-Pour Checklist 1
section | 1f5ad4e3-2440-49d1-8cc6-8da58cf41420 | Product Detail
checkpoint | d90bfa34-8b4c-4a15-bb28-723c46deeef4 | Details
textbox | ce8b5be3-ea75-58b1-a3e7-2967a0383f77 | Product ID
textbox | 57ba2d73-fb61-53ed-8da5-4f1f3c774daa | Weight
textbox | b5306076-958a-5cc4-8f8e-67426ad1dc5f | Manufacture Date
section | 42c9fa11-750c-4886-a6b6-88596bff77de | Formwork
checkpoint | 3f0cdcab-4b3f-476d-b56b-b16ee107e388 | Check Length
textbox | aa821181-55ff-5434-9c60-590f582ffa1a | length
checkpoint | 52ec7df5-ba4b-4cfb-a76e-660dcfff8f63 | Check Width
textbox | 24e33343-a8e9-549c-b3fa-c26f874bb8c4 | width
checkpoint | 478266b9-d083-4b39-8262-306e351e2909 | Check Thickness
textbox | 0570df06-5d73-5fa2-a207-7cd5401af655 | thickness
checkpoint | dcc56b68-3340-44ea-92f1-17fa5704ae43 | Check Diagnonal
checkpoint | 5320e261-0158-45f1-80f6-3ac8bfd372dd | Sideform Trueness
checkpoint | 826c421c-3819-4e01-a290-04d4799f9553 | Magnets / Forms Secure
checkpoint | fbfd6b1e-be95-4fed-ace9-bd78d0e8e3f9 | Splayed forms checked
checkpoint | 809900d9-8079-4836-8656-f6783a846e5c | Penotration dimensions checked
checkpoint | 344dceb0-c2d3-4e2c-afd4-2f75ec739272 | Curves / Radius Checked
checkpoint | 26a843b1-0618-4e73-9fb7-82c2d06c617c | Rebates size and location checked
checkpoint | f2115ccc-c889-4060-9566-a6369573178a | Weather steps dimensions checked
checkpoint | b8c4f4f1-454e-4936-a39c-ed94b5d75f1e | Weather steps orientation checked
checkpoint | 26681f59-631d-4176-aa8e-8dcb2fcc9401 | Form release applied correctly
section | 67e25267-f2b1-4a07-855d-ecbd0989ca8f | Reinforcement
checkpoint | 2f21ec73-92fc-4e82-836f-b3989297918d | Reinforcement mat as per shop drawings
checkpoint | 1e0aeba2-4fe3-4650-8304-d891167a56a9 | Reo Mat Orientation
checkpoint | 0c210185-a25b-4466-84b2-1a5e37dcaa5d | Perimeter Bars Size Correct
checkpoint | 9a489e36-4f9d-4f76-b76d-f289d5e9e5b8 | Perimeter Bars No. Off Correct
checkpoint | 947f18c1-05a0-4f0e-9d2e-8b6895718245 | Additional Bars Correct
checkpoint | 0921695a-8f0a-471f-b834-4beb5804a7a0 | Reo Changes Noted
checkpoint | 1adcf415-b514-4ed5-ab0b-4a5706df10d7 | Reo Changes Passed By PM
checkpoint | 2b194a7c-1046-4ad3-af5a-5e70144d6d87 | COGS / Laps As Per SD
checkpoint | 5dcaf330-b436-4a1a-a794-710950fb0b0a | Any Splice 40 x Dia Min
checkpoint | 78b57408-913e-4838-8887-f9f714bfe8d9 | Rebar Photos
section | 6abd83fe-cb5a-4016-b8af-151bbb00796c | Fixings / Cast Ins
checkpoint | 2a353ad3-4ca2-4a79-a2ff-22f917e27dc8 | Ferrule Location Checked
checkpoint | 976aa919-133c-4371-af4a-65684fe4851d | Ferrule Cross Bars Inserted
checkpoint | 014bcf87-a1fd-4abd-ab69-4cf240288554 | Lifting Inserts as Per Lift Design
checkpoint | 04949cef-6019-4944-9abf-bc21c636b45d | Lifter Type correct
dropdown | 98ba53ce-8947-5e57-b8b0-b08b91d643fc | Lifter Type | Leviat Edj Pro Mini 8.5T, Leviat Edj Pro Max 15T, Foot Anchor 1.3T, Foot Anchor 2.5T, Foot Anchor 5T, Foot Anchor 10T, Foot Anchor 20T
checkpoint | 0e605e4f-634a-42b2-97b8-af21d479bcf2 | Lifting V Bars Inserted
checkpoint | c4ec3f31-2fc9-42de-882d-31d8f5f7c1a6 | Cast Plates Per Design
checkpoint | 140de006-93d1-4cc6-8d8a-175509f130b2 | Cast Plate Location Checked
checkpoint | e4b203fb-fcb1-4e06-93dc-1fbccdd4ec34 | Additional Cast Plate Bars Inserted
checkpoint | 1ef55d89-2b7e-4009-81c3-5e8f3153538a | Starter Bars Correct Per SD
checkpoint | e446f9b8-7a10-4207-93df-b1e230f0ec45 | Pertruding Bars Orientation
checkpoint | a417c0c9-137f-42cb-a33e-36be0df4875b | Grout Tube Size Checked
checkpoint | 77f6b57d-9e42-4987-acff-cc1cfadef084 | Grout Tube Exit Orientation Checked
checkpoint | 84a235aa-1b45-4714-9676-71e05dbd6e80 | Grout Tube Photo
checkpoint | 3814317c-2f36-41f8-90ff-3e82d38d9f19 | Lifting Insert Photo
checkpoint | c1b2e65e-761e-4cbd-8e49-2327b604394e | Cast In Plate Photo
checkpoint | 7f6e72fd-61e0-4019-aef5-f1811355e1b7 | Penetration Photo
section | 21422afa-f6af-4343-83e4-64da9761b74d | Final Checks
checkpoint | 6c8bbf16-a6ff-4bd9-8ed4-933a91d76417 | All SD Dimensions Shown
checkpoint | 9bfb6b82-4553-425d-8c5d-f7b11ccef887 | Photo of For "Construction" Shop Drawing
checkpoint | f6a6f3c3-e8de-4f22-bb4b-82a888ed9b8d | Panel ID Tag Placed
checkpoint | 788889ae-a4ca-46d9-a1b6-b83c0a5d78c8 | Product Cleared For Pouring
checkpoint | c23f8dac-cfd1-4d5b-b829-38f3c8573c22 | Inspector sign off attached below
checklist | 22be868c-7a4e-48f3-b51b-0fbcb7efdf87 | Site Details |  | Site Details
checkpoint-no-value | 4cf5d2d2-43cf-48e6-a703-f391ccaa7fb4 | Site Details
textbox | 80f12b4c-891d-5984-9ae8-345ebfb15f32 | Number
textbox | 1f1a1b7a-4b89-5458-b91e-8ab88c4cf9df | Name
textbox | ef4bce91-9955-5b8d-bd0b-b4bdfc381620 | Customer
tickbox | bf247050-efe6-59e3-826a-23258e483e48 | Mark Job as Completed
textbox | 0079152c-4e8f-5664-bc2e-59938031f242 | Address
textbox | baf185f7-0bb2-5862-95ab-96b81b28c498 | Contact Name
textbox | 17c870e1-b393-57aa-acd8-00ebf277a5a9 | Contact Phone Number
textbox | 5acf748e-296d-54fe-b7f2-f959f536613f | Install Co-ordinator
textbox | 20ddcc7e-a008-5c4c-a23f-60b721f855ce | Install Co-ordinator Contact Number