## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-068
Revision : 1
Client: |  | Surf Coast Shire |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Fischer St Road Safety Project |  | Trench Grate |  | Name: | Jackson Kay | Name: |  |  | Name: | Simon Jawoski
Contract No: |  | T24-015 |  | Specifications: VicRoads Standard Specification – Section 703
|  |  |  | Structure / Component: Drainage |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Fischer St / Inshore Dr |  | Date : |  | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | Inshore Dr |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP | QMP, TMP, JSEA, SWMS, WP | Visual inspection | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
| Trench Grate Material Procurement |  | Prior to commencing any activity | Approved durham ductile heelguard trench grate and frame product NO. CHP30C or approved | Drawings | Check Material Specs | ITP SIGNED | HP | Project Engineer/ Site Foreman | N/A |  | N/A
2 | Construction Works
2.1 | Setting Out |  | Prior to start | Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works. | 703.17 | Verify | ITP Signed | HP | Project Engineer/ Superintendent
2.2 | Temporary Drainage Provisions |  | If Required | If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place. | Cl 703.18 | Visual inspection | ITP Signed | WP | Project Engineer/ Site Foreman | N/A |  | N/A
2.3 | Bedding |  | Each lot | All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively. Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm. Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted. A Slurry of low to medium slump concrete should be poured on the base of the excavated trench prior to placing the PVC in position. The Height of the slurry bed should be determined based on figure c in the intallation guildlines | Cl 703.21 Installation guidelines | Visual inspection | ITP Signed | WP | Project Engineer/ Superintendent | N/A
2.4 | Joining PVC sections |  | Each lot | Place each section of PVC in position under the string line. Align each end of the connecting PVC/frame sections so that they are touching. use clamp or bolts to hold the PVC/frame sections together | Installation Guidelines | Visual inspection | ITP Signed | HP | Project Engineer | N/A
2.5 | 1st Pour |  | Each lot | Pour Concrete to approximately half the depth of the excavated trench. The concrete should now be compacted to remove air pockets and ensure that the grooves of the. PVC trench are sufficiently filled. | Installation Guidelines Drawings | Site Inspection | ITP Signed | HP | Project Engineer | N/A
2.6 | Final Pour |  | Each Lot | The final concrete pour should be completed to finish height, with the finish surface being graded towards the trench, as required. | Installation Guidelines Drawings | Visual inspection | ITP Signed | IP | Site Engineer/ Site Foreman | N/A
2 | Tie Into existing curb |  | Each Lot | Transition from trench grate to existing curb in a neat transition | Drawings | Visual inspection | ITP Signed | HP | Site Engineer/ Site Foreman | N/A
2.7 | Joints |  | Each joint | Transverse joints constructed at intervals not exceeding 2.5m. Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section). Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen | 703.26 | Verify | ITP Signed | IP | Project Engineer/ Site Foreman | N/A
2.8 | Backfilling |  | Each Lot | Not earlier than 3 days after casting. Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified. Layers shall not exceed 150mm compacted depth | 703.29 | Verify | ITP Signed | IP | Project Engineer | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.