## Abutment Riser
AR-01 | Abutment Riser | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Testing
section | Transport
Checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Final Inspection
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
checklist | Checkers Checklist
checkpoint | Overall Measurements
checkpoint | Ferrules - Measurements & Size - 8 x M20 x96mm
checkpoint | Lifters Correct - Position, Size, Orientation - 2 x 2.5T Edge Lifters
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 40mm
checkpoint | Panel Thickness confirmed
dropdown |  | 100mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Edge Lifters 2.5T x 4
checkpoint | Ferrules - Measurements & Size - 8 x M20 x96mm
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK -
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Use Timber Formwork
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Check Concrete cover around reo 40mm
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required -Off Form Steel Trowel
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER |  | signoff?