## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
6670fef5-5b02-4c57-a457-1ae520042efc | checklist | Checkers Checklist |  | Checkers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
0c2d7142-7a86-478f-adde-6ba96fda4fb7 | checkpoint | Overall Measurements
35b75e42-7dbd-4bca-8f08-acb38ff97649 | checkpoint | Void Correct Position
0907d84d-727c-4bbc-a73f-80bc6755add2 | checkpoint | Ferrules - Measurements & Size - NS / FS
ab394b96-a0db-4c1e-a91c-280e012257da | checkpoint | Lifters Correct - Position, Size, Orientation
3a8aa315-c910-485c-b0e0-0526f08460cb | checkpoint | Fillet is Installed
c7f478fd-64d8-4c72-a48a-ffd3a3a5a77a | checkpoint | Check Concrete cover around Reo 30mm
c286c579-5052-4d84-ae77-3e088454c81f | checkpoint | Panel Thickness confirmed
124d4994-8aea-52cc-8b12-06063f89d3fa | dropdown | Panel Thickness: | 150mm
a59caee6-c377-4868-9dd3-4e31f70e7946 | checkpoint | Magnets are 100% Secure
a46b514e-04a9-4f8e-92f8-07addacbda04 | checkpoint | Panel is Clean
de0635a3-2505-406f-b5ba-a136542e554a | checkpoint | Photo Taken
c1afc747-73cb-4bc0-9f4f-c38cefcfe3fe | checklist | Installers Checklist |  | Installers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
e7e1223f-6d84-4864-88c1-d7ad5a8a57be | checkpoint | Complete Material "Bucket List"
2a116148-db83-5d9f-8e09-17be670a021e | textbox | Eye Anchor - 2.5T
8fc9886c-3c56-5393-9613-a2f1a6df5dd9 | textbox | Ferrules - M20 x 96mm
ba533381-12b7-5bd5-9f24-3802ddbe9464 | textbox | ID Plate
9fa1c0b0-d39a-4227-b990-b2e8dbd4d587 | checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
e09238c3-b923-4e66-8492-48adeb0c559c | checkpoint | Apply bond breaker or wax 1 2 3
fa634608-1bf7-44a6-8526-735d7c436229 | checkpoint | Temporary Fix ID Plate to Formwork
d3e8dc5d-f1a0-4ace-bb88-5ae1a54933dc | checkpoint | Use Bridge Plank Mould
3135d41e-898a-4966-97b4-56859029d9ab | checkpoint | Install Reo as-per Shop Drawing Plan
b19d8a90-c2ae-469a-a0b2-866df9888741 | checkpoint | Lifters to be Firm & Square against Formwork
b522e787-697e-4c2f-91d6-0b722877cbbb | checkpoint | Check Concrete cover around reo 30mm
dc44078e-e415-44b2-bd57-167df1516dcf | checkpoint | DOUBLE CHECK EVERYTHING
b7b2c635-012c-4c30-8c04-026750cec3a9 | checkpoint | Finish Required - Broom
e9d7ce75-5637-4b94-aa70-b38c8a66dc68 | checkpoint | QA - Final Check of ALL measurerments & Photos
c6e69fc3-9ec3-47b2-8b1b-5b47bcfb96c0 | checkpoint | QA - Concrete Mix N40 Panel Mix
747a41f2-3af5-471a-8d1b-7b535f72f011 | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
81c09d0b-1dc6-4364-bfc1-f9eb51c0065e | checkpoint | CONCRETE TEST TAKEN
7577081a-a9a8-54d8-a456-8483478f243e | date | Pour Date
2687b6f4-8a69-47b5-8670-fb01f56271da | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
eb2bd350-8f0f-4361-9001-d8bf137847d3 | signoff | Request Signoff
176dc775-fc55-44a1-bfd5-c8c4470e66fd | checklist | Installers Checklist (Abutment Base) |  | Installers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
71c682bb-8d9f-4845-8b30-f569e714e38e | checkpoint | Complete Material "Bucket List"
611f4656-584a-5b6f-a568-f444066de8e3 | textbox | Foot Anchors 2.5T 170mm
9ba35f45-736c-571e-aba1-dbc7579ea698 | textbox | Ferrules - M24 Elephant Foot
3bf09914-daf4-5f01-b4e1-01dd53675ad6 | textbox | Grout Tubes 290mm
2d5b6c29-3fd0-5512-9efb-5b4e306a2d1f | textbox | ID Plate
10d3b100-e207-4a17-a469-a5f78e482afa | checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
6df5dbcc-4031-48ab-8af8-60eb52c45125 | checkpoint | Apply bond breaker or wax 1 2 3
229300ab-e0c9-4e74-9716-5b2811992dab | checkpoint | Temporary Fix ID Plate to Formwork
b2dc9879-999f-49fb-b220-28f288f573c7 | checkpoint | Use Bridge Mould
34a68c14-b8d6-4cfd-9758-17ae06fae196 | checkpoint | Install Reo as-per Shop Drawing Plan
5d446d86-1f57-47f5-bb61-d3ffd5c3de12 | checkpoint | Lifters to be Firm & Square against Formwork
ff91ef80-e498-466e-9cba-6ae18ae81ed1 | checkpoint | Check Concrete cover around reo 30mm
e2db7e73-da3e-4d60-a050-41fd8102a33c | checkpoint | DOUBLE CHECK EVERYTHING
a34032f3-a9d1-46f6-a24b-fdb77d117e5c | checkpoint | Finish Required -Off Form Steel Trowel
be63e9d1-6f01-456e-aa11-3a7c8fa9b05b | checkpoint | QA - Final Check of ALL measurerments & Photos
b855ee68-c773-40e6-9258-a0950f2a1170 | checkpoint | QA - Concrete Mix N40 Panel Mix
99c15226-ce7a-453f-bb1d-e7fd55bde3ae | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
108c85d1-22a1-40d9-868f-5245868e5bf1 | checkpoint | CONCRETE TEST TAKEN
4907bbd7-a393-5838-85f9-ad1a953c7583 | date | Pour Date
c6ea8264-52fc-437a-956d-6b0822edcf7e | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
8354c8c7-4812-49e2-a57f-0efbcd321540 | signoff | Request Signoff
555f739e-e9cc-4ee9-9223-d897bbc6253c | checklist | Installers Checklist (Abutment Wall - 794mm) |  | Installers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
4136725e-fc46-4366-98b5-5202458857b4 | checkpoint | Complete Material "Bucket List"
aab92e53-abe5-589b-a6b0-50e7d233fe88 | textbox | Foot Anchors 2.5T 170mm
f3cf2333-0c12-5bcd-8bf8-7d2adfb3a246 | textbox | Grout Tubes 290mm
414495ee-fbd5-4bf6-8cc0-cf0a19dce206 | checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK - Wall Height 794mm
dfa7d738-8256-4634-bdc4-cff814b7b0b0 | checkpoint | Apply bond breaker or wax 1 2 3
5a155910-2129-4361-ae5b-d2897811ea1d | checkpoint | Temporary Fix ID Plate to Formwork
44427fb4-702a-4d05-81fe-8574e7a244dd | checkpoint | Use Bridge Plank Mould
e9dacad2-751e-448d-9b65-8f326c8ff323 | checkpoint | Install Reo as-per Shop Drawing Plan
65222d00-63c7-49f5-b3cc-c3652921f836 | checkpoint | Use Bridge Mould
d41abaf4-294b-48ea-937f-8f4313f24f0f | checkpoint | Check Concrete cover around reo 30mm
3f9ae984-a053-4530-87d2-0df28058f67d | checkpoint | Lifters to be Firm & Square against Formwork
d527a3fc-95e4-40e3-980a-3a46eea67a6c | checkpoint | DOUBLE CHECK EVERYTHING
21ce2fa5-f2a3-4bf9-8d4e-432cbc591e9f | checkpoint | Finish Required -Off Form Steel Trowel
b5f8f546-df37-42a3-ae3a-b00c3def3c49 | checkpoint | QA - Final Check of ALL measurerments & Photos
c1fec30c-df67-49bc-b203-db9a7555b90f | checkpoint | QA - Concrete Mix N40 Panel Mix
51a58397-68e5-4562-97ba-b2783f9d4f3f | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
ea272391-c273-4938-84d6-d837e93483c6 | checkpoint | CONCRETE TEST TAKEN
a1ef660d-44a2-5afa-a14f-8edec30f4c13 | date | Pour Date
99320b16-4b73-44f4-941b-e4731cc54585 | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
10638f9b-ffbd-4d83-a508-2eabe4025dae | signoff | Request Signoff
1b016389-1bbe-4c38-ba94-092a78139eea | checklist | Installers Checklist (Abutment Wall) |  | Installers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
4136725e-fc46-4366-98b5-5202458857b4 | checkpoint | Complete Material "Bucket List"
aab92e53-abe5-589b-a6b0-50e7d233fe88 | textbox | Foot Anchors 2.5T 170mm
f3cf2333-0c12-5bcd-8bf8-7d2adfb3a246 | textbox | Grout Tubes 290mm
414495ee-fbd5-4bf6-8cc0-cf0a19dce206 | checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK - Wall Height 884mm
dfa7d738-8256-4634-bdc4-cff814b7b0b0 | checkpoint | Apply bond breaker or wax 1 2 3
5a155910-2129-4361-ae5b-d2897811ea1d | checkpoint | Temporary Fix ID Plate to Formwork
44427fb4-702a-4d05-81fe-8574e7a244dd | checkpoint | Use Bridge Plank Mould
e9dacad2-751e-448d-9b65-8f326c8ff323 | checkpoint | Install Reo as-per Shop Drawing Plan
65222d00-63c7-49f5-b3cc-c3652921f836 | checkpoint | Use Bridge Mould
d41abaf4-294b-48ea-937f-8f4313f24f0f | checkpoint | Check Concrete cover around reo 30mm
3f9ae984-a053-4530-87d2-0df28058f67d | checkpoint | Lifters to be Firm & Square against Formwork
d527a3fc-95e4-40e3-980a-3a46eea67a6c | checkpoint | DOUBLE CHECK EVERYTHING
21ce2fa5-f2a3-4bf9-8d4e-432cbc591e9f | checkpoint | Finish Required -Off Form Steel Trowel
b5f8f546-df37-42a3-ae3a-b00c3def3c49 | checkpoint | QA - Final Check of ALL measurerments & Photos
c1fec30c-df67-49bc-b203-db9a7555b90f | checkpoint | QA - Concrete Mix N40 Panel Mix
51a58397-68e5-4562-97ba-b2783f9d4f3f | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
ea272391-c273-4938-84d6-d837e93483c6 | checkpoint | CONCRETE TEST TAKEN
a1ef660d-44a2-5afa-a14f-8edec30f4c13 | date | Pour Date
99320b16-4b73-44f4-941b-e4731cc54585 | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
10638f9b-ffbd-4d83-a508-2eabe4025dae | signoff | Request Signoff
554e1a06-dba2-4751-aed4-21044213fbfe | checklist | Precast Components ITP |  | Precast Components ITP
90ff7c4f-709b-4026-aa86-31ec18123419 | section | Manufacturing Documents
78eac3dc-e2ab-405f-995d-48dbc037117e | checkpoint | Shop drawings reviewed and updated. Issued "As For Construction"
ff970c7f-bf48-4865-93a4-d410be1591e2 | section | Pre-Pour Checks
a98650c7-a0b8-4dcf-a081-ec48b47d3e5b | checkpoint | Final Inspection - all placed in accordance with approved shop drawings
4c99a7bb-eaca-42e7-910a-b77f568ca379 | checkpoint | Upload sufficient number of photos pre pour
378943da-738f-4a09-b1b5-5d386dc0f44f | section | Transport
613914ee-c926-434b-88df-c2a990203d6c | checkpoint | Ensure loads are glutted correctly and chains are over gluts.
9448e13e-3cff-47a1-b372-f6ea40bdb831 | section | Final Inspection
31e2f3d9-54ae-4bab-a33e-2ea36ebcb827 | checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.