## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Checkers Checklist | [5 empty] | Checkers Checklist (Abutment Riser)
section | Details
checkpoint | Overall Measurements
checkpoint | Ferrules - Measurements & Size - 8 x M20 x96mm
checkpoint | Lifters Correct - Position, Size, Orientation - 2 x 2.5T Edge Lifters
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 40mm
checkpoint | Panel Thickness confirmed
dropdown | Panel Thickness: | 100mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist | [5 empty] | Installers Checklist (Abutment Riser)
section | Details
checkpoint | Complete Material "Bucket List"
textbox | Edge Lifters 2.5T x 4
checkpoint | Ferrules - Measurements & Size - 8 x M20 x96mm
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK -
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Use Timber Formwork
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Check Concrete cover around reo 40mm
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required -Off Form Steel Trowel
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
holdpoint | Request Signoff